## Slide 1
Cryomodule Installation Overview
Dominique White | Cryomodule Integration Lead | AD
SC Linac Installation Workshop
December 4, 2024

## Slide 2: What’s in a Cryomodule?
Dec 2024 | Cryomodule Installation | Dominique White
Beamline Cavities
He Process Pipes
Fundamental Power Couplers
Notes: And several connection to controls to keep everything going.

## Slide 3: Cryomodules Have Interfaces to Each Other
Vacuum Systems
Helium Process Pipes
Beamline Vacuum
Insulating Vacuum
Dec 2024 | Cryomodule Installation | Dominique White

## Slide 4: And Interfaces to Other Systems
Instrumentation Ports
Magnet Current Leads Port
Coupler Vacuum Manifold, Pump, Gauges
Cryo Valves
He Guard Ports
Iso Vac Gauges and
Scav Pumps
Waveguide Interface
RF Monitoring and Instrumentation Ports
CDA for Cryo Valves
Helium for Guard System
CDA for Scav Pumps
Controls
RF
Infrastructure/Utilities
Dec 2024 | Cryomodule Installation | Dominique White

## Slide 5: Cryomodules in the Housing
Cryomodules are installed in sections in the housing.
Interface to each other and Cryo Distribution System (CDS) components, resulting in different interconnect configurations. These were standardized as much as possible for HE
Particle Free beamline extends about 20 m on either side of Cryomodules
Dec 2024 | Cryomodule Installation | Dominique White
LCLS-II
LCLS-II HE
Notes: Going from 4 GeV to 8 GeV
Design Report: Published - LCLS-II-HE Final Design Report.pdf - LCLS-II-HE-Design Reports

## Slide 6: Interface to Cryo Distribution System (CDS) Components
Dec 2024 | Cryomodule Installation | Dominique White
Mechanical interfaces to CDS components have been standardized to match Cryomodule to Cryomodule interconnects.
Beam tube connections to CDS components are created with flanges that make up part of the CM insulating vacuum system.
Valve Ext
FC-7
EC-3
Valve Ext
VBB
Beam Tube

## Slide 7: Installation
Notes: How Cryomodules?

## Slide 8: Installation Sequence
Dec 2024 | Cryomodule Installation | Dominique White
6 Major Install Phases
  Unloading
  Receiving / acceptance testing
  Physical install / alignment
  Welding cryo pipes
  Particle free beamline install
  Insulation vacuum / cryo equip.
Notes: Welding needs to happen first before vacuum connection due to space constraints in interconnect

## Slide 9: Acceptance Testing- Cryomodule Systems
Dec 2024 | Cryomodule Installation | Dominique White
Acceptance Testing and Installation prep performed at storage location(s) and adit at SLAC
Acceptance Tests upon arrival
  Alignment
  RF
  Instrumentation and Magnet Check-out
  Vacuum testing - coupler, insulating, beamline
Mechanical Prep
  Mechanical prep - weld prep, heat shields, JT valves
  PF work - pump installation and gauge tree removal
  M-mount removal
Acceptance Testing

## Slide 10: Stand Installation
Dec 2024 | Cryomodule Installation | Dominique White
Stand Install
Cryomodules sit on two stands, fixed and sliding
California has seismic considerations- may be room for optimization

## Slide 11: Cryomodule Transport and Unload
Dec 2024 | Cryomodule Installation | Dominique White
Cryomodules shipped from FNL and JLab in special trailer with springs to avoid damage from shocks.
They are lifted from above with a spreader bar and moved with custom dollies.
Internals are protected with M-mounts, tie downs, and shipping caps. Trips are monitored with slam sticks.
Configuration for moving across site has fewer restraints.
Unload

## Slide 12: Cryomodule Transport and Unload
Dec 2024 | Cryomodule Installation | Dominique White
Use two dollies per Cryomodule and tow one Cryomodule at a time by tugger.
Attached with ratchet straps and used with a wooden hard stop on each end.
Use pneumatic jacks for a soft landing and to raise the Cryomodules into place over stands.
Detachable design allows dolly to roll into place under Cryomodule.
Need to be careful with placement. Ratchet straps need to avoid couplers.
Detachable Saddle
Guide wheels
Unload

## Slide 13: Cryomodule Physical Installation
Some installation is required before we place Cryomodules due to size of housing and risk of working above Cryomodules:
  All utilities and infrastructure- He Guard, Compressed Dry Air, etc
  Cryomodule stands in place
  Cable Plant Work- pulled cables coiled out of the way
  Ceiling and penetration waveguide
Dec 2024 | Cryomodule Installation | Dominique White
Physical Install
Align
Notes: Cable plant- for efficiency we need the bulk of this done, but we can come back and pull cables
CDS can come later

## Slide 14: Cryomodule Physical Installation
Cryomodules take up a lot of room
  Access to housing and is completely blocked during CM moves to the housing.
  Once on stands, the working space of the tunnel is cut in half.
  Cryomodules are sensitive to shocks and dust from surrounding work. Once in place, no work can happen above them.
Particle free installation and welding equipment limit access for other groups. Careful coordination with other groups is crucial.
Dec 2024 | Cryomodule Installation | Dominique White
Physical Install
Align

## Slide 15: Welding and Leak Check
Dec 2024 | Cryomodule Installation | Dominique White
He process pipes are welded together with orbital weld machine.
  HGRP connected with collar
  2” Lines connected with bellows
  Must be welded from the inside out
Important to match the metallurgy of cryo pipes at weld interfaces
  Sulfur content can affect pathway of weld and programming of orbital welder
  Use pipes from same batch of metal where possible
  Take care to standardize pipes between CM and CDS components
Cryo Pipe Leak Test
HGRP Weld & Exam
2” Pipe Weld & Exam
Notes: Helium gas return pipe

## Slide 16: Welding and Leak Check
Dec 2024 | Cryomodule Installation | Dominique White
Cryo Pipe Leak Test
HGRP Weld & Exam
2” Pipe Weld & Exam

## Slide 17: Welding and Leak Check
Dec 2024 | Cryomodule Installation | Dominique White
Several checks after welds are complete:
Visual examination- external and with borescope
  Internal completed with special long borescope
Helium Mass Spectrometry Leak Test
  Cryo lines are filled with helium and checked for leaks
Ultrasonic Examination
  Outside contractor
  Sample % of each welder’s joints
Cryo Pipe Leak Test
HGRP Weld & Exam
2” Pipe Weld & Exam
Internal Exam
Clamshell
Ultrasonic Exam
Notes: Add a full-scale system test to prevent so vac leaks in the future

## Slide 18: Pressure Test
Dec 2024 | Cryomodule Installation | Dominique White
Pressure Test - Full String
Pressure test of entire string once all welds are completed
  Fill all pipes with a mixture of Air and 5% Helium through Vertical Transfer line
  Joints are tested with a sniffer probe
  Completed over a weekend for reduced access and used SLAC’s LOTO for secure access
Notes: Pipes filled to 22 Bar

## Slide 19: BLA Installation
Dec 2024 | Cryomodule Installation | Dominique White
Particle-free operation to connect CM cavity strings
  Install Spools and Beamline Absorbers (BLA) with aluminum gaskets
  Spacing is tight and ergonomics are challenging
  Cryo pipes on top of the BLA hinder any laminar flow from above
  Use custom clean zone and supplemental clean bench for more working space
BLA Install
BLA Pump Down & Leak Test

## Slide 20: BLA Installation
Dec 2024 | Cryomodule Installation | Dominique White
BLA Install
BLA Pump Down & Leak Test
Handle for transport.
Remove for operation.
Protective top for transport
Remove for operation
Levelling feet
Fan filter unit (FFU)
BLA stage holder
CLEAN ZONE
Wall
side
Top Door

## Slide 21: BLA Installation
Dec 2024 | Cryomodule Installation | Dominique White
Particle-free set-up blocks Linac access for other groups/ people
Equipment:
  Particle-free pump carts
  Interconnect Clean zones for each kind of interconnect (FC-CM and VBB-CM, CM-CM)
  Laminar flow benches
  Ergonomic Equipment
One CM in interconnect MUST be open to an ion pump with gauge and controller installed to monitor beamline vacuum before BLA installation can take place
  Ion pumps at VBB and valve extensions
  Can use local controllers to monitor
BLA Install
BLA Pump Down & Leak Test

## Slide 22: BLA Pump Down and Leak Test
Dec 2024 | Cryomodule Installation | Dominique White
Gauge tree removed before Cryomodules are installed. Cryomodule vacuum is unknown when PF connections are made.
Need to start PF connections at a side of the string with a gauge to monitor beamline during installation
Always open to Cryomodule with unknown vacuum first
BLA Install
BLA Pump Down & Leak Test

## Slide 23: BLA Installation vs Welding
Dec 2024 | Cryomodule Installation | Dominique White
Welding wants to start here
BLA’s want to start here
BLA’s
BLA Install
BLA Pump Down & Leak Test
Pump
Welding needs to happen before vacuum connections
Welding wants to start one interconnect removed from EC and FC for more efficient purge of lines
BLA installation needs to start with ion pump to monitor and maintain beamline vacuum
Pumps are located at FC, EC, and VBB
This conflict is overcome by use of the VBB in the middle of the CM string
Pump
Pump
Pump

## Slide 24: Beamline Pump Down
Dec 2024 | Cryomodule Installation | Dominique White
Beamline needs to be less than 1e-8 Torr on the ends before cool down
Data from LCLS-II suggests this takes about 3 months to achieve for a string of 12 Cryomodules
BLA Install
BLA Pump Down & Leak Test
Notes: Used to inform outgassing rates and ceramic factor

## Slide 25: MLI and Interconnect Completion
Dec 2024 | Cryomodule Installation | Dominique White
MLI & Heat Shield Install
Interconnect completion:
  Wrap with MLI
  Install remaining equipment (heat strap, BLA spring support)
  Close up large bellows
  Install gauges and gate valves
  Take pictures of interconnect before close-up

## Slide 26: Cryomodule Insulating Pump Down
Dec 2024 | Cryomodule Installation | Dominique White
Insulation Vac Pump and Leak Test
  Divided into L4 US and DS at VBB for easier management
  Each insulating vacuum space needs to be pumped to 1x10-4 Torr. Expect 2-3 months to reach spec.
  Pump and purge each insulating vacuum space three times with nitrogen and check seals of big bellows.
  Roughing is completed with MU 600 pump
  Use He Scav Pumps (permanent) and aux pumps (temporary) to meet spec
Insulation Vac Pump and Leak Test

## Slide 27: Requirements and Specifications
SLAC-I-020-101-007-00 - Linac & FEL Facility Vacuum Specifications
18 September 2023 | L4 String and Beam Tube FDR | Dominique White
Notes: AD doc that covers accelerators
Vacuum pressure upper limit mainly pertains to switches

## Slide 28: Installation Sequence
Dec 2024 | Cryomodule Installation | Dominique White
6 Major Install Phases
  Unloading
  Receiving / acceptance testing
  Physical install / alignment
  Welding cryo pipes
  Particle free beamline install
  Insulation vacuum / cryo equip.
Notes: Welding needs to happen first before vacuum connection due to space constraints in interconnect

## Slide 29: Questions?
Notes: How Cryomodules?

## Slide 30: Schedule – CM 47-59
Nov 2024 | Cryomodule Installation | Dominique White
CM Start
Weld Start
BLA Start
First group of CM’s brought in - 47 to 59
Welding and BLA teams follow immediately behind. Welding and vacuum work for the first CM’s can happen while CM’s are being brought downstream. Equipment won’t block CM installation
Particle free work start from the VBB when welding for each interconnect is complete
Notes: Stacked animated with fade in timing

## Slide 31: Schedule – CM 37-47
Nov 2024 | Cryomodule Installation | Dominique White
CM Start
Weld Start
BLA Start
Once 58-59 welding is complete, bring in CM 37-46
Welding starts from 37-38 and works downstream
Once FC-7-CM 37 is complete, BLA work can resume
Pressure test of helium process pipes follows welding
Once BLA and process pipes are complete, interconnects are closed, and insulating vacuum pump down can begin
Other interface connections can be made (RF, Controls, Utilities)
Last two welds to complete
Notes: Second animation- welding to follow CM’s coming in

## Slide 32: Overall Schedule
How does this play out with other groups? To the color block!! and MSP
Nov 2024 | Cryomodule Installation | Dominique White

## Slide 33: Bonus: Requirements and Interfaces

## Slide 34: Requirements and Specifications
18 September 2023 | L4 String and Beam Tube FDR | Dominique White
 | Doc Number | Description
Physics Requirements and MAD Deck | LCLSII-HE-1.1-PR-0018 | LCLS-II-HE Linac Requirements
 | LCLSII-HE-1.1-PR-0039 | LCLS-II-HE Parameters
 | LCLSII-HE-1.2-PR-0029 | LCLS-II-HE SCRF 1.3 GHz CM
 | MADdeck | March 2023
Vacuum System Specifications | SLAC-I-020-101-007 | Linac & FEL Facility Vacuum Specifications
 | SLAC-I-020-101-008 | Linac Particle-Free Engineering Specifications
Physical Interface | LCLSII-4.5-IC-0661 | 1.3 GHz Cryomodule Physical Interfaces
Housing RDS | LCLSII-HE-1.6-RD-0290 | HE Linac Housing Sectors 0-10 for infrastructure requirements
**ICD** | LCLSII-HE-1.3-IC-0906 | HE L4 Cryomodule String to Controls, Infrastructure, and CM Systems ICD
Provides all information on interfaces between groups
Following docs list requirements for L4 Cryomodule String design
All are released
Delete?

## Slide 35: Requirements and Specifications
LCLSII-HE-1.1-PR-0018 - LCLS-II-HE Linac Requirements
18 September 2023 | L4 String and Beam Tube FDR | Dominique White
LCLS-II
LCLS-II HE
Delete?

## Slide 36: Requirements and Specifications
LCLSII-HE-1.2-PR-0029 - LCLS-II-HE SCRF 1.3 GHz CM
18 September 2023 | L4 String and Beam Tube FDR | Dominique White
Delete?
Notes: Recap of 1.3 GHz CM parameters
Drives installation procedures and layout of Cryomodules

## Slide 37: Layout and Technical Analysis

## Slide 38: Drawings and Schematics
In addition to partner lab drawings, SLAC team has released drawings of CM string and vacuum schematics
18 September 2023 | L4 String and Beam Tube FDR | Dominique White
Drawing | Description | Status
DSG-000063012 | Vacuum Schematic | Released
DSG-000007866 | L4A Cryomodule String Layout | Final Review
DSG-000007867 | L4B Cryomodule String Layout | Final Review
DSG-000048432 | ASSY, CM, 1.3GHz, HE, LCLS2 | Released
DSG-000056783 | CM Stand Installation Hardware Kit | Released
DSG-000066051 | CM Fixed Sliding Stand | Released
DSG-000066048 | CM Adjustable Sliding Stand | Released
ID-375-240-01 | Helium Scav Pump Installation | Released

## Slide 39: Drawings and Schematics
18 September 2023 | L4 String and Beam Tube FDR | Dominique White
Notes: What’s included here- mad deck positions and stands

## Slide 40: Vacuum Analysis
LCLSII-HE-1.3-EN-0938 - LCLS-II-HE Vacuum Analysis for L4B
  Updated outgassing rates for CM’s, BLA’s, and beam tubes to determine beamline vacuum
  Planned pumping is sufficient to meet requirements for cool down
18 September 2023 | L4 String and Beam Tube FDR | Dominique White
Pressure estimate when warm after 3 months

## Slide 41: To Delete

## Slide 42: Installation Sequence
Nov 2024 | Cryomodule Installation | Dominique White
6 Major Install Phases
  Unloading
  Receiving / acceptance testing
  Physical install / alignment
  Welding cryo pipes
  Particle free beamline install
  Insulation vacuum / cryo equip.
The time for one CM is ~15.75 days
  Duration is how long it will take a group to finish a defined task for one Cryomodule
  Pressure test and pump down include multiple Cryomodules at once.
Cryo Pipe Leak Test
Pressure Test - Full String
BLA Install
BLA Pump Down & Leak Test
MLI & Heat Shield Install
Insulation Vac Pump and Leak Test
Acceptance Testing
Unload
Physical Install
Align
HGRP Weld & Exam
2” Pipe Weld & Exam
Stand Install
2.25 Days
7 Days
1.5 Day
1.5 Day
3 Days
5 Days
10 Days
.75 Day
.75 Days
.5 Day
2.5 Days
2.5 Days
1 Day
LCLS-II
Notes: Welding needs to happen first before vacuum connection due to space constraints in interconnect

## Slide 43
Nov 2024 | Cryomodule Installation | Dominique White
Doc Number | Procedure
LCLSII-HE-1.2-PP-0375 | LCLS-II-HE Cryomodule Rigging and Alignment Procedure
LCLSII-4.5-PP-1602 | 1.3 GHz Cryomodule Cable Restraint Bracket Installation Procedure
LCLSII-4.5-PP-0933 | Cryomodule Stand Installation and Alignment Procedure
LCLSII-4.5-PP-2142 | Installation of Auxiliary Pump for Cryomodule Insulating Vacuum String
LCLSII-4.5-PP-1571 | Cryomodule Beamline Spool Installation Procedure
LCLSII-4.5-PP-0937 | Cryomodule BLA Installation Procedure
LCLSII-4.5-PP-0936 | Cryomodule Weld Examination Procedure
LCLSII-4.5-PP-2114 | LCLS-II Port Guard Helium System Leak Check Procedure
LCLSII-4.5-PP-2107 | LCLS-II Port Guard Helium System Testing Procedure
LCLSII-4.5-PP-0938 | Cryomodule Cryo Equip Installation Procedure
LCLSII-4.5-PP-1820 | Cryomodule Coupler Vacuum Pump Down Procedure
LCLSII-4.5-PP-1314 | Cryomodule Insulation Vacuum Pumping Procedure
LCLSII-4.5-PP-0932 | Cryomodule Anchor Installation Procedure
LCLSII-4.1-PP-2067 | Helium Leak Check of Cryomodule and End Cap Cryo Process Interfaces
LCLSII-4.5-PP-2143 | Cryomodule Insulation Vacuum RGA Testing
LCLSII-4.5-PP-0939 | Cryomodule String Pressure Test Procedure
LCLSII-4.5-PP-1560 | Cryomodule String Pressure Test Search Procedure
LCLSII-4.5-PP-0935 | Cryomodule Welding Procedure
LCLSII-4.5-PP-1871 | Setup And Demagnetization Of LCLS-II Production Cryomodules
LCLSII-4.5-PP-1959 | Setup and Demagnetization of Installed LCLS-II Production Cryomodules
LCLSII-4.5-PP-1964 | Cryomodule Helium Guard Installation Procedure
Installation Procedures