## Slide 1
Agenda (https://indico.bnl.gov/conferenceDisplay.py?confId=2631)
Schedule
Bldg. 1008 connections
AOB

## Slide 2
  Schedule
Return Yoke may finish construction in Feb. or Mar. (J. Hock) with platform ready
Cryo (C-AD) can finish making connections/setting up in Mar. or Apr. (P. Orfin) if we can find another tech or more
  Cool-down starts and then finishes in Apr. or May
Cryo Extension assembly (SMD) should be done in Dec. or early Jan. (M. Anerella)
Data acquisition/quench detector : ~Apr. (C. Schultheiss)
Power Supply/Dump Resistor : Middle of Mar. (P. Rosas)
  P. Rosas: “We have not touched the sPHENIX PS or Dump Resistor for a while, we are in the process of checking AGS and RHIC PS all this month. I think we will start again later next Month on sPHENIX.”