## Slide 1: RHIC Schedule Meeting
04/07/2025
Medani P. Sangroula
Scheduling Physicist

## Slide 2
Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
RHIC Operations FY25
2024
2026
Today
Revised: 04/07/2025
Scrub:
Jan 24
RHIC Cryo
45 K:
Feb 24
4 K:
Mar 24
Booster (Feb 3 - )
AGS operations (Mar 3 - Jun 30)
Assuming no polarized proton required after Jun 6
Linac (Jan 19 - Jun 6)
NSRL (Feb 3 - )
BLIP (Jan 24 - Jun 6)
4 K:
Jun 30
EBIS (May 12 – )
Upgrade
Planning basis: 4K cooldown on 3/24/25 for Au + Au and 7 weeks break on 06/30 (cryo remains on). Resume operation on 08/18 to 12/22 dependent on approved budget.
Tandem (Jan 23 - )
...
...
...
...
Break
Break
Planning basis may change!
EBIS got delayed for another week
May 12 instead of May 07

## Slide 3: Ongoing Work
NSRL is running Au and Iodine beams.
BLIP intend to run this week (Wed/Thu) for 24 hour with 117 MeV.
RHIC is warming up!
We are narrowing down the location (Blue main dipole return bus at sector 4) for repair.
Planning to use the Booster and AGS for AI/ML related beam study and polarized proton development with skew quads.