## Slide 1: TAKE FIVE for Safety- Work Planning for RHIC Repair
April 15, 2025
Frank Craner

## Slide 2: Job Scope (Initial Plan)
Prior to Repair:
  Arcs 12/1 and 2/3 warmed up to 45K and allowed to drift warmer
  Arc 4/5 warmed to ambient temperature, with cryogen supply locked out
  VODH system disabled in the 4/5 arc
  Arcs 6/7, 8/9, and 10/11 remain cold at 4.5 K.
Repair scope:
  Open RHIC Cryostat(s), Splice Can(s) Identify and Repair Shorted Bus Conductors, close Splice Can(s) and Cryostat(s)

## Slide 3: Identification of Potential Job Hazards (Initial Plan)
Activation
Cryogenic
Electrical
Ergonomics
Fumes/Mist/Dust
Material Handling
Oxygen Deficiency
Vacuum Systems
Welding/Cutting/Grinding/Brazing

## Slide 4: Primary Hazard Mitigations (Initial Plan)
LOTO of Hazardous Energy (Cryogen, Electrical, Instrument)
Permit and fire protection mitigations for Hot Work Activities
Exhaust Ventilation (ODH System)
Postings/Barricades
PPE for cutting

## Slide 5: Accelerator Safety- USI Evaluation (Initial Plan)
ODH System, including oxygen monitors with control of alarms and fans will remain enabled for entire RHIC ring.
VODH module for arc 4/5 will be bypassed; modules for other arcs will not be affected.
Arc 4/5 will not need VODH controls

## Slide 6: RHIC Tunnel Sextant ODH Controls (As related to Initial Plan)
Cryogenic System Condition | Relative ODH Risk | RHIC ASE Controls
Helium at 293K (Ambient Temp) | Low | None
40K<Helium< 80 K | Medium | ODH Monitoring, Alarms, Ventilation, Automatic Isolation 3 Exhaust Fans per sextant minimum
Helium < 40 K | High | Helium<80K Controls; PLUS: VODH Must be operable VODH Sensors must trip ODH Mitigations at 0.5 atm (nominal)

## Slide 7: Changing Conditions (This Week)
Identification of need for
  Adjustment to Cryogenic Isolation- Accelerator Safety “USI”
  Scaffolding to access point of work
  Material handling planning and evaluation

## Slide 8: Conclusion
Planning purpose to identify and mitigate issues related to worker safety and health, accident prevention, and compliance.
Questions were raised early
Reviews have been a team effort with input from several planners and Subject Matter Experts
Frequent communication to address changing needs and conditions
Work is affected by “Accelerator Hazards” and “Non-Accelerator Hazards”