## Slide 1
RRPL Operations
RRPL - Week of 11/17:
    Special Operating Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice
    Coming weeks:
    Solidification of LANL Th target waste after special operation restrictions are resolved
    Ni/Co Hot Cell set-up in TPL; preparation for BLIP irradiated foil processing
    Be-7 processing in TPL

## Slide 2
BLIP Operation – OFF Season Mode
  Special Operation Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice.
  - Both manipulators and chain drives have been physically secured and locked with both BLIP operator and RCD locks.
  Chillers require 24-hr for crankcase heater warmup prior to operation. Therefore, cannot immediately switch to backup chiller until installation of electrical panel is performed in the next phase of cooling system upgrade.
  Off-season maintenance/testing
      This week weekly alarms testing
      dP indication on target water filter is now reading correctly after some adjustments but still working with SME from water group to purchase new calibrated gauges and calibrating transducer.

## Slide 3
  Commissioning Path Forward: Commissioning in progress.
    Cyclotron is working under module 3 of the commissioning plan.
    19MeV tuning to dummy target – successful but issue with extraction probe found
    Cu foil irradiation successful
  Next step in commissioning plan is Ni target irradiation. Target ready, canning record approved, need RWP to cover target removal operation (in progress)
  WO submitted for filter and fluid change of hydraulic pump.
  WO submitted to replace air compressor scroll head.
  OPM revisions
  Cable connections of cobot into control room and testing.
Cyclotron Activities