## Slide 1
RRPL Operations
RRPL - Week of 12/1:
    Special Operating Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice
    LANL Th target waste neutralized, solidification after special operation restrictions are resolved.
    Coming weeks (pending continuation of operations):
    Ni/Co Hot Cell set-up in TPL; preparation for BLIP irradiated foil processing
    Be-7 processing in TPL

## Slide 2
BLIP Operation – OFF Season Mode
  Special Operation Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice.
  Canceled Th irradiation planned on December 19. Next irradiation is planned for March
  Roof started to leak again in the Control Room
  Off-season maintenance/testing
      This week weekly alarms testing
      December monthly alarms testing and inspection
      dP indication on target water filter is now reading correctly after some adjustments but still working with SME from water group to purchase new calibrated gauges and calibrating transducer

## Slide 3
  Commissioning Path Forward: Commissioning in progress.
    Cyclotron is working under module 3 of the commissioning plan.
    USI for new access controls ‘testing/tuning modes’ – Approved by DOE-BHSO on 11/4.
    Cobot (robotic arm for target movement) configuring software & hardware for remote operation from control room.
  Next step in commissioning plan is Ni target irradiation. Target ready, canning record approved, need RWP to cover target removal operation (in progress)
  WO submitted for filter and fluid change of hydraulic pump.
  WO submitted to replace air compressor scroll head.
  Vacuum leak checking around east target station
  OPM revisions
  Housekeeping
Cyclotron Activities