## Slide 1
RRPL Operations
RRPL - Week of 12/16:
    Special Operating Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice
    LANL Th target waste neutralized, solidification after special operation restrictions are resolved.
    Coming weeks (pending continuation of operations):
    Ni/Co Hot Cell set-up in TPL; preparation for BLIP irradiated foil processing
    Be-7 processing in TPL

## Slide 2
BLIP Operation – OFF Season Mode
  Special Operation Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice.
  Canceled Th irradiation planned on December 19. Next irradiation is planned for March
  Roof started to leak again in the Control Room - the water diverter installed as a temporary solution until the roof repair/replacement can be done. Most likely springtime when temperature allows.
  Off-season maintenance/testing
      This week weekly alarms testing
      dP indication on target water filter is now reading correctly after some adjustments but still working with SME from water group to purchase new calibrated gauges and calibrating transducer
      Request from water group to regenerate/replace the resin in the makeup water deionizer.

## Slide 3
  Commissioning Path Forward: Commissioning in progress.
    Cyclotron is working under module 3 of the commissioning plan.
    USI for new access controls ‘testing/tuning modes’ – Approved by DOE-BHSO on 11/4.
    Cobot (robotic arm for target movement) configuring software & hardware for remote operation from control room. Parts ordered, new remote pendant nearing completion
  Next step in commissioning plan is Ni target irradiation. Target ready, canning record approved, need RWP to cover target removal operation (in progress)
  WO submitted for filter and fluid change of hydraulic pump.
  RF/dummy load interrupt flow switch installed and tested.
  Continuing with OPM revisions
  OPM revisions
Cyclotron Activities