## Slide 1
RRPL Operations
RRPL - Week of 01/13:
    Special Operating Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice
    LANL Th target waste neutralized, solidification after special operation restrictions are resolved.
    Coming weeks (pending continuation of operations):
    Ni/Co Hot Cell set-up in TPL; preparation for BLIP irradiated foil processing
    Be-7 processing in TPL

## Slide 2
BLIP Operation – OFF Season Mode
  Special Operation Restriction: BNL has issued a pause in all operations associated with radioactive materials in RRPL and BLIP hot cells/boxes covered under the current SAD/ASE until further notice.
  Planned BLIP authorization to operate 2/27 (no irradiation until March)
  Off-season maintenance/testing
      This week weekly alarms testing
      dP indication on target water filter is now reading correctly after some adjustments but still working with SME from water group to purchase new calibrated gauges and calibrating transducer
      Request to water group to regenerate/replace the resin in the makeup water deionizer:
      It was recommended to abandon the existing 3 cu foot cartridge and install a smaller cartridge for the deionizer. It might suite better our requirements.

## Slide 3
  Commissioning Path Forward: Commissioning paused due to casual analysis investigation for non-performance of operational readiness check prior to running beam.
  Cyclotron is working under module 3 of the commissioning plan.
    Next step in commissioning plan is Ni target irradiation. Target ready, canning record approved, need RWP to cover target removal operation (in progress)
  WO submitted for filter and fluid change of hydraulic pump.
  Reprogramming target selector.
  Leak checking west side target station.
  Housekeeping and weekly maintenance checklist
Cyclotron Activities