## CB_DATA_ (hidden)
#NAME?

## Definitions
Consequence: Outcome of an event. (Normally includes scope, schedule, and cost).
External Risks: Risks outside the project control or global risks inherent in any project such as global economic downturn, trade difficulties affecting deliverables such as construction materials or political actions that are beyond the direct control of the project.
Internal Risks: Risks that the project has direct control over, such as organizational behavior and dynamics, organizational structure, resources, performance, financing, and management support.
Key Risk: Key risks are a set of risks considered to be of particular interest to the project team. These key risks are those estimated to have the most impact on cost and schedule and could include project, technical, internal, external, and other sub-categories of risk.
Mitigate: To eliminate or lessen the likelihood and/or consequence of a risk.
Opportunity: Risk with positive benefits.
Probability: Likelihood of an event occurring, expressed as a qualitative and/or quantitative metric.
Project Risk: Risks that are captured within the scope, cost, or schedule of the project
Qualitative Risk Analysis: Involves assessing the probability and impact of project risks using a variety of subjective and judgmental techniques to rank or prioritize the risks.
Quantitative Risk Analysis: Involves assessing the probability and impact of project risks and using more numerically based techniques, such as simulation and decision tree analysis for determining risk implications.
Residual Risk: Risk that remains after risk mitigation has been successfully implemented.
Risk: An uncertain event that, if it occurs, has an outcome that could either positively or negatively impact project objectives.
Risk Acceptance: An informed and deliberate decision to accept consequences and the likelihood of a particular risk.
Risk Analysis: Process by which risks are examined in further detail to determine the extent of risks, how they related to each other, and which ones are the highest risks.
Risk Assessment: Identification and analysis of project and program risks to ensure an understanding of each risk in terms of probability and consequences.
Risk Assumption: Any assumptions pertaining to the risk itself.
Risk Mitigation: Process to reduce the consequence and/or probability of a risk. After the mitigation plan has been approved, mitigation resources become part of project resource-loaded schedule.
Trigger Metric: Event, occurrence or sequence of events that indicates the risk may be about to occur, or the pre-step for the risk indicating that the risk will be initiated.

## Proposed Risk Form
Risk Identification | Risk Event (IF). Must be in the future, must be uncertain (probability <100%)
Risk Impacts (THEN). Describe cost, schedule, technical consequences if risk realizes.
Risk Title (Short but clear description)
L2 WBS
Risk Owner
P6 Schedule Milestone Affected (when MS reached, risk can be retired)
Qualitative Assessment (Pre-mitigated) | Risk Probability Range (<10%, 10-25%, 25-40%, 40-65%, >65%)
Cost Impact, $K
Schedule Delay, months
Minimal or no impact to threshold or objective KPPs? YES/NO
Possible impact to objective KPPs but workarounds available, no impact to threshold KPPs. YES/NO
Possible impact to an objective KPP, but likely no workaround available. No impact to threshold KPPs. YES/NO
Will impact objective KPP. Possible impact to threshold KPPs, but workaround available. YES/NO
Impacts a threshold KPP. YES/NO
Rsk Handling (Avoid, Accept, Enhance, Mitigate, Transfer)
Mitigation plan (what will be done to reduce probability and/or impacts)
Quantitative Assessment (Post-mitigated, aka Residual) | Residual risk probability (assuming all mitigations will be done)
Are mitigation resources (to implement the plan in row 14) in P6?
Low cost impact, $K
Likely cost impact, $K
High cost impact, $K
Low schedule impact, mo
Likely schedule impact, mo
High schedule impact, mo
How 3 point estimates were calculated (rows 16-21)
Minimal or no impact to threshold or objective KPPs? YES/NO
Possible impact to objective KPPs but workarounds available, no impact to threshold KPPs. YES/NO
Possible impact to an objective KPP, but likely no workaround available. No impact to threshold KPPs. YES/NO
Will impact objective KPP. Possible impact to threshold KPPs, but workaround available. YES/NO
Impacts a threshold KPP. YES/NO

## Risks
| Risk Identification | [9 empty] | Primary Risk (Unmitigated Risk Assessment) | [16 empty] | Risk Handling Plan (Mitigations) |  |  |  | Residual Risk (Post-Mitigation Assessment) | [21 empty] | Notes
Status | Risk ID | Threat/ Opportunity | L2 WBS | Lab | WBS Manager | Risk ID | Risk Owner | System Code | Risk Title | IF/THEN | Likelihood of Impact Category | Cost Impact Estimate ($K) | Cost Impact Category | Schedule Impact (months) | Schedule Impact Category | Technical Impact Category | Likelihood Score (1-5) | Cost Score (1-5) | Schedule Score (1-5) | Technical Score (1-5) | Risk Consequence Weight (Max of Cost/ Sched/ Tech) | Overall Impact Score | Pre-Mitigated Overall Category | Notes/Cost Estimate Basis for Primary Risks | Average Likelihood for Primary Risks | Primary Risk Expected Monetary Value (K$) | Handling Method | Mitigations / Enhancement Plans | Cost of Mitigations (NOT Costed in Baseline) ($K) | Risk Trigger Date (FQ or FY) | Risk Trigger P6 activity | P6 Milestone Affected | Residual Risk Likelihood (%) | Low Cost Impact ($K) | Likely Cost Impact ($K) | High Cost Impact ($K) | Low Schedule Impact (MOs) | Likely Schedule Impact (MOs) | High Schedule Impact (MOs) | Residual Risk Likelihood (Category) | Residual Cost Impact (Category) | Residual Schedule Impact (Category) | Residual Technical Impact (Category) | Likelihood Score (1-5) | Cost Score (1-5) | Schedule Score (1-5) | Technical Score (1-5) | Risk Consequence Weight (Max of Cost/Sched/Tech) | Overall Impact Score | Post-Mitigated Overall Category | Management Assessment: Overall Impact | Basis of Impact Estimates for Mitigated Risks | Mitigated Risk EMV (K$) | Last Reviewed / Updated | Review Meeting Questions / Risk Manager Notes | Risk Manager Notes - Burndown, Model, etc.… | Retirement Notes | Monte Carlo Model Notes | Category | Average Expected Value ($K) | Realized YES/NO | Retired Date | Proposed | Approved | Change History | PERT Value | Cost Impacts Low - Likely - High, $K | Sched Impacts Low - Likely - High, mo | AVG expected Cost, $K | AVG Expected Delay, mo | Risk ID Before May 2023
FORMULA | INPUT | INPUT | INPUT | INPUT | INPUT | COPY of B for reporting | INPUT | Dropdown | INPUT | INPUT | INPUT | INPUT | FORMULA | INPUT | INPUT | INPUT | FORMULA | FORMULA | FORMULA | FORMULA | FORMULA | FORMULA | FORMULA | INPUT | FORMULA | FORMULA | Dropdown | INPUT |  | INPUT |  | INPUT | INPUT | INPUT | INPUT | INPUT | INPUT | INPUT | INPUT | FORMULA | FORMULA | FORMULA | INPUT | FORMULA | FORMULA | FORMULA | FORMULA | FORMULA | FORMULA | FORMULA | INPUT | INPUT | 43444.25 | INPUT | INPUT | INPUT | INPUT | INPUT | INPUT | FORMULA | DROPDOWN | INPUT | INPUT | INPUT | INPUT | 43074.6667 |  |  |  |  | Copy of old IDs
Active | RO-6-001-001 | Opportunity | 6.01 Project Management | BNL | L. Lari | RO-6-001-001 | L. Lari | PM | Additional In-Kind Contributions for Accelerator systems and Detector | If there are additional in-kind contributions beyond what is planned in the baseline then some critical accelerator components can be obtained which will result in a cost savings. | High (Risk is likely to occur with a probability of >40 to <65%) | -49578 | Crisis | 0 | Negligible | None | 4 | 5 | 1 | 0 | 5 | 20 | High | Assume 5% of Accelerator Systems cost (Sept CE) will be contributed. 991.5M at 5% at 50% probability. | 52% | -25780.56 | Enhance | Engage Project partners |  | Q2 FY25 |  | E1102_01180 Start Construction | 5% | -27000 | -76000 | -100000 | 0 | 0 | 0 | Very Low | Crisis | Negligible | None | 1 | 5 | 1 | 0 | 5 | 5 | Low |  | Current in-kind is assumed at 5% for the accelerator ($50M) and 30% for the detector ($100M). For Accelerator assume 6% for low; 8% for likely; 10% for high; For Detector assume 35% for low; 40% for likely; 45% for high. | -3800 | 2024-02-20 | [5 empty] | -3383.3333 |  |  | 2021-03-30 | 2021-09-27 |  | -3591.6667 | -27000 - -76000 - -100000 | 0 - 0 - 0 | -3383.3333 | 0 | 175 | 2024-03-31 | 916
Active | RO-6-001-002 | Opportunity | 6.01 Project Management | BNL | L. Lari | RO-6-001-002 | L. Lari | PM | G&A decrease | If the G& A rate decreases, the cost for the project will decrease on all budgeted items | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | -6000 | Critical | 0 | Negligible | None | 3 | 4 | 1 | 0 | 4 | 12 | Moderate | Based on sensitivity analysis | 32% | -1920 | Accept | Accept and include in contingency calculation. |  | Q1 FY25 |  | L1_090 CD-4 Approval Early Completion | 5% | -13000 | -13000 | -13000 | 0 | 0 | 0 | Very Low | Critical | Negligible | None | 1 | 4 | 1 | 0 | 4 | 4 | Low |  | Assume that the Labs will hold the rates as best they can and that a 1% increase/decrease would be the most likely. Use the opposite of Risk 177, but the likelihood is probably cut in half. | -650 | 2024-02-20 | [5 empty] | -650 |  |  | 2021-04-30 | 2021-09-27 | April 2023: Cobra rates change analysis for G&A 1% decrease, COMMON 1.5% decrease | -650 | -13000 - -13000 - -13000 | 0 - 0 - 0 | -650 | 0 | 178 | 2024-04-30 | 946
Active | RT-6-001-001 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-001 | L. Lari | PM | Reprioritized Redirect Funds FY25 | If the amount of redirected funds available is less than anticipated and DOE can't provide new funds to make up the difference, work will get delayed and the project will take longer and cost more. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 30000 | Critical | 12 | Significant | None | 3 | 4 | 3 | 0 | 4 | 12 | Moderate | 30M Assumption of possible loss of redirected funds | 32% | 9600 | Mitigate | Work closely with NPP Directorate to ensure that the redirected dollar amounts are understood and agreed. Work to get partners who could contribute to reduce the amount of funds required from ONP. |  | Q1 FY25 |  | L3_5180 FY24 Funding Available Including Anticipated CR | 10% | 30000 | 30000 | 30000 | 6 | 6 | 6 | Very Low | Critical | Marginal | None | 1 | 4 | 2 | 0 | 4 | 4 | Low |  | Assume very low probability and no impact to cost; assume 6mo delay for each of FY24-31 funds available MS. | 3000 | 2024-02-20 | [5 empty] | 3000 |  |  | 2020-06-30 | 2020-10-30 | Feb 2023: add $30M cost impact | 3000 | 30000 - 30000 - 30000 | 6 - 6 - 6 | 3000 | 0.6 | 4 | 2024-03-31 | 1248
Active | RT-6-001-002 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-002 | L. Lari | PM | Supply Chain Issues for non-LLP items | If the project procurements are affected by interruptions in the supply chain, then the schedule will be delayed and the cost will go up. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 18000 | Critical | 6 | Marginal | None | 2 | 4 | 2 | 0 | 4 | 8 | Moderate | Assume 1% of project cost | 17% | 3060 | Mitigate | Work closely with BNL and JLab management and procurement to identify procurements that might be affected; develop supply chain list. |  | Q3 FY25 |  | L1_090 CD-4 Approval Early Completion | 30% | 8475 | 16950 | 33900 | 3 | 6 | 12 | Moderate | Critical | Marginal | None | 3 | 4 | 2 | 0 | 4 | 12 | Moderate |  | Assume this is separate from Commodity Price Fluctuations. Assume Early Completion delays 3-6-12mo, SAC $40.8M | 5085 | 2024-04-15 |  | Sched only in MC model |  |  |  | 5932.5 |  |  | 2021-09-28 | 2021-09-28 |  | 5508.75 | 8475 - 16950 - 33900 | 3 - 6 - 12 | 5932.5 | 2.1 | 5 | 2024-03-31 | 915
Active | RT-6-001-003 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-003 | L. Lari | PM | Procurement Schedule | If procurements close to Critical Path get delayed, it will affect the Early Finish | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 16950 | Critical | 6 | Marginal | None | 3 | 4 | 2 | 0 | 4 | 12 | Moderate |  |  |  | Mitigate | Work in close coordination with BNL and TJ procurement departments |  | TBD |  | L1_090 CD-4 Approval Early Completion | 20% | 8475 | 16950 | 33900 | 3 | 6 | 12 | Low | Critical | Marginal | None | 2 | 4 | 2 | 0 | 4 | 8 | Moderate |  | Assume this is separate from Commodity Price Fluctuations and Supply Chain Issues. Assume Early Completion delays 3-6-12mo, SAC $40.8M | 3390 | 2024-02-20 |  | Sched only in MC model |  |  |  | 3955 |  |  | 2023-03-15 | 2023-03-15 |  | 3672.5 | 8475 - 16950 - 33900 | 3 - 6 - 12 | 3955 | 1.4 | 7 | 2024-03-31 | 382
Active | RT-6-001-004 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-004 | C. Montag | PM | Small Number of Magnet Vendors | If the number of vendors for eSR, RCS, IR Magnets and other accelerator components is small, it may drive up the price and end up costing more than we anticipated. | High (Risk is likely to occur with a probability of >40 to <65%) | 10000 | Critical | 6 | Marginal | None | 4 | 4 | 2 | 0 | 4 | 16 | High |  | 52% | 5200 | Mitigate | Build up vendor base for magnets, diagnostics, vacuum chambers, bellows, and copper. Develop strategy to engage and qualify vendors. Applies to 6.03 and 6.04 Procurement strategy - start as early as possible to control timing. Possible CD-3a.BNL procure materials. Make/buy perhaps with other labs. |  | Q3 FY25 |  | E1102_01180 Start Construction | 25% | 20000 | 40000 | 60000 | 3 | 6 | 12 | Low | Crisis | Marginal | None | 2 | 5 | 2 | 0 | 5 | 10 | Moderate |  | The EIC needs to procure more than 3000 normal-conducting magnets of different types. While the ANL magnets for the ESR help to reduce this number by about 15 percent, the remaining quantity is still challenging. In addition, several laboratories around the world have scheduled upgrade projects in the same time frame as the EIC construction, which increases the overall demand for magnets significantly. Careful planning of the magnet procurement schedule for the EIC is absolutely necessary to reduce competition for magnet vendors within the project. However, the project has no control over the schedule of outside projects. | 10000 | 2023-10-20 | [5 empty] | 10000 |  |  | 2020-06-30 | 2020-10-30 | March 2023: Probability 50%->40% because of ANL magnets. Updated justification. | 10000 | 20000 - 40000 - 60000 | 3 - 6 - 12 | 10000 | 1.75 | 116 | 2024-03-31 | 1248
Active | RT-6-001-005 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-005 | L. Lari | PM | Escalation Increase | If the prices for procurements increase beyond the expected escalation percentages, then there will be a cost impact to the project | High (Risk is likely to occur with a probability of >40 to <65%) | 50448 | Crisis | 0 | Negligible | None | 4 | 5 | 1 | 0 | 5 | 20 | High | A 1% increase in escalation results in $86M, a 1% decrease in escalation -$82M | 52% | 26232.96 | Mitigate | Prepare Acquisition Plans and prepare procurement specifications early and work to complete the bid process and award the procurements as early as reasonable consistent with the funding profile. |  | Q1 FY25 |  | L1_090 CD-4 Approval Early Completion | 40% | 50448 | 50448 | 50448 | 0 | 0 | 0 | Moderate | Crisis | Negligible | None | 3 | 5 | 1 | 0 | 5 | 15 | High |  | Kelly Krug's analysis May 12 2022. Took the time-phased P6 plan with no escalation and applied the rates Heather developed, and then compared it to the current P6 escalation. | 20179.2 | 2024-02-20 | [5 empty] | 20179.2 |  |  | 2020-06-30 | 2020-10-30 |  | 20179.2 | 50448 - 50448 - 50448 | 0 - 0 - 0 | 20179.2 | 0 | 159 | 2024-07-31 | 1370
Active | RT-6-001-006 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-006 | S. Nagaitsev | PM | RHIC Operations beyond June 2025 | If RHIC runs are delayed and run past June of 2025, then it will prohibit access to the tunnel and cause a delayed start in any destructive construction that has to be done in the tunnel. | Very High (Risk is likely to occur with a probability of >65%) | 30000 | Critical | 12 | Significant | None | 5 | 4 | 3 | 0 | 4 | 20 | High | There will be enhanced installation cost: Installation in shifts and during weekends will increase the labor cost by factor 1.25, that is 25 M$ There might be an additional cost because we are forced to interleaving installation and commissioning/operations, and we have to train temporary staff , corresponding inefficiency is estimated with 5M$ cost increase The whole project is likely to be delayed by 3 month which would increase the “hotel load” by 3 months ~2.5 Mio$ (97M$/40) Management cost x (1+3months/10years) This adds up to ~30 M$. | 82% | 24600 | Mitigate | Start installing equipment, non destructive work only, increase density of installation schedule multiple shifts to compress schedule, cross train staff in multiple work lines, ensure sufficient infrastructure (cranes, tools, test stands) to work in parallel to leverage available staff, staged for pre-installation. Engage sPHENIX and NPP management to coordinate schedules. |  | Q1 FY26 |  | E1102_01180 Start Construction | 10% | 8600 | 18200 | 27800 | 3 | 6 | 9 | Very Low | Critical | Marginal | None | 1 | 4 | 2 | 0 | 4 | 4 | Low |  | If RHIC shut down is delayed, we assume here that we would not stick to the shutdown during the summer and we would go straight through. Assume an extra 6 months as most likely; 3 months as low; 9 months as high. Assume the hotel load per month plus some amount of other delays and the need to store material. If we saw this coming we could get ready with planning for multiple shifts. There would probably be a shift factor of 1.5x on some portion of the installation labor. | 1820 | 2023-10-20 | [5 empty] | 1820 |  |  | 2020-06-30 | 2020-10-30 |  | 1820 | 8600 - 18200 - 27800 | 3 - 6 - 9 | 1820 | 0.6 | 3 | 2024-03-31 | 1248
Active | RT-6-001-007 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-007 | L. Lari | PM | Commodity Price Fluctuations | If the cost of key commodities (e.g., copper) increases, then the cost of the project may increase. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 2000 | Significant | 0 | Negligible | Negligible | 2 | 3 | 1 | 1 | 3 | 6 | Low | New risk based on ICR team assessment. | 17% | 340 | Accept | Include in contingency calculation |  | Q3 FY25 |  | L1_090 CD-4 Approval Early Completion | 30% | 2400 | 9700 | 24170 | 0 | 0 | 0 | Moderate | Critical | Negligible | None | 3 | 4 | 1 | 0 | 4 | 12 | Moderate |  | see tab ICR-002. Relative cost impact 5-20-50%. | 2910 | 2024-02-20 | [5 empty] | 3627 |  |  | 2021-02-20 | 2021-09-27 |  | 3268.5 | 2400 - 9700 - 24170 | 0 - 0 - 0 | 3627 | 0 | ICR-002 | 2024-03-31 | 916
Active | RT-6-001-008 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-008 | L. Lari | PM | Insufficient scientific, engineering and technical human resources | ​If qualified personnel are unavailable when needed, then it will result in higher cost and schedule delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 6 | Marginal | None | 4 | 2 | 2 | 0 | 2 | 8 | Moderate | Hire Temporary staff , delay is time to hire 3-6 months depending on Personnel level. | 52% | 520 | Mitigate | Workforce planning, expedite hiring, retention bonuses, succession planning at both Labs. |  | Q1 FY25 |  | L1_090 CD-4 Approval Early Completion | 10% | 8475 | 33900 | 50850 | 3 | 12 | 18 | Very Low | Crisis | Significant | None | 1 | 5 | 3 | 0 | 5 | 5 | Low |  | This risk would come to realization if we lost a number of key personnel all at one time. The schedule risk here is a 2 month delay in having someone in place. | 3390 | 2024-02-20 | [5 empty] | 3107.5 |  |  | 2020-01-30 | 2020-03-01 | Feb 2, 2022: probability changed to 10% from 50%; cost impacts changed to $K200-200-200 from 1000-1000-1000; schedule impact changed to 2-2-2 from 6-6-6. Reason: connect to 5 review milestones. March 2023: Consolidated with risks 2 and 9. Changed title and IF/THEN. Delays changed to 3-12-18mo, cost impacts are based on $40.8M SAC | 3248.75 | 8475 - 33900 - 50850 | 3 - 12 - 18 | 3107.5 | 1.1 | 1 | 2024-03-31 | 1491
Active | RT-6-001-009 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-009 | L. Lari | PM | Removal Work at BNL | If RHIC accelerator and detector equipment is not removed by the EIC planned date, then there will be schedule delays and cost increase. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 41000 | Crisis | 12 | Significant | None | 3 | 5 | 3 | 0 | 5 | 15 | High |  | 32% | 13120 | Mitigate | Work with BNL leadership on funding and due date for removal work. |  | Q3 FY25 |  |  | 20% | 5000 | 10000 | 40000 | 6 | 9 | 12 | Low | Critical | Significant | None | 2 | 4 | 3 | 0 | 4 | 8 | Moderate |  |  | 2000 | 2024-02-20 | [5 empty] | 3666.6667 |  |  | 2023-12-20 | 2023-12-20 |  | 2833.3333 | 5000 - 10000 - 40000 | 6 - 9 - 12 | 3666.6667 | 1.8 |  | 2024-03-31 | 102
Active | RT-6-001-010 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-010 | L. Lari | PM | NYS Funding not adequate to cover planned scope | If NYS Funding is reduced or advances are delayed, then the cost of NYS funded scope (6.11 impact) would increase and schedule for the project may be delayed. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 0 | Negligible | None | 2 | 4 | 1 | 0 | 4 | 8 | Moderate | Estimated 10% reduction in funding. | 17% | 1700 | Mitigate | Actively engage with NYS funding agency. |  | TBD |  | E110104_1070 | 10% | 4800 | 4800 | 4800 | 2 | 4 | 6 | Very Low | Significant | Marginal | None | 1 | 3 | 2 | 0 | 3 | 3 | Low |  | Schedule delay would likely be due to reduced ability to obtain advances according to plan. Cost impact would be due to inability to fund contracts with DOE funds, thereby incurring a delay claim by contractor(s). | 480 | 2024-02-20 | [5 empty] | 480 |  |  | 2020-06-30 | 2020-10-30 | Feb 2023: add $4.8M cost impact | 480 | 4800 - 4800 - 4800 | 2 - 4 - 6 | 480 | 0.4 | 123 | 2024-03-31 | 1248
Active | RT-6-001-011 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-011 | L. Lari | PM | Full year CR FY25 |  | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 33900 | Crisis | 3 | Negligible | None | 3 | 5 | 1 | 0 | 5 | 15 | High |  | 32% | 10848 | Mitigate | Continue to work improving schedule and performing analysis of CR impacts. |  | Q2 FY25 |  | Funding Available FY 24-31 | 30% | 33900 | 33900 | 33900 | 12 | 12 | 12 | Moderate | Crisis | Significant | None | 3 | 5 | 3 | 0 | 5 | 15 | High |  | Cost impact is a year of standing army cost | 10170 | 2024-02-20 |  |  |  | Remove cost impact. Delay to Early Completion will result in applying hotel load costs. |  | 10170 |  |  | 2020-06-30 | 2020-10-30 | Mar 2023: Delays changed from 3mo to 12mo. Cost estimates changed from 1 500 $K to 40 800 $K | 10170 | 33900 - 33900 - 33900 | 12 - 12 - 12 | 10170 | 3.6 | 174 | 2024-03-31 | 1248
Active | RT-6-001-012 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-012 | L. Lari | PM | G&A increase | If the G& A rate increases, the cost for the project will increase on all budgeted items | High (Risk is likely to occur with a probability of >40 to <65%) | 6000 | Critical | 0 | Negligible | None | 4 | 4 | 1 | 0 | 4 | 16 | High | Based on sensitivity analysis | 52% | 3120 | Accept | Accept and include in contingency calculation. |  | Q1 FY25 |  | L1_090 CD-4 Approval Early Completion | 40% | 16300 | 16300 | 16300 | 0 | 0 | 0 | Moderate | Critical | Negligible | None | 3 | 4 | 1 | 0 | 4 | 12 | Moderate |  | Assume that the Labs will hold the rates as best they can and that a 1% increase/decrease would be the most likely. Probably best to use a 1.5% increase in Common Support (as that was the last increase we saw) as a likely scenario. That increase resulted in a $1.5M increase in project cost (as calculated in the sensitivity analysis conducted for the CD-1 review (attached). I would say $1M low and $2M likely. | 6520 | 2024-02-20 | [5 empty] | 6520 |  |  | 2020-06-30 | 2020-10-30 | April 2023: Cobra rates change analysis for G&A 1% increase, COMMON 1.5% increase | 6520 | 16300 - 16300 - 16300 | 0 - 0 - 0 | 6520 | 0 | 177 | 2024-04-30 | 1278
Active | RT-6-001-013 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-013 | L. Lari | PM | Foreign Exchange Fluctuations | If the US dollar experiences weakness against key foreign currencies (e.g., Euro), then the cost of the project in US dollar terms may increase. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 0 | Negligible | Negligible | 2 | 4 | 1 | 1 | 4 | 8 | Moderate | Assume foreign procurements are $100M, and exchange rate increases 10%. Point value for cost impact converted to a range based on a Class 5 cost ROM (-30% to +50%). No schedule impact. | 17% | 1700 | Accept | Accept |  | TBD |  | L1_090 CD-4 Approval Early Completion | 20% | -21700 | 1 | 21700 | 0 | 0 | 0 | Low | Negligible | Negligible | None | 2 | 1 | 1 | 0 | 1 | 2 | Low |  | Foreign procurement list as of Oct 2022. Assume negative 10% - zero - positive 10% change of cost for low-likely-worst case scenarios. | 0.2 | 2024-02-20 | [5 empty] | 0.066667 |  |  | 2021-02-20 | 2021-09-27 | Oct 4 2022: cost estimate changed from -8600 - 0 - 12900 to -21700 - 0 - 21700. New BOE tab ICR-001. | 0.13333 | -21700 - 1 - 21700 | 0 - 0 - 0 | 0.066667 | 0 | ICR-001 | 2024-03-31 | 916
Active | RT-6-001-014 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-014 | L. Lari | PM | Delays in securing of In-Kind Contributions | If the level of in-kind contributions is less than anticipated, then the cost of the project to DOE may increase. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 24000 | Critical | 0 | Negligible | Negligible | 2 | 4 | 1 | 1 | 4 | 8 | Moderate | Assume in-kind contributions are targeted at $242M, and contributions fall short by 10%. Point value for cost impact converted to a range based on a Class 5 cost ROM (-30% to +50%). No schedule impact. | 17% | 4080 | Mitigate | Engage Project partners |  | Q2 FY25 |  | E1102_01180 Start Construction | 30% | 3600 | 7200 | 14400 | 0 | 0 | 0 | Moderate | Critical | Negligible | None | 3 | 4 | 1 | 0 | 4 | 12 | Moderate |  | Assume in-kind contributions are targeted at $242M, and contributions fall short by 10%. Point value for cost impact converted to a range based on a Class 5 cost ROM (-30% to +50%). No schedule impact. | 2160 | 2024-02-20 | [5 empty] | 2520 |  |  | 2021-02-20 | 2021-09-27 |  | 2340 | 3600 - 7200 - 14400 | 0 - 0 - 0 | 2520 | 0 | ICR-003 | 2024-03-31 | 916
Active | RT-6-001-015 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-015 | C. Schaefer | PM | ESH Issues | If an accident occurs, then corrective actions could result in schedule delays and increased costs. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 6 | Marginal | None | 2 | 3 | 2 | 0 | 3 | 6 | Low | Based on NSLS-II experience | 17% | 850 | Mitigate | Carefully plan all work in accordance with BNL SBMS. Include safety reviews and safety review recommendations implementation in EIC resource loaded schedule. |  | Q4 FY25 |  | L1_090 CD-4 Approval Early Completion | 10% | 5000 | 5000 | 5000 | 2 | 5 | 8 | Very Low | Significant | Marginal | None | 1 | 3 | 2 | 0 | 3 | 3 | Low |  | Based on ES&H statistics for similar projects. | 500 | 2024-01-29 | [5 empty] | 500 |  |  | 2020-06-30 | 2020-10-30 | Mar 2023: owner changed from L. Stiegler to C. Schaefer. Probability 20%->10%, delays 6-6-6-> 2-5-8mo. | 500 | 5000 - 5000 - 5000 | 2 - 5 - 8 | 500 | 0.5 | 10 | 2024-03-31 | 1248
Active | RT-6-001-016 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-016 | S. Nagaitsev | PM | Insufficient Number of Special Process Spares. | If the number of required Special Process Spares is greater than currently anticipated, then the cost of the project may increase. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 0 | Negligible | Negligible | 2 | 2 | 1 | 1 | 2 | 4 | Low | Spares are targeted at $9M. Assume most likely increase is $1M. Point value for cost impact converted to a range based on a Class 5 cost ROM (-30% to +50%). No schedule impact. | 17% | 170 | Mitigate | Include in contingency calculation |  | Q4 FY32 |  | L1_090 CD-4 Approval Early Completion | 30% | 0 | 1000 | 1500 | 0 | 0 | 0 | Moderate | Significant | Negligible | None | 3 | 3 | 1 | 0 | 3 | 9 | Moderate |  | We should assume that spares will be purchased with the larger quantity of items and then transferred to OPC funding at the end of the project. Spares are targeted at $9M. Assume most likely increase is $1M. Point value for cost impact converted to a range based on a Class 5 cost ROM (-30% to +50%). No schedule impact. | 300 | 2023-10-20 | [5 empty] | 250 |  |  | 2021-02-20 | 2021-09-27 |  | 275 | 0 - 1000 - 1500 | 0 - 0 - 0 | 250 | 0 | ICR-004 | 2024-03-31 | 916
Active | RT-6-001-017 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-017 | J. Yeck | PM | Accelerator Dependencies | If accelerator dependencies at BNL are not provided as planned, then there will be schedule delays and cost increase. | Very High (Risk is likely to occur with a probability of >65%) | 40800 | Crisis | 12 | Significant | Marginal | 5 | 5 | 3 | 2 | 5 | 25 | High |  | 32% | 13056 | Mitigate | Work with BNL leadership on funding and due dates for EIC external accelerator dependencies. |  | Q4 FY25 |  | L1_090 CD-4 Approval Early Completion | 30% | 10200 | 20400 | 40800 | 3 | 6 | 12 | Moderate | Critical | Marginal | Marginal | 3 | 4 | 2 | 2 | 4 | 12 | Moderate |  | Probability estimated as moderate. Delays are 3-6-12mo for low-likely-high impacts. Cost is calculated as Standing Army Cost based on current $40.8M/year | 6120 | 2024-02-20 | [5 empty] | 7140 |  |  | 2023-12-20 | 2023-12-20 |  | 6630 | 10200 - 20400 - 40800 | 3 - 6 - 12 | 7140 | 2.1 |  | 2024-03-31 | 102
Active | RT-6-001-018 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-018 | J. Yeck | PM | Detector Dependencies | If EIC dependencies at BNL are not provided as planned, then there will be schedule delays and cost increase. | Very High (Risk is likely to occur with a probability of >65%) | 40800 | Crisis | 24 | Critical | Marginal | 5 | 5 | 4 | 2 | 5 | 25 | High |  | 32% | 13056 | Mitigate | Work with BNL leadership on funding and due dates for EIC external detector dependencies. |  | Q4 FY25 |  | L1_090 CD-4 Approval Early Completion | 30% | 20400 | 40800 | 61200 | 6 | 12 | 18 | Moderate | Crisis | Significant | Marginal | 3 | 5 | 3 | 2 | 5 | 15 | High |  | Probability estimated as moderate. Delays are 6-12-18mo for low-likely-high impacts. Cost is calculated as Standing Army Cost based on current $40.8M/year | 12240 | 2024-02-20 | [5 empty] | 12240 |  |  | 2023-12-20 | 2023-12-20 |  | 12240 | 20400 - 40800 - 61200 | 6 - 12 - 18 | 12240 | 3.6 |  | 2024-03-31 | 102
Proposed | RT-6-001-019 | Threat | 6.01 Project Management | BNL | L. Lari | RT-6-001-019 | S. Nagaitsev | PM | RCS Integration into the Tunnel | TBD
Retired | 6 | Threat | 6.01 Project Management | BNL | L. Lari / A. Lung |  | L. Lari | PM | Long Lead Procurements | TBD | [7 empty] | #N/A | [8 empty] | Mitigate | Request CD-3A approval |  |  |  |  | 20% | 5000 | 10000 | 15000 | 2 | 4 | 6 | Low | Critical | Marginal | None | 2 | 4 | 2 | 0 | 4 | 8 | Retired |  |  | Retired |  |  |  | Individual LLP risks have been developed |  |  | 2000 | No | 2023-02-24 | 2022-10-18 | 2022-10-18 | Oct 2022: First added this risk, above the individual LLP risks | 2666.6667 | n/a | n/a | n/a | n/a | 6
Retired | 2 | Threat | 6.01 Project Management | BNL | L. Lari / A. Lung |  | L. Lari | PM | Skilled Labor Shortage | If skilled designers and engineers are not available on time, there will be schedule delays. | [6 empty] | 0 | #N/A | 0 | 0 | #N/A | #N/A | #N/A |  | 0% | 0 | Mitigate | Contract with other labs and offer remote work where appropriate. |  |  |  |  | 50% | 0 | 0 | 0 | 2 | 4 | 6 | High | None | Marginal | None | 4 | 0 | 2 | 0 | 2 | 8 | Retired |  | Recent project experience | Retired |  |  |  | Consolidate with risk 1 |  |  | 0 | No | 2023-02-24 | 2022-08-30 | 2022-08-30 | Aug 2022: Added to reflect newly available IRA funding | 0 | n/a | n/a | n/a | n/a | 2
Retired | 9 | Threat | 6.01 Project Management | BNL | L. Lari / A. Lung |  | L. Lari | PM | Matrixed Labor Conflicts | If matrixed labor is not available when needed by the EIC project, it could result in delays in work that would push out the schedule. | Very High (Risk is likely to occur with a probability of >65%) | 10000 | Critical | 6 | Significant |  | 5 | 4 | 3 | 0 | 4 | 20 | High |  | 82% | 8200 | Mitigate | 1. Develop tools to understand what resources we need when. DONE 2. Detail plan all EIC work. 3. Detail plan other work at C-AD. 4. Vigorously resource level . 5. Hire dedicated EIC staff whenever possible. |  |  |  | AS_0401_9090 | 20% | 0 | 0 | 0 | 3 | 6 | 12 | Low | None | Marginal | None | 2 | 0 | 2 | 0 | 2 | 4 | Retired |  | Applies to both BNL and TJ Labor. Assume all of TJ labor is matrixed. Assume 50% of BNL labor is matrixed. Total CD-1 labor = $710M. 25% of labor = TJ = $177.5M. 75% of labor = BNL = $532.5M x 50% = 266.25. Total matrixed labor = $443.75M. Schedule delays are assumed to be 3-6-12mo for Low-Likely-Best case scenarios. | Retired |  |  |  | Consolidate with risk 1 |  |  | 0 | NO | 2023-02-24 | 2020-06-30 | 2020-10-30 | Jan 27, 2022: Probability changed to 20% from 80%. Reason - MOUs in place, schedule maturity. | 0 | 0 - 0 - 0 | 3 - 6 - 12 | 0 | 1.4 | 9
Retired | 160 | Opportunity | 6.01 Project Management | BNL | C. Lavelle / A. Lung |  | C. Lavelle | PM | JLAB Scope Rate impact | If the JLAB work scope (assume 25%) of labor in the baseline is replaced with JLAB rates, then the cost will go down | Very High (Risk is likely to occur with a probability of >65%) | -28585 | Critical | 0 | Marginal |  | 5 | 4 | 2 | 0 | 4 | 20 | High | Assume 30% of labor costs (Sept Review) with a 15% reduction in rates at 90% confidence. | 82% | -23439.7 | Accept |  |  |  |  | L2_0320 | 30% | -66600 | -76300 | -78900 | 0 | 0 | 0 | Moderate | Crisis | Negligible | None | 3 | 5 | 1 | 0 | 5 | 15 | Retired |  | See tab Risk BOE 6_01 | Retired |  |  |  | JLAB rates are in P6 as of June 2022 |  |  | -22180 | NO | 2022-07-30 | 2021-03-30 | 2021-09-27 | June 2022: Retire | -29810 | -66600 - -76300 - -78900 | 0 - 0 - 0 | -22180 | 0 | 160
Retired | 176 | Opportunity | 6.01 Project Management | BNL | C. Lavelle / A. Lung |  | C. Lavelle | PM | Escalation Reduction | If the prices for procurements decreases 1% per year beyond the expected percentages, then there will be a positive cost impact to the project | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | -82000 | Crisis | 0 | Marginal |  | 3 | 5 | 2 | 0 | 5 | 15 | High |  | 32% | -26240 | Accept | Accept and include in contingency calculation. |  |  |  |  | 5% | -39667 | -56667 | -85000 | 0 | 0 | 0 | Very Low | Crisis | Negligible | None | 1 | 5 | 1 | 0 | 5 | 5 | Retired |  |  | Retired |  |  |  | May 2022 Escalation analysis. |  |  | -3022.2333 | NO | 2022-05-05 | 2021-03-30 | 2021-09-27 | Oct 8, 2021: Probability reduced to 5% from 30%. Reason - current inflation forecasts | -3966.6833 | -39667 - -56667 - -85000 | 0 - 0 - 0 | -3022.2333 | 0 | 176
Retired | 167 | Threat | 6.01 Project Management | BNL | L. Lari / A. Lung |  | L. Stiegler | PM | COVID-19 Delay in Work | If COVID-19 continues after FY22 , then there could be impact to the project schedule. | high (Risk is likely to occur with a probability of >40 to <65%) | 1140 | Significant | 6 | Negligible |  | 4 | 3 | 1 | 0 | 3 | 12 | Moderate | Cost Estimate-10% of Nov. Monthly Cost (Nov 2020 1.9M) for 6 mos. | 52% | 592.8 | Mitigate | Work closely with BNL and JLab management and implement all COVID safety protocols. |  |  |  | L1_050 CD-3 | 10% | 0 | 0 | 0 | 3 | 5 | 10 | Very Low | None | Marginal | None | 1 | 0 | 2 | 0 | 2 | 2 | Retired |  | This is already happening….. Schedule delays would be tied to R&D activities because that is the hands on work that is going on right now. | Retired |  |  |  | Current Covid restrictions do not impact the work being done, and if stricter restrictions are re-instated, we have experience in dealing with them without impacting work. |  |  | 0 | NO | 2023-01-31 | 2021-04-30 | 2021-09-27 |  | 0 | 0 - 0 - 0 | 3 - 5 - 10 | 0 | 0.6 | 167
Retired | 179 | Threat | 6.01 Project Management | BNL | L. Lari / A. Lung |  | L. Lari | PM | Management/Oversight of in-kind Contributions | If the If the in kind contributions are not properly managed, then the project could experience significant cost or schedule impacts. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 25000 | Critical | 6 | Significant | Significant | 3 | 4 | 3 | 3 | 4 | 12 | Moderate | 25M extra costs to replan and hire staff to address schedule impacts and loss of contributed labor. | 32% | 8000 | Mitigate | Document the commitments for in-kind contributions through CRADAs/MOUs that specify the agreement to meet technical specifications as well as schedule requirements. Incorporate key milestones for in-kind scope in the EIC P6 schedule to support tracking of progress and ensure integration. |  |  |  | L2_0400 | 30% | 25000 | 25000 | 25000 | 6 | 6 | 6 | Moderate | Critical | Marginal | Significant | 3 | 4 | 2 | 3 | 4 | 12 | Retired |  | 2.5M extra costs to replan and hire staff to address schedule impacts and loss of contributed labor. The cost would cover an additional dedicated individual for this. High estimate includes an additional person. Schedule risk associated with delays. | Retired |  |  |  | Management HR is in P6. |  |  | 7500 | NO | 2023-02-24 | 2020-06-30 | 2020-10-30 |  | 10000 | 25000 - 25000 - 25000 | 6 - 6 - 6 | 7500 | 1.8 | 179
Retired | 40 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / T. Satogata |  | M. Blaskiewicz | AD | Accelerator Physics | Proton Emittance Growth Observed with Finite Crab Frequency | High (Risk is likely to occur with a probability of >40 to <65%) | 10000 | Critical |  | Negligible | Marginal | 4 | 4 | 1 | 2 | 4 | 16 | High |  | 52% | 5200 | Mitigate | Task force has been assembled and is devoting 3FTEs to this problem. |  | CDR - Task Force complete by Sept, problem studied for additional year, should be addressed by CD-2. | [9 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Retired TO BE COMPLETED |  |  | 0 | NO | 2020-11-19 | 2019-02-20 | 2019-03-30 |  | 0 | - - | - - | 0 | 0 | 40
Retired | 33 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / Q. Wu |  | H. Witte | SC_MAG | IR Magnet Prototype Maturity | If the R&D Magnet Prototype construction is started before the design is fully mature and vetted, the successful completion could be jeopardized leading to additional cost and delays. | [7 empty] | #N/A | [8 empty] | Mitigate | Start R&D magnet prototype effort once design is fully mature and reviewed. |  |  |  | RD_0303_2359 | 90% | 1000 | 2000 | 4000 | 3 | 6 | 12 | Very High | Significant | Marginal | None | 5 | 3 | 2 | 0 | 3 | 15 | Retired |  | Engineering judgement | Retired |  |  |  | Not accepted | [5 empty] | 2022-10-18 | Not accepted |  | 2700 | 1000 - 2000 - 4000 | 3 - 6 - 12 | 0 | 6.3 | 30
Retired | 31 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / Q. Wu |  | H. Witte | SC_MAG | IR Magnet Prototype Completion | If the R&D Magnet Prototype is not constructed and tested before CD-2, performance issues of the IR magnets may be realized too late and the KPPs may need to be adjusted. | [7 empty] | #N/A | [8 empty] | Mitigate | Complete successful R&D magnet test before CD-2 |  |  |  | RD_0303_3310 | 95% | 1500 | 2000 | 3000 | 1 | 3 | 6 | Very High | Significant | Negligible | None | 5 | 3 | 1 | 0 | 3 | 15 | Retired |  | Engineering judgement | Retired |  |  |  | Risk didn't make it to the active status. The R&D Magnet Prototype WAS NOT constructed and tested before CD-2, so the IF event became reality. |  |  |  | YES |  | 2022-10-18 |  |  | 2691.6667 | 1500 - 2000 - 3000 | 1 - 3 - 6 | 0 | 3.1667 | 31
Retired | 79 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / T. Satogata |  | C. Montag | AD | Inadequate Momentum Aperture in the ESR | If we can't get adequate momentum aperture on or before CD-2, we will have reduced luminosity and won't be able to meet the likely objective KPPs of the EIC. | Very Low (There is a <10% chance that this event will occur) | 10000 | Critical | 0 | Negligible | Marginal | 1 | 4 | 1 | 2 | 4 | 4 | Low |  | 5% | 500 | Mitigate | FY20 change of injection scheme from longitudinal to on-axis. This resulted in a lower requirement and lower probability of risk realization. |  | Revisit upon completion of task force report expected Q1FY21. |  | None - no cost or sched. Impact | 10% | 0 | 0 | 0 | 0 | 0 | 0 | Very Low | None | Negligible | Significant | 1 | 0 | 1 | 3 | 3 | 3 | Retired |  |  | Retired |  |  |  | We have generated ESR lattices with sufficient momentum acceptance, demonstrated by dynamic aperture optimization and tracking. |  |  | 0 | NO | 2022-10-15 | 2020-06-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 79
Retired | 80 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / T. Satogata |  | M. Blaskiewicz | AD | Failure to Design a 90 Degree Lattice for 18GeV | If we can't design a 90-degree lattice for 18GeV by CD-2, we won't be able to reach the likely objective KPPs related to the luminosity required. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 0 | Negligible | Marginal | 3 | 4 | 1 | 2 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | FY20 task force updating design optics to accommodate dynamic aperture for 90-degree lattice. |  | Revisit upon completion of task force report expected Q1FY21. |  | HR_0100_1540 | 30% | 1000 | 2000 | 5000 | 0 | 0 | 0 | Moderate | Significant | Negligible | Marginal | 3 | 3 | 1 | 2 | 3 | 9 | Retired |  |  | Retired |  |  |  | 90 Degree Lattice for 18GeV has been designed |  |  | 800 | NO | 08.24.22 | 2020-06-30 | 2020-10-30 | Aug 24 2022: risk retired, design complete | 1000 | 1000 - 2000 - 5000 | 0 - 0 - 0 | 800 | 0 | 80
Retired | 88 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / T. Satogata |  | M. Blaskiewicz | AD | Electron Polarization | If predicted electron polarization is inadequate at or before CD-2, then additional technical measures, such as beam based alignment or additional snake, need to be included in the design which will increase the cost. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 15000 | Critical | 0 | Negligible | Marginal | 3 | 4 | 1 | 2 | 4 | 12 | Moderate |  | 32% | 4800 | Mitigate | FY20 task force is evaluating alternatives for additional electron snake design. Extension of task force may be needed. |  | Revisit upon completion of task force report expected Q1FY21. | [9 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Beam based alignment is in the design. Harmonic bumps are in the design. |  |  | 0 | NO | 2021-07-28 | 2020-06-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 88
Active | RT-6-002-001 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / Q. Wu | RT-6-002-001 | H. Witte | SC_MAG | IR Prototype collared magnet does not meet performance | If the R&D Magnet Prototype fails to meet the performance requirements, the reasons need to be investigated and the design might need to be changed leading to delays and additional costs. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 6 | Marginal | None | 4 | 2 |  | 0 |  |  | Low |  |  |  | Accept | Use contingency |  | Q3 FY25 |  | E0203_09650 Q1ABpF Complete | 50% | 500 | 1000 | 1500 | 3 | 6 | 12 | High | Significant | Marginal | Significant | 4 | 3 | 2 | 3 | 3 | 12 | Moderate |  | Engineering judgement | 500 | 2024-01-24 | [5 empty] | 500 |  |  | 2022-10-18 | 2022-10-18 |  | 500 | 500 - 1000 - 1500 | 3 - 6 - 12 | 500 | 3.5 | 404 | 2024-03-31 | 530
Active | RT-6-002-002 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / Q. Wu | RT-6-002-002 | H. Witte | SC_MAG | Complete R&D prototype collared magnet failure | If the R&D magnet prototype construction fails at a fundamental level, the reasons need to be investigated and remedies have to be implemented leading to substantial delays and costs. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 3000 | Significant | 12 | Significant | None | 3 | 3 |  | 0 |  |  | Low |  |  |  | Accept | Use contingency |  | Q3 FY25 |  | E0203_09650 Q1ABpF Complete | 25% | 2000 | 3000 | 5000 | 6 | 12 | 18 | Low | Significant | Significant | Critical | 2 | 3 | 3 | 4 | 4 | 8 | Moderate |  | Engineering judgement | 750 | 2024-01-24 | [5 empty] | 833.3333 |  |  | 2022-10-18 | 2022-10-18 |  | 791.6667 | 2000 - 3000 - 5000 | 6 - 12 - 18 | 833.3333 | 3 | 405 | 2024-03-31 | 530
Retired | RT-6-002-003 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / T. Satogata |  | M. Blaskiewicz | VAC | Fast Ion Instability | If the vacuum conditions are poor during commissioning, we may see the fast ion instability in the electrons which will blow up the protons and likely lead to an impact on objective KPPs related to luminosity. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1 | Negligible | 0 | Negligible | Significant | 2 | 1 | 1 | 3 | 3 | 6 | Low |  | 17% | 0.17 | Mitigate | Work with vacuum group to minimize likelihood. |  | TBD |  | TBD | 20% | 1 | 1 | 10 | 0 | 3 | 6 | Low | Negligible | Negligible | Significant | 2 | 1 | 1 | 3 | 3 | 6 | Retired |  | Engineering Judgment | Retired |  |  |  | Design changes have dropped the pressure in the electron storage ring to safe levels |  |  | 0.8 | NO | 2024-01-10 | 2020-06-30 | 2020-10-30 |  | 0.5 | 1 - 1 - 10 | 0 - 3 - 6 | 0.8 | 0.6 | 83 | 2023-11-30 | 1126
Retired | RT-6-002-004 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / T. Satogata | RT-6-002-004 | C. Hetzel | VAC | Vacuum Channel Welding | If vacuum channel welding is not successful, then it could be necessary to perform ebeam welding, which is more expensive than TIG welding and therefore a cost risk. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 100 | Negligible | 0 | Negligible | Marginal | 3 | 1 | 1 | 2 | 2 | 6 | Low |  | 32% | 32 | Mitigate | Coordinate with the design group |  | Q3 FY24 |  | E0405_01300 PDR: ESR Arc Vacuum Chambers - Preliminary Design Review Complete | 30% | 150 | 250 | 300 | 0 | 0 | 6 | Moderate | Negligible | Negligible | Marginal | 3 | 1 | 1 | 2 | 2 | 6 | Retired |  | Engineering judgement | Retired | 2024-01-29 |  |  | There have been many changes to the ESR chamber design with the switch to NEG coating and EB welding or soldering will have to be used to join the cooling tubes to the vacuum chamber. This will be reflected in the baseline cost. |  |  | 70 | NO | 2024-01-29 | 2020-06-30 | 2020-10-30 |  | 72.5 | 150 - 250 - 300 | 0 - 0 - 6 | 70 | 0.6 | 106 | 2023-12-30 | 1156
Retired | RT-6-002-005 | Threat | 6.02 Accelerator Development and R&D | BNL | M. Blaskiewicz / T. Satogata |  | M. Blaskiewicz | AD | Feedback Noise in the ESR | If noise from the feedback system is too large by CD-2, then the electrons will blow up the hadron beam, which will impact the likely objective KPPs related to the luminosity. | Very Low (There is a <10% chance that this event will occur) | 100 | Negligible | 0 | Negligible | Marginal | 1 | 1 | 1 | 2 | 2 | 2 | Low |  | 5% | 5 | Mitigate | Research low noise BPMs. |  | Q1 FY26 |  | E0202_05580 FY25 - ESM - Document Algorithm Trouble Shooting - Controls, Instrumentation, & LLRF Systems Results in a Tech Note | 5% | 100 | 100 | 1000 | 0 | 0 | 0 | Very Low | Negligible | Negligible | Significant | 1 | 1 | 1 | 3 | 3 | 3 | Retired |  | Engineering judgement | Retired |  |  |  | No feedback will be required during luminosity production so there is no |  |  | 20 | NO | 2024-01-10 | 2020-06-30 | 2020-10-30 |  | 12.5 | 100 - 100 - 1000 | 0 - 0 - 0 | 20 | 0 | 81 | 2023-11-30 | 1126
Retired | 12 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames |  | V. Ranjbar | PD | RCS Polarization Transmission | If we achieve less than 95% polarization at 18GeV, it impacts our ultimate key performance parameters. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 2500 | Significant | 0 | Negligible | Marginal | 2 | 3 | 1 | 2 | 3 | 6 | Low |  | 17% | 425 | Mitigate | Partial snake added |  |  |  | EJ_0305_3020 | [7 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | risk of the feedback system causing harm. |  |  | 0 | NO | 2021-06-06 | 2020-06-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 12
Retired | 13 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames |  | V. Ranjbar | AD | Electron Ion Insufficient Performance | If the polarized electron gun, which is carried over from the corresponding R&R effort, does not deliver sufficient charge, then an alternative method must be used and the cost for this is not taken into account. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 7000 | Critical | 6 | Negligible |  | 2 | 4 | 1 | 0 | 4 | 8 | Moderate |  | 17% | 1190 | Mitigate | [12 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | There is now money in the current budget to build a new gun since it was anticipated that the existing gun might not be able to deliver the full charge necessary I think it was designed under R&D during the linac-Ring days for 5 nC but now we need 7nC. So in the budget John and Erdong already have funds for the rebuild. |  |  | 0 | NO | 2020-10-30 | 2020-02-20 | 2020-03-01 |  | 0 | - - | - - | 0 | 0 | 13
Retired | 147 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames |  | V. Ranjbar | PD | Pulsed Devices | Kicker Performance into the ESR | Very Low (There is a <10% chance that this event will occur) |  |  |  |  | Critical | 1 | #N/A | 0 | 4 | #N/A | #N/A | #N/A |  | 5% | 0 | Mitigate | R&D for this area at BNL and other labs is in the project baseline. | [11 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | If the fast kicker cannot inject bunches spaced at 10 ns THEN we increase our bunch spacing which decreases luminosity. |  |  | 0 | NO | 2020-11-19 | 2020-03-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 147
Retired | 148 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames |  | V. Ranjbar | AD | Instability in the RCS if Accumulator Ring is Utilized | If the kicker does not work and if instability in the RCS is not suppressed THEN we would add more linac after the accumulator. This would add more cost. | Very Low (There is a <10% chance that this event will occur) | 11000 | Critical | 6 | Marginal | Marginal | 1 | 4 | 2 | 2 | 4 | 4 | Low |  | 5% | 550 | Mitigate | Increase the dynamic aperture |  |  |  | EJ_0305_3020 | [7 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Retired in July 2021 since this risk is based on an extremely low risk of the RF kicker not working. |  |  | 0 | NO | 2021-07-07 | 2020-06-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 148
Retired | 180 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames |  | V. Ranjbar | AD | Supply of Photocathode Wafers for Polarized Gun | If commercial supply of wafers for the polarized gun are not sufficient we will have to invest to help develop the manufacturing capacity for these wafers. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 0 | Negligible | Negligible | 4 | 3 | 1 | 1 | 3 | 12 | Moderate |  | 52% | 1040 | Mitigate | Work with Commercial vendors to help them develop capacity. Invest in development of manufacturing capacity. |  |  |  | EJ_0402_6225 | 5% | 0 | 0 | 0 | 0 | 0 | 0 | Very Low | None | Negligible | Negligible | 1 | 0 | 1 | 1 | 1 | 1 | Retired |  |  | Retired | Could be retired in July 2021 since this risk only affects ultimate KPP, but it's useful to track this risk. Residual cost & sched. Impacts set to zero. |  | Could be retired in July 2021 since this risk only affects ultimate KPP, but it's useful to track this risk. Residual cost & sched. Impacts set to zero. | Retired Nov 18 2021. Found the supplier. |  |  | 0 | NO | 2021-11-18 | 2020-06-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 180
Retired | RT-6-003-001 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-001 | J. Skaritka | INJ | 400 MeV Linac Delivery is late | If 400 MeV Linac experiences production delays, then there will be project schedule delays and cost increase. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 150 | Negligible | 9 | Significant | None | 2 | 1 | 3 | 0 | 3 | 6 | Low |  |  |  | Mitigate | Close communication with vendor. |  | Q1 FY26 |  | E0304_03200 400 MeV Linac - Delivery Milestone (Vendor) | 5% | 100 | 150 | 250 | 3 | 9 | 18 | Very Low | Negligible | Significant | None | 1 | 1 | 3 | 0 | 3 | 3 | Retired |  | The gradual cost increases with increasing delays in LINAC delivery and or commissioning is based on the rational that additional program oversite, in person travel, some inefficiencies and additional work for BNL stall will be required to support the program while we wait upon LINAC system delivery and or commissioning under three different and progressively worsening delay scenarios . | Retired | 2024-09-24 |  |  | latest technical decisions resulted in delays |  |  | 8.3333 | YES | 2024-09-24 | 2022-11-30 | 2022-11-30 |  | 7.9167 | 100 - 150 - 250 | 3 - 9 - 18 | 8.3333 | 0.5 | LLP_6.03_1 | 2024-03-31 | 487
Active | RT-6-003-002 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-002 | S. Philip | NC_MAG | RCS Dipole Magnets First Article Delay | If RCS Dipole FA contract is delayed and/or vendor experiences production delays, then it will negatively impact the project schedule | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 9 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Work with procurement to award the contract on time; good communication with vendors. |  | Q3 FY25 |  | need MS after E0402_01645 | 40% | 0 | 0 | 0 | 3 | 6 | 12 | Moderate | None | Marginal | None | 3 | 0 | 2 | 0 | 2 | 6 | Low |  | Probability is estimated as moderate. No cost impacts. Delays stem from uncertainties with foreign vendors, vendor quality, vendor availability, tech challenges. | 0 | 2024-03-26 | [5 empty] | 0 |  |  | 2023-01-02 | 2023-01-04 |  | 0 | 0 - 0 - 0 | 3 - 6 - 12 | 0 | 2.8 | LLP_6.03_2 | 2024-03-31 | 452
Active | RT-6-003-003 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-003 | S. Philip | NC_MAG | RCS Dipole Magnet First Article Requires Modifications | If RCS Dipole First Article tests identify issues, then it will negatively impact the project cost & schedule | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 50 | Negligible | 3 | Negligible | None | 3 | 1 | 1 | 0 | 1 | 3 | Low |  | 32% | 16 | Mitigate | Have an activity in P6 for addressing issues found in tests. |  | Q1 FY26 |  | E0302_07260 is not there, need new connection | 20% | 40 | 50 | 60 | 1 | 3 | 5 | Low | Negligible | Negligible | None | 2 | 1 | 1 | 0 | 1 | 2 | Low |  | Probability is estimated as low. Cost and schedule impacts are estimated based on the current design and most recent project experience. | 10 | 2024-03-26 | [5 empty] | 10 |  |  | 2023-01-02 | 2023-01-06 |  | 10 | 40 - 50 - 60 | 1 - 3 - 5 | 10 | 0.6 | LLP_6.03_3 | 2024-03-31 | 450
Active | RT-6-003-004 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-004 | V. Ranjbar | PS | Power Supply Footprint | If the power supply footprint increases, there will be an increase in associated building costs. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 0 | Negligible | Negligible | 2 | 4 | 1 | 1 | 4 | 8 | Moderate |  | 17% | 1700 | Accept |  |  | Q4 FY33 |  | E0302_12472 | 10% | 5000 | 10000 | 15000 | 0 | 0 | 0 | Very Low | Critical | Negligible | None | 1 | 4 | 1 | 0 | 4 | 4 | Low |  | Engineering judgement | 1000 | 2023-10-20 | [5 empty] | 1000 |  |  | 2020-06-30 | 2020-10-30 |  | 1000 | 5000 - 10000 - 15000 | 0 - 0 - 0 | 1000 | 0 | 15 | 2024-03-31 | 1248
Retired | RT-6-003-005 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-005 | V. Ranjbar | INF | Reconfigure/rebuild the IR12 Central Tunnel to provide space for RCS to ESR Transfer Systems. | If the IR12 central tunnel area is not reconfigured and rebuilt to provide lateral space for the EIC RCS to ESR beam lines and transfer systems then the systems will have to be moved to another location. If the IR12 rebuild is delayed, it will delay the overall installation schedule. | [7 empty] | #N/A | [8 empty] | Mitigate | If the IR12 tunnel is not rebuilt, then an alternative location will be needed for the RCS to ECR transfer. At this time there are no open locations in either ring lattice around the ring. This would be a significant redesign effort that may not provide a closed lattice. Other mitigation would be to complete the central tunnel rebuild/reconfiguration in 2024 prior to the end of the RHIC run program. |  | TBD |  | not linked | 1% | 1 | 1 | 1 | 1 | 1 | 1 | Very Low | Negligible | Negligible | None | 1 | 1 | 1 | 0 | 1 | 1 | Retired |  |  | Retired |  |  |  | The IR12 Central Tunnel needs to be reconfigured to provide space for RCS to ESR Transfer Systems. There is no other solution that has been put forward. |  |  | 0.01 | YES | 2023-10-23 | 2022-10-20 | 2022-10-20 |  | 0.01 | 1 - 1 - 1 | 1 - 1 - 1 | 0.01 | 0.01 | 60
Active | RT-6-003-006 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-006 | H. Witte | NC_MAG | RCS Magnets Field Quality | If the field quality requirements for the RCS magnets are tighter than assumed, then shimming and magnet sorting may become necessary leading to delays and cost increase. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 6 | Marginal | None | 4 | 3 | 2 | 0 | 3 | 12 | Moderate |  | 52% | 1040 | Mitigate |  |  | Q3 FY27 |  | E0302_05930 Magnetic Measurement Complete - AS09 | 40% | 1000 | 2000 | 3300 | 3 | 6 | 12 | Moderate | Significant | Marginal | None | 3 | 3 | 2 | 0 | 3 | 9 | Moderate |  | Engineering judgement | 800 | 2024-01-24 | [5 empty] | 840 |  |  | 2022-10-18 | 2022-10-18 |  | 820 | 1000 - 2000 - 3300 | 3 - 6 - 12 | 840 | 2.8 | 406 | 2024-03-31 | 530
Retired | RT-6-003-007 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-007 | J. Skaritka |  | 400 MeV Linac Procurement Needs More Project Labor Support | If Linac vendor requires more engineering support due to unexpected technical issues, then the project will provide more support that will increase cost. | [7 empty] | #N/A | [8 empty] | Mitigate | Work closely with Linac vendor to resolve issues early |  | Q3 FY25 |  | TBD | 20% | 100 | 200 | 400 | 0 | 0 | 0 | Low | Negligible | Negligible | None | 2 | 1 | 1 | 0 | 1 | 2 | Retired |  | Assume 0.75 - 1.5 - 2.5 FTE of a senior engineer for low-likely-high cost impacts. Assume no schedule delay since additional support will result in all issues resolution on time. | Retired |  |  |  | 2 FTE’s of labor and additional travel budget was approved to be added for EIC support of the 400MeV Linac Systems procurement. |  |  | 46.6667 | NO | 2023-07-20 | 2023-06-28 | 2023-07-11 |  | 43.3333 | 100 - 200 - 400 | 0 - 0 - 0 | 46.6667 | 0
Retired | RT-6-003-008 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-008 | J. Skaritka |  | 400 MeV Linac Final Design is Delayed | [8 empty] | #N/A | [8 empty] | Mitigate |  |  |  |  | EJ_0401_2224 400 MeV LINAC – FDR/MRR – Final Design Review Complete (Vendor) | 20% | 0 | 0 | 0 | 1 | 2 | 4 | Low | None | Negligible | None | 2 | 0 | 1 | 0 | 1 | 2 | Retired |  | Probability is estimated low. Delays are estimated based on most recent project experience. | Retired |  |  |  | 2 FTE’s of labor and additional travel budget was approved to be added for EIC support of the 400MeV Linac Systems procurement. |  |  | 0 | NO | 2023-08-20 | 2023-08-15 | 2023-08-15 |  | 0 | 0 - 0 - 0 | 1 - 2 - 4 | 0 | 0.46667
Proposed | RT-6-003-009 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-009 | V. Ranjbar | INJ | 400 MeV LINAC doesn't meet RCS reqs
Proposed | RT-6-003-010 | Threat | 6.03 Electron Injector | BNL | V. Ranjbar / J. Grames | RT-6-003-010 | V. Ranjbar | INJ | RCS performance doesn't meet ESR reqs
Retired | RO-6-004-001 | Opportunity | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev |  | C. Montag | NC_MAG | APS quadrupoles and sextupoles are suitable for the ESR | If the APS quadrupoles and sextupoles are suitable for the ESR, we will use them throughout the ring where possible. This will reduce the cost and mitigate the risk of schedule delays. | [7 empty] | #N/A | [8 empty] | Enhance | Perform early APS magnets tests |  | Q2 FY24 |  | SR_0200_2220 ESR Sextupole - Magnet II - Fabrication | 75% | -6000 | -3500 | -8000 | -6 | -12 | -18 | Very High | Significant | Significant | None | 5 | 3 | 3 | 0 | 3 | 15 | Retired |  | Latest Project Experience | Retired |  |  |  | Opportunity realized |  |  | -4375 | YES | 2023-12-15 | 2022-12-08 | 2022-12-08 | March 2023: change HERA to APS | -3500 | -6000 - -3500 - -8000 | -6 - -12 - -18 | -4375 | -9 | 19_LLP | 2023-11-30 | 357
Active | RT-6-004-001 | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-001 | C. Hetzel | VAC | Vacuum Fab Facility Delivery Delay | If the Vacuum Fab Facility is not operational by the time when the vacuum chambers arrive, then the project will experience schedule delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 9 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  |  |  | Mitigate | Request CD-3B approval |  | Q3 FY25 |  | E0202_05580 | 40% | 0 | 0 | 0 | 3 | 9 | 12 | Moderate | None | Significant | None | 3 | 0 | 3 | 0 | 3 | 9 | Moderate |  | Engineering estimates | 0 | 2024-01-29 | [5 empty] | 0 |  |  | 2023-01-09 | 2023-01-09 |  | 0 | 0 - 0 - 0 | 3 - 9 - 12 |  | 3.2 | LLP_6.04_1 | 2024-03-31 | 447
Retired | RT-6-004-002 | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-002 | Zack Conway | AD | Beam Loading in SRF cavities | If beam loading effects with the design beam parameters are unacceptable, then we have to operate using a different, less aggressive parameter set with a different bunch pattern, reduced number of bunches, and/or reduced bunch intensity. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 1 | Negligible | 0 | Negligible | Marginal | 2 | 1 | 1 | 2 | 2 | 4 | Low |  | 17% | 0.17 | Mitigate | Cavity design optimization via R&D. develop feedback control systems. |  | TBD |  | RD_0202_1260 Transient beam loading in ESR 2 | 20% | 500 | 750 | 1000 | 0 | 0 | 0 | Low | Significant | Negligible | Marginal | 2 | 3 | 1 | 2 | 3 | 6 | Retired |  | Engineering judgement | Retired |  |  |  | Accelerator performance/design requirements within this risk scope are addressed in existing calculations (Themis M.) Hardware risks are accounted for under 6.08 |  |  | 150 | NO | 2024-01-29 | 2020-06-30 | 2020-10-30 |  | 150 | 500 - 750 - 1000 | 0 - 0 - 0 | 150 | 0 | 16 | 2023-11-30 | 1126
Active | RT-6-004-003 | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-003 | C. Hetzel | AD | Vacuum System Impedance | If the vacuum system impedance is higher than the design value required for stable operation, then the electron beam intensity has to be lowered until stability is achieved. This will impact the luminosity performance. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 0 | Negligible | None | 3 | 2 | 1 | 0 | 2 | 6 | Low |  | 32% | 320 | Mitigate | Additional simulations and light source testing to validate simulations. |  | Q2 FY25 |  | RD_0309_1580 Vacuum Design ready for PDR (CD-2) | 30% | 1000 | 1500 | 2000 | 0 | 0 | 6 | Moderate | Significant | Negligible | Marginal | 3 | 3 | 1 | 2 | 3 | 9 | Moderate |  | Engineering judgement | 450 | 2024-01-29 | [5 empty] | 450 |  |  | 2020-06-30 | 2020-10-30 |  | 450 | 1000 - 1500 - 2000 | 0 - 0 - 6 | 450 | 0.6 | 17 | 2024-03-31 | 1248
Active | RT-6-004-004 | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-004 | C. Montag | MAP | Detector Background During Bunch Replacement | If the detector background during electron bunch replacement is too high to safely operate the detector during this process, then continuous bunch replacement at approximately 1 Hz cannot be performed. This will impact the performance of the collider. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 0 | Negligible | Significant | 2 | 2 | 1 | 3 | 3 | 6 | Low |  | 17% | 85 | Mitigate | Do more extensive simulations. |  | Q2 FY25 |  | RD_0201_2580 Beam commission support | 20% | 250 | 500 | 750 | 0 | 0 | 0 | Low | Significant | Negligible | Significant | 2 | 3 | 1 | 3 | 3 | 6 | Low |  | Engineering judgement | 100 | 2024-01-29 | [5 empty] | 100 |  |  | 2020-06-30 | 2020-10-30 |  | 100 | 250 - 500 - 750 | 0 - 0 - 0 | 100 | 0 | 18 | 2024-03-31 | 1248
Retired | RT-6-004-005 | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev |  | C. Hetzel | VAC | Heating of accelerator vacuum components | If dedicated vacuum elements experience unexpected heating, then additional mitigation would be required to avoid performance impacts or equipment damage. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 2000 | Significant | 0 | Negligible | None | 3 | 3 | 1 | 0 | 3 | 9 | Moderate |  | 32% | 640 | Mitigate | R&D |  | Q2 FY25 |  | RD_0309_1580 Vacuum Design ready for PDR (CD-2) | 30% | 1500 | 2500 | 3500 | 0 | 0 | 6 | Moderate | Significant | Negligible | Negligible | 3 | 3 | 1 | 1 | 3 | 9 | Retired |  | Engineering judgement | Retired | 2024-01-29 |  |  | it should not be considered a project risk. It is really something we would have to deal with after we move to operations and increase the current to higher levels (>0.5A) |  |  | 750 | NO | 2024-01-29 | 2020-06-30 | 2020-10-30 |  | 750 | 1500 - 2500 - 3500 | 0 - 0 - 6 | 750 | 0.6 | 126 | 2023-11-30 | 1126
Active | RT-6-004-006-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-006-LLP-CD3B | H. Witte | NC_MAG | ESR Dipole Magnets Field Quality | If the performance of the ESR magnets is not sufficient, then newly designed prototypes would need to be purchased leading to delays and cost increase. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 18 | Critical | Significant | 4 | 2 | 4 | 3 | 4 | 16 | High |  | 52% | 520 | Mitigate | Get CD-3B approval and test magnets early |  | Q1 FY28 |  | E0402_04690 ESR Magnetic Measurement Complete - AS03 | 40% | 500 | 750 | 1000 | 6 | 9 | 18 | Moderate | Significant | Significant | Marginal | 3 | 3 | 3 | 2 | 3 | 9 | Moderate |  | Probability estimated as low, cost is based on P6 magnet costs for labor and material, schedule delays estimated as 6-9-18mo | 300 | 2024-01-24 | [5 empty] | 300 |  |  | 2022-10-18 | 2022-10-18 |  | 300 | 500 - 750 - 1000 | 6 - 9 - 18 | 300 | 4.4 | 407 | 2024-03-31 | 530
Active | RT-6-004-007 | Threat | 6.04 Electron Storage Ring | JLAB | C. Montag /S. Nagaitsev | RT-6-004-007 | S. Nagaitsev | PM | Radioactive waste disposal from APS girders | IF APS girder components planned to be excessed or sold as scrap, are found to be radioactive, THEN the project will have to pay additional LLRW disposal costs. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 600 | Marginal | 0 | Negligible | None | 2 | 2 | 1 | 0 | 2 | 4 | Low |  | 17% | 102 | Mitigate | Conduct radiological surveys of components from initial girders delivered to JLab and BNL promptly to verify assessments/assumptions. |  | Q2 FY25 |  | TBD | 5% | 500 | 600 | 700 | 0 | 0 | 0 | Very Low | Significant | Negligible | None | 1 | 3 | 1 | 0 | 3 | 3 | Low |  | The assessment is budgeted for at JLab and is required by waste management planning and RadCon procedures for worker safety and health so there is no additional cost. Conducting detailed RadCon surveys of all materials from all girders to reduce LLRW stream will be time consuming and will largely offset cost savings of reducing LLRW disposal. | 30 | 2024-01-24 | [5 empty] | 30 |  |  | 2023-09-01 | 2023-10-04 |  | 30 | 500 - 600 - 700 | 0 - 0 - 0 | 30 | 0 |  | 2024-03-31 | 179
Active | RT-6-004-008 | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-008 | D. Bruno | PS | ESR Main Dipole PS Low Ripple Reqs | If the ESR main Dipole PS has a low ripple requirement (0.5ppm rms) then it will result in additional cost and schedule delay. | High (Risk is likely to occur with a probability of >40 to <65%) | 1084 | Significant | 12 | Significant | None | 4 | 3 |  | 0 |  |  | Low |  |  |  | Mitigate | Investigate changing dipole wiring scheme or changing dipole magnet design to stay with less strict ripple reqs. |  | Q1 FY25 |  | E0404_01980 Main Dipole / Arc Quads / Arc Sext - Delivery | 40% | 1084 | 1084 | 1084 | 9 | 12 | 15 | Moderate | Significant | Significant | None | 3 | 3 | 3 | 0 | 3 | 9 | Moderate |  | Cost impact is $500K plus Euro 500K (more R&D cost - vendor communication). Assuming average $ to Euro rate of 0.85669, the total is $1,084K. Probability assumed moderate, schedule impacts are estimates for more R&D and additional components. | 433.6 | 2024-01-24 | [5 empty] | 433.6 |  |  | 2023-10-13 | 2023-10-13 |  | 433.6 | 1084 - 1084 - 1084 | 9 - 12 - 15 | 433.6 | 4.8 |  | 2024-07-31 | 292
Retired | 125 | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /M. Wiseman |  | C. Montag |  | Accelerator layout in the tunnel |  | low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 6 | Marginal | Marginal | 2 | 2 | 2 | 2 | 2 | 4 | Low |  | 17% | 170 | Mitigate | [5 empty] | 20% | 500 | 1000 | 5000 | 3 | 6 | 12 | Low | Significant | Marginal | Marginal | 2 | 3 | 2 | 2 | 3 | 6 | Retired |  |  | Retired |  |  |  | Layout exists |  |  | 433.3333 | NO | 2021-11-19 | 2020-06-30 | 2020-10-30 |  | 500 | 500 - 1000 - 5000 | 3 - 6 - 12 | 433.3333 | 1.4 | 125
Active | RT-6-004-009-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-009-LLP-CD3B | C. Montag | NC_MAG | Damaged APS sextupole coils | If APS sextupole coils are damaged beyond repair, then we have to procure new sextupole coils from industry. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 1800 | Significant | 12 | Significant | Crisis | 2 | 3 | 3 | 5 | 5 | 10 | Moderate |  | 17% | 306 | Mitigate | Get CD-3B approval and test sextupole coils early on to have sufficient time to procure new coils if necessary |  | Q1 FY25 |  | E0402_05985 ESR Magnets - APS Sextupole - Magnet Testing - Complete | 20% | 900 | 1800 | 2700 | 3 | 6 | 12 | Low | Significant | Marginal | None | 2 | 3 | 2 | 0 | 3 | 6 | Low |  | Probability estimated as very low. Assuming 20% of sextupole need all new coils. That's 336 coils. Cost per coil is $5380, based on PO 397730 and 397438, escalated to 2023 and doubled to take into account larger coils size | 360 | 2024-03-24 | [5 empty] | 360 |  |  | 2024-01-06 | 2024-01-08 |  | 360 | 900 - 1800 - 2700 | 3 - 6 - 12 | 360 | 1.4 |  | 2024-03-31 | 83
Active | RT-6-004-010-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-010-LLP-CD3B | S. Philip | NC_MAG | Unsuitable APS quadrupole coils | If the APS quadrupole coils are damaged beyond repair, then we have to procure new quadrupole coils from industry. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 4000 | Significant | 12 | Significant | Crisis | 2 | 3 | 3 | 5 | 5 | 10 | Moderate |  | 17% | 680 | Mitigate | Get CD-3B approval and test coils early to provide sufficient time to procure replacements |  | Q1 FY25 |  | E0403_01915 APS Magnets - Refurbishment Parts - Contract Award Batch 1 | 30% | 796 | 3076 | 6116 | 6 | 12 | 18 | Moderate | Significant | Significant | None | 3 | 3 | 3 | 0 | 3 | 9 | Moderate |  | #VALUE! | 922.8 | 2024-09-09 | [5 empty] | 998.8 |  |  | 2024-01-06 | 2024-01-08 |  | 960.8 | 796 - 3076 - 6116 | 6 - 12 - 18 | 998.8 | 3.6 |  | 2024-03-31 | 83
Active | RT-6-004-011-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-011-LLP-CD3B | G. Mahler | NC_MAG | ESR Dipole Magnets Unfavorable Steel Market | If ESR Dipole Magnets steel contract award is delayed because of tight market, or vendor fabrication is delayed, then the project will experience schedule delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 12 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Get CD-3B approval. Work with procurement to award the contract on time; good communication with vendor(s). |  | Q1 FY26 |  | E0402_01572 | 35% | 0 | 0 | 0 | 3 | 9 | 12 | Moderate | None | Significant | None | 3 | 0 | 3 | 0 | 3 | 9 | Moderate |  | Probability estimated as low. No cost impact. Schedule delays estimated 3-6-9mo for low-likely-high schedule impacts based on prior experience. | 0 | 2024-09-09 | [5 empty] | 0 |  |  | 2024-08-13 | 2024-08-13 |  | 0 | 0 - 0 - 0 | 3 - 9 - 12 | 0 | 2.8
Active | RT-6-004-012-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-012-LLP-CD3B | G. Mahler | NC_MAG | Measurement Bench for ESR Dipole Magnets Delivery Delay | If the magnet measurement bench market is tight and there are many competing customers, or a contract is placed later than planned, then the delivery will be delayed | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 12 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Get CD-3B approval. Work with procurement to award the contract on time; good communication with vendor(s). |  | Q3 FY26 |  | E0402_06162 | 20% | 0 | 0 | 0 | 2 | 4 | 6 | Low | None | Marginal | None | 2 | 0 | 2 | 0 | 2 | 4 | Low |  | Probability estimated as low. No cost impact. Schedule delays estimated 2-4-6mo for low-likely-high schedule impacts based on prior experience. | 0 | 2024-09-09 | [5 empty] | 0 |  |  | 2024-08-13 | 2024-08-13 |  | 0 | 0 - 0 - 0 | 2 - 4 - 6 | 0 | 0.8
Active | RT-6-004-012a-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-012a-LLP-CD3B | G. Mahler | NC_MAG | Measurement Bench for ESR Quad Magnets Delivery Delay | If the magnet measurement bench market is tight and there are many competing customers, or a contract is placed later than planned, then the delivery will be delayed | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 12 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Get CD-3B approval. Work with procurement to award the contract on time; good communication with vendor(s). |  | Q3 FY26 |  | E0402_03706 | 20% | 0 | 0 | 0 | 2 | 4 | 6 | Low | None | Marginal | None | 2 | 0 | 2 | 0 | 2 | 4 | Low |  | Probability estimated as low. No cost impact. Schedule delays estimated 2-4-6mo for low-likely-high schedule impacts based on prior experience. | 0 | 2024-09-27 | [5 empty] | 0 |  |  | 2024-09-27 | 2024-09-27 |  | 0 | 0 - 0 - 0 | 2 - 4 - 6 | 0 | 0.8
Active | RT-6-004-013-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-013-LLP-CD3B | G. Mahler | NC_MAG | Specialty Steel For ESR magnets: bids come back higher | If specialty steel bids come higher than planned and beyond the EU because of unforeseen market forces, there will be additional project cost. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 0 | Negligible | None | 4 | 2 | 1 | 0 | 2 | 8 | Moderate |  | 52% | 520 | Accept | Accept and include in contingency calculation. |  | Q1 FY27 |  | E0402_01627 | 25% | 300 | 600 | 1200 | 0 | 0 | 0 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Low |  | Specialty steel market is affected by the commodity price fluctuation and availability issues. Probability estimated as low, costs are 5%, 10% and 20% above planned cost | 150 | 2024-09-09 | [5 empty] | 175 |  |  | 2024-08-13 | 2024-08-13 |  | 162.5 | 300 - 600 - 1200 | 0 - 0 - 0 | 175 | 0
Active | RT-6-004-013a-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-013a-LLP-CD3B | G. Mahler | NC_MAG | Specialty Steel For ESR magnets: currency fluctuations | If foreign currency exchange rate is different at the contract award time, then the cost will be different from the planned | low (Risk is likely to occur with a probability of > 10% to < 25%) | 0 | Negligible | 0 | Negligible | None | 2 | 1 | 1 | 0 | 1 | 2 | Low |  | 17% | 0 | Accept | Accept and include in contingency calculation. |  | Q1 FY27 |  | E0402_01627 | 25% | -500 | 0 | 500 | 0 | 0 | 0 | Low | None | Negligible | None | 2 | 0 | 1 | 0 | 1 | 2 | Low |  | Probability estimated as low, cost is -10%, 0%, 10% | 0 | 2024-09-09 | [5 empty] | 0 |  |  | 2024-08-13 | 2024-08-13 |  | 0 | -500 - 0 - 500 | 0 - 0 - 0 | 0 | 0
Active | RT-6-004-013b-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-013b-LLP-CD3B | G. Mahler | NC_MAG | Specialty Steel For ESR magnets: delivery delay | If the contract is awarded later than planned and/or vendors have problems manufacturing specialty steel, then there will be schedule delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 9 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Get CD-3B approval. Work with procurement to award the contract on time; good communication with vendor(s). |  | Q1 FY27 |  | E0402_01627 | 25% | 0 | 0 | 0 | 3 | 6 | 9 | Low | None | Marginal | None | 2 | 0 | 2 | 0 | 2 | 4 | Low |  | Probability estimated as low, delays are based on planned procurement duration. | 0 | 2024-09-09 | [5 empty] | 0 |  |  | 2024-08-13 | 2024-08-13 |  | 0 | 0 - 0 - 0 | 3 - 6 - 9 | 0 | 1.5
Active | RT-6-004-013c-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-013c-LLP-CD3B | G. Mahler | NC_MAG | Specialty Steel For ESR magnets: magnetic properties | If we do not procure the steel for ALL the dipoles from one heat up front, then the dynamic aperture of the ESR and therefore the performance of the collider will be affected. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 0 | Negligible | Significant | 4 | 1 | 1 | 3 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Get CD-3B approval to procure steel for all dipoles |  | Q1 FY27 |  | Not in Monte Carlo Analysis | 25% | 0 | 0 | 0 | 0 | 0 | 0 | Low | None | Negligible | Significant | 2 | 0 | 1 | 3 | 3 | 6 | Low |  | Professional expertise | 0 | 2024-09-09 | [5 empty] | 0 |  |  | 2024-08-13 | 2024-08-13 |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0
Active | RT-6-004-014-LLP-CD3B | Threat | 6.04 Electron Storage Ring | BNL | C. Montag /S. Nagaitsev | RT-6-004-014-LLP-CD3B | G. Mahler | NC_MAG | First Production ESR Dipole Magnets | if magnet market conditions change since the last quote and a contract is placed later than planned, then there will be cost increase and schedule delay | High (Risk is likely to occur with a probability of >40 to <65%) | 3800 | Significant | 12 | Significant | None | 4 | 3 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 1976 | Mitigate | Get CD-3B approval. Work with procurement to award the contract on time; good communication with vendor(s). |  | Q4 FY27 |  | E0402_01647 | 20% | 475 | 2375 | 3800 | 3 | 9 | 12 | Low | Significant | Significant | None | 2 | 3 | 3 | 0 | 3 | 6 | Low |  | Probability estimated as low, cost is 5%, 25%, 40% of $9.5M | 475 | 2024-09-09 | [5 empty] | 443.3333 |  |  | 2024-08-13 | 2024-08-13 |  | 459.1667 | 475 - 2375 - 3800 | 3 - 9 - 12 | 443.3333 | 1.6
Retired | RO-6-005-001 | Opportunity | 6.05 Hadron Ring | BNL | V. Ptitsyn | RO-6-005-001 | D. Gassner | INS | Possibility of needing a second HSR BPM pick-up design as a potential cost saving measure | If a second HSR BPM pick-up design presents potential cost saving measure, then it will be pursued. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | -450 | Marginal | 3 | Negligible | None | 2 | 2 |  | 0 |  |  | Low |  | 17% | -76.5 | Enhance | Review coming up in the next few weeks to decide if second BPM design is needed, schedule will be taken into consideration |  | TBD |  | TBD | 10% | -450 | -450 | -450 | 3 | 3 | 3 | Very Low | Significant | Negligible | None | 1 | 3 | 1 | 0 | 3 | 3 | Retired |  | Probability is assumed low. Cost impacts are based on estimated potential saving of $500K offset by additional $50K designer & mechanical engineer labor. Delays are based on required new design time of 3mo. | Retired | 2024-08-16 |  |  | Retire (D. Gassner email from 16.08.2024) |  |  | -45 |  |  | 06.27.23 | 2023-06-27 |  | -45 | -450 - -450 - -450 | 3 - 3 - 3 | -45 | 0.3 |  | 2024-03-31 | 278
Active | RT-6-005-001 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-001 | D. Bruno | PS | Radiation Damage to the Diodes | If testing of an assumed good diode that has been removed from a magnet shows it has suffered radiation damage by measuring the forward voltage drop then the other magnet diodes may have to be replaced | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 3 | Negligible | None | 3 | 4 | 1 | 0 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | Make the study a priority |  | Q1 FY25 |  | RD_0202_1890 | 10% | 10000 | 10000 | 10000 | 2 | 3 | 5 | Very Low | Critical | Negligible | Negligible | 1 | 4 | 1 | 1 | 4 | 4 | Low |  | Engineering judgement | 1000 | 2024-01-24 | [5 empty] | 1000 |  |  | 2020-05-30 | 2020-10-30 |  | 1000 | 10000 - 10000 - 10000 | 2 - 3 - 5 | 1000 | 0.33333 | 76 | 2024-04-30 | 1278
Active | RT-6-005-002 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-002 | V. Ptitsyn | PD | Injection Kicker has to have pulse profile Flat, and be Reliable | If the injection kicker is not flat, reliable and strong, it could lead to larger emittance which would result in larger bunch size and reduced luminosity. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 0 | Negligible | Marginal | 3 | 1 | 1 | 2 | 2 | 6 | Low |  | 32% | 0 | Mitigate | Take into account during polarization and cooling design studies that the beam emittance margin might be needed R&D program |  | Q3 FY25 |  | HR_0404_1580 | 10% | 0 | 0 | 0 | 0 | 0 | 0 | Very Low | None | Negligible | Marginal | 1 | 0 | 1 | 2 | 2 | 2 | Low |  | Engineering judgement | 0 | [6 empty] | 0 |  |  | 2020-05-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 74 | 2024-03-31 | 1248
Active | RT-6-005-003 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-003 | V. Ptitsyn | PS | Inadequacy of existing power supplies and leads | If the existing power supplies are not adequate then we will need better power supplied which will impact cost. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 0 | Negligible | None | 2 | 2 | 1 | 0 | 2 | 4 | Low |  | 17% | 170 | Mitigate | Try to complete the hadron lattice sooner to identify possible PS and leads problems. Consider optics optimization to address some of the PS limits. |  | Q1 FY25 |  | RD_0201_2060 | 10% | 300 | 500 | 1000 | 0 | 0 | 0 | Very Low | Significant | Negligible | Negligible | 1 | 3 | 1 | 1 | 3 | 3 | Low |  | Engineering judgement | 50 | [6 empty] | 60 |  |  | 2020-05-30 | 2020-10-30 |  | 55 | 300 - 500 - 1000 | 0 - 0 - 0 | 60 | 0 | 152 | 2024-03-31 | 1248
Active | RT-6-005-004 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-004 | B. Gallagher | VAC | aC Coating Facility Delivery Delay | If the aC Coating Facility is not operational by the time when the beam screens arrive, then the project will experience schedule delays | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 6 | Marginal | None | 3 | 1 |  | 0 |  |  | Low |  |  |  | Mitigate | Request CD-3B approval |  | Q2 FY25 |  | HR_0500_5230 | 20% | 0 | 0 | 0 | 3 | 6 | 9 | Low | None | Marginal | None | 2 | 0 | 2 | 0 | 2 | 4 | Low |  | Engineering estimates | 0 | 2024-02-12 | [5 empty] | 0 |  |  | 2023-01-06 | 2023-01-06 |  | 0 | 0 - 0 - 0 | 3 - 6 - 9 |  | 1.2 | LLP_6.05_1 | 2024-03-31 | 450
Retired | RT-6-005-005 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-005 | V. Ptitsyn | AD | HSR Beam Screen Coating Performance | If the R&D program for the amorphous carbon coating indicates it does not provide secondary electron yield (SeY) expected or degrades over time in air needed for installation or the coating increases the surface resistivity of the copper liner; then beam tube heating will be higher and SC magnet coil temperature will be higher than required. It will require an upgrade to the cryo system to lower the coil temperature. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 0 | Negligible | Significant | 4 | 1 | 1 | 3 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Concentrate efforts on the aC coating R&D to get conclusions on the aC coating adhesion and its degradation as soon as possible. |  | Q4 FY25 |  | RD_0306_4210 | 30% | 0 | 500 | 1000 | 0 | 0 | 0 | Moderate | Significant | Negligible | Marginal | 3 | 3 | 1 | 2 | 3 | 9 | Retired |  | Engineering judgement | Retired |  |  |  | This risk was based on coating the magnet cold bore, which goes directly to the magnet coil. With the actively cooled beam screen we can increase the flow and handle higher loads. | 150 |  | 150 |  | 2024-04-12 | 2020-05-30 | 2020-10-30 |  | 150 | 0 - 500 - 1000 | 0 - 0 - 0 | 150 | 0 | 72 | 2024-03-31 | 1248
Retired | RT-6-005-006 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-006 | D. Bruno | PS | Reuse Cold Crossing Bus (CCB) in WBS 6.5.2.2 and 6.5.4.2 | If the CCB cannot be salvaged and reused due to problems with the green insulation , then we will need to purchase them. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 0 | Negligible | None | 2 | 2 | 1 | 0 | 2 | 4 | Low |  | 17% | 170 | Mitigate | Open communications with Vendor. Give vendor length of required CCB. Get cost estimates and delivery time for CCB. We have 400ft of spare CCB at BNL. Recommend modifications of cryostats so short CCB will be done |  | Q3 FY25 |  | RD_0201_2060 | 20% | 1500 | 1500 | 1500 | 0 | 0 | 0 | Low | Significant | Negligible | Negligible | 2 | 3 | 1 | 1 | 3 | 6 | Retired |  | $1200K material + $300K labor. Probability estimated as low. | Retired | 2024-01-24 |  | we have decided we will not re-use the old cold crossing bus. Realized risk is about 1.5 $M. | With the actively cooled beam screen we can increase the flow and handle higher loads. |  |  | 300 | YES |  | 2020-05-30 | 2020-10-30 |  | 300 | 1500 - 1500 - 1500 | 0 - 0 - 0 | 300 | 0 | 161 | 2024-03-31 | 1248
Active | RT-6-005-007 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-007 | V. Ptitsyn | SHC | IR 2 cooling space | if IR2 straight cannot provide sufficient space requested by cooler elements , the cooling performance will drop | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1 | Negligible | 0 | Negligible | Significant | 3 | 1 | 1 | 3 | 3 | 9 | Moderate |  | 32% | 0.32 | Mitigate | Put accent on IR2 hadron ring and cooler lattice studies to identify the problem as soon as possible. |  | Q2 FY25 |  | Tech only risk. No connection needed. | 10% | 0 | 0 | 0 | 0 | 0 | 0 | Very Low | None | Negligible | Significant | 1 | 0 | 1 | 3 | 3 | 3 | Low |  | Engineering judgement | 0 | [6 empty] | 0 |  |  | 2020-05-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 170 | 2024-04-30 | 1278
Active | RT-6-005-008 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-008 | V. Ptitsyn | AD | Electron Source | If electron source R&D cannot meet the cathode lifetime or quality requirement, we need longer time to address this difficulties | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 3 | Negligible | None | 3 | 2 | 1 | 0 | 2 | 6 | Low |  | 32% | 320 | Mitigate | Extend R&D time. |  | Q2 FY25 |  | TBD | 10% | 100 | 500 | 700 | 2 | 3 | 4 | Very Low | Significant | Negligible | Negligible | 1 | 3 | 1 | 1 | 3 | 3 | Low |  | Engineering judgement | 50 | [6 empty] | 43.3333 |  |  | 2020-05-30 | 2020-10-30 |  | 46.6667 | 100 - 500 - 700 | 2 - 3 - 4 | 43.3333 | 0.3 | 169 | 2024-03-31 | 1248
Active | RT-6-005-009 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-009 | V. Ptitsyn | SHC | Beam halo and beam | If during cooler commissioning it will be found that the beam halo is higher than predicted by simulation and analysis, and ERL cannot achieve design current, then one needs redesign the optics and redesign the beam pipe. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 12 | Significant | Significant | 3 | 2 | 3 | 3 | 3 | 9 | Moderate |  | 32% | 320 | Mitigate | Put more effort on simulation and theoretical analysis of potential sources of beam halo. |  | Q2 FY32 |  | HR_0801_1470 | 20% | 500 | 1500 | 3000 | 6 | 12 | 15 | Low | Significant | Significant | Marginal | 2 | 3 | 3 | 2 | 3 | 6 | Low |  | Engineering judgement | 300 | [6 empty] | 333.3333 |  |  | 2020-05-30 | 2020-10-30 |  | 316.6667 | 500 - 1500 - 3000 | 6 - 12 - 15 | 333.3333 | 2.2 | 171 | 2024-03-31 | 1248
Active | RT-6-005-010 | Opportunity | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-010 | V. Ptitsyn | SHC | SHC performance Issues | If further development would reveal that SHC based on the coherent electron cooling approach does not work to the required performance level, the luminosity will be below 1034cm-2s-1, unless this shortcoming is mitigated by alternative cooling schemes. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 24 | Critical | Significant | 3 | 1 | 4 | 3 | 4 | 12 | Moderate |  | 32% | 0 | Mitigate | Design low energy cooler to achieve the objective KPP (but not the ultimate KPP) |  | Q4 FY25 |  | HR_0801_1490 | 35% | -100000 | -100000 | -100000 | 0 | 0 | 0 | Moderate | Crisis | Negligible | Significant | 3 | 5 | 1 | 3 | 5 | 15 | High |  | EIC-HDR-PLN-019-The Roadmap of Electron Cooler for EIC_update_Oct2023_final.pdf | -35000 | [6 empty] | -35000 |  |  | 2020-05-30 | 2020-10-30 |  | -35000 | -100000 - -100000 - -100000 | 0 - 0 - 0 | -35000 | 0 | 183 | 2024-03-31 | 1248
Active | RT-6-005-011-LLP-CD3A | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-011-LLP-CD3A | C. Hetzel | VAC | Beam Screen Materials & Forming cannot be obtained on time | If Cu clad/P506 stainless steel cannot be obtained in time, then the beam screens availability will be delayed. | Very High (Risk is likely to occur with a probability of >65%) | 0 | Negligible | 18 | Critical | None | 5 | 1 | 4 | 0 | 4 | 20 | High |  | 82% | 0 | Mitigate | Work closely with BNL procurement and cognizant engineers to ensure timely award of contract. Regular communication with vendor. |  | Q2 FY25 |  | E0504_02280 Beam Screen Material - Ready for Profile Fabrication - CD3A Scope Complete | 50% | 0 | 0 | 0 | 6 | 9 | 12 | High | None | Significant | None | 4 | 0 | 3 | 0 | 3 | 12 | Moderate |  | Probability estimated as high because P506 vendor pool is very limited. Schedule delays estimated on recent conversations with P506 vendor. | 0 | 2024-08-13 | [5 empty] | 0 |  |  | 06.27.23 | 2023-06-27 | Aug 6, 2024: added 'Forming' to the title; changed sched. Impacts from 6-9-12 to 3-6-9mo | 0 | 0 - 0 - 0 | 6 - 9 - 12 |  | 4.5 |  | 2024-03-31 | 278
Active | RT-6-005-012 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-012 | C. Hetzel | VAC | Equipment and tooling not available for beam screen fabrication. | If the beam screen fabrication equipment and tooling is not ready for the scheduled start of beam screen production, then the beam screens will not be ready in time to support the installation schedule. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 9 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Request CD-3B(3X) approval |  | Q2 FY25 |  | TBD | 50% | 0 | 0 | 0 | 6 | 9 | 12 | High | None | Significant | None | 4 | 0 | 3 | 0 | 3 | 12 | Moderate |  | Beam screen fixturing, coating process and fabrication facility designs are still not sufficiently mature. | 0 | 2024-02-12 | [5 empty] | 0 |  |  | 06.27.23 | 2023-06-27 |  | 0 | 0 - 0 - 0 | 6 - 9 - 12 | 0 | 4.5 |  | 2024-03-31 | 278
Active | RT-6-005-013 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-013 | B. Gallagher | VAC | aC coating equipment is not ready to support the production schedule | If the horizontal coating systems are not fully qualified in time, then the beam screens will not be ready in time to support the installation schedule. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 6 | Marginal | None | 3 | 1 |  | 0 |  |  | Low |  |  |  | Mitigate | Request CD-3B approval |  | Q2 FY25 |  | TBD | 30% | 0 | 0 | 0 | 3 | 6 | 9 | Moderate | None | Marginal | None | 3 | 0 | 2 | 0 | 2 | 6 | Low |  | Prototype 3m long horizontal coating system is currently being tested. Scaling to 10m length is required for production beam screens. | 0 | 2024-02-12 | [5 empty] | 0 |  |  | 06.27.23 | 2023-06-27 |  | 0 | 0 - 0 - 0 | 3 - 6 - 9 | 0 | 1.8 |  | 2024-03-31 | 278
Active | RT-6-005-014 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-014 | B. Gallagher | VAC | aC Coating Facility: Full length horizontal coating approach is not viable | If the full length horizontal coating system is not viable, then the time required to coat a beam screen will need to be increased and the coating time for each arc will escalate. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 500 | Marginal | 9 | Significant | None | 3 | 2 |  | 0 |  |  | Low |  |  |  | Mitigate | Expedite the testing of full length horizontal coating approach. |  | Q3 FY25 |  | TBD | 20% | 250 | 500 | 750 | 6 | 9 | 12 | Low | Significant | Significant | None | 2 | 3 | 3 | 0 | 3 | 6 | Low |  | Prototype 3m long horizontal coating system is currently being tested. Scaling to 10m length is required for production beam screens. | 100 | 2024-02-12 | [5 empty] | 100 |  |  | 06.27.23 | 2023-06-27 |  | 100 | 250 - 500 - 750 | 6 - 9 - 12 | 100 | 1.8 |  | 2024-03-31 | 278
Active | RT-6-005-015 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-015 | D. Gassner | INS | BPM cryo-button: Lack of opportunity to evaluate design verification buttons before FDR | If design verification BPM cryo-buttons are not fully evaluated before the FDR, then the vendor might need to make small design changes. | High (Risk is likely to occur with a probability of >40 to <65%) | 100 | Negligible | 2 | Negligible | None | 4 | 1 |  | 0 |  |  | Low |  |  |  | Mitigate | Work closely with BNL procurement and cognizant engineers to ensure timely award of contract(s). Regular communication with vendor(s) |  | Q2 FY25 |  | TBD | 50% | 50 | 100 | 200 | 1 | 2 | 3 | High | Negligible | Negligible | None | 4 | 1 | 1 | 0 | 1 | 4 | Low |  | We expect to order the design verification buttons soon, and expect to receive them soon after the FDR | 50 | 2023-12-21 | [5 empty] | 58.3333 |  |  | 06.27.23 | 2023-06-27 |  | 54.1667 | 50 - 100 - 200 | 1 - 2 - 3 | 58.3333 | 1 |  | 2024-03-31 | 278
Active | RT-6-005-016-LLP-CD3A | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-016-LLP-CD3A | D. Gassner | INS | BPM cryo-button: Vendor fabrication problems | If BPM cryo-button vendor experiences material, and/or design, and/or fabrication problems, then it will increase the cost and delay the delivery. | High (Risk is likely to occur with a probability of >40 to <65%) | 25 | Negligible | 6 | Marginal | None | 4 | 1 | 2 | 0 | 2 | 8 | Moderate |  | 52% | 13 | Mitigate | Work closely with BNL procurement and cognizant engineers to ensure timely award of contract. Regular communication with vendors. |  | Q1 FY26 |  | E0505_02320 HSR BPM Buttons - CD3A Scope Complete | 20% | 25 | 25 | 200 | 1 | 3 | 6 | Low | Negligible | Negligible | None | 2 | 1 | 1 | 0 | 1 | 2 | Low |  | Probability is assumed low. There could be material problems, design problems, fabrication problems that would result in 1-3-6mo delays for best, likely and worst case scenarios. Cost to re-order design verification buttons ~$25k. Cost of changing the vendor ~200K. | 5 | 2024-08-13 | [5 empty] | 16.6667 |  |  | 2023-06-27 | 2023-06-27 |  | 10.8333 | 25 - 25 - 200 | 1 - 3 - 6 | 16.6667 | 0.66667 |  | 2024-03-31 | 278
Active | RT-6-005-017-LLP-CD3A | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-017-LLP-CD3A | D. Gassner | INS | BPM cryo-cables: Vendor Issues | If there are any problems with BPM cryo-cable vendor, then it will increase the cost and delay the delivery. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 12 | Significant | None | 4 | 2 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 520 | Mitigate | Work closely with BNL procurement and cognizant engineers to ensure timely award of contract(s). Regular communication with vendor(s). |  | Q3 FY25 |  | E0505_03300 HSR BPM Cryo Cables - CD3A Scope Complete | 50% | 100 | 500 | 1000 | 3 | 6 | 12 | High | Significant | Marginal | None | 4 | 3 | 2 | 0 | 3 | 12 | Moderate |  | Probability is assumed high. Cost and schedule impacts are based on the following: there are only 2 known vendors, one has a better reputation than other. If the chosen vendor has problems, there is only one other vendor to choose from. Cost is assumed to go up 40% in the worst case. | 250 | 2024-08-13 | [5 empty] | 266.6667 |  |  | 06.27.23 | 2023-06-27 |  | 258.3333 | [5 empty] | 2024-03-31 | 278
Retired | RT-6-005-018 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn |  | D. Gassner | INS | BPM cryo-cables: Late Delivery | If there are any problems with cryo-cable fabrication, then there will be delays to project schedule. | [7 empty] | #N/A | [8 empty] | Mitigate | (1) Work closely with BNL procurement and cognizant engineers to ensure timely award of contract(s), (2) Regular communication with vendor(s) |  | Q1 FY 25 HSR BPM Cryo Cables - RCV: Production Units Delivery (Arc 9) |  | TBD | 30% | 0 | 0 | 0 | 2 | 4 | 6 | Moderate | None | Marginal | None | 3 | 0 | 2 | 0 | 2 | 6 | Retired |  | Probability is assume moderate. Historically (at BNL and other labs) the delivery of SiO2 cables are later than planned. | Retired |  |  |  | Combined with risk RT-6-05-017-LLP-CD3A |  |  |  | NO | 2023-09-04 | 06.27.23 | 06.27.23 |  | 0 | 0 - 0 - 0 | 2 - 4 - 6 | 0 | 1.2
Active | RT-6-005-019 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-019 | V. Ptitsyn | VAC | Screen Coating Rate | If the screen fabrication and coating rate is longer than anticipated during R&D additional time needed to validate prototypes, then design of production systems will be delayed and the schedule will be impacted and/or the cost will go up. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 2000 | Significant | 0 | Negligible | None | 3 | 3 | 1 | 0 | 3 | 9 | Moderate |  | 32% | 640 | Mitigate | Additional Staffing , material and resources for R&D, e.g. Equipment |  | Q4 FY25 |  | RD_0306_5340 | 10% | 1000 | 2000 | 2000 | 0 | 0 | 0 | Very Low | Significant | Negligible | Negligible | 1 | 3 | 1 | 1 | 3 | 3 | Low |  | Engineering judgement | 200 | [6 empty] | 166.6667 |  |  | 2020-05-30 | 2020-10-30 |  | 183.3333 | 1000 - 2000 - 2000 | 0 - 0 - 0 | 166.6667 | 0 | 153 | 2024-03-31 | 1248
Retired | RT-6-005-020 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-020 | S. Nagaitsev | SHC | Strong Hadron Cooling Design Late | If the team cannot resolve the design challenges on Strong Hadron Cooling in a timely fashion, then design and construction of the cooling facility might be delayed and this might have an impact on project completion | High (Risk is likely to occur with a probability of >40 to <65%) | 1 | Negligible | 0 | Negligible | Marginal | 4 | 1 | 1 | 2 | 2 | 8 | Moderate | Not technical risk for KPPs and no schedule impact. | 52% | 0.52 | Mitigate | Devoting a strong, very skilled and motivated workforce. Involving worldwide experts to obtain advice on technical challenges and the path forward. Investment into a modified cooling scheme by an independent team. |  | Q1 FY25 |  | HR_0801_1490 | 40% | 5000 | 18200 | 36400 | 3 | 6 | 12 | Moderate | Critical | Marginal | Marginal | 3 | 4 | 2 | 2 | 4 | 12 | Retired |  | Plan for a strong cooling design team activity to be active until satisfactory answers for all questions have been resolved ~6FTE, plan for a team to work on dte development of a modified scheme (6FTE) until a feasible solution has been developed | Retired | 2023-10-20 |  |  | Risk triggered since SHC design is later than planned. |  |  | 7946.6667 | YES | 2024-02-10 | 2020-06-30 | 2020-10-30 |  | 7613.3333 | 5000 - 18200 - 36400 | 3 - 6 - 12 | 7946.6667 | 2.8 | 11 | 2024-03-31 | 1248
Active | RT-6-005-021 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-021 | V. Ptitsyn | AD | Solenoidal Windings addition | If in the course of further accelerator design studies or hadron beam parameter modifications the electron cloud accumulation in warm beam pipes will be found not acceptable then solenoidal windings have to be added around these pipes | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 3000 | Significant | 0 | Negligible | None | 3 | 3 |  | 0 |  |  | Low |  |  |  | Accept | Risk is accepted, no mitigation. |  | Q1 FY25 |  | HR_0203_5350 IR12 - Pre-Tunnel Assembly, Installation and Testing | 20% | 3000 | 3000 | 3000 | 0 | 0 | 0 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Low |  | Probability estimated as low. $3M is the cost to mitigate this risk by installing beam tube solenoid windings, power supplies, cables, and controls on the HSR warm drift vacuum sections in IR04, IR06, IR08, IR10, and IR12. No schedule impact. | 600 | [6 empty] | 600 |  |  | 2023-02-24 | 2023-03-13 |  | 600 | 3000 - 3000 - 3000 | 0 - 0 - 0 | 600 | 0 | 185 | 2024-03-31 | 384
Active | RT-6-005-022 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn | RT-6-005-022 | C. Hetzel | VAC | Amorphous carbon coating performance | If a sufficiently low SEY aC coating cannot be maintained throughout beam screen production then beam screens not meeting the required performance level will need to be stripped and recoated which will result in a longer than planned production time. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 6 | Marginal | Marginal | 2 | 2 | 2 | 2 | 2 | 4 | Low |  | 17% | 85 | Mitigate | Continue development of coating parameters, Constant monitoring and sampling throughout coating production, Tight process control |  | Q2 FY25 |  | Need to add a milestone after activity E0504_07480 | 20% | 300 | 500 | 1000 | 1 | 6 | 12 | Low | Significant | Marginal | Negligible | 2 | 3 | 2 | 1 | 3 | 6 | Low |  | Engineering judgement | 100 | 2024-04-16 | [5 empty] | 120 |  |  | 2024-04-16 | 2024-04-16 |  | 110 | 300 - 500 - 1000 | 1 - 6 - 12 | 120 | 1.2667 |  | 2024-03-31 | -16
Retired | 151 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn |  | J. Tuozzolo | VAC | Screen Performance during Commissioning | If the coating starts flaking during commissioning, then vacuum and beam performance may be compromised and there would be cost/schedule impacts. | Very Low (There is a <10% chance that this event will occur) | 20000 | Critical | 24 | Crisis |  | 1 | 4 | 5 | 0 | 5 | 5 | Low |  | 5% | 1000 | Mitigate | Extend R&D if there is any indication of poor coating performance, poor coating adhesion (flaking), poor coating performance (dust) or poor coating performance after exposure to air during installation. |  | Additional R&D CHECK: MAYBE TO BE REMOVED |  | PO_0304_1140 | 5% | 5000 | 10000 | 20000 | 24 | 24 | 24 | Very Low | Critical | Critical | Negligible | 1 | 4 | 4 | 1 | 4 | 4 | Retired |  |  | Retired |  |  |  | Retired | 583.3333 |  | 583.3333 | NO | 2022-08-03 | 2020-05-30 | 2020-10-30 |  | 750 | 5000 - 10000 - 20000 | 24 - 24 - 24 | 583.3333 | 1.2 | 151
Retired | 68 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn |  | V. Ptitsyn | VAC | In-Situ Pipe Coating Rate | If the In-situ pipe coating rate is longer than anticipated, the schedule will be impacted and/or the cost will go up. | Very High (Risk is likely to occur with a probability of >65%) | 40000 | Crisis | 0 | Significant |  | 5 | 5 | 3 | 0 | 5 | 25 | High |  | 82% | 32800 | Mitigate | Retired , consider new residual risks, Brainstorm new risk | [11 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Risk Workshop #3 retired by WBS 6.05 |  |  | 0 | NO | 2021-01-01 | 2020-05-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 68
Retired | 71 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn |  | V. Ptitsyn | AD | Beam Current Increase | If the current increases to 1A, then without cooling, there is a performance risk that could impact the assumed KPPs. | Low (Risk is likely to occur with a probability of > 10% to < 25%) |  |  |  |  | Significant | 2 | #N/A | 0 | 3 | #N/A | #N/A | #N/A |  | 17% | 0 | Mitigate | [12 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Initially it was introduced for a scope without hadron cooling. Present scope is fully based on strong hadron cooling and does not have this risk. |  |  | 0 | NO | 2021-05-05 | 2020-05-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 71
Retired | 168 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn |  | V. Ptitsyn | INS | Inadequacy of RHIC BLM system | If the existing RHIC Beam Loss Monitor System cannot provide the required beam loss measurements and machine protection capability, then it will need to be upgraded. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 0 | Negligible | Marginal | 3 | 2 | 1 | 2 | 2 | 6 | Low |  | 32% | 320 | Mitigate | Study the capability of the existing RHIC BLM system with the planned EIC beam parameters. This includes calculations, simulations and possibly beam tests during a RHIC run to confirm the study results. |  |  |  | IR_0301_2000 | 25% | 500 | 1000 | 2000 | 1 | 3 | 6 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Retired |  | Engineering judgement | Retired | 2024-05-16 |  |  | Risk realized |  |  | 291.6667 |  | 2024-05-16 | 2020-05-30 | 2020-05-30 |  | 375 | 500 - 1000 - 2000 | 1 - 3 - 6 | 291.6667 | 0.83333 | 168
Retired | 150 | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn |  | D. Bruno | PS | Dipole Magnet PS limit | If the existing RHIC dipole magnet power supply to be used for EIC cannot meet the top energy (275 GeV) performance goal for the EIC Hadron ring then it will have to replaced or the top energy goal reduced. | Very High (Risk is likely to occur with a probability of >65%) | 1050 | Significant | 0 | Crisis | Crisis | 5 | 3 | 5 | 5 | 5 | 25 | High | We have a quote from Applied Power Systems for this new Dipole power Supply. As long as we purchase it far enough in advance there will be no schedule impact. We also need 1 engineer working on this, 2 technicians, riggers and 2 electricians. | 82% | 861 | Mitigate | The mitigation would be to purchase a new main dipole power supply. |  | Getting files to procurement and placing the order: 1 year; Construction of PS and delivery: 1.5 years; Total 2.5 years |  | RD_0201_2060 | 10% | [6 empty] | Very Low | None |  | None | 1 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired | We are waiting for approval to put the purchase of this new power supply into the cost and schedule |  |  | New power supplies purchase was approved |  |  | 0 | NO | 2022-12-08 | 2020-05-30 | 2021-11-08 |  | 0 | - - | - - | 0 | 0 | 150
Retired | 150a | Threat | 6.05 Hadron Ring | BNL | V. Ptitsyn |  | D. Bruno | PS | Quad Magnet PS Limit | If we have a phase advance of 90 degree per cell in both planes then the Yellow Quad Main PS will have to be replaced because the current will be approximately 5485 A for the defocusing buss and 5478 A for the focusing buss which is to close to the PS max limit of 5500A | Very High (Risk is likely to occur with a probability of >65%) | 750 | Marginal | 0 | Crisis | Crisis | 5 | 2 | 5 | 5 | 5 | 25 | High | We have a quote from Applied Power Systems for this new Dipole power Supply. As long as we purchase it far enough in advance there will be no schedule impact. We also need 1 engineer working on this, 2 technicians, riggers and 2 electricians. | 82% | 615 | Mitigate | The mitigation would be to purchase a new main quad power supply. |  | Getting files to procurement and placing the order: 1 year Construction of PS and delivery: 1.5 years Total 2.5 years |  | RD_0201_2060 | 20% | [6 empty] | Low | None |  | None | 2 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired | We are waiting for approval to put the purchase of this new power supply into the cost and schedule |  |  | New power supplies purchase was approved |  |  | 0 | NO | 2022-12-08 | 2021-07-30 | 2021-11-08 |  | 0 | - - | - - | 0 | 0 | 150a
Active | RO-6-006-001 | Opportunity | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RO-6-006-001 | H. Witte | SC_MAG | High field direct wind magnets prove to be possible | If the R&D high field direct wind magnet is successful, the collared IR magnets can be replaced with direct wind magnets | Very High (Risk is likely to occur with a probability of >65%) | -15000 | Critical | -24 | Critical | Significant | 5 | 4 | 4 | 3 | 4 | 20 | High |  | 82% | -12300 | Enhance | Q1ABpF R&D Magnet included in R&D budget. |  | Q1 FY25 |  | E0203_09650 Q1ABpF Complete | 30% | -4000 | -10000 | -15000 | -12 | -18 | -24 | Moderate | Critical | Critical | Significant | 3 | 4 | 4 | 3 | 4 | 12 | Moderate |  | Engineering judgement | -3000 | 2024-03-24 | [5 empty] | -2900 |  |  | 2021-07-30 | 2021-09-27 |  | -2950 | -4000 - -10000 - -15000 | -12 - -18 - -24 | -2900 | -5.4 | 121 | 2024-04-30 | 946
Retired | RO-6-006-002-LLP-CD3A | Opportunity | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RO-6-006-002-LLP-CD3A | H. Witte | SC_MAG | Superconducting NbTi strand specification | If the specification for the superconducting NbTi strand can be relaxed, then cost and Leadtime can be reduced. | Very Low (There is a <10% chance that this event will occur) | -640 | Marginal | -6 | Marginal | Critical | 1 | 2 | 2 | 4 | 4 | 4 | Low |  | 5% | -32 | Accept | Include savings in contingency calculation |  | Q3 FY24 |  | E0602_19400 SC Strand - Collared Magnets - Delivery | 5% | -400 | -600 | -800 | -3 | -6 | -9 | Very Low | Significant | Marginal | Negligible | 1 | 3 | 2 | 1 | 3 | 3 | Retired |  | Recent engineering estimates | Retired | 2024-01-24 |  |  | Placed contract | identified after MC was done for CD-3A review |  | -30 | YES | 2024-06-08 | 2022-03-10 | 2023-03-10 |  | -30 | -400 - -600 - -800 | -3 - -6 - -9 | -30 | -0.3 |  | 2024-03-31 | 387
Active | RT-6-006-002 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-002 | A. Drees | MAP | Beam Dump System | If the present beam dump system won't be satisfactory due to secondary particles leaking out of the dump, then we would need to upgrade them which would cause a cost increase. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 0 | Negligible | None | 4 | 2 | 1 | 0 | 2 | 8 | Moderate |  | 52% | 520 | Mitigate | Replace beam pipe with thicker shielding and additional shielding for the Q4 quadrupole |  | Q1 FY26 |  | E0603_02680 | 50% | 1000 | 1000 | 1000 | 0 | 0 | 0 | High | Significant | Negligible | Marginal | 4 | 3 | 1 | 2 | 3 | 12 | Moderate |  | Engineering judgement | 500 | 2024-01-29 | [5 empty] | 500 |  |  | 2020-06-30 | 2020-10-30 |  | 500 | 1000 - 1000 - 1000 | 0 - 0 - 0 | 500 | 0 | 75 | 2024-03-31 | 1248
Retired | RT-6-006-003 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-003 | A. Drees | MAP | Abort Kicker System | If the present abort kicker system heats up with high intensity beams, then we would need to upgrade the kicker which would cause a cost increase. | High (Risk is likely to occur with a probability of >40 to <65%) | 500 | Marginal | 0 | Negligible | None | 4 | 2 | 1 | 0 | 2 | 8 | Moderate |  | 52% | 260 | Mitigate | Install and insert what can carry the image current |  | Q1 FY25 |  | E0603_03160 | 50% | 500 | 500 | 500 | 0 | 0 | 0 | High | Significant | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Retired |  | Engineering judgement | Retired | 2024-01-29 |  |  | Risk realized. |  |  | 250 | YES | 2024-05-09 | 2020-06-30 | 2020-10-30 |  | 250 | 500 - 500 - 500 | 0 - 0 - 0 | 250 | 0 | 154 | 2024-04-30 | 1278
Active | RT-6-006-004 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-004 | H. Witte | SC_MAG | Skilled Labor Not Available For Design | If skilled designers and engineers are not available on time, then there will be schedule delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 12 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  |  |  | Mitigate | Use Resource Comparison Tool to plan design work |  | Q1 FY25 |  | E0203_02280; E0203_02500; E0203_02940; E0203_03140 | 50% | 0 | 0 | 0 | 3 | 9 | 12 | High | None | Significant | None | 4 | 0 | 3 | 0 | 3 | 12 | Moderate |  | Engineering judgement | 0 | 2024-01-24 | [5 empty] | 0 |  |  | 2023-01-06 | 2023-01-06 |  | 0 | 0 - 0 - 0 | 3 - 9 - 12 |  | 4 | LLP_6.03_4 | 2024-03-31 | 450
Active | RT-6-006-005 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-005 | H. Witte | SC_MAG | Delays due to Limited Number of Magnet Vendors | If the number of magnet vendors is limited or there is competition with other projects, then magnet delivery will be late | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 18 | Critical | None | 4 | 1 | 4 | 0 | 4 | 16 | High |  |  |  | Mitigate | Evaluate all production possibilities (industry, Nat. Labs, …) |  | Q3 FY26 |  | E0602_08780; E0602_13280 | 50% | 0 | 0 | 0 | 6 | 12 | 18 | High | None | Significant | None | 4 | 0 | 3 | 0 | 3 | 12 | Moderate |  | Engineering judgement | 0 | 2024-01-24 | [5 empty] | 0 |  |  | 2023-01-06 | 2023-01-06 |  | 0 | 0 - 0 - 0 | 6 - 12 - 18 |  | 6 | LLP_6.03_5 | 2024-03-31 | 450
Active | RT-6-006-006-LLP-CD3A | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-006-LLP-CD3A | H. Witte | SC_MAG | NbTi Strand Delivery is late | If the NbTi strand delivery is later than planned, then the project schedule will be delayed. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 13 | Critical | None | 4 | 1 | 4 | 0 | 4 | 16 | High |  | 52% | 0 | Mitigate | Work closely with BNL procurement and cognizant engineers to ensure timely award of contract(s). Regular communication with vendor(s). |  | Q1 FY25 |  | E0602_19400 SC Strand - Collared Magnets - Delivery | 30% | 0 | 0 | 0 | 1 | 3 | 6 | Moderate | None | Negligible | None | 3 | 0 | 1 | 0 | 1 | 3 | Low |  | Probability is estimated as moderate, no cost impacts. Delays are estimated based on recent communications with vendor and considering the limited number of vendors worldwide. Raw material shortage can potentially cause delivery delays. | 0 | 2024-08-13 | [5 empty] | 0 |  |  | 2020-06-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 1 - 3 - 6 | 0 | 1 | 127_LLP | 2024-03-31 | 1248
Active | RT-6-006-007 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-007 | H. Witte | SC_MAG | IR SC Magnet Procurement problems | If the correct magnet procurement strategy isn’t taken and alternative lower tier magnet vendors have to be chosen, this could have a large negative impact on both cost and schedule. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 15000 | Critical | 48 | Crisis | Significant | 3 | 4 | 5 | 3 | 5 | 15 | High |  | 32% | 4800 | Mitigate | Finalize magnet specifications to begin early detail design. Hire qualified SC magnet engineers / designers to increase throughput. Write the SOW and specification and do effective vendor qualification. Procure materials such as SC strands and have cables fabricated by the Project to shorten magnet deliver schedules. (see “New Risk 1” below) Investigation of and outreach to known and new SC magnet vendors for interest / capability/ availability. Plan and stage procurements to fit availability and interest to bid of first tier vendors. Building magnets in house can allow more delivery control (note: in-house capability is limited) Plan to hold an early vendor procurement conference. (see first bullet above) |  | Q1 FY27 |  | E0602_08780 | 30% | 5000 | 15000 | 20000 | 9 | 18 | 24 | Moderate | Critical | Critical | Negligible | 3 | 4 | 4 | 1 | 4 | 12 | Moderate |  | Engineering judgement | 4500 | 2024-01-24 | [5 empty] | 4000 |  |  | 2020-06-30 | 2020-10-30 |  | 4250 | 5000 - 15000 - 20000 | 9 - 18 - 24 | 4000 | 5.1 | 23 | 2024-03-31 | 1248
Retired | RT-6-006-008 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl |  | H. Witte | SC_MAG | Use of Quads and Dipoles Needs to be Proven | If the available RHIC SC magnets can't fulfill the IR physics-matching optics requirements, new magnets will have to be purchased creating the need for the design and purchase of additional SC magnets. This will have resource, cost and schedule impact. (Note: Progress in the successfully matching the hadron ring into the IR, may allow this risk to be reduced in both cost and schedule categories). | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 12 | Marginal | Marginal | 3 | 2 | 2 | 2 | 2 | 6 | Low |  | 32% | 320 | Mitigate | Complete matching of hadron ring by 9/30/20 to determine if additional magnets will be required or existing magnets modified. Indicated costs and schedule impacts will have to be assessed and addressed at that time. (see Risk ID 23 and Risk ID 91) |  | May be moderate not high risk making good progress. |  | EJ_0201_1599 | 30% | 0 | 3000 | 5000 | 0 | 12 | 18 | Moderate | Significant | Significant | Marginal | 3 | 3 | 3 | 2 | 3 | 9 | Retired |  |  | Retired |  |  |  | Retire, can largely use RHIC magnets |  |  | 800 |  |  | 2020-06-30 | 2020-10-30 |  | 850 | 0 - 3000 - 5000 | 0 - 12 - 18 | 800 | 3 | 92
Active | RT-6-006-009 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-009 | H. Witte | SC_MAG | Complete failure single direct wind magnet | If at least one single direct wind magnet is unusable, the project cannot be completed as planned and will be delayed. | High (Risk is likely to occur with a probability of >40 to <65%) | 1500 | Significant | 12 | Significant | Critical | 4 | 3 | 3 | 4 | 4 | 16 | High | Average cost single direct wind magnet | 52% | 780 | Mitigate | Prototype R&D direct wind magnet program |  | Q2 FY30 |  | E0602_10130 - Direct Wind Magnets - Horizontal Cold Test Complete | 50% | 100 | 500 | 1500 | 0 | 9 | 12 | High | Significant | Significant | Critical | 4 | 3 | 3 | 4 | 4 | 16 | High |  | Engineering judgement | 250 | 2024-03-24 | [5 empty] | 350 |  |  | 2021-08-30 | 2021-09-27 |  | 300 | 100 - 500 - 1500 | 0 - 9 - 12 | 350 | 3.5 | 124c | 2024-03-31 | 916
Active | RT-6-006-010 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-010 | H. Witte | SC_MAG | Single direct wind magnet does not meet performance | If a single direct wind magnet fails to meet the performance requirements, the physics programme may be temporarily impacted. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 3 | Negligible | Significant | 3 | 2 | 1 | 3 | 3 | 9 | Moderate | Average cost single direct wind magnet, downgraded assuming magnet can be fixed | 32% | 320 | Accept | Use contingency |  | Q3 FY27 |  | E0602_11580 | 10% | 0 | 250 | 1000 | 0 | 0 | 12 | Very Low | Negligible | Negligible | Negligible | 1 | 1 | 1 | 1 | 1 | 1 | Low |  | Engineering judgement | 25 | 2024-01-24 | [5 empty] | 41.6667 |  |  | 2021-08-30 | 2021-09-27 |  | 33.3333 | 0 - 250 - 1000 | 0 - 0 - 12 | 41.6667 | 0.4 | 124d | 2024-03-31 | 916
Active | RT-6-006-011 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-011 | H. Witte | SC_MAG | At least one single collared magnet doesn't meet performance | If a single collared magnet fails to meet the performance requirements, the physics programme may be temporarily impacted. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 18 | Critical | Significant | 4 | 3 | 4 | 3 | 4 | 16 | High | Replacement cost collared magnet, downgraded assuming fix is possible | 52% | 1040 | Accept | Use contingency & develop response plans |  | Q1 FY30 |  | E0602_11660 | 50% | 75 | 300 | 2000 | 0 | 18 | 24 | High | Significant | Critical | Critical | 4 | 3 | 4 | 4 | 4 | 16 | High |  | Engineering judgement | 150 | 2024-03-24 | [5 empty] | 395.8333 |  |  | 2021-08-30 | 2021-09-27 |  | 272.9167 | 75 - 300 - 2000 | 0 - 18 - 24 | 395.8333 | 7 | 124e | 2024-03-31 | 916
Active | RT-6-006-012 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-012 | H. Witte | SC_MAG | Complete failure multiple direct wind magnets | If multiple direct wind magnets fail, the project cannot be completed as planned and will be delayed. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 2000 | Significant | 18 | Critical | Significant | 2 | 3 | 4 | 3 | 4 | 8 | Moderate | Average cost single direct wind magnet, downgraded assuming magnet can be fixed, assuming two magnets | 17% | 340 | Accept | Use contingency |  | Q1 FY27 |  | superseded by 124b connected to individual magnets | 5% | 4000 | 12500 | 25000 | 12 | 18 | 24 | Very Low | Critical | Critical | Significant | 1 | 4 | 4 | 3 | 4 | 4 | Low |  | Engineering judgement | 625 | 2024-01-24 |  | superseded by 124b connected to individual magnets |  |  |  | 691.6667 |  |  | 2021-08-30 | 2021-09-27 |  | 658.3333 | 4000 - 12500 - 25000 | 12 - 18 - 24 | 691.6667 | 0.9 | 124f | 2024-03-31 | 916
Active | RT-6-006-013 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-013 | H. Witte | SC_MAG | Complete failure multiple (>2) collared magnets | If multiple collared magnets fail, the project cannot be completed as planned and will be delayed. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 6000 | Critical | 24 | Critical | Significant | 2 | 4 | 4 | 3 | 4 | 8 | Moderate | Replacement cost collared magnet, downgraded assuming fix is possible, assuming two magnets | 17% | 1020 | Accept | Use contingency |  | Q1 FY27 |  | Safran simulation of individual failures | 5% | 4000 | 5000 | 10000 | 12 | 18 | 24 | Very Low | Significant | Critical | Significant | 1 | 3 | 4 | 3 | 4 | 4 | Low |  | Engineering judgement | 250 | 2024-01-24 |  | Safran simulation of individual failures |  |  |  | 316.6667 |  |  | 2021-08-30 | 2021-09-27 |  | 283.3333 | 4000 - 5000 - 10000 | 12 - 18 - 24 | 316.6667 | 0.9 | 124g | 2024-03-31 | 916
Active | RT-6-006-014 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-014 | H. Witte | SC_MAG | Multiple (>2) direct wind magnets do not meet performance | If multiple direct wind magnets fail to meet the performance requirements, the physics programme may be temporarily impacted. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 2000 | Significant | 3 | Negligible | Significant | 2 | 3 | 1 | 3 | 3 | 6 | Low | Average cost single direct wind magnet, downgraded assuming magnet can be fixed, assuming two magnets | 17% | 340 | Accept | Include in contingency calculation |  | Q1 FY27 |  | TBD | 15% | 4000 | 12500 | 25000 | 12 | 18 | 24 | Low | Critical | Critical | Significant | 2 | 4 | 4 | 3 | 4 | 8 | Moderate |  | Engineering judgement | 1875 | 2024-01-24 |  | Safran simulation of individual risks |  |  |  | 2075 |  |  | 2021-08-30 | 2021-09-27 |  | 1975 | 4000 - 12500 - 25000 | 12 - 18 - 24 | 2075 | 2.7 | 124h | 2024-03-31 | 916
Active | RT-6-006-015 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-015 | H. Witte | SC_MAG | Multiple (>2) collared magnets do not meet performance | If multiple collared magnets fail to meet the performance requirements, the physics programme may be temporarily impacted. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 4000 | Significant | 3 | Negligible | Significant | 3 | 3 | 1 | 3 | 3 | 9 | Moderate | Replacement cost collared magnet, downgraded assuming fix is possible, assuming two magnets | 32% | 1280 | Accept | Include in contingency calculation |  | Q1 FY27 |  | TBD | 15% | 4000 | 5000 | 10000 | 12 | 18 | 24 | Low | Significant | Critical | Significant | 2 | 3 | 4 | 3 | 4 | 8 | Moderate |  | Engineering judgement | 750 | 2024-01-24 |  | Safran simulation of individual risks |  |  |  | 950 |  |  | 2021-08-30 | 2021-09-27 |  | 850 | 4000 - 5000 - 10000 | 12 - 18 - 24 | 950 | 2.7 | 124i | 2024-03-31 | 916
Active | RT-6-006-016 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-016 | A. Drees | MAP | Momentum Collimation | If the detector background studies will demonstrate a need in momentum collimation, this collimation must be arranged, at additional cost. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 0 | Negligible | None | 3 | 2 | 1 | 0 | 2 | 6 | Low |  | 32% | 320 | Mitigate | Speed up studies defining the need in momentum collimation. Take into account when developing the lattice design allocating potential space for momentum collimator. |  | Q1 FY25 |  | E0603_03160 | 30% | 1000 | 1000 | 1000 | 0 | 0 | 0 | Moderate | Significant | Negligible | None | 3 | 3 | 1 | 0 | 3 | 9 | Moderate |  | Engineering judgement | 300 | 2024-01-29 | [5 empty] | 300 |  |  | 2020-06-30 | 2020-10-30 |  | 300 | 1000 - 1000 - 1000 | 0 - 0 - 0 | 300 | 0 | 78 | 2024-07-31 | 1370
Retired | RT-6-006-017 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / W. Wittmer |  | H. Witte | AD | Scope Change for IR & Detector Interface | If there are significant design changes after CD-1 in other areas of the EIC Project, it could impact the interaction region, which would change the current interaction region plans and result in significant rework. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 9 | Significant |  | 2 | 3 | 3 | 0 | 3 | 6 | Low |  | 17% | 850 | Mitigate | [5 empty] | 25% | 0 | 5000 | 10000 | 0 | 9 | 12 | Low | Significant | Significant | Significant | 2 | 3 | 3 | 3 | 3 | 6 | Retired |  |  | Retired |  |  |  | Risk realized. |  |  | 1250 | YES | 2021-07-12 | 2020-06-30 | 2020-10-30 |  | 1666.6667 | 0 - 5000 - 10000 | 0 - 9 - 12 | 1250 | 1.75 | 20
Active | RT-6-006-018 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-018 | H. Witte | SC_MAG | Complete failure single collared magnet | If a single collared magnet is unusable, the project cannot be completed as planned and will be delayed. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 3000 | Significant | 24 | Critical | Critical | 3 | 3 | 4 | 4 | 4 | 12 | Moderate | Replacement cost collared magnet | 32% | 960 | Mitigate | Prototype R&D collared magnet program |  | Q1 FY27 |  | E0602_08780 | 5% | 0 | 1000 | 3000 | 0 | 0 | 24 | Very Low | Significant | Negligible | Significant | 1 | 3 | 1 | 3 | 3 | 3 | Low |  | Engineering judgement | 50 | 2024-01-24 | [5 empty] | 66.6667 |  |  | 2021-07-30 | 2021-09-27 |  | 58.3333 | 0 - 1000 - 3000 | 0 - 0 - 24 | 66.6667 | 0.4 | 124b | 2024-03-31 | 916
Active | RT-6-006-019 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-019 | A. Drees | MAP | HSR abort kicker prefire prevention | If delayed aborts and mechanical switches prove unsafe or unsatisfactory, an alternative prefire prevention scheme has to be implemented at additional cost. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 0 | Negligible | None | 4 | 3 |  | 0 |  |  | Low |  |  |  | Mitigate | Perform all potential tests with enhanced MPS system and mechanical switches in the remaining RHIC and sPHENIX runs. |  | Q3 FY25 |  | IR_0301_34090 | 50% | 2000 | 2000 | 2000 | 0 | 0 | 0 | High | Significant | Negligible | Negligible | 4 | 3 | 1 | 1 | 3 | 12 | Moderate |  | Engineering judgement | 1000 | 2024-01-29 | [5 empty] | 1000 |  |  | 2022-03-10 | 2022-03-10 |  | 1000 | 2000 - 2000 - 2000 | 0 - 0 - 0 | 1000 | 0 | 125 | 2024-03-31 | 752
Active | RT-6-006-020-LLP-CD3A | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl | RT-6-006-020-LLP-CD3A | H. Witte | SC_MAG | NbTi Strand cost increase (Collared Magnets) | If the vendor supplying the NbTi strand increases the price for the remaining 50% of the NbTi strand for the collared magnets because of raw material price increase, then additional costs will be incurred. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 450 | Marginal | 0 | Negligible | None | 3 | 2 | 1 | 0 | 2 | 6 | Low |  | 32% | 144 | Accept | No mitigation, accept and include in contingency calculation |  | Q1 FY26 |  | E0602_19400 SC Strand - Collared Magnets - Delivery | 30% | 450 | 450 | 450 | 0 | 0 | 0 | Moderate | Significant | Negligible | None | 3 | 3 | 1 | 0 | 3 | 3 | Low |  | Probability estimated as moderate. Cost: $3.6M in the procurement, so $1.8M for 50% of the order, 25% of 1.8M is 450K | 135 | 2024-08-13 | [5 empty] | 135 |  |  | 2024-08-15 | 2024-08-15 |  | 135 | 450 - 450 - 450 | 0 - 0 - 0 | 135 | 0
Retired | 24 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / W. Wittmer |  | H. Witte | SC_MAG | Time constraints related to Magnets | If the prototype magnet design is not started by CD-1 (to be ready one year later), then their unique nature could cause delays in final design and fabrication. | High (Risk is likely to occur with a probability of >40 to <65%) | 1 | Negligible | 12 | Significant |  | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0.52 | Mitigate | [5 empty] | 15% | 0 | 500 | 3000 | 6 | 12 | 18 | Low | Significant | Significant | Marginal | 2 | 3 | 3 | 2 | 3 | 6 | Retired |  |  | Retired |  |  |  | Risk has been realized |  |  | 175 | YES | 2021-09-30 | 2020-06-30 | 2020-10-30 |  | 200 | 0 - 500 - 3000 | 6 - 12 - 18 | 175 | 1.8 | 24
Retired | 93 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / W. Wittmer |  | H. Witte | SC_MAG | Dressing IR magnets - Requirements Need to be Settled. | If the requirements for defining the details of the IR magnets is not settled by CD-1, redesign may be necessary, which will take more time. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 18 | Significant |  | 3 | 2 | 3 | 0 | 3 | 9 | Moderate |  | 32% | 320 | Mitigate | [5 empty] | 20% | 0 | 1000 | 5000 | 0 | 18 | 18 | Low | Significant | Critical | Marginal | 2 | 3 | 4 | 2 | 4 | 8 | Retired |  |  | Retired |  |  |  | Risk has been realized |  |  | 400 | YES | 2021-09-30 | 2020-06-30 | 2020-10-30 |  | 466.6667 | 0 - 1000 - 5000 | 0 - 18 - 18 | 400 | 2.4 | 93
Retired | 129 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / W. Wittmer |  | H. Witte | DET | Proposed Detector doesn’t fit in +/- 4.5 meters (distance rqmts)/physics rqmts Correlated to Detectors | if there is not sufficient space allowed for the optimized detector then the physics performance will be at impacted | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 500 | Marginal |  | Critical | Critical | 3 | 2 | 4 | 4 | 4 | 12 | Moderate |  | 32% | 160 | Mitigate | Define the optimized detector size as soon as possible – 09/30/20. Evaluate the impact on accelerator performance and the IR dimensional layout. If size occupied by the detector must be increased, determine impact on IR magnet and crab cavity locations. Determine if re-design is necessary and its impact on cost & schedule. |  | Verifying sizing of magnets and placement are what is needed vs. space rqmts |  |  | 20% | 0 | 500 | 3000 | 0 | 3 | 6 | Low | Significant | Negligible | Critical | 2 | 3 | 1 | 4 | 4 | 8 | Retired |  |  | Retired |  |  |  | Retired: assuming detectors are designed to fit |  |  | 233.3333 | NO | 500500 | 2020-06-30 | 2020-10-30 |  | 266.6667 | 0 - 500 - 3000 | 0 - 3 - 6 | 233.3333 | 0.6 | 129
Retired | 124a | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / W. Wittmer |  | H. Witte | SC_MAG | Magnet Failure | If one unique SC magnet fails then it has to be replaced and the schedule and/or performance of the EIC will be impacted. | [6 empty] | 0 | #N/A | 0 | 0 | #N/A | #N/A | #N/A |  | 0% | 0 | Mitigate | [5 empty] | 25% | 1500 | 3000 | 4000 | 3 | 6 | 9 | Low | Significant | Marginal | Critical | 2 | 3 | 2 | 4 | 4 | 8 | Retired |  |  | Retired |  |  |  | Detailed into risks 124b-i |  |  | 708.3333 | NO | 2021-09-22 | 2021-07-30 | 2021-09-27 |  | 958.3333 | 1500 - 3000 - 4000 | 3 - 6 - 9 | 708.3333 | 1.5 | 124a
Retired | 124 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / W. Wittmer |  | H. Witte | SC_MAG | Magnets Fail to Meet Performance Parameters | If a solution for the IR SC magnets, that are based on novel design ideas, cannot be found for yet unknown reasons, then the performance of the EIC will be impacted. | Very High (Risk is likely to occur with a probability of >65%) | 1500 | Significant | 12 | Critical | Critical | 5 | 3 | 4 | 4 | 4 | 20 | High |  | 82% | 1230 | Mitigate | Prioritize IR magnet design and procurement to have testing of IR SC magnet testing as early in the project as possible. (see Risk ID 23) Through continuous oversight and cooperation, work with the selected magnet vendor(s) to insure work is progressing within specifications and according to the contract schedule. Require in the magnet contract that effort must be close and cooperative with Project. Identify production issues early and resolve with vendor quickly. Procure needed cable prior to placement of magnet contract to compress fabrication schedule to testing. |  | 1-Magnet fails to meet performance parameters in field limits -2- Magnet fails to meet performance parameters in field quality |  |  | 30% | 1000 | 1500 | 5000 | 3 | 12 | 18 | Moderate | Significant | Significant | Critical | 3 | 3 | 3 | 4 | 4 | 12 | Retired |  |  | Retired |  |  |  | Detailed into risks 124b-i |  |  | 750 | NO | 2022-02-02 | 2020-06-30 | 2020-10-30 |  | 900 | 1000 - 1500 - 5000 | 3 - 12 - 18 | 750 | 3.3 | 124
Retired | 400 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl |  | H. Witte | SC_MAG | Start of final collared magnet design | If the final design of the collared magnets is started before completion of the R&D prototype magnet test, the designs may need to be revisited to incorporate necessary changes leading to delays and additional costs. | [7 empty] | #N/A | [8 empty] | Mitigate | Start final design of collared magnets after successful test of R&D collared magnet. |  |  |  | IR_0212_1000 IR_0212_1180 IR_0212_1360 IR_0212_1540 IR_0212_1720 | 90% | 1250 | 2000 | 2500 | 6 | 12 | 18 | Very High | Significant | Significant | None | 5 | 3 | 3 | 0 | 3 | 15 | Retired |  | Engineering judgement | Retired |  |  |  | Risk didn't make it to the active status. The final design of the collared magnets started before completion of the R&D prototype magnet test, so the IF event became reality. |  |  | 1725 | YES | 2023-09-15 | 10.18.2022 |  |  | 2325 | 1250 - 2000 - 2500 | 6 - 12 - 18 | 1725 | 10.8 | 400
Retired | 401 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl |  | H. Witte | SC_MAG | Number of prototype magnets | If not every collared magnet is prototyped, unique challenges of each magnet design may not be discovered, leading to issues in the magnet production. | [7 empty] | #N/A | [8 empty] | Mitigate | Prototype each collared magnet |  |  |  | RD_0303_2359 | 95% | 5000 | 7500 | 15000 | 6 | 12 | 24 | Very High | Critical | Significant | None | 5 | 4 | 3 | 0 | 4 | 20 | Retired |  | Engineering judgement | Retired |  |  |  | Risk didn't make it to the active status. Not every collared magnet is planned to be prototyped. |  |  | 8708.3333 | YES | 2023-09-15 | 10.18.2022 |  |  | 11083.3333 | 5000 - 7500 - 15000 | 6 - 12 - 24 | 8708.3333 | 13.3 | 401
Retired | 402 | Threat | 6.06 Interaction Region and Detector Interface | BNL | A. Drees / B. Wahl |  | H. Witte | SC_MAG | Start of R&D tapered direct wind quadrupole prototype magnet | If the tapered direct wind quadrupole R&D magnet is started too late, the anticipated budget advantages may be reduced. | [7 empty] | #N/A | [8 empty] | Mitigate | Start of R&D tapered direct wind quadrupole prototype magnet in time. |  |  |  | RD_0303_1900 | 10% | -2000 | -7500 | -10000 | 0 | 0 | 0 | Very Low | Critical | Negligible | None | 1 | 4 | 1 | 0 | 4 | 4 | Retired |  | Engineering judgement | Retired |  |  |  | Risk didn't make it to the active status. The tapered direct wind quadrupole R&D magnet is started later than optimal. |  |  | -650 | YES | 2023-09-15 | 10.18.2022 |  |  | -900 | -2000 - -7500 - -10000 | 0 - 0 - 0 | -650 | 0 | 402
Active | RT-6-007-001 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo | RT-6-007-001 | J. Jamilkowski | CONT | Changes in Technology | If significant changes in technology occur during the life of the project, then our plans will need to be adjusted accordingly which could result in having to rethink or redo some work, which could cost more $ and/or take more time. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 6 | Marginal | Marginal | 4 | 2 | 2 | 2 | 2 | 8 | Moderate |  | 52% | 520 | Mitigate | NOTE: After Discussion, this could potentially be converted to an Opportunity. Would the additional cost be under Operations or the Project? |  | Q1 FY26 |  | E1009_06070 | 60% | 1000 | 1000 | 1000 | 6 | 6 | 6 | High | Significant | Marginal | None | 4 | 3 | 2 | 0 | 3 | 12 | Moderate |  | Engineering judgement | 600 | 2024-03-21 | [5 empty] | 600 |  |  | 2020-06-30 | 2020-10-30 |  | 600 | 1000 - 1000 - 1000 | 6 - 6 - 6 | 600 | 3.6 | 54 | 2024-03-31 | 1248
Active | RT-6-007-002 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo | RT-6-007-002 | J. Jamilkowski | CONT | Cybersecurity Oversight / Assessment Increases | If the amount of cybersecurity oversight or assessment increases then there will be increased labor to address the responses. This could affect cost and schedule. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 150 | Negligible | 6 | Marginal | Marginal | 2 | 1 | 2 | 2 | 2 | 4 | Low |  | 17% | 25.5 | Mitigate | Continually review Cybersecurity needs |  | Q1 FY26 |  | E0702_10810 | 30% | 0 | 0 | 0 | 6 | 6 | 6 | Moderate | None | Marginal | Marginal | 3 | 0 | 2 | 2 | 2 | 6 | Low |  | Engineering judgement | 0 | 2024-03-21 | [5 empty] | 0 |  |  | 2020-06-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 6 - 6 - 6 | 0 | 1.8 | 55 | 2024-03-31 | 1248
Active | RT-6-007-003 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo | RT-6-007-003 | J. Tuozzolo | INST | Space Constraints | If space constraints in the tunnel make it difficult to disassemble components that need to be removed or modified, then additional components may need to be removed to make space. This will require additional labor and will affect schedule. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 250 | Negligible | 6 | Marginal | Negligible | 2 | 1 | 2 | 1 | 2 | 4 | Low |  | 17% | 42.5 | Mitigate | 1) Detailed work planning for disassembling approach |  | Q4 FY26 |  | TBD | 20% | 250 | 250 | 250 | 6 | 6 | 6 | Low | Negligible | Marginal | Negligible | 2 | 1 | 2 | 1 | 2 | 4 | Low |  | Engineering judgement | 50 | 01.26.24 | [5 empty] | 50 |  |  | 2020-06-30 | 2020-10-30 |  | 50 | 250 - 250 - 250 | 6 - 6 - 6 | 50 | 1.2 | 63 | 2024-03-31 | 1248
Active | RT-6-007-004 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo | RT-6-007-004 | J. Tuozzolo | INST | Screen Installation | If screen is not correctly installed according to vacuum standards (contamination) or RF fingers do not establish good connection, impact on vacuum and dynamic heat load expected. (Many connections, so likelihood increases.) | Very Low (There is a <10% chance that this event will occur) | 100 | Negligible | 0 | Negligible | None | 1 | 1 | 1 | 0 | 1 | 1 | Low |  | 5% | 5 | Mitigate | 1.Proper training, work planning, procedures, and QA inspection check (schedule presently includes an inspection with a video mole after installation) during rolling installation (don’t wait until the entire arc is done to check continuity). 2.Develop an electrical continuity test method that can be done in sections before the entire section is completed. |  | Q2 FY25 |  | TBD | 5% | 100 | 100 | 100 | 0 | 0 | 0 | Very Low | Negligible | Negligible | Marginal | 1 | 1 | 1 | 2 | 2 | 2 | Low |  | Engineering judgement | 5 | 01.26.24 | [5 empty] | 5 |  |  | 2020-06-30 | 2020-10-30 |  | 5 | 100 - 100 - 100 | 0 - 0 - 0 | 5 | 0 | 149 | 2024-03-31 | 1248
Active | RT-6-007-005 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo | RT-6-007-005 | J. Tuozzolo | INST | Damage to Recycled / Reused Equipment | If there is damaged equipment that needs to reused for EIC during removals, then additional labor and materials will be needed for repair or replacement. This could affect cost and schedule. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 0 | Negligible | Negligible | 2 | 2 | 1 | 1 | 2 | 4 | Low |  | 17% | 170 | Mitigate | 1) Detailed work planning for equipment removal |  | Q4 FY26 |  | TBD | 20% | 1000 | 1000 | 1000 | 0 | 0 | 0 | Low | Significant | Negligible | Negligible | 2 | 3 | 1 | 1 | 3 | 6 | Low |  | Engineering judgement | 200 | 01.26.24 | [5 empty] | 200 |  |  | 2020-06-30 | 2020-10-30 |  | 200 | 1000 - 1000 - 1000 | 0 - 0 - 0 | 200 | 0 | 62 | 2024-03-31 | 1248
Active | RT-6-007-006 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo | RT-6-007-006 | J. Tuozzolo | INST | Hadron Ring Sleeving Installation | If there are delays with preparing and installing the Hadron ring sleeves and bellows assemblies then other tunnel installations that are staged after that will be delayed as well. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 0 | Negligible | Negligible | 2 | 2 | 1 | 1 | 2 | 4 | Low |  | 17% | 85 | Mitigate | 1. Early planning, design, and procurement of beam screens. 2. Early planning, design, and procurement of beam screen aCarbon facility and storage systems. 3. Early aCarbon coating testing on full length beam screens. 4. Installation planning and test installations in short RHIC sections in 2024 shutdown before RHIC run ends. |  | Q2 FY25 |  | HR_0500_1500 | 20% | 500 | 500 | 500 | 0 | 0 | 0 | Low | Significant | Negligible | Negligible | 2 | 3 | 1 | 1 | 3 | 6 | Low |  | Engineering judgement | 100 | 01.26.24 | [5 empty] | 100 |  |  | 2020-06-30 | 2020-10-30 |  | 100 | 500 - 500 - 500 | 0 - 0 - 0 | 100 | 0 | 158 | 2024-03-31 | 1248
Active | RT-6-007-007 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo | RT-6-007-007 | C. Hetzel | VAC | Jump quad beam screens | If the planned arc beam screen design is not adequate to meet the needs of transition crossing during the HSR ramp, then a new beam design which reduces the impact from Eddy currents will need to be designed and fabricated. This will require additional engineering resources to develop a new fabrication approach. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 300 | Marginal | 8 | Significant | Marginal | 3 | 2 | 3 | 2 | 3 | 9 | Moderate |  | 32% | 96 | Mitigate | APEX studies, physics simulations |  | Q4 FY25 |  | E0703_11160 - AS09 - HSR Cryostat Modifications Complete | 30% | 200 | 300 | 500 | 6 | 8 | 12 | Moderate | Significant | Significant | Marginal | 3 | 3 | 3 | 2 | 3 | 9 | Moderate |  | Engineering judgement | 90 | 2024-03-25 | [5 empty] | 100 |  |  | 2024-03-25 | 2024-04-16 |  | 95 | 200 - 300 - 500 | 6 - 8 - 12 | 100 | 2.6
Retired | 66 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Lack of Proper Installation Staging | If beamline components are late and proper staging can't take place, then installation will be delayed or more time consumed. This could affect cost and schedule. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 400 | Marginal | 6 | Marginal | Negligible | 3 | 2 | 2 | 1 | 2 | 6 | Low |  | 32% | 128 | Mitigate | 1) Detailed work planning for procurement, vendor oversights, deliveries, and installation plans |  | End of FY26 |  |  | 15% | 1 | 1 | 1 | 6 | 6 | 6 | Low | Negligible | Marginal | Negligible | 2 | 1 | 2 | 1 | 2 | 4 | Retired |  |  | Retired |  |  |  | Risk originates from the upstream schedule. |  |  | 0.15 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 0.2 | 1 - 1 - 1 | 6 - 6 - 6 | 0.15 | 0.9 | 66
Retired | 157 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo | NC_MAG | Magnet Girder Acceptance & Assembly Facility | If the conventional magnet acceptance testing and girder assembly facility is not fully equipped and staffed when production magnets begin to arrive and reach their production peak then there will be a schedule delay or the quality of early test, magnet measurement, and assembly may be poor. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 18 | Marginal | Negligible | 2 | 2 | 2 | 1 | 2 | 4 | Low |  | 17% | 85 | Mitigate | 1. Early planning, design, and assembly of the magnet acceptance facility. 2. Early procurement of the eRCS magnets to allow a controlled ramp up of the facility with schedule float for the RCS magnet installation to allow for acceptance and assembly system modifications and improvements. 3. Careful staging of the project schedule so magnet procurements do not create a peak that can not be handled by the magnet assembly teams. 4. Magnet measurements by vendors with testing and oversight by the EIC. Partial or complete girder assembly by vendors including survey and alignment, bus connections, and hosing. |  |  |  |  | 20% | 500 | 500 | 500 | 18 | 18 | 18 | Low | Significant | Critical | Negligible | 2 | 3 | 4 | 1 | 4 | 8 | Retired |  |  | Retired |  |  |  | Risk originates from the upstream schedule. |  |  | 100 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 133.3333 | 500 - 500 - 500 | 18 - 18 - 18 | 100 | 3.6 | 157
Retired | 52 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Scope Change | If scope changes in other systems with a significant impact on controls support (prior to CD-3) then it would impact schedule late in the project (when there is less time to catch up or make adjustments). | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 500 | Marginal | 6 | Marginal | Marginal | 3 | 2 | 2 | 2 | 2 | 6 | Low |  | 32% | 160 | Mitigate | 1) Early definition of size of the scope change. 2) Determine needs of resources/cost based upon the defined scope change. Engineering by CD-2; Cost by CD-3 |  | Cost impact will retire by CD-3 |  |  | 10% | 500 | 500 | 500 | 6 | 6 | 6 | Very Low | Significant | Marginal | Marginal | 1 | 3 | 2 | 2 | 3 | 3 | Retired |  |  | Retired |  |  |  | Scope is now defined |  |  | 50 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 66.6667 | 500 - 500 - 500 | 6 - 6 - 6 | 50 | 0.6 | 52
Retired | 143 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Quench margin: Hadron Storage Ring SC magnets | If the EIC beam heat load is too high for the SC magnet helium system then a quench may occur, then a cold compressor system would need to be added to lower the operating temperatures of the magnets. This will affect design and installation labor, cost, and schedule. | Very Low (There is a <10% chance that this event will occur) | 2300 | Significant | 0 | Negligible | Marginal | 1 | 3 | 1 | 2 | 3 | 3 | Low | Apr 2021 - primary risk probability reduced from high to very low, | 5% | 115 | Mitigate | 1) Completing the Task Force Effort to determine estimated Beam heating load (Estimate to complete by end of FY21) 2) Addition of 2 cold compressors [1+1hot standby] at the 1005 central cryogenic plant, to decrease operating temperatures by 0.4K, will increase electric power for plant by 1.5MW, 3) If the beam tube heating is higher then expected, then the EIC bunch intensity will have to be reduced lowering luminosity goals until the cold compressors are installed. |  | May not be able to simulate/test quench margin. Trigger would be based on completion of FY21 Task Force Effort and design of the Beam screen. |  |  | 10% | 50 | 102 | 205 | 18 | 24 | 30 | Very Low | Negligible | Critical | Marginal | 1 | 1 | 4 | 2 | 4 | 4 | Retired |  | .5 FTE MD and .5 FTE ME = $205k (loaded) | Retired |  |  |  | Dec 2021: Risk is replaced with Hadron Ring risks |  |  | 11.9 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 15.3 | 50 - 102 - 205 | 18 - 24 - 30 | 11.9 | 2.4 | 143
Retired | 145 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Existing RHIC Upgrades | If RHIC existing system upgrades, maintenance, and repairs are not completed then they will compete with engineering and technical resources during EIC construction. This includes possible further diode repairs, upgrades to communications infrastructure and network systems, site power distribution, etc. The estimates assume these are off project. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 0 | Marginal | Negligible | 2 | 2 | 2 | 1 | 2 | 4 | Low |  | 17% | 85 | Mitigate | 1) Good communication with CAD Engineering Team: RHIC and EIC 2) Assumption is proper RHIC upgrade funding from DOE |  | Resolved by CD-2 |  |  | 10% | 500 | 500 | 500 | 0 | 0 | 0 | Very Low | Significant | Negligible | Negligible | 1 | 3 | 1 | 1 | 3 | 3 | Retired |  |  | Retired |  |  |  | External risk - RHIC Upgrades MS exists in the schedule |  |  | 50 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 66.6667 | 500 - 500 - 500 | 0 - 0 - 0 | 50 | 0 | 145
Retired | 53 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Change in Data Volume (combine with risk 52) | If there is a significant change in data volume (more systems/more monitoring), then controls systems requirements will need to be adjusted (Network and Data Management). This could affect cost and schedule. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 0 | Marginal | Marginal | 3 | 2 | 2 | 2 | 2 | 6 | Low |  | 32% | 320 | Mitigate | 1) Pre-emptive request/analysis of data needs of teams, 2) Early definition of size of the scope change. 3) Determine needs of resources/cost based upon the defined scope change. |  | Engineering by CD-2; Cost by CD-3 |  |  | 20% | 1000 | 1000 | 1000 | 0 | 0 | 0 | Low | Significant | Negligible | Marginal | 2 | 3 | 1 | 2 | 3 | 6 | Retired |  |  | Retired |  |  |  | Scope is now defined |  |  | 200 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 266.6667 | 1000 - 1000 - 1000 | 0 - 0 - 0 | 200 | 0 | 53
Retired | 56 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Changes to Controls Interfaces (Duplicate?) | If controls interfaces from vendor/partner-supplied systems change, then the controls systems interfaces might need to change also, which could change the controls plan and cause a cost or schedule increase. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 0 | Marginal | Marginal | 2 | 2 | 2 | 2 | 2 | 4 | Low |  | 17% | 85 | Mitigate | 1) Good communication and information with vendor and partners 2) Collaboration in specification development |  | CD-3 to mid-CD-3 |  |  | 30% | 500 | 500 | 500 | 0 | 0 | 0 | Moderate | Significant | Negligible | Marginal | 3 | 3 | 1 | 2 | 3 | 9 | Retired |  |  | Retired |  |  |  | Scope is now defined |  |  | 150 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 200 | 500 - 500 - 500 | 0 - 0 - 0 | 150 | 0 | 56
Retired | 57 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Changes in Pre-Operations Requirements for Controls (Duplicate?) | If the pre-operations requirements change for controls before commissioning, then it will take more time to complete additional software development. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 250 | Negligible | 0 | Marginal | Marginal | 2 | 1 | 2 | 2 | 2 | 4 | Low |  | 17% | 42.5 | Mitigate | 1) Good communication with commissioning team 2) Start commissioning planning early CD-3 |  |  |  |  | 20% | 250 | 250 | 250 | 0 | 0 | 0 | Low | Negligible | Negligible | Marginal | 2 | 1 | 1 | 2 | 2 | 4 | Retired |  |  | Retired |  |  |  | Scope is now defined |  |  | 50 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 66.6667 | 250 - 250 - 250 | 0 - 0 - 0 | 50 | 0 | 57
Retired | 59 | Threat | 6.07 Accelerator Support Systems | BNL | J. Tuozzolo |  | J. Tuozzolo |  | Adopting other Control System Components to RHIC Controls | If major systems procurements that include controls systems are not fully compatible with the RHIC controls system design then additional time and $ will be required to modify or adapt the systems and this could lead to an increase in cost and schedule. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 250 | Negligible | 0 | Marginal | Negligible | 2 | 1 | 2 | 1 | 2 | 4 | Low |  | 17% | 42.5 | Mitigate | NOTE: Evaluate if this risk is needed. If so, further definition is required. |  |  |  |  | 20% | 250 | 250 | 250 | 0 | 0 | 0 | Low | Negligible | Negligible | Negligible | 2 | 1 | 1 | 1 | 1 | 2 | Retired |  |  | Retired |  |  |  | Scope is now defined |  |  | 50 | NO | 2021-12-03 | 2020-06-30 | 2020-10-30 |  | 66.6667 | 250 - 250 - 250 | 0 - 0 - 0 | 50 | 0 | 59
Active | RT-6-008-001 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-001 | Zack Conway | RF | Kicker Performance | If the kicker cannot inject into a neighboring RF bucket, THEN we would have to utilize the accumulator ring for the merge which may increase the costs | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 6 | Marginal | Marginal | 2 | 4 | 2 | 2 | 4 | 8 | Moderate |  | 17% | 1700 | Mitigate | Use an accumulator ring |  | TBD |  | TBD | 5% | 7000 | 10000 | 15000 | 4 | 6 | 12 | Very Low | Critical | Marginal | Marginal | 1 | 4 | 2 | 2 | 4 | 4 | Low |  | Engineering judgement | 500 | 2024-01-31 | [5 empty] | 533.3333 |  |  | 2020-06-30 | 2020-10-30 |  | 516.6667 | 7000 - 10000 - 15000 | 4 - 6 - 12 | 533.3333 | 0.36667 | 146 | 2024-03-31 | 1248
Active | RT-6-008-002 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-002 | Zack Conway | RF | LLRF Supply Chain Delays | If the electronic supply chain delays currently being experienced continue beyond CY 21, then design and prototype PED efforts for the LLRF systems will be delayed. | High (Risk is likely to occur with a probability of >40 to <65%) | 300 | Marginal | 12 | Significant | Negligible | 4 | 2 | 3 | 1 | 3 | 12 | Moderate |  | 52% | 156 | Mitigate | Procure critical electronic components as early as practical but no too early as this would increase risk of early obsolescence. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 50% | 300 | 300 | 300 | 0 | 0 | 0 | High | Significant | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Moderate |  | Engineering judgement | 150 | 2024-01-31 | [5 empty] | 150 |  |  | 2021-09-24 | 2021-09-27 |  | 150 | 300 - 300 - 300 | 0 - 0 - 0 | 150 | 0 | 310 | 2024-03-31 | 916
Active | RT-6-008-003 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-003 | Zack Conway | AD | Accelerator design maturity | If the final accelerator design changes requirements for RF systems then new designs will need to be developed (jp) | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 5000 | Significant | 12 | Significant | None | 3 | 3 | 3 | 0 | 3 | 9 | Moderate |  | 32% | 1600 | Mitigate | Work closely with accelerator team to keep RF design current. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 30% | 5000 | 5000 | 5000 | 0 | 0 | 0 | Moderate | Significant | Negligible | Marginal | 3 | 3 | 1 | 2 | 3 | 9 | Moderate |  | Engineering judgement | 1500 | 2024-01-31 | [5 empty] | 1500 |  |  | 2021-09-24 | 2021-09-27 |  | 1500 | 5000 - 5000 - 5000 | 0 - 0 - 0 | 1500 | 0 | 318 | 2024-03-31 | 916
Active | RT-6-008-004 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-004 | M. Blaskiewicz | RF | Crab Cavity Prototype | If the 197 MHz crab cavity prototype R&D effort exposes unexpected challenges in fabrication, processing or test, then physics and/or engineering redesign will be required to address and remediate the problem, causing schedule delay and added cost for another prototype. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 3000 | Significant | 12 | Significant | Significant | 3 | 3 | 3 | 3 | 3 | 9 | Moderate |  | 32% | 960 | Mitigate | Complete crab cavity prototype R&D |  | Q1 FY26 |  | E0502_01320, Path Length Variation Magnets - Pin Procurement | 30% | 1000 | 3000 | 5000 | 6 | 12 | 18 | Moderate | Significant | Significant | Significant | 3 | 3 | 3 | 3 | 3 | 9 | Moderate |  | Engineering judgement | 900 | 2024-04-16 | [5 empty] | 900 |  |  | 2020-06-30 | 2020-10-30 |  | 900 | 1000 - 3000 - 5000 | 6 - 12 - 18 | 900 | 3.6 | 184 | 2024-03-31 | 1248
Active | RT-6-008-005 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-005 | Zack Conway | RF | Scaling of IR Crab Cavity Design | If scaling of the successfully tested BNL/LHC cavity design leads to unexpected results, more time will be needed to adjust the design which could lead to schedule delays. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1 | Negligible | 12 | Significant | None | 3 | 1 | 3 | 0 | 3 | 9 | Moderate |  | 32% | 0.32 | Mitigate | TBD |  | TBD |  | TBD | 30% | 0 | 0 | 0 | 12 | 12 | 12 | Moderate | None | Significant | Marginal | 3 | 0 | 3 | 2 | 3 | 9 | Moderate |  | Engineering judgement | 0 | 2024-01-31 | [5 empty] | 0 |  |  | 2020-06-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 12 - 12 - 12 | 0 | 3.6 | 26 | 2024-03-31 | 1248
Active | RT-6-008-006 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-006 | C. Folz | RF | Increase in Power Rqmts. Specific to RF | If the project decides to use solid state technology, then there needs to be a cost/benefit analysis between RF and energy losses within conventional design resulting in larger cable energy rqmts and additional cost and technical impacts. | High (Risk is likely to occur with a probability of >40 to <65%) | 5000 | Significant | 0 | Negligible | Negligible | 4 | 3 | 1 | 1 | 3 | 12 | Moderate |  | 52% | 2600 | Mitigate | Participate in the RF decision. |  | Retire after scope changes |  | E0502_01320, Path Length Variation Magnets - Pin Procurement | 50% | 5000 | 5000 | 5000 | 0 | 0 | 0 | High | Significant | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Moderate |  | Engineering judgement | 2500 | 2024-01-25 | [5 empty] | 2500 |  |  | 2020-06-30 | 2020-10-30 |  | 2500 | 5000 - 5000 - 5000 | 0 - 0 - 0 | 2500 | 0 | 134 | 2024-03-31 | 1248
Active | RT-6-008-007 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-007 | Zack Conway | RF | RCS Multi-Harmonic RF Kicker | If the RCS Multi-Harmonic RF Kicker prototype fails to achieve specified performance, then an alternate set of conventional cavities will need to be designed and fabricated to perform the injection kicker function. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 3000 | Significant | 24 | Critical | Crisis | 2 | 3 | 4 | 5 | 5 | 10 | Moderate |  | 17% | 510 | Mitigate | Expedite kicker prototype and high power test effort. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 20% | 3000 | 3000 | 3000 | 18 | 18 | 18 | Low | Significant | Critical | None | 2 | 3 | 4 | 0 | 4 | 8 | Moderate |  | Engineering judgement | 600 | 2024-01-31 | [5 empty] | 600 |  |  | 2021-09-24 | 2021-09-27 |  | 600 | 3000 - 3000 - 3000 | 18 - 18 - 18 | 600 | 3.6 | 301 | 2024-03-31 | 916
Active | RT-6-008-008 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-008 | Zack Conway | RF | ESR Cryomodule Space Constraints | If the IR-10 lattices and devices can't be tailored to provide sufficient space for the ESR single cavity cryomodules, then the ESR cryomodule will need to be redesigned to accommodate 2x ESR cavities per cryomodule. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 12 | Significant | Marginal | 2 | 2 | 3 | 2 | 3 | 6 | Low |  | 17% | 170 | Mitigate | Dedicate resources to the IR-10 lattice design. Dedicate resources to the ESR 2-cavity cryomodule design. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 20% | 1000 | 1000 | 1000 | 0 | 0 | 0 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Low |  | Engineering judgement | 200 | 2024-01-31 | [5 empty] | 200 |  |  | 2021-09-24 | 2021-09-27 |  | 200 | 1000 - 1000 - 1000 | 0 - 0 - 0 | 200 | 0 | 302 | 2024-03-31 | 916
Active | RT-6-008-009 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-009 | Zack Conway | RF | ESR Cavity Prototype | If the prototype ESR 591 MHz Cavity does not achieve design performance specifications in vertical test … then an additional cavity will need to be built (jp). | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 9 | Significant | None | 2 | 2 | 3 | 0 | 3 | 6 | Low |  | 17% | 85 | Mitigate | Expedite cavity prototype effort. Order spare material for SRF cavity prototyping. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 20% | 500 | 500 | 500 | 0 | 0 | 0 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Low |  | Engineering judgement | 100 | 2024-01-31 | [5 empty] | 100 |  |  | 2021-09-24 | 2021-09-27 |  | 100 | 500 - 500 - 500 | 0 - 0 - 0 | 100 | 0 | 303 | 2024-03-31 | 916
Active | RT-6-008-010-LLP-CD3A | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-010-LLP-CD3A | Zack Conway | RF | ESR Cryo FA doesn't meet performance | If ESR cryomodule FA doesn't achieve specified performance and requires mos, then additional time and labor will be needed to identify and remediate the issues. | High (Risk is likely to occur with a probability of >40 to <65%) | 1500 | Significant | 12 | Significant | Critical | 4 | 3 | 3 | 4 | 4 | 16 | High |  | 52% | 780 | Mitigate | Plan design reviews with associated resources in P6 schedule. Keep good communication with vendor(s). |  | Q3 FY25 |  | E0803_11460 Complete First Article Cavity Dressed Qualification (591 1-Cell 1st Art) | 60% | 851 | 1134 | 1701 | 6 | 14 | 18 | High | Significant | Critical | Significant | 4 | 3 | 4 | 3 | 4 | 16 | High |  | Probability estimated as low. Cost impacts are based on previous project experience that includes disassembly, modifications and re-assembly. It could be $750K/$1M/$1.5M Burdened. Compounded escalation rate of 1.134 applied for delivery year 2027. The schedule reflects past experience with LCLS-II and CEBAF. | 680.4 | 2024-08-13 | [5 empty] | 737.2 |  |  | 2021-09-24 | 2021-09-27 |  | 708.8 | 851 - 1134 - 1701 | 6 - 14 - 18 | 737.2 | 7.6 | 304_LLP | 2024-03-31 | 916
Active | RT-6-008-011 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-011 | Zack Conway | RF | 197 Crab Cryomodule First Article | If the first article 197 MHz Crab cryomodule does not achieve specified performance and requires significant redesign, then additional time and labor will be needed to identify and remediate the issue. | Very High (Risk is likely to occur with a probability of >65%) | 1500 | Significant | 12 | Significant | Significant | 5 | 3 | 3 | 3 | 3 | 15 | High |  | 82% | 1230 | Mitigate | Expedite first article cryomodule development and test. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 50% | 1000 | 1500 | 2000 | 3 | 9 | 12 | High | Significant | Significant | Critical | 4 | 3 | 3 | 4 | 4 | 16 | High |  | Engineering judgement | 750 | 2024-09-30 | [5 empty] | 750 |  |  | 2021-09-24 | 2021-09-27 |  | 750 | 1000 - 1500 - 2000 | 3 - 9 - 12 | 750 | 4 | 307 | 2024-03-31 | 916
Active | RT-6-008-012 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-012 | Zack Conway | AD | ESR Lattice Change | If the ESR 18 GeV lattice changes to a 60 degree phase advance, then substantially more installed voltage will be required, requiring redesign of the cavities and cryomodules, and potentially more IR and support building space. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 2000 | Significant | 12 | Significant | Critical | 2 | 3 | 3 | 4 | 4 | 8 | Moderate |  | 17% | 340 | Mitigate | Expedite the ESR lattice design effort. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 20% | 2000 | 2000 | 2000 | 0 | 0 | 0 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Low |  | Engineering judgement | 400 | 2024-01-31 | [5 empty] | 400 |  |  | 2021-09-24 | 2021-09-27 |  | 400 | 2000 - 2000 - 2000 | 0 - 0 - 0 | 400 | 0 | 314 | 2024-03-31 | 916
Active | RT-6-008-013 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-013 | Zack Conway | AD | RCS Lattice Change | If the RCS 18 GeV lattice changes to a 60 degree lattice then substantially more installed voltage will be required, requiring one or two extra cryomodules to be installed, increasing cost and required IR and support building space. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 4000 | Significant | 0 | Negligible | Critical | 2 | 3 | 1 | 4 | 4 | 8 | Moderate |  | 17% | 680 | Mitigate | Expedite the RCS lattice design effort. |  | Q2 FY25 |  | E0203_22680, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 20% | 4000 | 4000 | 4000 | 0 | 0 | 0 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Low |  | Engineering judgement | 800 | 2024-01-31 | [5 empty] | 800 |  |  | 2021-09-24 | 2021-09-27 |  | 800 | 4000 - 4000 - 4000 | 0 - 0 - 0 | 800 | 0 | 315 | 2024-03-31 | 916
Active | RT-6-008-014 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-014 | C. Montag | RF | Power Couplers | If we cannot reach 500kW CW, but successfully achieve a somewhat lower power, then we need to install more cryomodules to reduce power per coupler to an acceptable limit. This adds cost and required beamline space in IR10. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 2000 | Significant | 0 | Negligible | Marginal | 2 | 3 | 1 | 2 | 3 | 6 | Low |  | 17% | 340 | Mitigate | Increase number of cryomodules or additional R&D effort. |  | Q2 FY25 |  | E0502_01320, Path Length Variation Magnets - Pin Procurement | 20% | 2000 | 2000 | 2000 | 0 | 0 | 0 | Low | Significant | Negligible | Marginal | 2 | 3 | 1 | 2 | 3 | 6 | Low |  | Engineering judgement | 400 | 2024-01-24 | [5 empty] | 400 |  |  | 2020-06-30 | 2020-10-30 |  | 400 | 2000 - 2000 - 2000 | 0 - 0 - 0 | 400 | 0 | 114 | 2024-03-31 | 1248
Active | RT-6-008-015 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-015 | C. Montag | RF | HOM Absorbers | If we cannot achieve required power, then we need to install likely two more absorbers per cryomodule. This adds to cost and required beamline space in IR10. | low (Risk is likely to occur with a probability of > 10% to < 25%) | 2000 | Significant | 0 | Negligible | Marginal | 2 | 3 | 1 | 2 | 3 | 6 | Low |  | 17% | 340 | Mitigate | R&D to validate the design. Add more absorbers or do additional R&D. |  | Q2 FY25 |  | E0502_01320, Path Length Variation Magnets - Pin Procurement | 20% | 2000 | 2000 | 2000 | 0 | 0 | 0 | Low | Significant | Negligible | Marginal | 2 | 3 | 1 | 2 | 3 | 6 | Low |  | Engineering judgement | 400 | 2024-01-24 | [5 empty] | 400 |  |  | 2020-06-30 | 2020-10-30 |  | 400 | 2000 - 2000 - 2000 | 0 - 0 - 0 | 400 | 0 | 115 | 2024-03-31 | 1248
Active | RT-6-008-016 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-016 | Zack Conway | RF | Changes to Crab Cavities | If the crab cavity frequencies are not finalized soon, this will stall the formulation of reasonable, maximum cryomodule-required spacing in the IR. This will negatively impact the present magnet layout, requiring the repeating of the ongoing magnet design work. This will lead to a negative impact on the magnet procurement schedule. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 12 | Significant | Marginal | 2 | 3 | 3 | 2 | 3 | 6 | Low |  | 17% | 850 | Mitigate | Complete determination of crab cavity frequency and define overall required cryomodule spacing in the IR by 9/30/20. (See Risk ID 23) |  | TBD |  | E0502_01320, Path Length Variation Magnets - Pin Procurement | 20% | 5000 | 5000 | 5000 | 12 | 12 | 12 | Low | Significant | Significant | Marginal | 2 | 3 | 3 | 2 | 3 | 6 | Low |  | Engineering judgement | 1000 | 2024-01-31 | [5 empty] | 1000 |  |  | 2020-06-30 | 2020-10-30 |  | 1000 | 5000 - 5000 - 5000 | 12 - 12 - 12 | 1000 | 2.4 | 91 | 2024-03-31 | 1248
Active | RT-6-008-017 | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-017 | Zack Conway | RF | ESR Cryomodule Transportation Issues | If there are unexpected CM transportation issues, then it would increase the cost and result in delays. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 1 | Negligible | None | 3 | 1 |  | 0 |  |  | Low |  |  |  | Mitigate | Carefully plan and monitor CM transportation, use qualified vendors and use realistic durations. |  | TBD |  | TBD | 20% | 0 | 0 | 0 | 0.25 | 0.5 | 1 | Low | None | Negligible | None | 2 | 0 | 1 | 0 | 1 | 2 | Low |  | 20 years experience with CM transportation | 0 | 2024-01-31 | [5 empty] | 0 |  |  | 2023-06-27 | 2023-06-27 |  | 0 | 0 - 0 - 0 | 0.25 - 0.5 - 1 | 0 | 0.11667 |  | 2024-03-31 | 278
Active | RT-6-008-018-LLP-CD3A | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-018-LLP-CD3A | Zack Conway | RF | ESR Cryo FA Delivery Delay | If Cryo FA is delivered later than planned, then the project will experience schedule delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 9 | Significant | None | 4 | 1 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 0 | Mitigate | Work with procurement to award the contract on time; good communication with vendor(s). |  | Q3 FY25 |  | E0803_16980 Start First Article Cavity String Assembly (591 1-Cell 1st Art) | 40% | 0 | 0 | 0 | 3 | 9 | 12 | Moderate | None | Significant | None | 3 | 0 | 3 | 0 | 3 | 9 | Moderate |  | Probability estimated as low. No cost impact. Schedule delays estimated 3-6-9mo for low-likely-high schedule impacts based on prior experience. | 0 | 2024-08-13 | [5 empty] | 0 |  |  | 2023-08-14 | 2023-08-14 |  | 0 | 0 - 0 - 0 | 3 - 9 - 12 | 0 | 3.2 |  | 2024-03-31 | 230
Active | RT-6-008-019-LLP-CD3A | Threat | 6.08 RF | JLAB | Z. Conway /P. Berrutti | RT-6-008-019-LLP-CD3A | Zack Conway | RF | ESR Cryo FA Bids come higher than expected | If Cryo FA contract cost is higher than planned, then the project will have cost increase. | High (Risk is likely to occur with a probability of >40 to <65%) | 3000 | Significant | 0 | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Moderate |  | 52% | 1560 | Accept | Include in contingency calculation |  | Q3 FY25 |  | E0803_10065 04 10 2024 AWARD: First Article Cavity (591 1-Cell 1st Art) COMPLETE | 30% | 366 | 549 | 732 | 0 | 0 | 0 | Moderate | Significant | Negligible | None | 3 | 3 | 1 | 0 | 3 | 9 | Moderate |  | Probability estimated as moderate. Cno schedule impacts. Cost impacts are 10-15-20 % of total burdened and escalated cost. | 164.7 | 2024-08-13 | [5 empty] | 164.7 |  |  | 2023-08-14 | 2023-08-14 |  | 164.7 | 366 - 549 - 732 | 0 - 0 - 0 | 164.7 | 0 |  | 2024-03-31 | 230
Retired | 84 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | M. Blaskiewicz | RF | RF | 3rd Harmonic RF | High (Risk is likely to occur with a probability of >40 to <65%) | 3000 | Significant |  | Negligible | Marginal | 4 | 3 | 1 | 2 | 3 | 12 | Moderate |  | 52% | 1560 | Mitigate | Removing 3rd Harmonic system and increase complexity of vacuum components. (No longer have 3rd Hamonic systems) |  | Could cause additional impact or increase probability of risks in vacuum components |  |  | 20% | 3000 | 3000 | 3000 | 0 | 0 | 0 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Retired |  |  | Retired |  |  |  | Retired TO BE COMPLETED |  |  | 600 | NO | 2020-12-22 | 2020-06-30 | 2020-10-30 |  | 800 | 3000 - 3000 - 3000 | 0 - 0 - 0 | 600 | 0 | 84
Retired | 300 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | 591 MHz 5-Cell Cryomodule | If PED reveals that the single cavity 5-cell cryomodule can't be used as a common cryomodule design for the ERL, RCS and HSR, then one or more customized cavity and cryomodule combinations will need to be developed. | High (Risk is likely to occur with a probability of >40 to <65%) | 5000 | Significant | 12 | Significant | Critical | 4 | 3 | 3 | 4 | 4 | 16 | High |  | 52% | 2600 | Mitigate | Dedicate resources to the 591 MHz 5-cell evaluation and design effort. |  |  |  | HR_0805_1060, RF-ERL-1-CM: Ready for Installation | 75% | 2000 | 3000 | 4000 | 6 | 15 | 24 | Very High | Significant | Critical | None | 5 | 3 | 4 | 0 | 4 | 20 | Retired |  | Scaled based on estimates for CM design, procurement and assembly in other areas for RF systems. | Retired |  |  |  | Oct 21, 2022. Risk realized. More design effort will be in proposed Baseline. |  |  | 2250 | YES | 2022-10-21 | 2021-09-24 | 2021-09-27 | Oct 21, 2022: Realized, retired | 3000 | 2000 - 3000 - 4000 | 6 - 15 - 24 | 2250 | 11.25 | 300
Retired | 306 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | ESR 400 kW Solid State Amplifiers 2 | If the ESR 400 kW SSA footprint or volume increases during the vendor detailed design phase, then the RF1010 building size will need to increase to accommodate the larger amplifiers. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 18 | Significant | Negligible | 3 | 4 | 3 | 1 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | Ensure that the first article amplifier procurement receives high priority. |  |  |  | IF_0204_1440, Ready for Accelerator Installation - 1010 RF Building | 30% | 8000 | 10000 | 12000 | 6 | 12 | 18 | Moderate | Critical | Significant | None | 3 | 4 | 3 | 0 | 4 | 12 | Retired |  |  | Retired |  |  |  | Oct 21, 2022. This risk was a duplicate. |  |  | 3000 | NO | 2022-10-21 | 2021-09-24 | 2021-09-27 | Oct 21, 2022: Was a duplicate, retired | 4000 | 8000 - 10000 - 12000 | 6 - 12 - 18 | 3000 | 3.6 | 306
Retired | 308 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | Crab Cavity Performance Requirements 1 | If the crab cavity performance requires greater than state of the are RF noise control, then additional time and labor will be needed to address the RF control challenges. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 12 | Significant | Marginal | 4 | 2 | 3 | 2 | 3 | 12 | Moderate |  | 52% | 520 | Mitigate | Expedite analysis and simulation efforts to mature requirements as early as possible. |  |  |  | AS_0302_6040, Controls - Crab Cavity Systems - Ready for Systems Readiness Review | 50% | 1000 | 1000 | 1000 | 0 | 0 | 0 | High | Significant | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Retired |  |  | Retired |  |  |  | Oct 21, 2022. Risk realized. |  |  | 500 | YES | 2022-10-21 | 2021-09-24 | 2021-09-27 | Oct 21, 2022: Realized, retired | 666.6667 | 1000 - 1000 - 1000 | 0 - 0 - 0 | 500 | 0 | 308
Retired | 309 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | Crab Cavity Performance Requirements 2 | If the crab cavity performance requires strong RF feedback for impedance control , then the resulting high gain, low group delay feedback implementation will require a new RF support building due to siting and proximity requirements. | High (Risk is likely to occur with a probability of >40 to <65%) | 5000 | Significant | 6 | Marginal | Critical | 4 | 3 | 2 | 4 | 4 | 16 | High |  | 52% | 2600 | Mitigate | Expedite analysis and simulation efforts to mature requirements as early as possible. |  |  |  | IF_0203_1265, Cryogenic 1002I - BORE | 50% | 5000 | 5000 | 5000 | 6 | 12 | 18 | High | Significant | Significant | None | 4 | 3 | 3 | 0 | 3 | 12 | Retired |  |  | Retired |  |  |  | Oct 21, 2022. Risk realized. |  |  | 2500 | YES | 2022-10-21 | 2021-09-24 | 2021-09-27 | Oct 21, 2022: Realized, retired | 3333.3333 | 5000 - 5000 - 5000 | 6 - 12 - 18 | 2500 | 6 | 309
Retired | 316 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | ERL Injector RF | If the ERL Injector physics requirement calls for an SRF injector cryomodule, then the injector RF cost will increase, significant additional design time will be required and cryogenic requirements will increase. | High (Risk is likely to occur with a probability of >40 to <65%) | 3000 | Significant | 12 | Significant | Critical | 4 | 3 | 3 | 4 | 4 | 16 | High |  | 52% | 1560 | Mitigate | Expedite the ERL Injector design effort. |  |  |  | HR_0802_1280, Milestone: High Current HCeS - High Current Hadron cooling e-source subsystems complete | 75% | 10000 | 16000 | 20000 | 12 | 24 | 36 | Very High | Critical | Critical | None | 5 | 4 | 4 | 0 | 4 | 20 | Retired |  | Scaled based on estimates for CM design, procurement and assembly in other areas fro RF systems. | Retired |  |  |  | Oct 21, 2022. Realized, will be part of proposed Baseline. |  |  | 11500 | YES | 2022-10-21 | 2021-09-24 | 2021-09-27 | Oct 21, 2022: Realized, retired | 15500 | 10000 - 16000 - 20000 | 12 - 24 - 36 | 11500 | 18 | 316
Retired | 323 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | K. Smith | RF | Power Couplers | If Alumina window design which is robust against transportation stresses is not developed, then test couplers would need to be removed after test at JLAB, and final cryomod assembly with the current BeO FPC will need to occur at BNL. This would cause schedule delay, added cost and add significant risk for degradation of cavity performance. | High (Risk is likely to occur with a probability of >40 to <65%) | 3000 | Significant | 18 | Negligible | Significant | 4 | 3 | 1 | 3 | 3 | 12 | Moderate |  | 52% | 1560 | Mitigate | Expedite R&D on a new alumina window design. If this fails, think about a backup plan... |  |  |  | RD_0309_1580, ESR Vacuum Development - Vacuum design ready for PDR (CD-2) | 50% | 3000 | 3000 | 3000 | 18 | 18 | 18 | High | Significant | Critical | Significant | 4 | 3 | 4 | 3 | 4 | 16 | Retired |  |  | Retired |  |  |  | Oct 21, 2022. New couplers design is in the proposed Baseline. |  |  | 1500 | YES | 2022-10-21 | 2021-09-24 | 2021-09-27 | Oct 21, 2022: Realized, retired | 2000 | 3000 - 3000 - 3000 | 18 - 18 - 18 | 1500 | 9 | 323
Retired | 305 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | ESR 400 kW Solid State Amplifiers 1 | If the ESR 400 kW SSA first article does not achieve specified performance, then the vendor will require more time to develop a solution. (Should there be an entry about getting the long lead procurement placed? This speaks to having a CD03a. Jp, below #37 kss) | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 0 | Negligible | 6 | Marginal | Marginal | 2 | 1 | 2 | 2 | 2 | 4 | Low |  | 17% | 0 | Mitigate | Ensure that the first article amplifier procurement receives high priority. |  |  |  | None - no cost or sched. Impact | 20% | 0 | 0 | 0 | 0 | 0 | 0 | Low | None | Negligible | None | 2 | 0 | 1 | 0 | 1 | 2 | Retired |  |  | Retired |  |  | None - no cost or sched. Impacts, not in Safran | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 305
Retired | 311 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | HSR HPRF Tetrodes | Any risk of note? | [6 empty] | 0 | #N/A | 0 | 0 | #N/A | #N/A | #N/A |  | 0% | 0 | Mitigate |  |  |  |  | TBD | 0% |  |  |  | 0 | 0 | 0 | INSERT LIKELIHOOD | None | Negligible | None | 0 | 0 | 1 | 0 | 1 | 0 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | - - | 0 - 0 - 0 | 0 | 0 | 311
Retired | 312 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | HSR 1004 HPRF Space | Any risk of note? | [6 empty] | 0 | #N/A | 0 | 0 | #N/A | #N/A | #N/A |  | 0% | 0 | Mitigate |  |  |  |  | TBD | 0% |  |  |  | 0 | 0 | 0 | INSERT LIKELIHOOD | None | Negligible | None | 0 | 0 | 1 | 0 | 1 | 0 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | - - | 0 - 0 - 0 | 0 | 0 | 312
Retired | 313 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | HSR 1004 Cooling Water | Any risk of note? | [6 empty] | 0 | #N/A | 0 | 0 | #N/A | #N/A | #N/A |  | 0% | 0 | Mitigate |  |  |  |  | TBD | 0% |  |  |  | 0 | 0 | 0 | INSERT LIKELIHOOD | None | Negligible | None | 0 | 0 | 1 | 0 | 1 | 0 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | - - | 0 - 0 - 0 | 0 | 0 | 313
Retired | 317 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | Facility Upgrades (JLAB) | If JLab SRF facility upgrades are not started by January 2022 then there will be delays in fabricating prototype cavities. (jp) |  |  |  | 6 | Marginal |  | 0 | #N/A | 2 | 0 | #N/A | #N/A | #N/A |  | 0% | 0 | Mitigate |  |  |  |  | TBD | 0% |  |  |  | 0 | 0 | 0 | INSERT LIKELIHOOD | None | Negligible | None | 0 | 0 | 1 | 0 | 1 | 0 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | - - | 0 - 0 - 0 | 0 | 0 | 317
Retired | 319 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | Design team | If the design team is not able to ramp up at the same rate as funding is available then there will be a delay in completing designs (jp) | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 12 | Significant |  | 3 | 1 | 3 | 0 | 3 | 9 | Moderate |  | 32% | 0 | Mitigate | Ensure RF, HR and BizOps teams at JLAB and BNL are well prepared and positioned to open new staff requisitions, MOUs, contracts as needed to address staffing needs. |  |  |  | TBD | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | None | Negligible | None | 3 | 0 | 1 | 0 | 1 | 3 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 319
Retired | 320 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | SRF cavity vendor availability | If the existing cavity vendors have long lead times then cavity deliveries will be delayed (jp) |  |  |  | 12 |  |  | 0 | #N/A | 0 | 0 | #N/A | #N/A | #N/A |  | 0% | 0 | Mitigate |  |  |  |  | TBD | 0% |  |  |  | 0 | 0 | 0 | INSERT LIKELIHOOD | None | Negligible | None | 0 | 0 | 1 | 0 | 1 | 0 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | - - | 0 - 0 - 0 | 0 | 0 | 320
Retired | 321 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | ESR 400 kW Solid State Amplifiers 3 | If the ESR 400 kW/200kW Solid State Amplifier first articles are not available by (date), then acceptance testing of the first article ESR cryomodule at JLAB and BNL will be delayed. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 12 | Significant | Negligible | 3 | 1 | 3 | 1 | 3 | 9 | Moderate |  | 32% | 0 | Mitigate | CD-3A Long Lead Procurement |  |  |  | TBD | 30% | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | None | Negligible | None | 3 | 0 | 1 | 0 | 1 | 3 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 321
Retired | 322 | Threat | 6.08 RF | JLAB | S. Nagaitsev / K. Smith |  | S. Nagaitsev / K. Smith | RF | Facility Upgrades (BNL) | If BNL SRF facility upgrades are required, then |  | 5000 | Significant | 0 | Negligible | Negligible | 0 | 3 | 1 | 1 | 3 | 0 | Low |  | 0% | 0 | Mitigate |  |  |  |  | TBD | 0% | 5000 | 5000 | 5000 | 0 | 0 | 0 | INSERT LIKELIHOOD | Significant | Negligible | None | 0 | 3 | 1 | 0 | 3 | 0 | Retired |  |  | Retired |  |  |  | Never detailed |  |  | 0 | NO | 2024-05-16 | 2021-09-24 | Never detailed |  | 0 | 5000 - 5000 - 5000 | 0 - 0 - 0 | 0 | 0 | 322
Retired | RT-6-009-001 | Threat | 6.09 Cryogenics | BNL | T. Michalski / R. Than |  | T. Michalski | CRYO | Cryogenic system Long lead items (Design) | If cryogenic system design is delayed then accelerator commissioning will be delayed. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 250 | Negligible | 12 | Significant |  | 3 | 1 | 3 | 0 | 3 | 9 | Moderate |  | 32% | 80 | Mitigate | 1) Early Start of Interface Design Infrastructure Engineering /Resources 2) Add Engineering and Design Resources 3) Early Vendor Engineering Start prior to CD-3 |  | Q2 FY24 |  | L2_090, DOE Independent Project Review (IPR) for CD-2/3A Approval | 10% | 250 | 409 | 818 | 0 | 0 | 0 | Very Low | Significant | Negligible | Marginal | 1 | 3 | 1 | 2 | 3 | 3 | Retired |  | 2 FTEs MD (ACI) and 2 FTEs ME (SEIII) = $818k (loaded) 1 FTE MD and 1 FTE ME = $409k (loaded) | Retired |  |  |  | Cryo design complete. |  |  | 49.2333 | No | 2024-01-08 | 2020-06-30 | 2020-10-30 |  | 45.0667 | 250 - 409 - 818 | 0 - 0 - 0 | 49.2333 | 0 | 144 | 2023-11-30 | 1126
Retired | RT-6-09-008 | Threat | 6.09 Cryogenics | JLAB | T. Michalski / R. Than |  | T. Michalski | CRYO | Cryo LLP Refrigerators (non 3A) | If cryogenic system design is delayed at the vendor( design, procurement, fabrication), then the project will have cost & sched. Cons. | [7 empty] | #N/A | [8 empty] | Mitigate | [5 empty] | 30% | [23 empty] | replaced with RT-6-09-009 |  |  |  | No | 2024-05-02 | 2024-01-08 | Deleted
Active | RT-6-009-009 | Threat | 6.09 Cryogenics | JLAB | B. Shell | RT-6-009-009 | S. Yang | CRYO | Cryo LLP Distribution Sys | If the cryogenic distribution system design/procurement/fabrication is delayed, then the project will experience schedule delays and incur additional cost | [7 empty] | #N/A | [8 empty] | Mitigate | 1. Work with interface partners closely hoping to be able to nail down the design options ASAP. 2. Request more support for design effort when necessary. 3. Separate procurement contracts for IR02, IR06, and IR10 cryogenic distribution system. 4. Regular comm. with vendors. 5. Request separate shipment for different sections of CDS |  | Q4 FY26 |  | E0904_02820 | 30% | 107.3 | 294.6 | 589.2 | 3 | 6 | 12 | Moderate | Significant | Marginal | None | 3 | 3 | 2 | 0 | 3 | 9 | Moderate |  | Probability estimated as moderate. Assumed 2 FTE ME (SEIII & SEII) to be on each vendor site 100% for extended period. Assume total 13 weeks for Low, 26 weeks for Likely, and 52 weeks for High @ $2100/wk travel/lodging. | 88.38 | 2024-05-02 | [5 empty] | 99.11 |  |  | 2024-01-08 | 2024-01-08 |  | 93.745 | 107.3 - 294.6 - 589.2 | 3 - 6 - 12 | 99.11 | 2.1
Active | RT-6-009-002-LLP-CD3A | Threat | 6.09 Cryogenics | JLAB | B. Shell | RT-6-009-002-LLP-CD3A | B. Shell | CRYO | Cryogenic Sys LLP items procurement delay | If the satellite plant for IR10 is delayed because of the contract award delay or vendor issues, then the project will experience schedule delays and incur additional cost. | High (Risk is likely to occur with a probability of >40 to <65%) | 250 | Negligible | 15 | Critical | None | 4 | 1 | 4 | 0 | 4 | 16 | High |  | 52% | 130 | Mitigate | 2. Request more support for design effort when necessary |  | Q3 FY25 |  | E0902_04680 First Satellite Cryo Refrigerator Plant - IR10 - CD3A Scope Complete | 30% | 160 | 314 | 4314 | 3 | 12 | 18 | Moderate | Significant | Significant | None | 3 | 3 | 3 | 0 | 3 | 9 | Moderate |  | Probability estimated as moderate. Assume 1 FTE ME (SEIII) to be on site 100% for 1 year. Assume 50 weeks @ $1500/wk travel/lodging TOTAL = $239k + $75k = $314k. For the worst case add 10% vendor Incentive = $4,000k | 94.2 | 2024-08-14 | [5 empty] | 478.8 |  |  | 2021-07-30 | 2021-09-27 |  | 286.5 | 160 - 314 - 4314 | 3 - 12 - 18 | 478.8 | 3.3 | 144a_LLP | 2024-03-31 | 916
Active | RT-6-009-003 | Threat | 6.09 Cryogenics | BNL | B. Shell | RT-6-009-003 | R. Than | CRYO | 4K Cryogenics Modifications | If modifications to the RHIC cryogenic distribution system is more complicated than anticipated during detail engineering, then additional design and installation labor will be required. This will affect cost and schedule. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 250 | Negligible | 6 | Marginal | Negligible | 3 | 1 | 2 | 1 | 2 | 6 | Low |  | 32% | 80 | Mitigate | 3. Separate procurement contracts for IR02, IR06, and IR10 cryogenic distribution system |  | Q1 FY26 |  | L3_0280, CD-2/3A Director's Review Complete | 30% | 110 | 250 | 409 | 0 | 6 | 6 | Moderate | Negligible | Marginal | Negligible | 3 | 1 | 2 | 1 | 2 | 6 | Low |  | 1 FTE MD and 1 FTE ME = $409k (loaded) | 75 | 2024-01-29 | [5 empty] | 76.9 |  |  | 2020-06-30 | 2020-10-30 |  | 75.95 | 110 - 250 - 409 | 0 - 6 - 6 | 76.9 | 1.2 | 46 | 2024-03-31 | 1248
Active | RT-6-009-004 | Threat | 6.09 Cryogenics | BNL | B. Shell | RT-6-009-004 | B. Shell | CRYO | Tunnel Space Availability for Cryogenic Systems | If the space for installing the vacuum jacketed piping is not identified by CD-2 then it would result in more complicated and expensive VJP design that is difficult for installation. This could affect cost and schedule. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 800 | Marginal | 6 | Marginal | Negligible | 3 | 2 | 2 | 1 | 2 | 6 | Low |  | 32% | 256 | Mitigate | Early Start of Interface Design Infrastructure Engineering /Resources, add Engineering and Design Resources |  | Q2 FY25 |  | L2_100, CD-3A Independent Cost Review (ICR) Complete | 20% | 110 | 250 | 409 | 3 | 6 | 12 | Low | Negligible | Marginal | Negligible | 2 | 1 | 2 | 1 | 2 | 4 | Low |  | 1 FTE MD and 1 FTE ME = $409k (loaded) | 50 | 2024-02-08 | [5 empty] | 51.2667 |  |  | 2020-06-30 | 2020-10-30 |  | 50.6333 | 110 - 250 - 409 | 3 - 6 - 12 | 51.2667 | 1.4 | 47 | 2024-03-31 | 1248
Active | RT-6-009-005 | Threat | 6.09 Cryogenics | JLAB | B. Shell | RT-6-009-005 | B. Shell | CRYO | Large, Expensive Equipment QA | If large, expensive equipment, such as satellite refrigerators and He distribution systems, are not verified for quality and operation prior to arriving on site, being installed, and commissioned, then accelerator commissioning will be delayed. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 4152 | Significant | 9 | Significant | Negligible | 3 | 3 | 3 | 1 | 3 | 9 | Moderate | Assume 10% cost of Satellite Plant Cold Box and Distribution Systems. | 32% | 1328.64 | Mitigate | Perform verification testing at vendors (leak tests, preliminary functional tests), on-site inspection of received |  | Q3 FY28 |  | E0902_08800 TWR - 10 O'clock Bldg - Testing and Commissioning 06/22/28 | 10% | 400 | 1000 | 4000 | 3 | 9 | 18 | Very Low | Significant | Significant | Marginal | 1 | 3 | 3 | 2 | 3 | 3 | Low |  | Probability is estimated moderate. For the likely cost impact assume 1 additional FTE ME (SEIII) to be on site 100% for 1 year. Assume 50 weeks @ $1500/wk travel/lodging TOTAL $239k + $75K = $314k. Low cost impact is half of the likely. Add 10% vendor incentive = $1,400k for the worst case. Sched. impacts are estimated based on recent history of similar procurements at a different DOE lab. | 100 | 2024-02-08 | [5 empty] | 180 |  |  | 2022-04-13 | 2022-04-13 |  | 140 | 400 - 1000 - 4000 | 3 - 9 - 18 | 180 | 1 | 324 | 2024-03-31 | 718
Active | RT-6-009-006-LLP-CD3A | Threat | 6.09 Cryogenics | JLAB | B. Shell | RT-6-009-006-LLP-CD3A | B. Shell | CRYO | Cryo LLP items (Procuring 1 sat. refrigerator rather than 3) | If the contract award is late and a single satellite refrigerator for IR10 costs more than 1/3 of the estimated cost for 3 plants (losing economies of scale), then it will lead to increased cost and project delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 12 | Significant | None | 4 | 3 | 3 | 0 | 3 | 12 | Moderate |  | 52% | 1040 | Mitigate | Request IR06 and IR02 costing as options during the RFP process. Exercise the option for IR06 as early as feasible towards regaining some economies of scale for procuring 2 plants simultaneously |  | Q3 FY25 |  | E0902_04680 First Satellite Cryo Refrigerator Plant - IR10 - CD3A Scope Complete | 30% | 750 | 1400 | 2800 | 1 | 3 | 6 | Moderate | Significant | Negligible | None | 3 | 3 | 1 | 0 | 3 | 9 | Moderate |  | Probability estimated as moderate. Cost impacts - assume 5% 10% 20% total cost increase for low, likely, high impacts. Schedule delays estimated based on recent communications with potential vendors. | 420 | 2024-08-14 | [5 empty] | 495 |  |  | 2023-09-05 | 2023-09-05 |  | 457.5 | 750 - 1400 - 2800 | 1 - 3 - 6 | 495 | 1 |  | 2024-03-31 | 208
Active | RT-6-009-007-LLP-CD3A | Threat | 6.09 Cryogenics | JLAB | B. Shell | RT-6-009-007-LLP-CD3A | B. Shell | CRYO | IR10 Satellite Refrigerator Equipment Storage | If the satellite plant building for the IR10 satellite refrigerator is not ready for equipment, then the IR10 satellite refrigerator equipment will need to be stored until the building is ready. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 140 | Negligible | 0 | Negligible | None | 2 | 1 | 1 | 0 | 1 | 2 | Low |  | 17% | 23.8 | Mitigate | Currently, the satellite refrigerator delivery is showing 7 months prior to BORE complete. We should revise the delivery schedule in advance to set the baseline for BORE complete (plus 3 months float[?]) at the time of the Contract Award. |  | Q2 FY28 |  | E0902_04640 Deliver First Satellite Cryo Refrigerator Plant - IR10 - Milestone: 23-Apr-27 | 10% | 20 | 120 | 240 | 0 | 0 | 0 | Very Low | Negligible | Negligible | None | 1 | 1 | 1 | 0 | 1 | 1 | Low |  | https://www.statista.com/statistics/527845/warehouse-primary-rent-cost-logistics-market-netherlands-europe/ Assume Rotterdam, 73 Euro/sq.meter x 250 sq.meter - monthly rate Exchange rate from Google is 1.06 USD = 1 Euro (date - 10/25/2023) | 12 | 2024-08-14 | [5 empty] | 12.6667 |  |  | 2023-10-25 | 2023-10-25 |  | 12.3333 | 20 - 120 - 240 | 0 - 0 - 0 | 12.6667 | 0 |  | 2024-03-31 | 158
Retired | 182 | Threat | 6.09 Cryogenics | BNL | T. Michalski / R. Than |  | J. Tuozzolo | CRYO | Existing RHIC Helium Refrigerator Upgrade | If the existing RHIC Helium refrigerator upgrade (or replacement of the refrigerator) is not completed in time, it will delay the commissioning of the installed SRF Cavities at IR10. This will then delay commissioning of all three ring systems - the RCS, ESR, and HRS with beam. The estimate assumes this upgrade or replacement is off project. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 2000 | Significant | 0 |  |  | 2 | 3 | 0 | 0 | 3 | 6 | Low |  | 17% | 340 | Mitigate | If the existing refrigerator will be upgraded; then the planning and execution most be well planned with integration and support for the EIC team. If the refrigerator is to be replaced; then the replacement schedule most be integrated with a revised EIC commissioning schedule. It may be necessary to maintain the existing refrigerator for EIC commissioning and schedule a down period to convert the LHe supply from the old system to the new system. This will result in added cost. | [11 empty] | INSERT LIKELIHOOD | None |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Off Project. Milestones added to monitor progress. |  |  | 0 | NO | 2022-03-22 | 2020-06-30 | 2020-10-30 | March 2022. Retired since this risk is off project. Milestones added to RLS to monitor progress. | 0 | - - | - - | 0 | 0 | 182
Retired | RO-6-010-001-LLP-CD3A | Opportunity | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RO-6-010-001-LLP-CD3A | R. Ent | DET | PbWO4 Crystals Provided in-kind | If NSF proposal is successful, then PbWO4 crystals become in-kind. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 0 | Negligible | None | 4 | 1 | 1 | 0 | 1 | 4 | Low |  | 52% | 0 | Enhance | Submit NSF proposal |  | Q2 FY26 |  | E1005_01425 AWARD: Electron Endcap EMCal - PWO Crystals Batch 2 COMPLETE | 50% | -3117 | -3117 | -3117 | 0 | 0 | 0 | High | Significant | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Retired |  | Probability estimated as high. Cost impacts are crystals total cost (Burdened & escalated in P6). No schedule delays. | Retired | 2024-01-25 |  |  | opportunity didn't realize on time |  |  | -1558.5 | No | 2024-08-21 | 2023-06-06 | 2023-06-06 |  | -1558.5 | -3117 - -3117 - -3117 | 0 - 0 - 0 |  | 0 |  | 2024-07-31 | 421
Active | RO-6-010-002-LLP-CD3A | Opportunity | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RO-6-010-002-LLP-CD3A | R. Ent | DET | New Experimental Solenoid Provided In-Kind | If INFN in Italy and Saclay in France are able to ensure in-kind contribution from their funding agencies. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 0 | Negligible | None | 4 | 1 | 1 | 0 | 1 | 4 | Low |  | 52% | 0 | Enhance | Good communication with foreign agencies |  | Q4 FY25 |  | E1007_02120 CD3A Scope Complete - Kick Off Meeting Held | 25% | -13971 | -13971 | -13971 | 0 | 0 | 0 | Low | Critical | Negligible | None | 2 | 4 | 1 | 0 | 4 | 8 | Moderate |  | Probability estimated as low. Cost impacts are based on the full total solenoid magnet cost in P6 (burdened & escalated). No schedule impact. | -3492.75 | 2024-09-20 | [5 empty] | -3492.75 |  |  | 2023-08-28 | 2023-08-28 |  | -3492.75 | -13971 - -13971 - -13971 | 0 - 0 - 0 |  | 0 |  | 2024-07-31 | 338
Active | RO-6-010-003-LLP-CD3A | Opportunity | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RO-6-010-003-LLP-CD3A | R. Ent | DET | PbWO4 Crystals Provided in-kind | If NSF proposal is successful, then phase 2,3,4 PbWO4 crystals become in-kind. | High (Risk is likely to occur with a probability of >40 to <65%) | 0 | Negligible | 0 | Negligible | None | 4 | 1 | 1 | 0 | 1 | 4 | Low |  | 52% | 0 | Enhance | Re-submit NSF proposal |  | Q2 FY26 |  | E1005_01425 AWARD: Electron Endcap EMCal - PWO Crystals Batch 2 COMPLETE | 50% | -3847 | -3847 | -3847 | 0 | 0 | 0 | High | Significant | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Moderate |  | Probability estimated as high. Cost impacts are crystals total cost (Burdened & escalated in P6). No schedule delays. | -1923.5 | 2024-08-13 |  |  | first batch was no in-kind |  |  | -1923.5 |  | 2024-08-21 | 2023-09-05 | 2023-09-05 |  | -1923.5 | -3847 - -3847 - -3847 | 0 - 0 - 0 |  | 0
Active | RT-6-010-001-LLP-CD3A | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-001-LLP-CD3A | R. Ent | DET | New Experimental Solenoid Delivery Delay | If central magnet is delayed, then the project will be delayed and the project cost will increase. | High (Risk is likely to occur with a probability of >40 to <65%) | 10000 | Critical | 12 | Significant | Crisis | 4 | 4 | 3 | 5 | 5 | 20 | High | Estimated cost of a new magnet | 52% | 5200 | Mitigate | Work closely with JLab procurement to advance the procurement package following the earlier RFI; include cognizant engineers on the bid evaluation team; provide the conductor after QA as GFI; have regular communication with vendors including frequent visits by cognizant staff for vendor oversight; ensure attention to QA and transport requirements early in the procurement |  | Q1 FY25 |  | E1007_02460 CD3A Scope Complete - Detector Solenoid Arrival Checks Complete | 50% | 5000 | 7000 | 10000 | 6 | 12 | 24 | High | Critical | Significant | None | 4 | 4 | 3 | 0 | 4 | 16 | High |  | Large detector solenoids are one of a kind and can have technical, cost and schedule risks at vendor during construction. Probability and schedule estimates are based on experience with similar magnets. Cost impacts: Worst case - extreme problems with magnet contract lead to big magnet repairs and a need for new components. Likely and best case - cost increases to resolve various technical issues. Cost impacts estimated in burdened & escalated dollars. | 3500 | 2024-09-20 | [5 empty] | 3666.6667 |  |  | 2020-06-30 | 2020-10-30 |  | 3583.3333 | 5000 - 7000 - 10000 | 6 - 12 - 24 | 3666.6667 | 7 | 137_LLP | 2024-07-31 | 1370
Active | RT-6-010-001a-LLP-CD3A | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-001a-LLP-CD3A | R. Ent | DET | Detector Solenoid Doesn't Pass Acceptance Tests | If central magnet is failing the Q&A at arrival at BNL (factually not working), then a new magnet is required. | High (Risk is likely to occur with a probability of >40 to <65%) | 18000 | Critical | 54 | Crisis | Critical | 4 | 4 | 5 | 4 | 5 | 20 | High |  | 52% | 9360 | Mitigate | Fold in technical and QA strength of vendor in procurement process. Work close together with vendor with frequent vendor visits to ensure quality control during construction and transport phase. Add parallel thermosiphons as backup, and sufficient quench protection and thermistors with backups to diagnose magnet during operations. |  | Q3 FY29 |  | E1007_02460 CD3A Scope Complete - Detector Solenoid Arrival Checks Complete | 10% | 17805 | 17805 | 17805 | 48 | 54 | 60 | Very Low | Critical | Crisis | Critical | 1 | 4 | 5 | 4 | 5 | 5 | Low |  | Probability estimated low. Cost impact is based on the current magnet cost of 15M FY2023 $. Non-labor compound escalation factor 1.18698 for 2029 is applied to $15M. Schedule impacts estimated based on current solenoid magnet production time. | 1780.5 | 2024-09-20 | [5 empty] | 1780.5 |  |  | 2023-06-27 | 2023-06-27 |  | 1780.5 | 17805 - 17805 - 17805 | 48 - 54 - 60 | 1780.5 | 5.4 |  | 2024-07-31 | 400
Active | RT-6-010-002 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-002 | R. Ent | DET | Accelerator & detector scope are not aligned and coupled | If the collider and especially the IR design develop independently of the detector design then EIC science cannot be delivered. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 500000 | Crisis | 48 | Crisis | Critical | 3 | 5 | 5 | 4 | 5 | 15 | High |  | 32% | 160000 | Mitigate | Intent to keep CD-2, CD-3 aligned. Keep IR and detector design integrated. Develop interface control documents and have a dedicated person following closely the accelerator design to realize conflicts early. |  | Q1 FY26 |  | L1_050 CD-2/3 Approve Start of Construction | 20% | 20000 | 100000 | 150000 | 12 | 36 | 48 | Low | Crisis | Crisis | Critical | 2 | 5 | 5 | 4 | 5 | 10 | Moderate |  | Residual risk remains due to unknowns even if we remain working together among detector and IR to ensure nothing is forgotten. Impact of an unknown can be large though, including finding out late that one can not make all KPPs with only mitigation some beam line vacuum or magnet fixes. | 20000 | 2024-01-25 | [5 empty] | 18000 |  |  | 2020-06-30 | 2020-10-30 |  | 19000 | 20000 - 100000 - 150000 | 12 - 36 - 48 | 18000 | 6.4 | 138 | 2024-07-31 | 1370
Active | RT-6-010-003 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-003 | R. Ent | DET | No redundancy in detectors built | If inner detectors fail after installation, then repair can only be done outside of Hall causing long schedule delays. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 9 | Significant | Marginal | 2 | 3 | 3 | 2 | 3 | 6 | Low |  | 17% | 850 | Mitigate | Prioritize detector elements with multi-purpose use above performance. Minimize the time from installation to maintenance mode. Ensure detectors have sufficient segmentation and redundancy in the design. Integrate as possible protection systems into the electronics. |  | Q3 FY25 |  | L1_050 CD-2/3 Approve Start of Construction | 20% | 1000 | 5000 | 7000 | 3 | 6 | 9 | Low | Significant | Marginal | Marginal | 2 | 3 | 2 | 2 | 3 | 6 | Low |  | Can require additional scope or repairs to ensure redundancy, and a down to move detector to assembly hall and back in.. | 1000 | 2024-01-25 | [5 empty] | 866.6667 |  |  | 2020-06-30 | 2020-10-30 |  | 933.3333 | 1000 - 5000 - 7000 | 3 - 6 - 9 | 866.6667 | 1.2 | 139 | 2024-07-31 | 1370
Active | RT-6-010-004 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-004 | R. Ent | MAP | Background impact on Detector performance | If the background in the IR region are not sufficiently controlled, then KPPs will be at risk. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 12 | Significant | Marginal | 2 | 4 | 3 | 2 | 4 | 8 | Moderate |  | 17% | 1700 | Mitigate | Maintain strong communication with Accelerator design teams developing hardware that could impact or mitigate backgrounds, e.g. collimator design, vacuum systems, beamlines, etc. Continue modeling of physics processes to estimate backgrounds and use the results to guide accelerator and integrated interaction region/detector design. As soon as possible, identify key accelerator components that are likely to generate backgrounds, and develop Interface Control Documents prior to CD-2. |  | Q1 FY32 |  | L1_090 CD-4 Approval Early Completion | 20% | 5000 | 10000 | 15000 | 9 | 12 | 18 | Low | Critical | Significant | Marginal | 2 | 4 | 3 | 2 | 4 | 8 | Moderate |  | Can require additional scope to ensure KPPs can be met, an example can be special shielding. Due to unknowns relate to unique e-p/ion collider probability for this remains. | 2000 | 2024-01-25 | [5 empty] | 2000 |  |  | 2020-06-30 | 2020-10-30 |  | 2000 | 5000 - 10000 - 15000 | 9 - 12 - 18 | 2000 | 2.6 | 141 | 2024-07-31 | 1370
Retired | RT-6-010-005 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | R. Ent | DET | Detector DIRC technologies | If DIRC technology for particle identification up to 8 GeV/c momenta in the Central detector barrel region proves prohibitive, then we do not have an alternate technology. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 6 | Marginal | Marginal | 2 | 3 | 2 | 2 | 3 | 6 | Low |  | 17% | 850 | Mitigate | DIRC development supported as part of generic EIC-related detector R&D program to reduce risk. OPC activity to resolve interference with need of hermetic EM calorimetry. Project R&D to resolve remaining optics issues with readout. Fold in expected timeline for (R&D and) PED of proximity RICH as alternate candidate detector. Move to this backup solution as needed. |  |  |  | DE_0200_3000, Detector R&D and Physics Design - Complete | 20% | 5000 | 10000 | 15000 | 6 | 12 | 18 | Low | Critical | Significant | Marginal | 2 | 4 | 3 | 2 | 4 | 8 | Retired |  | Signs are positive this does not happen, but remains a probability until R&D is completed and further design maturity is reached for integration. | Retired |  |  |  | Elke and Rolf |  |  | 2000 |  | 2023-05-23 | 2020-06-30 | 2020-10-30 |  | 2666.6667 | 5000 - 10000 - 15000 | 6 - 12 - 18 | 2000 | 2.4 | 156
Active | RT-6-010-005b | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-005b | R. Ent | DET | Detector DIRC technologies | If it turns out the reuse of the DIRC bars from the BaBar experiment is not possible, one will have to find a vendor to do this quarz bars and the tedious polishing. This will lead to a delay in schedule DIRC might not be ready for CD-4 deadline. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 18 | Critical | Marginal | 2 | 4 | 4 | 2 | 4 | 8 | Moderate |  | 17% | 1700 | Mitigate | DIRC development supported as part of generic EIC-related detector R&D program to reduce risk. Off project activity to secure the BaBAR DIRC bars and test as soon as possible to take on of the boxes apart and refurbish individual bars. |  | Q1 FY27 |  | E1002_04080 Detector R&D and Physics Design - Complete | 20% | 5000 | 10000 | 15000 | 6 | 12 | 18 | Low | Critical | Significant | Marginal | 2 | 4 | 3 | 2 | 4 | 8 | Moderate |  | Signs are positive this does not happen, but remains a probability until R&D and work to complete the refurbishment of one bar is complete. | 2000 | 2024-01-25 | [5 empty] | 2000 |  |  | 2020-06-30 | 2020-10-30 |  | 2000 | 5000 - 10000 - 15000 | 6 - 12 - 18 | 2000 | 2.4 | 156 | 2024-07-31 | 1370
Active | RT-6-010-006 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-006 | E. Aschenauer | DET | Failure to Secure in-Kind Detector Components | If collaborators are not available to support in kind contributions, the cost of the detector to DOE will increase. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 100000 | Crisis | 9 | Significant | Critical | 2 | 5 | 3 | 4 | 5 | 10 | Moderate |  | 17% | 17000 | Mitigate | Call for Eol and international engagement. Keep international community aligned and well informed. Collaborate with DOE/NP on written agreements to secure in-kind contributions in dynamic environment. Verify that reuse of existing equipment is available and functional. |  | Q3 FY25 |  | L1_050 CD-2/3 Approve Start of Construction | 20% | 30000 | 60000 | 100000 | 6 | 9 | 12 | Low | Crisis | Significant | Critical | 2 | 5 | 3 | 4 | 5 | 10 | Moderate |  | Assume 1/3 of the detector cost as worst-case scenario - this was assumed as in-kind contribution to detector scope at start of EIC project. | 12000 | 2024-01-25 | [5 empty] | 12666.6667 |  |  | 2020-06-30 | 2020-10-30 |  | 12333.3333 | 30000 - 60000 - 100000 | 6 - 9 - 12 | 12666.6667 | 1.8 | 120 | 2024-07-31 | 1370
Retired | RT-6-010-007 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | E. Aschenauer | DET | Detector Sci-Glass Technologies | If final stage of R&D for Sci-Glass towards large-scale production is not successful, the detector technology choices in some region of the reference detector need to be changed to either more costly options or one will have to sacrify science performance. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 6 | Significant | Marginal | 2 | 4 | 3 | 2 | 4 | 8 | Moderate |  | 17% | 1700 | Mitigate | Continue R&D as supported by SBIR and the generic EIC-related R&D for high-density glass suitable for electromagnetic calorimetry (Sci-Glass). Early tests show good quality and good radiation hardness. Continue scale-up to glass of up to 50 cm longitudinal dimension, and large-scale glass production in furnaces to make many tens of glass blocks per day. Alternatives would be more costly lead-tungstate, reuse (if possible) of sufficient Pb-glass, or worsened science reach. |  | Q3 FY23 |  | E1002_11170 | 20% | 5000 | 10000 | 12000 | 3 | 6 | 12 | Low | Critical | Marginal | Marginal | 2 | 4 | 2 | 2 | 4 | 8 | Retired |  | Initial R&D looks positive. Remains a risk until detector tests with 8x8 prototype completed. Alternate backup options are significantly more expensive. | Retired |  |  |  | Retired April 2023. Sci-Glass is not the technology chosen by the collaboration |  |  | 1800 | NO | 2023-04-04 | 2020-06-30 | 2020-10-30 |  | 1900 | 5000 - 10000 - 12000 | 3 - 6 - 12 | 1800 | 1.4 | 172
Active | RT-6-010-008 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-008 | E. Aschenauer | DET | Hadron Polarimeter technology not applicable for EIC | If Hadron Polarimeter technology from RHIC is not applicable to EIC, especially with the increased bunch current and bunch frequency, then the physics performance requirements of 1% to 1.5% systematics will not be achieved | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 12 | Significant | Negligible | 3 | 2 | 3 | 1 | 3 | 9 | Moderate |  | 32% | 320 | Mitigate | 1) improved detector read-out technology, 2) Find new target technology with R&D , 3) Find new physics process with R&D |  | Q3 FY25 |  | L1_050 CD-2/3 Approve Start of Construction | 30% | 1000 | 2000 | 3000 | 6 | 12 | 18 | Moderate | Significant | Significant | Negligible | 3 | 3 | 3 | 1 | 3 | 9 | Moderate |  | Engineering judgement | 600 | 2024-01-25 | [5 empty] | 600 |  |  | 2020-06-30 | 2020-10-30 |  | 600 | 1000 - 2000 - 3000 | 6 - 12 - 18 | 600 | 3.6 | 128 | 2024-07-31 | 1370
Retired | RT-6-010-009 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | R. Ent | DET | Location of detector is IP6 | If detector location is IP6, then a dependency on STAR operations is introduced. | Very Low (There is a <10% chance that this event will occur) | 5000 | Significant | 3 | Significant | Negligible | 1 | 3 | 3 | 1 | 3 | 3 | Low | Estimate/guess what the costs would be if one has to expedite the schedule, may need to expedite work/people on the removal of existing equipment with unknowns, expedite IR integration and matching of the IR with the accelerator optics/dynamics much up-down stream (that is done for IP6 already). My personal experience is that expediting schedules can easily cost a few M$. | 5% | 250 | Mitigate | Expedite time to deinstall STAR apparatus after STAR operations cease. Ensure moving the STAR apparatus to the assembly Hall remains common procedure. Ensure there are no additional legacy equipment installed to increase needed removal time of DX magnets. |  |  |  | L2_0510, STAR Detector R&R Complete and Dismantled | 5% | 2000 | 3000 | 5000 | 1 | 3 | 6 | Very Low | Significant | Negligible | Negligible | 1 | 3 | 1 | 1 | 3 | 3 | Retired |  | Main residual risk is underestimate of cost or schedule for STAR removal due to unforeseen. | Retired |  |  |  | Replaced with risk 009b |  |  | 166.6667 | No | 2023-06-07 | 2020-06-30 | 2020-10-30 |  | 216.6667 | 2000 - 3000 - 5000 | 1 - 3 - 6 | 166.6667 | 0.16667 | 188
Active | RT-6-010-009b | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-009b | R. Ent | DET | R&R for STAR, IP6 and sPHENIX is not done in time for starting construction of ePIC | If either there are workforce or funding issues for the R&R work for STAR, IP6 and sPHENIX a delay for the construction of the ePIC detector is introduced | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 5000 | Significant | 9 | Significant | None | 3 | 3 | 3 | 0 | 3 | 9 | Moderate |  |  |  | Mitigate | Develop a reliable schedule, cost and workforce needs for the R&R of STAR, sPHENIX and IP-6. Ensure deinstallation of STAR and the IR-6 accelerator components are possible in parallel. The sPHENIX R&R needs to be planned in equal detail as STAR. |  | Q4 FY26 |  | L2_320, STAR Detector D&D Complete and Dismantled | 20% | 4000 | 5000 | 6000 | 6 | 9 | 12 | Low | Significant | Significant | Negligible | 2 | 3 | 3 | 1 | 3 | 6 | Low |  | Engineering judgement | 1000 | 2024-01-25 | [5 empty] | 1000 |  |  | 2023-06-07 | 2023-06-07 |  | 1000 | 4000 - 5000 - 6000 | 6 - 9 - 12 | 1000 | 1.8 |  | 2024-07-31 | 420
Active | RT-6-010-010 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-010 | R. Ent | DET | Detector ASIC technologies | If design of new ASIC readout is required for streaming readout the EIC detectors, it takes 5 years on average for a new ASIC design to get to the fabrication stage. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 12 | Significant | Marginal | 2 | 3 | 3 | 2 | 3 | 6 | Low |  | 17% | 850 | Mitigate | Develop a document as part of OPC activities to detail the requirements for the needs from the different subdetectors on the ASIC and FPGA design. Fold in expected timelines for alternate ASIC, PCB and FPGA candidates beyond those existing. Start potential new ASIC design as early as possible with R&D. Move to backup solution (at the cost of reduced science output) as needed. |  | Q1 FY27 |  | E1002_04060 Detector R&D - Electronics - eRD109 (ASICs/FEEs, PID LAPPDs and or MCPMTs) complete | 20% | 3000 | 5000 | 10000 | 6 | 12 | 18 | Low | Significant | Significant | Marginal | 2 | 3 | 3 | 2 | 3 | 6 | Low |  | We have more time for ASICs completion as electronics can come late in the detector assembly schedule. Main risk is which exact ASICs would be late as some are needed for the beam line elements. | 1000 | 2024-01-25 | [5 empty] | 1200 |  |  | 2020-06-30 | 2020-10-30 |  | 1100 | 3000 - 5000 - 10000 | 6 - 12 - 18 | 1200 | 2.4 | 142 | 2024-07-31 | 1370
Retired | RT-6-010-011 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | E. Aschenauer | DET | Detector Photosensor Technologies | If SiPM choice of photosensors proves unfeasible due to radiation sensitivity, then will need to develop alternate photosensor technology (LAPPD, MCP-PMT in high field) that requires R&D and will increase cost and schedule. There is a chance that in some regions of the detectors it will be extremely difficult to find with equal performance and at the same low price. | Very Low (There is a <10% chance that this event will occur) | 20000 | Critical | 12 | Critical | Significant | 1 | 4 | 4 | 3 | 4 | 4 | Low |  | 5% | 1000 | Mitigate | All indications are that neutron background levels are such that SiPMs can work at EIC and provide a photosensor in high magnetic field. Alternatives are MaPMTs that add cost and it is unclear how to operate them near the high-field solenoid. Microchannel plate photomultipliers (MCP-PMTs) from commercial vendors have shown extraordinarily good timing and position resolution and high magnetic field tolerance, but are generally far too expensive for large instrumentation. Continued R&D on a new type of MCP-PMT using atomic layer deposition technique (LAPPD) as cost-effective MCP-PMT option, towards 6x6 cm2 and 10x10 cm2 sizes, including beam test validation is needed. |  |  |  | DE_0200_3000, Detector R&D and Physics Design - Complete | 5% | 15000 | 20000 | 25000 | 6 | 12 | 18 | Very Low | Critical | Significant | Significant | 1 | 4 | 3 | 3 | 4 | 4 | Retired |  | Residual risk is if a brute-force more expensive maPMT option needs to be implemented or a cost-effective LAPPD option will also do. | Retired |  |  |  | Elke and Rolf |  |  | 1000 |  | 2023-05-23 | 2020-06-30 | 2020-10-30 |  | 1333.3333 | 15000 - 20000 - 25000 | 6 - 12 - 18 | 1000 | 0.6 | 173
Active | RT-6-010-011b | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-011b | E. Aschenauer | DET | PID Detector Photosensor Technologies | Backward RICH: If LAPPDs are not a viable option as photosensors, one can replace them by MCP-PMTs. This will add significant cost. Forward dRICH: Because of the location of the dRICH SiPMs are the only possible solution as photonsensors. If the data rate due to noise due to radiation damage will become to large one needs to find a way to suppress noise early in the readout electronics or replace the SiPMs regularly. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 25000 | Critical | 12 | Significant | None | 2 | 4 | 3 | 0 | 4 | 8 | Moderate |  |  |  | Mitigate | All indications are that neutron background levels are such that SiPMs can work at EIC and provide a photosensor in high magnetic field. The alternatives for the bRICH are MaPMTs that add cost but are readily available from vendors.. |  | Q1 FY27 |  | E1002_04080 Detector R&D and Physics Design - Complete | 10% | 20000 | 25000 | 30000 | 6 | 12 | 18 | Moderate | Significant | Significant | Significant | 3 | 3 | 3 | 3 | 3 | 9 | Moderate |  | Residual risk is if a brute-force more expensive maPMT option needs to be implemented for the bRICH and for the dRICH a solution in the electronics or during operations needs to be found. | 2500 | 2024-01-25 | [5 empty] | 2500 |  |  | 2022-04-15 | 2022-04-15 |  | 2500 | 20000 - 25000 - 30000 | 6 - 12 - 18 | 2500 | 1.2 |  | 2024-07-31 | 838
Active | RT-6-010-012 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-012 | R. Ent | DET | Detector AC-LGAD Technology | If final stage R&D towards using AC-LGAD for a ToF detector is delayed, then different technologies are needed to provide this function. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 9 | Significant | None | 3 | 4 | 3 | 0 | 4 | 12 | Moderate |  |  |  | Mitigate | Continue project R&D and strengthen the AC-LGAD consortium. Investigate alternative technologies for Barrel and far forward detectors. |  | Q3 FY25 |  | L1_050 CD-2/3 Approve Start of Construction | 30% | 5000 | 10000 | 15000 | 6 | 9 | 15 | Moderate | Critical | Significant | Significant | 3 | 4 | 3 | 3 | 4 | 12 | Moderate |  | Residual is the delta to allow to change technology for the ToF system | 3000 | 2024-01-25 | [5 empty] | 3000 |  |  | 2022-04-15 | 2022-04-15 |  | 3000 | 5000 - 10000 - 15000 | 6 - 9 - 15 | 3000 | 3 | 190 | 2024-07-31 | 838
Active | RT-6-010-013-LLP-CD3A | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-013-LLP-CD3A | R. Ent | DET | Detector Forward HCal Steel Delivery delay | If HCal vendor selection takes longer than planned due to vendor reqs, or production is delayed at the vendor, then there will be project delays & cost increase. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 4000 | Significant | 9 | Significant | None | 3 | 3 | 3 | 0 | 3 | 9 | Moderate |  | 32% | 1280 | Mitigate | Work closely with procurement and cognizant engineers to ensure timely award of contracts, regular communication with vendors. |  | Q3 FY25 |  | E1006_13780 CD3A Scope Complete - LFHCal - 8M Module Casing steel | 20% | 1000 | 2000 | 4000 | 6 | 9 | 12 | Low | Significant | Significant | None | 2 | 3 | 3 | 0 | 3 | 6 | Low |  | Probability is estimated as low. Delays are estimated to be 6-9-12 mo depending on competition for vendors from other projects worldwide. Cost impacts are vendor incentives to expedite vendor schedule. | 400 | 2024-09-20 | [5 empty] | 466.6667 |  |  | 2022-11-30 | 2022-11-30 |  | 433.3333 | 1000 - 2000 - 4000 | 6 - 9 - 12 | 466.6667 | 1.8 | LLP_6.10_1 | 2024-07-31 | 609
Active | RT-6-010-014-LLP-CD3A | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-014-LLP-CD3A | R. Ent | DET | Backward EMCal PbWO4 Crystals Delivery Delay | If the PbWO4 towers vendor is busy with demands from other experiments world wide, then this can lead to a oversubscription of this vendor ​and result in schedule delays. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 12 | Significant | None | 3 | 4 | 3 | 0 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | Work closely with procurement and cognizant engineers to ensure timely award of contract(s), Regular communication with vendor(s) |  | Q2 FY26 |  | E1005_1500 CD3A Scope Complete - Electron Endcap EMCal PWO Crystals | 10% | 2000 | 6000 | 10000 | 6 | 12 | 24 | Very Low | Critical | Significant | None | 1 | 4 | 3 | 0 | 4 | 4 | Low |  | Probability and schedule impacts are based on 20 year experience on similar projects. Cost impacts: Best and likely scenarios are vendor incentives to expedite vendor schedule, worst case: one additional oven for the vendor. | 600 | 2024-09-20 | [5 empty] | 600 |  |  | 2022-11-30 | 2022-11-30 |  | 600 | 2000 - 6000 - 10000 | 6 - 12 - 24 | 600 | 1.4 | LLP_6.10_2 | 2024-07-31 | 609
Active | RT-6-010-015-LLP-CD3A | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-015-LLP-CD3A | R. Ent | DET | Detector SiPM based Photon sensors Delivery Delay | If SiPMs are delivered late, then it will result in cost increase and schedule delays. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 2000 | Significant | 6 | Marginal | None | 3 | 3 | 2 | 0 | 3 | 9 | Moderate |  | 32% | 640 | Mitigate | Work closely with procurement and cognizant engineers to ensure timely award of contract(s), Regular communication with vendor(s) |  | Q1 FY25 |  | E1006_07920 CD3A Scope Complete - LFHCal - SiPMs 1.3mm | 10% | 500 | 1000 | 2000 | 3 | 6 | 12 | Very Low | Significant | Marginal | None | 1 | 3 | 2 | 0 | 3 | 3 | Low |  | Probability estimated as very low. Costs are vendor incentives to expedite schedule. World wide demand for SiPMs could delay our production by 3-6-12 mo. | 100 | 2024-09-20 | [5 empty] | 116.6667 |  |  | 2022-11-30 | 2022-11-30 |  | 108.3333 | 500 - 1000 - 2000 | 3 - 6 - 12 | 116.6667 | 0.7 | LLP_6.10_3 | 2024-07-31 | 609
Active | RT-6-010-016-LLP-CD3A | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-016-LLP-CD3A | R. Ent | DET | Detector Sci Fiber for Barrel and Hadron Endcap delivery delay | If SciFi for Barrel and Hadron Endcap is delayed, then calorimeter block and sector production will be late. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1500 | Significant | 6 | Marginal | None | 3 | 3 | 2 | 0 | 3 | 9 | Moderate |  | 32% | 480 | Mitigate | Work closely with procurement and cognizant engineers to ensure timely award of contract(s), Regular communication with vendor(s) |  | Q3 FY25 |  | E1005_04640 CD3A Scope Complete - Barrel EMCal - Scintillation Fibers | 10% | 500 | 1000 | 1500 | 3 | 6 | 12 | Very Low | Significant | Marginal | None | 1 | 3 | 2 | 0 | 3 | 3 | Low |  | 7km of fibers are needed to construct the individual calorimeter sectors and blocks. There is only one vendor world wide providing SciFi with the required performance. The 2nd vendor would need significant R&D time to reach the required performance. Costs are vendor incentives to expedite schedule. Probability is estimated as very low. Schedule impacts estimated based on experience with similar procurements. | 100 | 2024-09-20 | [5 empty] | 100 |  |  | 06.27.23 | 2023-06-27 |  | 100 | 500 - 1000 - 1500 | 3 - 6 - 12 | 100 | 0.7 |  | 2024-07-31 | 400
Active | RT-6-010-017-LLP-CD3A | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-017-LLP-CD3A | R. Ent | DET | Currency fluctuations on Detector LLPs | If the exchange rates for Euro and/or Yen are different from the ones used to estimate Detector LLP cost, then the cost will be affected. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 0 | Negligible | 0 | Negligible | None | 2 | 1 | 1 | 0 | 1 | 2 | Low |  | 17% | 0 | Accept | Accept and use contingency |  | Q1 FY25 |  | E1005_1500 CD3A Scope Complete - Electron Endcap EMCal PWO Crystals | 20% | -3200 | 0 | 3200 | 0 | 0 | 0 | Low | None | Negligible | None | 2 | 0 | 1 | 0 | 1 | 2 | Low |  | Several of the LLP, PbWO4 crystals, SciFi and SIPMS have world wide only one vendor, who sits outside the US. Due to the world market the exchange rate to the US-dollar to the Euro and the Yen can vary. Assume probability 20%. Assume -10% for best case, 0% for likely and +10% for the worst case of cost impact. | 0 | 2024-09-20 | [5 empty] | 0 |  |  | 06.27.23 | 2023-06-27 |  | 0 | -3200 - 0 - 3200 | 0 - 0 - 0 | 0 | 0 |  | 2024-07-31 | 400
Active | RT-6-010-018 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-018 | R. Ent | DET | Anticipated ASTROPIX Waver size is not available | If the 12 inch wavers at the date of ASTROPIX production are not available the 8 inch more expensive wavers need to be used | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 2000 | Significant | 0 | Negligible | None | 3 | 3 | 1 | 0 | 3 | 9 | Moderate |  | 32% | 640 | Accept | Include in contingency calculation |  | Q1 FY26 |  | E1005_06120 Barrel EMCal First Article Preproduction - Procurement Readiness Review | 30% | 1500 | 2000 | 2500 | 0 | 0 | 0 | Moderate | Significant | Negligible | Significant | 3 | 3 | 1 | 3 | 3 | 9 | Moderate |  | Probability is assumed moderate. The cost increase is based on the additional number of wavers needed and the potential Q&A loses | 600 | 2024-01-25 | [5 empty] | 600 |  |  | 2023-08-10 | 2023-08-10 |  | 600 | 1500 - 2000 - 2500 | 0 - 0 - 0 | 600 | 0 |  | 2024-07-31 | 356
Active | RT-6-010-019 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-019 | R. Ent | DET | 2nd engineering run is needed for the sensors of the outer MAPS layers | If there are still unresolved technical issues after the first engineering run for the large MAPS sensors in the outer layers, a 2nd engineering run is needed. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 12 | Significant | None | 3 | 2 | 3 | 0 | 3 | 9 | Moderate |  | 32% | 320 | Accept | Accept and use contingency |  | Q1 FY25 |  | E1003_01160 RQN: Tracking FY 25 Procurements | 25% | 770 | 1000 | 1500 | 9 | 12 | 15 | Low | Significant | Significant | Significant | 2 | 3 | 3 | 3 | 3 | 6 | Low |  | Probability is assumed low. The cost and schedule impact is calculated based on the typical cost and time for an engineering run for similar complexity | 250 | 2024-01-25 | [5 empty] | 272.5 |  |  | 2023-08-10 | 2023-08-10 |  | 261.25 | 770 - 1000 - 1500 | 9 - 12 - 15 | 272.5 | 3 |  | 2024-07-31 | 356
Active | RT-6-010-020-LLP-CD3B | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-020-LLP-CD3B | R. Ent | DET | Detector Magnet Power Supply Delivery Delay | If magnet power supply is delivered late, then acceptance testing of the detector solenoid can not be completed and there will be schedule delays for installation of accelerator components. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 500 | Marginal | 12 | Significant | Critical | 2 | 2 | 3 | 4 | 4 | 8 | Moderate |  | 17% | 85 | Mitigate | Get CD-3B approval to ensure procurement starts early to be able to run magnet at full current early and move magnet to Assembly Hall for continued subsystem installation. |  | Q3 FY25 |  | E1007_03060 Solenoid Ready for Integration | 15% | 50 | 100 | 250 | 3 | 9 | 18 | Low | Negligible | Significant | Negligible | 2 | 1 | 3 | 1 | 3 | 6 | Low |  | Probability is estimated very low. Delays are due to worldwide vendor competition. Costs are a combination of vendor incentives to expedite schedule. | 15 | 2024-08-02 | [5 empty] | 20 |  |  | 2024-08-02 | 2024-08-02 |  | 17.5 | 50 - 100 - 250 | 3 - 9 - 18 | 20 | 1.5 |  | 2024-07-31 | -2
Active | RT-6-010-021-LLP-CD3B | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-021-LLP-CD3B | R. Ent | DET | Detector Magnet Flux Steel Delivery Delay | If magnet flux return steel is delivered late due to tight steel market and Buy American reqs, then acceptance of the detector solenoid can not be completed and there will be schedule delays for installation of accelerator components. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 24 | Critical | Critical | 4 | 3 | 4 | 4 | 4 | 16 | High |  | 52% | 1040 | Mitigate | Get CD-3B approval to ensure procurement starts early to be able to run magnet at full current early and move magnet to Assembly Hall for continued subsystem installation. |  | Q1 FY26 |  | E1007_03060 Solenoid Ready for Integration | 20% | 500 | 1000 | 1500 | 6 | 12 | 18 | Low | Significant | Significant | Negligible | 2 | 3 | 3 | 1 | 3 | 6 | Low |  | Probability is estimated very low. Delays are due to worldwide vendor competition. Costs are a combination of vendor incentives to expedite schedule. | 200 | 2024-08-02 | [5 empty] | 200 |  |  | 2024-08-02 | 2024-08-02 |  | 200 | 500 - 1000 - 1500 | 6 - 12 - 18 | 200 | 2.4 |  | 2024-07-31 | -2
Active | RT-6-010-022-LLP-CD3B | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-022-LLP-CD3B | R. Ent | DET | Detector Electronics Readout Components Become Obsolete | If we can not purchase VTRx+/lpGBT linked to CERN production, then manufacturer will not assemble anymore, components can become obsolete, and a new design for these readout components is needed. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 24 | Critical | Critical | 4 | 3 | 4 | 4 | 4 | 16 | High |  | 52% | 1040 | Mitigate | CD-3B Long-Lead Procurement to ensure we are in phase with manufacturer last assembly process |  | Q3 FY25 |  | E1004_03365 dRICH - Photo Sensors/Electronics/DAQ Readout Sys - Constr - Complete | 15% | 50 | 100 | 150 | 3 | 6 | 12 | Low | Negligible | Marginal | Negligible | 2 | 1 | 2 | 1 | 2 | 4 | Low |  | Probability is estimated very low, cost & schedule are calculated as possible uncertainty in costs and schedule as the production run of these components must follow completion of the ATLAS and CMS components. | 15 | 2024-08-02 | [5 empty] | 15 |  |  | 2024-08-02 | 2024-08-02 |  | 15 | 50 - 100 - 150 | 3 - 6 - 12 | 15 | 1.05 |  | 2024-07-31 | -2
Active | RT-6-010-023 | Opportunity | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-023 | R. Ent | DET | Additional in-kind contributions after CD-2 | If the funding cycles at several international countries are not aligned with the CD-schedule of the EIC project, then the funding proposals will be approved after CD-2. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | -10000 | Critical | 0 | Negligible | Negligible | 3 | 4 | 1 | 1 | 4 | 12 | Moderate |  | 32% | -3200 | Mitigate | Good communication with foreign agencies. If in-kind contributions are not confirmed by CD-2 the costs are included in the Project costs to DOE. If the additional in-kind contributions can be realized beyond CD-2 it reduces stress on the DOE Project cost. |  |  |  | T1-040 3B LLP approval | 30% | -10000 | -20000 | -30000 | 0 | 0 | 0 | Moderate | Critical | Negligible | Negligible | 3 | 4 | 1 | 1 | 4 | 12 | Moderate |  | Probability is estimated low. Costs are calculated from the cost currently implemented in P6. | -6000 | 2024-08-02 | [5 empty] | -6000 |  |  | 2024-08-02 | 2024-08-02 |  | -6000 | -10000 - -20000 - -30000 | 0 - 0 - 0 | -6000 | 0 |  | 2024-07-31 | -2
Active | RT-6-010-024-LLP-CD3B | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-024-LLP-CD3B | R. Ent | DET | Delay of Next Phases of Detector CD-3A LLP: Sci Fiber for Barrel and Hadron Endcap | If CD-3B funds are not available to fulfill the obligations in the CD-3A contracts to continue the productions of the Sci Fiber for Barrel and Hadron Endcap, then additional cost and delays will incur | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 5823 | Critical | 12 | Significant | Critical | 3 | 4 | 3 | 4 | 4 | 12 | Moderate |  | 32% | 1863.36 | Mitigate | Request CD-3B approval. Work closely with procurement and cognizant engineers to ensure timely award of remaining contract phases. |  | Q4 FY25 |  | E1005_04655 | 15% | 250 | 500 | 1000 | 3 | 6 | 12 | Low | Significant | Marginal | Negligible | 2 | 3 | 2 | 1 | 3 | 6 | Low |  | Probability is estimated low. Sched. Impacts are calculated as half of the impact of the delay of the full risk impacts from the LLP items. Cost estimates are to fund double shifts and vendor incentives to recover the schedule. | 75 | 2024-08-21 | [5 empty] | 87.5 |  |  | 2024-08-21 | 2024-08-21 |  | 81.25 | 250 - 500 - 1000 | 3 - 6 - 12 | 87.5 | 1.05 |  | 2024-07-31 | -21
Active | RT-6-010-025-LLP-CD3B | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-025-LLP-CD3B | R. Ent | DET | Delay of Next Phases of Detector CD-3A LLP: PbWO4 crystals | If CD-3B funds are not available to fulfill the obligations for the PbW04 crystal CD-3A contracts to continue the productions of the quantities in the next phases, then additional cost and delays will incur. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 2348 | Significant | 12 | Significant | Critical | 3 | 3 | 3 | 4 | 4 | 12 | Moderate |  | 32% | 751.36 | Mitigate | Request CD-3B approval. Work closely with procurement and cognizant engineers to ensure timely award of remaining contract phases. |  | Q1 FY27 |  | E1005_01515 | 15% | 500 | 1000 | 2000 | 3 | 6 | 12 | Low | Significant | Marginal | Negligible | 2 | 3 | 2 | 1 | 3 | 6 | Low |  | Probability is estimated low. Sched. Impacts are calculated as half of the impact of the delay of the full risk impacts from the LLP CD-3A items. Cost estimates are to fund double shifts and vendor incentives to recover the schedule. | 150 | 2024-08-21 | [5 empty] | 175 |  |  | 2024-08-21 | 2024-08-21 |  | 162.5 | 500 - 1000 - 2000 | 3 - 6 - 12 | 175 | 1.05 |  | 2024-07-31 | -21
Active | RT-6-010-026-LLP-CD3B | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-026-LLP-CD3B | R. Ent | DET | Delay of Next Phases of Detector CD-3A LLP: forward HCal steel | If CD-3B funds are not available to fulfill the CD-3A obligations for the forward Hadron calorimeter steel plates and casing steel contract to continue the productions of the quantities in the next phases, then additional cost and delays will incur | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 12 | Significant | Critical | 3 | 2 | 3 | 4 | 4 | 12 | Moderate |  | 32% | 320 | Mitigate | Request CD-3B approval. Work closely with procurement and cognizant engineers to ensure timely award of remaining contract phases. |  | Q1 FY26 |  | E1006_07395 | 15% | 250 | 500 | 1000 | 3 | 6 | 12 | Low | Significant | Marginal | Negligible | 2 | 3 | 2 | 1 | 3 | 6 | Low |  | Probability is estimated low. Sched. Impacts are calculated as half of the impact of the delay of the full risk impacts from the LLP items. Cost estimates are to fund double shifts and vendor incentives to recover the schedule. | 75 | 2024-08-21 | [5 empty] | 87.5 |  |  | 2024-08-21 | 2024-08-21 |  | 81.25 | 250 - 500 - 1000 | 3 - 6 - 12 | 87.5 | 1.05 |  | 2024-07-31 | -21
Active | RT-6-010-027 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-027 | R. Ent | DET | Delay in off-project activities | If the off project activities impacting the beneficial occupancy of the experimental hall at IP-6 are delayed. All installation activities of the EIC experiment will be delayed. This will result in a standing army. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 20000 | Critical | 12 | Significant | Crisis | 3 | 4 | 3 | 5 | 5 | 15 | High |  | 32% | 6400 | Mitigate | Work closely with BNL and NPP management to coordinate the off-project dependencies. |  |  |  | Beneficial occupancy of IP-6 | 10% | 5000 | 10000 | 15000 | 6 | 12 | 24 | Very Low | Critical | Significant | Negligible | 1 | 4 | 3 | 1 | 4 | 4 | Low |  | Probability and schedule - professional judgement; the details of the off-project dependencies are not fully known yet. Costs are to pay for a second shift and get additional resources to speed up the off-project work and the project installation work to recover the schedule loss. | 1000 | 2024-08-02 | [5 empty] | 1000 |  |  | 2024-08-02 | 2024-08-02 |  | 1000 | 5000 - 10000 - 15000 | 6 - 12 - 24 | 1000 | 1.4 |  | 2024-07-31 | -2
Active | RT-6-010-028 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-028 | R. Ent | DET | Delay in MAPS Sensors | If the ITS-3 and/or the LAS MAPS sensors are delayed then the tracking performance and installation of the inner detectors is impacted | Very High (Risk is likely to occur with a probability of >65%) | 15000 | Critical | 36 | Crisis | Critical | 5 | 4 | 5 | 4 | 5 | 25 | High |  | 82% | 12300 | Mitigate | Work closely with the laboratory management on an agreement to share the CERN ITS3 design for which access is crucial for the EIC detector. Work with the ePIC SVT DSC leadership to detect any delays in the sensor design and production as early as possible, this requires for the LAS and other designs access to the ITS3 design database. Expedite sensor production which requires access to the Si foundry through a CERN agreement. Integrate the variousprospective in-kind partners effectively to increase work force. Add additional designers to speed up the production. At appropriate decision points, implement backup planning based on MPGDs and/or ITS2 which will both add costs and degrade performance. |  | Q4 FY30 |  | Early Finish CD-4 | 15% | 2000 | 4000 | 10000 | 6 | 9 | 12 | Low | Significant | Significant | Negligible | 2 | 3 | 3 | 1 | 3 | 6 | Low |  | The low and likely assume additional designers with each 500k / year and additional cost to expedite the detector integration and assembly. The high assumes an independent ITS2 effort needs to be started at a key decision point for the inner barrel silicon layers. | 600 | [6 empty] | 800 |  |  | 2024-09-23 | 2024-09-23 |  | 700 | 2000 - 4000 - 10000 | 6 - 9 - 12 | 800 | 1.35
Active | RT-6-010-029 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer | RT-6-010-029 | R. Ent | DET | Delay in subsystem installation into ePIC | If there are unforeseen complications during the installation of the many different subsystems into ePIC then the overall readiness of the assembled ePIC detector and tests with cosmics will be delayed and potentially even the readiness for commisioning with beam | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 5000 | Significant | 18 | Critical | Critical | 3 | 3 | 4 | 4 | 4 | 12 | Moderate |  | 32% | 1600 | Mitigate | Enhance presence of engineers and scientists in the assembly and wide-angle Halls during assembly and installation phases to expedite and find problems and mitigation solutions early. Find additional workforce technicians and mechanical engineers to work extra shifts and resolve the installation issues |  | Q4 FY30 |  | Early Finish CD-4 | 15% | 1000 | 2000 | 3000 | 4 | 8 | 12 | Low | Significant | Significant | Negligible | 2 | 3 | 3 | 1 | 3 | 6 | Low |  | The estimates assumes additional teams of MEs and MTs to resolve the installation issues. | 300 | [6 empty] | 300 |  |  | 2024-09-23 | 2024-09-23 |  | 300 | 1000 - 2000 - 3000 | 4 - 8 - 12 | 300 | 1.2
Retired | 155 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | R. Ent | DET | Location of detector not finalized | If detector location is in IP6, the layout of the collider hall introduces significantly more challenges to the integration of the detector, due to the limited door size to roll into maintenance position. Reuse of the existing sPHENIX magnet seems difficult as the magnet needs to be relocated after sPHENIX operations and modifications need to be made. | Very High (Risk is likely to occur with a probability of >65%) | 10000 | Critical | 12 | Crisis | Marginal | 5 | 4 | 5 | 2 | 5 | 25 | High |  | 82% | 8200 | Mitigate | [12 empty] | INSERT LIKELIHOOD |  |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | We updated the risk mitigation text on validation of the collider Hall and assembly Hall that all first through the door, and since we carry the magnet risk contingency elsewhere, this one is complete |  |  | 0 | NO |  | 2020-06-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 155
Retired | 137a | Opportunity | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | R. Ent | DET | Reuse of 35 year old BABAR Solenoid Magnet | If the sPHENIX operation in 2023 shows the BaBAR magnet is performing well and the additional risk analysis of the refurbishment of the BaBAR magnet does not indicate potential show stoppers and significant cost increases compared to building a new magnet. | Very High (Risk is likely to occur with a probability of >65%) | 25000 | Critical | 12 | Critical | Crisis | 5 | 4 | 4 | 5 | 5 | 25 | High | Estimated cost of a new 3T magnet | 82% | 20500 | Enhance |  |  |  |  | DE_0700_3390 Detector Magnets - Contract Award | 10% | -10000 | -10000 | -10000 | -3 | -6 | -9 | Very Low | Critical | Marginal | Crisis | 1 | 4 | 2 | 5 | 5 | 5 | Retired |  | Residual opportunity likelihood reduced as tracking requirements folding in realistic silicon sensor sizes and material distribution to mitigate fringe field requirement would imply we would need to operate the magnet at far higher currents to still achieve at least 1.5 T. | Retired |  |  |  | The BaBar magnet design can reach safely 1.5 T yet EIC physics simulation show a need of 1.7 T to ensure tracking resolution requirements are met. Due to the specific EIC detector and flux return geometry the achievable field value of the BaBar magnet as designed is only 1.15 T. To possibly operate the magnet in the 1.5-1.7 T range will require both invasive surgery and requirement of higher-current operating than originally designed. This is judged as far too high a risk and it is not even given that it is achievable, the magnet is not designed for this. Even if it would be achievable, the final temperature margin and critical current margin are not in safe operating range, which makes a long term operation for 15+ years of this magnet as the basis of the EIC project detector too high of a risk. |  |  | -1000 |  | 2023-03-13 | 2022-04-30 | 2022-05-03 |  | -1333.3333 | -10000 - -10000 - -10000 | -3 - -6 - -9 | -1000 | -0.6 | 137a
Retired | 140 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | R. Ent | DET | Location of detector is IP8 | If detector location is IP8, then the installation of the IR magnets and the detector is delayed as more work is needed to be done to prepare the hall for installation, that includes among other things the removal of the remains of the PHENIX muon arms and move of the sPHENIX detector to allow installation of the IR magnets and subsequent EIC detector installation work, can only begin after sPHENIX operation is finished. | Very High (Risk is likely to occur with a probability of >65%) | 10000 | Critical | 12 | Crisis | Marginal | 5 | 4 | 5 | 2 | 5 | 25 | High | Estimate/guess what the costs would be if one has to expedite the schedule. It is similar as the $5M of Risk 188 but a bit higher as one may also need to expedite work/people on the removal of existing equipment with unknowns, expedite IR integration and matching of the IR with the accelerator optics/dynamics much up-down stream (that is done for IP6 already). My personal experience is that expediting schedules can easily cost a few M$. | 82% | 8200 | Mitigate | Choose IP6 as EIC detector location assuming reference EIC Project timeline. |  |  |  | L1_060, early finish for CD4a | 80% | 10000 | 10000 | 15000 | 6 | 12 | 18 | Very High | Critical | Significant | Marginal | 5 | 4 | 3 | 2 | 4 | 20 | Retired |  |  | Retired |  |  |  | retired - DPAP review agreed IP-6 is the location of the Project Detector |  |  | 9333.3333 | NO | 2022-03-15 | 2020-06-30 | 2020-10-30 |  | 12000 | 10000 - 10000 - 15000 | 6 - 12 - 18 | 9333.3333 | 9.6 | 140
Retired | 187 | Threat | 6.10 Detector | BNL | R. Ent / E. Aschenauer |  | R. Ent | DET | Collaboration Formation Delayed | If the formation of the detector collaborations are delayed, then there is a risk of not meeting the CD-4a timeline | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 12 | Critical | Critical | 2 | 4 | 4 | 4 | 4 | 8 | Moderate |  | 17% | 1700 | Mitigate | Ensure timely completion of final EIC detector choice by EIC community. Issue the call for detector proposals by March 2021 with a deadline to submit proposals by September 2021 and the goal of the selection process to be finalized by December 2021. In addition initiate a process to support the users in the formation of collaborations and writing the proposals. |  |  |  | L1_070, CD4-a | 20% | 5000 | 10000 | 30000 | 6 | 12 | 24 | Low | Critical | Significant | Critical | 2 | 4 | 3 | 4 | 4 | 8 | Retired |  |  | Retired |  |  |  | retired - DPAP process completed March 8th 2022, collaboration formation started |  |  | 3000 | NO | 2022-03-10 | 2020-06-30 | 2020-10-30 |  | 3666.6667 | 5000 - 10000 - 30000 | 6 - 12 - 24 | 3000 | 2.8 | 187
Active | RO-6-011-001 | Opportunity | 6.11 Infrastructure | BNL | C. Folz | RO-6-011-001 | T. Nehring | INF | Transfer RF unit substation installation from RF to Infrastructure | If scope and funding are transferred to infrastructure, then one installation contractor can be more efficient | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 50 | Negligible | 6 | Marginal | Negligible | 3 | 1 | 2 | 1 | 2 | 6 | Low | RF group is not organized for commercial construction management role | 32% | 16 | Enhance | Have infrastructure manage the installation |  | TBD |  | TBD | 10% | -20 | 0 | 10 | -6 | -4 | -2 | Very Low | None | Marginal | Negligible | 1 | 0 | 2 | 1 | 2 | 2 | Low |  | Engineering judgement | 0 | 2024-03-21 | [5 empty] | -0.33333 |  |  | 2021-06-30 | 2021-09-27 |  | -0.16667 | -20 - 0 - 10 | -6 - -4 - -2 | -0.33333 | -0.4 | 203 | 2024-03-31 | 916
Active | RT-6-011-001 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-001 | C. Folz | INF | Existing cooling water systems | If the existing cooling water systems structures and components are not functionally adequate, then additional material and installation will be required and this will cause cost increase ans schedule delay. | High (Risk is likely to occur with a probability of >40 to <65%) | 5000 | Significant | 12 | Significant | Negligible | 4 | 3 | 3 | 1 | 3 | 12 | Moderate | This number is a plug in assumed as roughly 50% of the cost of the EIC. | 52% | 2600 | Mitigate | Conduct capacity and condition assessments of existing cooling water SSCs that will be retained for EIC. |  | Q1 FY27 | trigger is the same as affected MS | TBD | 40% | 5000 | 5000 | 5000 | 0 | 12 | 12 | Moderate | Significant | Significant | None | 3 | 3 | 3 | 0 | 3 | 9 | Moderate |  | Cost estimate is based on installation of a 2000 ton cooling system at a new location. | 2000 | 2024-01-09 | [5 empty] | 2000 |  |  | 2021-06-30 | 2021-09-27 |  | 2000 | 5000 - 5000 - 5000 | 0 - 12 - 12 | 2000 | 3.2 | 213 | 2024-03-31 | 916
Active | RT-6-011-002 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-002 | C. Folz | INF | Low cooling water temp. for RF power amplifiers | If the maximum allowable cooling water temperature for the RF power amplifiers is below 86F then chillers will need to be installed and 4 MW of additional power will be required to operate the cooling water sys. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 13900 | Critical | 12 | Significant | Marginal | 3 | 4 | 3 | 2 | 4 | 12 | Moderate | The cost is based on installing a total of 6600 tons of chillers at the 2, 4, 6, 10 o Clock locations. The chiller cost is based on a 77F CWIT. The $3.9 million net present value of additional electricity consumed is not included in the cost impact. | 32% | 4448 | Mitigate | CW temp. constraints should be provided to RFPA vendors to determine if there will be any issues with the higher CW inlet temps. A technical paper has been prepared for consideration. |  | Q2 FY25 | E0806_01360 | E0806_01360 ESR 591 1-Cell 400 kW Test Power Amplifier - Ready for Test Facilities 12/16/25 | 25% | 13900 | 13900 | 13900 | 2 | 12 | 12 | Low | Critical | Significant | None | 2 | 4 | 3 | 0 | 4 | 8 | Moderate |  | The cost is based on installing a total of 6600 tons of chillers at the 2, 4, 6, 10 o'clock locations. The chiller cost is based on a 77F CWIT. The $3.9 million net present value of additional electricity consumed by chiller compressors is not included in the cost impact. | 3475 | 2024-01-09 | [5 empty] | 3475 |  |  | 2021-06-30 | 2021-09-27 |  | 3475 | 13900 - 13900 - 13900 | 2 - 12 - 12 | 3475 | 2.1667 | 207 | 2024-03-31 | 916
Active | RT-6-011-003 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-003 | C. Folz | INF | Cooling water performance for EIC operation in the summer months | If the EIC is required to operate throughout the year including the summer months, then there will be peak periods during the summer months where the CW supply temperature to the machine components will exceed the allowable limits. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 13900 | Critical | 12 | Significant | Marginal | 3 | 4 | 3 | 2 | 4 | 12 | Moderate | The cost estimate is based on 15,000 tons of cooling at $5,000 per ton that is over and above the $ 30 million in base costs. | 32% | 4448 | Mitigate | CW temp. constraints should be provided to RFPA vendors to determine if there will be any issues with the higher CW inlet temps. A technical paper has been prepared for consideration. |  | Q2 FY25 |  | E1202_02000 HSR - Systems Ready for Commissioning 11/13/30/ | 25% | 13900 | 13900 | 13900 | 2 | 12 | 12 | Low | Critical | Significant | Significant | 2 | 4 | 3 | 3 | 4 | 8 | Moderate |  | The cost is based on installing a total of 6600 tons of chillers at the 2, 4, 6, 10 o'clock locations. The chiller cost is based on a 77F CWIT. The $3.9 million net present value of additional electricity consumed by chiller compressors is not included in the cost impact. | 3475 | 2024-01-09 | [5 empty] | 3475 |  |  | 2021-06-30 | 2021-09-27 |  | 3475 | 13900 - 13900 - 13900 | 2 - 12 - 12 | 3475 | 2.1667 | 208 | 2024-03-31 | 916
Active | RT-6-011-004 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-004 | C. Folz | INF | Refrigerants in AC Systems | If the NY standards on Hydrofluorocarbon standards and reporting result in a scarcity of vendors and/or allowable refrigerants, then alternative means of cooling such as absorption chillers may increase cost. | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 12 | Significant | Marginal | 4 | 3 | 3 | 2 | 3 | 12 | Moderate | This number is a plug in assumed as roughly 50% of the cost of the EIC. | 52% | 1040 | Mitigate | Communicate with vendors in advance and determine joint strategy with utilities. |  | Q3 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 50% | 1500 | 2000 | 2000 | 0 | 12 | 12 | High | Significant | Significant | None | 4 | 3 | 3 | 0 | 3 | 12 | Moderate |  | Assumed as roughly 50% of the cost of the chilled water system for the EIC. | 1000 | 2024-01-09 | [5 empty] | 916.6667 |  |  | 2021-06-30 | 2021-09-27 |  | 958.3333 | 1500 - 2000 - 2000 | 0 - 12 - 12 | 916.6667 | 4 | 214 | 2024-03-31 | 916
Active | RT-6-011-005 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-005 | C. Folz | INF | Cooling Water Specification | If cooling water quality requirements for vacuum, magnets and power supplies inside the ring are not compatible, then a separate piping and pumping loop will be required for the cooling. | High (Risk is likely to occur with a probability of >40 to <65%) | 4000 | Significant | 12 | Significant | Marginal | 4 | 3 | 3 | 2 | 3 | 12 | Moderate | Cost estimate is based on a 3 inch supply and return header inside the ring to accommodate | 52% | 2080 | Mitigate | Cooling water parameters and quality requirements should be specified early on by all groups. |  | Q2 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 50% | 4000 | 4000 | 4000 | 2 | 12 | 12 | High | Significant | Significant | None | 4 | 3 | 3 | 0 | 3 | 12 | Moderate |  | Engineering judgement | 2000 | 2024-01-09 | [5 empty] | 2000 |  |  | 2021-06-30 | 2021-09-27 |  | 2000 | 4000 - 4000 - 4000 | 2 - 12 - 12 | 2000 | 4.3333 | 209 | 2024-03-31 | 916
Active | RT-6-011-006 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-006 | C. Folz | INF | Cooling water activation potential | If there is potential for cooling water activation then additional costs will be incurred due to the consideration of separate systems and handling. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 6 | Marginal | Marginal | 4 | 2 | 2 | 2 | 2 | 8 | Moderate | Depending on the water that is susceptible to activation, separate water loops will be required. If closed cycle cooling towers are required then double wall piping may be required. | 52% | 520 | Mitigate | Conduct a water activation potential study to determine what systems could be potentially exposed to contamination. |  | Q1 FY25 |  | ?? PM_0101_2250 Prelim Design/LLP Final Design Ready for CD-2/3A - All Systems | 25% | 1000 | 1000 | 1000 | 2 | 6 | 6 | Low | Significant | Marginal | None | 2 | 3 | 2 | 0 | 3 | 6 | Low |  | Engineering judgement | 250 | 2024-01-09 | [5 empty] | 250 |  |  | 2021-06-30 | 2021-09-27 |  | 250 | 1000 - 1000 - 1000 | 2 - 6 - 6 | 250 | 1.1667 | 210 | 2024-03-31 | 916
Retired | RT-6-011-007 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-007 | C. Folz | INF | Increase in power reqs. specific to RF | If the project decides to use solid state technology, then there needs to be a cost/benefit analysis between RF and energy losses within conventional design resulting in larger cable energy rqmts and additional cost and technical impacts. | High (Risk is likely to occur with a probability of >40 to <65%) | 5000 | Significant | 0 | Negligible | Negligible | 4 | 3 | 1 | 1 | 3 | 12 | Moderate |  | 52% | 2600 | Mitigate | Participate in the RF decision. |  | Q1 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 25% | 5000 | 5000 | 7000 | 0 | 0 | 6 | Low | Significant | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Retired |  | Engineering judgement | Retired | 2024-01-09 |  |  | RF technology that will be use on EIC is known now. |  |  | 1416.6667 | No | 2024-08-14 | 2020-06-30 | 2020-10-30 |  | 1333.3333 | 5000 - 5000 - 7000 | 0 - 0 - 6 | 1416.6667 | 0.5 | 134 | 2024-03-31 | 1248
Active | RT-6-011-008 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-008 | C. Folz | INF | Construction Market Escalation 6.11.2 | If the availability of contractors and the cost of construction varies due to market conditions, it could increase the cost estimate. | High (Risk is likely to occur with a probability of >40 to <65%) | 30000 | Critical | 3 | Negligible | Negligible | 4 | 4 | 1 | 1 | 4 | 16 | High |  | 52% | 15600 | Mitigate | Contractor workshops, CM/GC early in design process to identify opportunities to get into market at right time. Establish construction management group. |  | Q3 FY25 |  | E1102_01900 READY FOR INSTALL - Cryogenic 1002I - BORE Complete 08/06/29 | 50% | 25206 | 25206 | 25206 | 0 | 3 | 9 | High | Critical | Negligible | None | 4 | 4 | 1 | 0 | 4 | 16 | High |  | Distribute the risk portion of the escalation across the 3 WBS areas in simple proportion to the value of the WBS. Based on 6.5%/6.0% FY23&24 plus the 3.0%/3.0% FY25+ escalation split. | 12603 | 2024-01-09 | [5 empty] | 12603 |  |  | 2020-06-30 | 2020-10-30 | Dec 14 2022: New cost impact based on updated escalation assumptions. | 12603 | 25206 - 25206 - 25206 | 0 - 3 - 9 | 12603 | 2 | 36 | 2024-03-31 | 1248
Active | RT-6-011-008a | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-008a | C. Folz | INF | Construction Market Escalation 6.11.3 | If the availability of contractors and the cost of construction varies due to market conditions, it could increase the cost estimate. | High (Risk is likely to occur with a probability of >40 to <65%) | 25000 | Critical | 3 | Negligible | Negligible | 4 | 4 | 1 | 1 | 4 | 16 | High |  | 52% | 13000 | Mitigate | Contractor workshops, CM/GC early in design process to identify opportunities to get into market at right time. Establish construction management group. |  | Q3 FY26 |  | E1103_10740 138kW Substation - Substation Testing and Commissioning and ready 06/14/32 | 50% | 24216 | 24216 | 24216 | 0 | 3 | 9 | High | Critical | Negligible | None | 4 | 4 | 1 | 0 | 4 | 16 | High |  | Distribute the risk portion of the escalation across the 3 WBS areas in simple proportion to the value of the WBS. Based on 6.5%/6.0% FY23&24 plus the 3.0%/3.0% FY25+ escalation split. | 12108 | 2024-01-09 | [5 empty] | 12108 |  |  | 2020-06-30 | 2020-10-30 | Dec 14 2022: New cost impact based on updated escalation assumptions. | 12108 | 24216 - 24216 - 24216 | 0 - 3 - 9 | 12108 | 2 | 36a | 2024-03-31 | 1248
Active | RT-6-011-008b | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-008b | C. Folz | INF | Construction Market Escalation 6.11.4 | If the availability of contractors and the cost of construction varies due to market conditions, it could increase the cost estimate. | High (Risk is likely to occur with a probability of >40 to <65%) | 10000 | Critical | 3 | Negligible | Negligible | 4 | 4 | 1 | 1 | 4 | 16 | High |  | 52% | 5200 | Mitigate | Contractor workshops, CM/GC early in design process to identify opportunities to get into market at right time. Establish construction management group. |  | Q3 FY26 |  | E1104_03200 TWR - Cooling Tower Water System - Startup and Testing Complete 08/23/28 | 50% | 9432 | 9432 | 9432 | 0 | 3 | 9 | High | Critical | Negligible | None | 4 | 4 | 1 | 0 | 4 | 16 | High |  | Distribute the risk portion of the escalation across the 3 WBS areas in simple proportion to the value of the WBS. Based on 6.5%/6.0% FY23&24 plus the 3.0%/3.0% FY25+ escalation split. | 4716 | 2024-01-09 | [5 empty] | 4716 |  |  | 2020-06-30 | 2020-10-30 | Dec 14 2022: New cost impact based on updated escalation assumptions. | 4716 | 9432 - 9432 - 9432 | 0 - 3 - 9 | 4716 | 2 | 36b | 2024-03-31 | 1248
Active | RT-6-011-009 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-009 | C. Folz | INF | Undetermined Need to Modify the Existing Facility | If facility modification needs are identified after design is complete and contractor pricing is established, redesign may be needed. This will cause additional costs and schedule delay. If code compliance drives facility or system upgrades, additional resources will be required to address the design and installation. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 6 | Marginal | Negligible | 3 | 4 | 2 | 1 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | Monitor and participate in design discussions |  | Q1 FY25 |  | E1103_01700 Substation Installation Contract - Ready for Accelerator Systems Testing and Commissioning 01/23/29 | 30% | 500 | 10000 | 15000 | 0 | 6 | 12 | Moderate | Critical | Marginal | None | 3 | 4 | 2 | 0 | 4 | 12 | Moderate |  | Engineering judgement | 3000 | 2024-01-09 | [5 empty] | 2550 |  |  | 2020-06-30 | 2020-10-30 |  | 2775 | 500 - 10000 - 15000 | 0 - 6 - 12 | 2550 | 1.8 | 38 | 2024-03-31 | 1248
Active | RT-6-011-010 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-010 | C. Folz | INF | Code compliance upgrades | If code compliance drives facility or system upgrades, additional resources will be required to address the design and installation. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 6 | Marginal | Negligible | 3 | 4 | 2 | 1 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | Monitor and participate in design discussions |  | Q1 FY25 |  | E1103_01700 Substation Installation Contract - Ready for Accelerator Systems Testing and Commissioning 01/23/29 | 20% | 500 | 10000 | 15000 | 0 | 6 | 12 | Low | Critical | Marginal | None | 2 | 4 | 2 | 0 | 4 | 8 | Moderate |  | Engineering judgement | 2000 | 2024-01-09 | [5 empty] | 1700 |  |  | 2020-06-30 | 2020-10-30 |  | 1850 | 500 - 10000 - 15000 | 0 - 6 - 12 | 1700 | 1.2 | 38a | 2024-03-31 | 1248
Active | RT-6-011-011 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-011 | C. Folz | INF | Delay in getting Scenic River Permit | If the permit is not obtained on time, there will be a schedule delay | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 0 | Negligible | 3 | Negligible | None | 3 | 1 |  | 0 |  |  | Low |  |  |  | Mitigate | Include River Permit in P6 plan |  | Q2 FY25 | E1101_07060 | E1101_07060 | 20% | 0 | 0 | 0 | 1 | 3 | 6 | Low | None | Negligible | None | 2 | 0 | 1 | 0 | 1 | 2 | Low |  | Engineering judgement | 0 | 2024-01-09 | [5 empty] | 0 |  |  | 2021-11-29 | 2021-11-29 |  | 0 | 0 - 0 - 0 | 1 - 3 - 6 | 0 | 0.66667 | 41 | 2024-03-31 | 853
Active | RT-6-011-012 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-012 | C. Folz | INF | Contractors Resource/Scheduling Issues | IF contractors cannot or will not meet schedule or unexpected or unusual hazards are encountered or are delayed in completion due to late award of contract, THEN infrastructure installation will be delayed or become more expensive. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 5000 | Significant | 6 | Marginal | Negligible | 3 | 3 | 2 | 1 | 3 | 9 | Moderate |  | 32% | 1600 | Mitigate | Clear Statement of Work with a complete set of construction documents; Job specific source selection plan; Best value trade off CM/GC selection if allowed; Interview CM/GC teams for scope, schedule, cost, safety, and quality * Clearly define project requirements in RFPs * Clearly define good selection criteria for subcontractors. * Build partnership with Subcontractor from beginning of contract * Regularly engage Subcontractor Executive level to address hot issues in project Clearly defined performance periods and delivery expectation. Through work planning and control engineer out hazards where possible, precise work planning detailing hazards and mitigations (JSA), use of PPE; utilize administrative controls in the form of task specific work plans and permits, and task specific training, signage, tailgate meetings, policies. Specific attention to Hoisting and rigging, develop fall protection plans for work at heights. Define the work planning and control requirement in RFP to set the expectation with subcontractors. Subcontractor to provide work plans for BNL approval on Elevated Work Surface, Fall protection, Asbestos abatement, penetration permit, Hot work, Electrical Work Plan, etc. A detailed review will be performed by the PM, FCM and ESH. |  | Q2 FY25 |  | E1102_02180 TODO: List of major contracts, use % for impacts | 30% | 500 | 5000 | 8000 | 3 | 6 | 9 | Moderate | Significant | Marginal | None | 3 | 3 | 2 | 0 | 3 | 9 | Moderate |  | Engineering judgement | 1500 | 2024-01-09 | [5 empty] | 1350 |  |  | 2020-06-30 | 2020-10-30 |  | 1425 | 500 - 5000 - 8000 | 3 - 6 - 9 | 1350 | 1.8 | 162 | 2024-03-31 | 1248
Active | RT-6-011-013 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-013 | C. Folz | INF | Construction Site Logistics | IF infrastructure contracts and technical installation have delays due to coordination , THEN spatial and schedule conflicts will occur resulting in increased cost and schedule. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 6 | Marginal | Negligible | 3 | 4 | 2 | 1 | 4 | 12 | Moderate | Key Concerns: Coordination with technical installation teams/contractors - duration of construction activities of when co-occupancy begins. Changes by technical team leading to schedule delays and cost impacts. Scope added by technical team will impact schedule and cost. Coordination between Infrastructure Project and Technical Systems Installation. Area by area - interface with technical installation group - Could increase safety issues, work in co-occupied space. Potential delays due to multiple contractors working in same area. Projects at BNL not related to EIC are need to be coordinated continuously, if not successful, this could impact / delay EIC work. Co-occupancy requirements to meet completion dates, possibly leads to higher bids. Other project milestones (F&O, AD, etc.), contractors, etc. may impact the EIC infrastructure Project schedule. Clearing experimental areas to allow start of construction. | 32% | 3200 | Mitigate | All changes need to go through Project Office for approval, and impacts analyzed and approved. Due to compressed schedule infrastructure team will complete as much as possible during non-co-occupied work times. Commissioning to be completed during co-occupancy. Validate the compressed schedule with the independent scheduler. Detailed schedule activities, Determine owners/coordinators, Daily tailgate meetings including coordination, CM knowledgeable with technical installations, Work force to fit within schedule constraints, Multiple and/or staggered shift, Contract strategy. CM to coordinate with BNL labor on site. |  | Q3 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 30% | 1000 | 10000 | 15000 | 3 | 6 | 9 | Moderate | Critical | Marginal | None | 3 | 4 | 2 | 0 | 4 | 12 | Moderate |  | Engineering judgement | 3000 | 2024-01-09 | [5 empty] | 2600 |  |  | 2020-06-30 | 2020-10-30 |  | 2800 | 1000 - 10000 - 15000 | 3 - 6 - 9 | 2600 | 1.8 | 163 | 2024-03-31 | 1248
Active | RT-6-011-014 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-014 | C. Folz | INF | Lack of cost/schedule coordination | IF infrastructure project is not coordinated with other projects, THEN there may be schedule delays and cost increase. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 6 | Marginal | Negligible | 3 | 4 | 2 | 1 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | Coordinate with Project Managers on schedule, utilities, termination of the utilities, site logistics plan, traffic routing, use of the facility. Interface with F&O projects during long down time. |  | Q3 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 30% | 500 | 10000 | 12000 | 3 | 6 | 12 | Moderate | Critical | Marginal | None | 3 | 4 | 2 | 0 | 4 | 12 | Moderate |  | Engineering judgement | 3000 | 2024-01-09 | [5 empty] | 2250 |  |  | 2020-06-30 | 2020-10-30 |  | 2625 | 500 - 10000 - 12000 | 3 - 6 - 12 | 2250 | 2.1 | 165 | 2024-03-31 | 1248
Active | RT-6-011-015 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-015 | C. Folz | INF | Unforeseen Field Conditions | IF unforeseen field conditions are discovered, schedule delays and/or cost increases may result | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 10000 | Critical | 6 | Marginal | Negligible | 3 | 4 | 2 | 1 | 4 | 12 | Moderate |  | 32% | 3200 | Mitigate | Conduct field verifications of utilities when executing digging permits, work with Site Planning to identify potential legacy issues, require CM/GC to perform field verification of conditions prior to finalizing contract. Example of verification is the plan to perform NDT wall thickness survey of existing RHIC Tunnel steel arch plate structure. |  | Q3 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 30% | 1000 | 10000 | 15000 | 3 | 6 | 12 | Moderate | Critical | Marginal | None | 3 | 4 | 2 | 0 | 4 | 12 | Moderate |  | Engineering judgement | 3000 | 2024-01-09 | [5 empty] | 2600 |  |  | 2020-06-30 | 2020-10-30 |  | 2800 | 1000 - 10000 - 15000 | 3 - 6 - 12 | 2600 | 2.1 | 166 | 2024-03-31 | 1248
Active | RT-6-011-016 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-016 | D. Nassar | INF | RHIC Tunnel distoration/collapse due to jackport installations | If the existing RHIC tunnel archplate structure is damaged (i.e., distorted, collapse, etc.) due to installation of jackports for the necessary power feeds, wave guides, cooling ducts, etc., excavation then additional engineering design work and construction activities will be required to restore the existing RHIC tunnel to repair the damage. This will cause additional construction cost and schedule for completion. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 6 | Marginal | Negligible | 2 | 2 | 2 | 1 | 2 | 4 | Low | Cost estimate is based on a single occurrence of damage in an area less than 260 SF. Cost estimate is based on employing the primary A-E firm or outside contractor to assess the damage and to provide an engineered solution (250k) and for construction activities to excavate the damaged section and to replace the arch plate sections and backfill (750k). | 17% | 170 | Mitigate | Independent third-party review of design approach to stabilize the excavation site by subject matter experts. Increased oversight of construction activities in close proximity to existing RHIC tunnel infrastructure with designated hold points. Implementation of a structural monitoring plan utilizing instrumentation and visual inspection during excavation activities. |  | Q3 FY25 |  | E1102_03300 READY FOR INSTALL - 1011A - BORE Complete | 10% | 250 | 1000 | 2000 | 0 | 3 | 6 | Very Low | Significant | Negligible | Negligible | 1 | 3 | 1 | 1 | 3 | 3 | Low |  | Engineering judgement | 100 | 2024-01-09 | [5 empty] | 108.3333 |  |  | 2020-06-30 | 2020-10-30 |  | 104.1667 | 250 - 1000 - 2000 | 0 - 3 - 6 | 108.3333 | 0.3 | 181 | 2024-03-31 | 1248
Active | RT-6-011-017 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-017 | D. Nassar | INF | Adverse weather conditions | IF adverse weather conditions occur that prevent use of mobile cranes and other material handling equipment, THEN infrastructure installation will be delayed or become more expensive. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 250 | Negligible | 0 | Negligible | Negligible | 3 | 1 | 1 | 1 | 1 | 3 | Low | Cost impact is based on 1 week non-productive work of craft labor during construction activities associated with erection of building steel for new EIC buildings. | 32% | 80 | Mitigate | Review weather conditions during look ahead meetings and plan of day meetings. Reallocate rigging resources to project tasks not impacted by weather if outdoor conditions does not support use of mobile cranes and other large rigging equipment that are adversely impacted by high winds. |  | Q3 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 5% | 50 | 100 | 350 | 0 | 0 | 1 | Very Low | Negligible | Negligible | Negligible | 1 | 1 | 1 | 1 | 1 | 1 | Low |  | Engineering judgement | 5 | 2024-01-09 | [5 empty] | 8.3333 |  |  | 2020-06-30 | 2020-10-30 |  | 6.6667 | 50 - 100 - 350 | 0 - 0 - 1 | 8.3333 | 0.016667 | 200 | 2024-03-31 | 1248
Retired | RT-6-011-018 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-018 | C. Folz | INF | Cooling tower water discharge envir. permit | If there are any copper materials in the components that are directly cooled by tower water (for eg.cryo compressors), then the required chemical treatment for cooling water will result in blowdown water quality that exceeds permissible values. | Very High (Risk is likely to occur with a probability of >65%) | 2500 | Significant | 0 | Negligible | Marginal | 5 | 3 | 1 | 2 | 3 | 15 | High | Includes (2) plate and frame heat exchangers, (3) secondary water pumps and interconnecting piping for each of the (3) cryo buildings. | 82% | 2050 | Mitigate | Utilize a secondary heat exchanger and thus avoid the copper to be directly exposed to the cooling tower water. Discuss with Power and Utilities group and to begin early discussions with permitting authorities. |  | Q1 FY25 |  | No cost, no schedule impact, not in Safran | 10% | 0 | 0 | 0 | 0 | 0 | 0 | Very Low | None | Negligible | None | 1 | 0 | 1 | 0 | 1 | 1 | Retired |  | The estimate is based on utilizing dedicated secondary heat exchangers (2), pumps (3) and associated additional piping each at 1002, 1006 and 1010 that will prevent the open loop flow path to be in direct contact with copper. The risk is eliminated once the mitigation is performed. | Retired | 2024-01-09 |  | Not in Safran since 0 impact | Retire as per Dirul Nassar |  |  | 0 | NO | 2024-08-14 | 2020-06-30 | 2020-10-30 |  | 0 | 0 - 0 - 0 | 0 - 0 - 0 | 0 | 0 | 206 | 2024-03-31 | 1248
Active | RT-6-011-019 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-019 | C. Folz | INF | CW Piping Inside Tunnel | If there are multiple disciplines/trades scheduled for work in the same area of the tunnel simultaneously, then there will be delays in installation of cooling water piping. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 1000 | Marginal | 2 | Negligible | Negligible | 3 | 2 | 1 | 1 | 2 | 6 | Low | Cost estimate is a place holder. The schedule estimate is based on reducing the man power from a (3) 4man crew to a (2) 4 man crew | 32% | 320 | Mitigate | Active schedule communication with all impacted groups should be held and project should be tracked with a schedule that shows sufficient details. |  | Q3 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 15% | 0 | 250 | 1000 | 0 | 2 | 2 | Low | Negligible | Negligible | Negligible | 2 | 1 | 1 | 1 | 1 | 2 | Low |  | Proper planning and communication of construction schedule can eliminate the risk completely. More often than not, some schedule inefficiencies are expected to remain. | 37.5 | 2024-01-09 | [5 empty] | 62.5 |  |  | 2020-06-30 | 2020-10-30 |  | 50 | 0 - 250 - 1000 | 0 - 2 - 2 | 62.5 | 0.2 | 215 | 2024-03-31 | 1248
Retired | RT-6-011-020 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-020 | C. Folz | INF | Existing Equipment Viability | If the existing infrastructure and/or equipment proves no longer serviceable, then new items will need to be purchased or more time will be needed for repairs. This will cost more money and take more time. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 9 | Significant | Negligible | 2 | 3 | 3 | 1 | 3 | 6 | Low |  | 17% | 850 | Mitigate | Maintain close coordination with RHIC/CAD and Facilities and Operations organizations to ensure that existing SSC's are maintained adequately. |  | Q3 FY25 |  | E1102_01460 READY FOR INSTALL - New LINAC Tunnel 1002 - BORE Complete 04/19/27 | 20% | 2000 | 5000 | 8000 | 6 | 9 | 12 | Low | Significant | Significant | None | 2 | 3 | 3 | #N/A | #N/A | #N/A | Retired |  | Engineering judgement | Retired | 2024-01-09 |  |  | Combined with RT-6-011-001 |  |  | 1000 | No | 2024-08-14 | 2020-06-30 | 2020-10-30 |  | 1000 | 2000 - 5000 - 8000 | 6 - 9 - 12 | 1000 | 1.8 | 33 | 2024-03-31 | 1248
Retired | RT-6-011-021 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-021 | D. Nassar | INF | RHIC Tunnel distoration/collapse due to Building 1002 excavation instability | If the existing RHIC tunnel archplate structure is damaged (i.e., distorted, collapse, etc.) due to excavation activities associated with construction of the new EIC building 1002 then additional engineering design work and construction activities will be required to restore the existing RHIC tunnel to repair the damage. This will cause additional construction cost and schedule for completion. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1000 | Marginal | 6 | Marginal | Negligible | 2 | 2 | 2 | 1 | 2 | 4 | Low | Cost estimate is based on a single occurrence of damage in an area less than 260 SF. Cost estimate is based on employing the primary A-E firm or outside contractor to assess the damage and to provide an engineered solution (250k) and for construction activities to excavate the damaged section and to replace the arch plate sections and backfill (750k). | 17% | 170 | Mitigate | Interdependent third-party review of design approach to stabilize the excavation site by subject matter experts. Increased oversight of construction activities in close proximity to existing RHIC tunnel infrastructure with designated hold points. Implementation of a structural monitoring plan utilizing instrumentation and visual inspection during excavation activities. |  | Q3 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 10% | 250 | 1000 | 2000 | 0 | 3 | 6 | Very Low | Significant | Negligible | Negligible | 1 | 3 | 1 | 1 | 3 | 3 | Retired |  | Engineering judgement | Retired | 2024-01-09 |  |  | SHC to be remove from scope |  |  | 108.3333 | No | 2024-08-14 | 2020-06-30 | 2020-10-30 |  | 104.1667 | 250 - 1000 - 2000 | 0 - 3 - 6 | 108.3333 | 0.3 | 34 | 2024-03-31 | 1248
Active | RT-6-011-022 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-022 | C. Folz | INF | Construction and Envir. Regulatory Requirements | If regulatory agencies have requirements, they could impact the design configuration, which would cause rework. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 12 | Significant | Negligible | 2 | 3 | 3 | 1 | 3 | 6 | Low |  | 17% | 850 | Mitigate | Maintain awareness of environmental regulations through coordination with BNL Environmental Compliance personnel. |  | Q3 FY25 |  | E1102_01460 READY FOR INSTALL - New LINAC Tunnel 1002 - BORE Complete 04/19/27 | 20% | 1000 | 5000 | 8000 | 6 | 12 | 24 | Low | Significant | Significant | None | 2 | 3 | 3 | 0 | 3 | 6 | Low |  | Engineering judgement | 1000 | 2024-01-09 | [5 empty] | 933.3333 |  |  | 2020-06-30 | 2020-10-30 |  | 966.6667 | 1000 - 5000 - 8000 | 6 - 12 - 24 | 933.3333 | 2.8 | 35 | 2024-03-31 | 1248
Active | RT-6-011-023 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-023 | C. Folz | INF | Modifications to Experimental Hall | If the detector configuration changes as the detector design matures, the ideal configuration may require infrastructure modifications beyond our current plan. This will cause rework. | Very High (Risk is likely to occur with a probability of >65%) | 15000 | Critical | 12 | Significant | Negligible | 5 | 4 | 3 | 1 | 4 | 20 | High |  | 82% | 12300 | Mitigate | Monitor and participate in detector develop design discussions |  | Q1 FY25 |  | E1010_10060 PDR - Detector Utilities - Preliminary Design Review Complete 11/24/25 | 70% | 2000 | 15000 | 25000 | 0 | 12 | 12 | Very High | Critical | Significant | None | 5 | 4 | 3 | 0 | 4 | 20 | High |  | Engineering judgement | 10500 | 2024-01-09 |  | ready to retire April 1 2024 |  |  |  | 9800 |  |  | 2020-06-30 | 2020-10-30 |  | 10150 | 2000 - 15000 - 25000 | 0 - 12 - 12 | 9800 | 5.6 | 37 | 2024-03-31 | 1248
Active | RT-6-011-024 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-024 | C. Folz | INF | Energy Isolation Hazards | If all hazards are not identified prior to start of work and/or if mechanical / electrical work is not planned adequately, then there could be risk to personal safety and / or damage to facilities, workers could come into contact with live circuits or terminals or other uncontrolled energy sources. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 5000 | Significant | 6 | Marginal | Negligible | 2 | 3 | 2 | 1 | 3 | 6 | Low | Key Concerns:*BNL staff availability (lock/tag especially) may impact schedule. * Discovery of unknown/unexpected energy hazard during the "RHIC shutdown" process. | 17% | 850 | Mitigate | Thorough work planning and control; engineer out hazards where possible, precise work planning detailing hazards and mitigations (JSA), use of PPE; utilize administrative controls in the form of task specific work plans and permits, and task specific training, signage, tailgate meetings, policies. Specific attention to Hoisting and rigging, develop fall protection plans for work at heights. * Enforce strict compliance with Accelerator Material Management Plan (AMMP) by PM, FCM and ESH. * Verify field conditions before implementation by SLAC and Contractor. * Define the work planning and control requirement in RFP to set the expectation with subcontractors. Subcontractor to provide work plans for SLAC approval on Elevated Work Surface, Fall protection, Asbestos abatement, penetration permit, Hot work, Electrical Work Plan, etc. (Completed) * Develop a detailed Energy Isolation Plan (EIP)and LOTO procedure at early stage of the project. Identify, tagging and air gapping all energized source by SLAC in-house staff prior to decommission. Contingency Planning- “What if”- Stop work, evaluate change of scope, restart plan defined in EIP. (Completed) * Turn over “cold and dark” facilities to subcontractor for removal. Clear understanding of the existing systems and the work planning controls must be in place. Details of daily activities shall be communicated between project team and Subcontractor. A detailed review will be performed by the PM, FCM and ESH. (Completed) Start energy isolation plans at least 4 months prior to activity. Early engagement with inspectors - real-time inspections. SLAC and sub electricians went through additional training in 4/2019 regarding electrical demo. |  | Q3 FY25 |  | E1102_01460 READY FOR INSTALL - New LINAC Tunnel 1002 - BORE Complete 04/19/27 | 20% | 500 | 5000 | 7000 | 3 | 6 | 9 | Low | Significant | Marginal | None | 2 | 3 | 2 | 0 | 3 | 6 | Low |  | Engineering judgement | 1000 | 2024-01-09 | [5 empty] | 833.3333 |  |  | 2020-06-30 | 2020-10-30 |  | 916.6667 | 500 - 5000 - 7000 | 3 - 6 - 9 | 833.3333 | 1.2 | 164 | 2024-03-31 | 1248
Active | RT-6-011-025 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-025 | C. Folz | INF | Rack Temperature Stabilization | If the need for precision temperature control and stability is required on power supply racks then temperature control racks will need to be procured for power supply. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 480 | Marginal | 0 | Negligible | Negligible | 3 | 2 | 1 | 1 | 2 | 6 | Low | Cost estimate is based on $2,000 per temperature controlled rack enclosure in (8) buildings with 30 racks in each building. | 32% | 153.6 | Avoid | Monitor via periodic CW interface meetings. |  | Q1 FY25 |  | E1102_02160 Cryogenic 1010E – BORE 09/08/27 | 50% | 480 | 480 | 480 | 0 | 0 | 0 | High | Significant | Negligible | None | 4 | 3 | 1 | 0 | 3 | 12 | Moderate |  | Engineering judgement | 240 | 2024-01-09 | [5 empty] | 240 |  |  | 2021-06-30 | 2021-09-27 |  | 240 | 480 - 480 - 480 | 0 - 0 - 0 | 240 | 0 | 211 | 2024-03-31 | 916
Active | RT-6-011-026 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-026 | C. Folz | INF | Preliminary cooling loads | If the final cooling loads from the components are higher than what is provided during design, then additional cost and schedule impacts will be incurred due to increased scope and out of sequence design and installation. | High (Risk is likely to occur with a probability of >40 to <65%) | 5000 | Significant | 12 | Significant | Negligible | 4 | 3 | 3 | 1 | 3 | 12 | Moderate | Cost estimate is based on installation of a 2000 ton cooling system at a new location. | 52% | 2600 | Mitigate | Communicate with system engineers and L3 managers to discuss reqs and current basis for cooling reqs. Use a formal process to receive cooling reqs. Communicate downstream impacts of design decisions such as cooling system cost impacts directly to the accelerator and cryo L3 managers and system engineers. Communicate with AE regarding cooling requirements and changes. Utilize reasonably bounding estimates where possible while avoiding conservatism |  | Q2 FY25 |  | E1102_01460 READY FOR INSTALL - New LINAC Tunnel 1002 - BORE Complete 04/19/27 | 20% | 5000 | 5000 | 5000 | 0 | 6 | 12 | Low | Significant | Marginal | None | 2 | 3 | 2 | 0 | 3 | 6 | Low |  | Cost estimate is based on installation of a 2000 ton cooling system at a new location. | 1000 | 2024-01-09 |  | These costs cannot be controlled. The risk can be monitored and the key is to identify and communicate changes to the cooling requirements to the detail engineering and design personnel. |  |  |  | 1000 |  |  | 2021-06-30 | 2021-09-27 |  | 1000 | 5000 - 5000 - 5000 | 0 - 6 - 12 | 1000 | 1.2 | 212 | 2024-03-31 | 916
Active | RT-6-011-027 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-027 | C. Folz | INF | More expensive Infrastructure Contractor Insurance | If Contractor and/or Subcontractor’s Insurance costs are higher than anticipated, the project will lose time negotiating terms and conditions and may need to pay more than estimated.” | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 1200 | Significant | 0 | Negligible | None | 2 | 3 | 1 | 0 | 3 | 6 | Low | Assume 0.5% of 6.11 budgeted cost | 17% | 204 | Mitigate | Investigate Owner Controlled Insurance Policy, negotiate contractor’s insurance up-front. |  | Q3 FY25 |  | E1102_01000 Start Construction - CM/GC Phase II 07/24/25 | 5% | 1200 | 1200 | 1200 | 0 | 0 | 0 | Very Low | Significant | Negligible | None | 1 | 3 | 1 | 0 | 3 | 3 | Low |  | Assume 0.5% of WBS 6.11 budgeted cost | 60 | 2024-01-09 | [5 empty] | 60 |  |  | 2021-09-29 | 2021-09-29 |  | 60 | 1200 - 1200 - 1200 | 0 - 0 - 0 | 60 | 0 | 216 | 2024-03-31 | 914
Retired | RT-6-011-028 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-028 | C. Folz | INF | Potential need for new buildings for 1006 Crab Cavities | If the need for support buildings and utilities for the Crab Cavities at 1006 is confirmed, then additional funds will be required to design and construct them. | Very High (Risk is likely to occur with a probability of >65%) | 13000 | Critical | 0 | Negligible | None | 5 | 4 |  | 0 | [6 empty] | Mitigate | Monitor accelerator design process and Change Control status |  | Q3 FY25 |  | E1102_01000 Start Construction - CM/GC Phase II 07/24/25 | 90% | 10000 | 13000 | 18000 | 0 | 0 | 0 | Very High | Critical | Negligible | None | 5 | 4 | 1 | 0 | 4 | 20 | Retired |  | Engineering judgement | Retired | 2024-01-09 |  | ready to retire April 1 2024 | Realized |  |  | 12300 | Yes | 2024-07-09 | 2022-04-04 | 2022-04-04 |  | 12000 | 10000 - 13000 - 18000 | 0 - 0 - 0 | 12300 | 0 | 217 | 2024-03-31 | 727
Active | RT-6-011-029 | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-029 | C. Folz | INF | High-voltage power funding | If funding is not provided for BNL high-voltage power distribution system upgrades via programs such as SLI, sufficient reliable electrical power will not be available for operating the EIC at full machine power. Additional costs may be incurred to guarantee this power availability | Very High (Risk is likely to occur with a probability of >65%) | 10000 | Critical | 0 | Negligible | None | 5 | 4 | 1 | 0 | 4 | 20 | High |  |  |  | Mitigate | Integrate BNL long-term power plan into Project Schedule; identify need-by dates and track. |  | Q1 FY25 |  | E0806_01360 ESR 591 1-Cell 400 kW Test Power Amplifier - Ready for Test Facilities 12/16/25 | 50% | 3728 | 9320 | 14912 | 0 | 0 | 0 | High | Critical | Negligible | None | 4 | 4 | 1 | 0 | 4 | 16 | High |  | Assume 20, 50 and 80% of WBS 6.11.03.07, '138kV Substation' total cost of $18,640K for best, likely and worst scenarios. | 4660 | 2024-01-09 |  | ready to retire April 1 2024 |  |  |  | 4660 |  |  | 2022-06-15 | 2022-06-15 |  | 4660 | 3728 - 9320 - 14912 | 0 - 0 - 0 | 4660 | 0 | 218 | 2024-03-31 | 655
Active | RT-6-011-030-LLP-CD3A | Threat | 6.11 Infrastructure | BNL | C. Folz | RT-6-011-030-LLP-CD3A | C. Folz | INF | Unit substations Delivery Delay | If the fifteen (15) unit substations required for the thirteen (13) BOREs are delivered later than planned, then the project will experience schedule delays. | High (Risk is likely to occur with a probability of >40 to <65%) | 6000 | Critical | 9 | Significant | None | 4 | 4 | 3 | 0 | 4 | 16 | High |  | 52% | 3120 | Mitigate | Work closely with BNL procurement and cognizant engineers to ensure timely award of contract(s). Regular communication with vendor(s). |  | Q1 FY25 |  | E1103_02960 Unit Substation Xfmrs for Buildings - Delivery of last Unit Substation at BNL - LLP CD-3A - Scope Complete | 20% | 0 | 0 | 0 | 1 | 3 | 6 | Low | None | Negligible | None | 2 | 0 | 1 | 0 | 1 | 2 | Low |  | Probability estimated as low, no cost impact, schedule impacts estimated considering long lead delivery time and potential competition from other projects. | 0 | 2024-01-09 | [5 empty] | 0 |  |  | 2023-06-26 | 2023-06-27 |  | 0 | 0 - 0 - 0 |  | 0 |  |  | 2024-03-31 | 278
Active | RO-6-011-030a-LLP-CD3A | Opportunity | 6.11 Infrastructure | BNL | C. Folz | RO-6-011-030a-LLP-CD3A | C. Folz | INF | Substation Low Bids | If Substation bids come lower than planned, then the project will have costs reduced | Very High (Risk is likely to occur with a probability of >65%) | 5000 | Significant | 0 | Negligible | None | 5 | 3 | 1 | 0 | 3 | 15 | High |  | 82% | 4100 | Enhance | Work with vprocurement and vendors |  | Q1 FY26 |  | E1103_02475 | 95% | 5200 | 5200 | 5200 | 0 | 0 | 0 | Very High | Critical | Negligible | None | 5 | 4 | 1 | 0 | 4 | 20 | High |  | Conversation with procurement Sep 30 2024 | 4940 | 2024-09-30 | [8 empty] | 2024-09-30 | 2024-09-30
Retired | 30 | Threat | 6.11 Infrastructure | BNL | C. Folz |  | C. Folz | INF | Availability of Existing RHIC Facilities Staff to Support EIC during the Design Phase | If staff are not available when needed, then lack of manpower will delay EIC tasks. | High (Risk is likely to occur with a probability of >40 to <65%) | 1000 | Marginal | 8 | Significant | Negligible | 4 | 2 | 3 | 1 | 3 | 12 | Moderate |  | 52% | 520 | Mitigate | Hire project staff for Infrastructure |  | HR posting and hiring. |  | IF_2102_1460, Infr. Eng Design FY24 | 50% | 500 | 1000 | 1500 | 3 | 8 | 12 | High | Significant | Significant | Negligible | 4 | 3 | 3 | 1 | 3 | 12 | Retired |  |  | Retired |  |  |  | Retired Feb 22 2022. Infrastructure Division staff has been hired. |  |  | 500 | No | 2022-02-02 | 2020-06-30 | 2020-10-30 |  | 666.6667 | 500 - 1000 - 1500 | 3 - 8 - 12 | 500 | 3.8333 | 30
Retired | 204 | Threat | 6.11 Infrastructure | BNL | T. Nehring |  | T. Nehring |  | Tie-Line Upgrade | When the 69kV Tie Line is upgraded, then E-IC and the BNL Lab will have to provide operating funds to pay PSEG-LI to install an upgraded Tie Line in order to carry the EIC projected load | High (Risk is likely to occur with a probability of >40 to <65%) | 2000 | Significant | 3 | Marginal | Marginal | 4 | 3 | 2 | 2 | 3 | 12 | Moderate | The lab and EIC will have to generate operating funds to pay for this work | 52% | 1040 | Mitigate | White paper has been written and submitted to PSEG-LI. The local utility and supplier are reviewing. |  | The evaluation of the system is a multi-year task. Various studies will be performed. BNL and utilities will have to exchange operating scenarios. |  | commissioning | 100% | 200 | 200 | 200 | 0 | 2 | 4 | Very High | Negligible | Negligible | Negligible | 5 | 1 | 1 | 1 | 1 | 5 | Retired |  |  | Retired |  |  |  | Not a project risk. Commissioning cost. |  |  | 200 | NO | 2021-09-27 | 2020-06-30 | 2020-10-30 |  | 266.6667 | 200 - 200 - 200 | 0 - 2 - 4 | 200 | 2 | 204
Retired | 136 | Threat | 6.11 Infrastructure | BNL | C. Folz |  | C. Folz | INF | Distributed or centralized Data Center | If a decision is made to implement a distributed data center instead of centralized data center then it would require a change in architecture and design resulting in increase costs. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 4000 | Significant | 0 | Negligible | Negligible | 2 | 3 | 1 | 1 | 3 | 6 | Low |  | 17% | 680 | Mitigate | Develop design proposals. Engage outside consultants. |  | insert deadline, dates, triggers (decisions to be made by others) |  | IF_0202_1125 | 20% | 4000 | 4000 | 4000 | 2 | 3 | 6 | Low | Significant | Negligible | Negligible | 2 | 3 | 1 | 1 | 3 | 6 | Retired |  | Based on conversation with a former ITD expert | Retired |  |  |  | Data center configuration is not part of WBS 6.11 Infrastructure Scope. Controls configurations are being managed by a separate group and we will provide square footage as needed, just like other Accelerator Systems. |  |  | 800 | NO | 2022-01-25 | 2020-06-30 | 2020-10-30 |  | 1066.6667 | 4000 - 4000 - 4000 | 2 - 3 - 6 | 800 | 0.73333 | 136
Retired | 133 | Threat | 6.11 Infrastructure | BNL | C. Folz |  | C. Folz | INF | Second Detector | If a second detector is included after CD-2, then it will impact design and required additional utilities, power, infrastructure changes resulting in additional costs. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 5000 | Significant | 12 | Crisis | Negligible | 3 | 3 | 5 | 1 | 5 | 15 | High |  | 32% | 1600 | Mitigate | Monitor and participate in the EIC user group discussions related to detector configuration. Establish design development milestones to the project schedule related to second detector selection. |  | Revisions need to be designed into building and power/utilities upgrades from PSE&G. |  |  | 15% | 1000 | 5000 | 7000 | 6 | 12 | 18 | Low | Significant | Significant | Significant | 2 | 3 | 3 | 3 | 3 | 6 | Retired |  |  | Retired |  |  |  | Retired Sep 2021 since risk assumptions are no longer valid |  |  | 650 | No | 09.27.2021 | 2020-06-30 | 2020-10-30 |  | 900 | 1000 - 5000 - 7000 | 6 - 12 - 18 | 650 | 1.8 | 133
Active | RT-6-012-001 | Threat | 6.12 PreOperations | BNL | A. Blednykh | RT-6-012-001 | A. Blednykh | COM | Unforeseen Severe Events During Commissioning | If an unforeseen severe event occurs during commissioning, it will set back the schedule and cost additional funds as we work to get back on track. | High (Risk is likely to occur with a probability of >40 to <65%) | 30000 | Critical | 6 | Marginal | None | 4 | 4 | 2 | 0 | 4 | 16 | High |  | 52% | 15600 | Mitigate | Work across Project WBS to identify interface points and points of failure. Hardware redundancy, reliability, flexibility, operating margins. |  | Q3 FY33 |  | L2_0900, Beam Commiss. Complete | 50% | 5000 | 19000 | 68000 | 2 | 6 | 12 | High | Critical | Marginal | Significant | 4 | 4 | 2 | 3 | 4 | 16 | High |  | Estimated based on 40 year experience with similar facilities and EIC 'hotel load' rate. | 9500 | 2024-01-25 | [5 empty] | 15333.3333 |  |  | 2020-06-30 | 2020-10-30 |  | 12416.6667 | 5000 - 19000 - 68000 | 2 - 6 - 12 | 15333.3333 | 3.3333 | 135 | 2024-03-31 | 1248
Active | RT-6-012-002 | Threat | 6.12 PreOperations | BNL | A. Blednykh | RT-6-012-002 | A. Blednykh | COM | ARR Pre-start completion | If time to complete pre-start ARR items is longer that planned, then the project will experience schedule delays and increased cost | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 200 | Negligible | 3 | Negligible | None | 3 | 1 | 1 | 0 | 1 | 3 | Low |  | 32% | 64 | Mitigate | Full completion of Readiness Plan. Implement a comprehensive check out plan. Engage the review team early. |  | Q2 FY30 |  | PO_0704_1160, SHC - System Readiness Reviews Complete and ready for Integrated Systems Testing | 30% | 1500 | 3000 | 4500 | 1 | 3 | 6 | Moderate | Significant | Negligible | Marginal | 3 | 3 | 1 | 2 | 3 | 9 | Moderate |  | Engineering judgement | 900 | 2024-01-25 | [5 empty] | 900 |  |  | 2020-06-30 | 2020-10-30 |  | 900 | 1500 - 3000 - 4500 | 1 - 3 - 6 | 900 | 1 | 131 | 2024-03-31 | 1248
Active | RT-6-012-003 | Threat | 6.12 PreOperations | BNL | A. Blednykh | RT-6-012-003 | A. Blednykh | COM | ASE Violation | If ASE violation occurs during the beam commissioning, then then the project will experience schedule delays and increased cost | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 10000 | Critical | 6 | Marginal | None | 2 | 4 | 2 | 0 | 4 | 8 | Moderate |  | 17% | 1700 | Mitigate | Train personnel, establish procedures, engineered controls where feasible. |  | Q2 FY30 |  | L2_0900, Beam Commiss. Complete | 20% | 4000 | 11000 | 28000 | 2 | 6 | 12 | Low | Critical | Marginal | Significant | 2 | 4 | 2 | 3 | 4 | 8 | Moderate |  | Estimated based on 40 year experience with similar facilities and EIC 'hotel load' rate. | 2200 | 2024-01-25 | [5 empty] | 2866.6667 |  |  | 2020-06-30 | 2020-10-30 |  | 2533.3333 | 4000 - 11000 - 28000 | 2 - 6 - 12 | 2866.6667 | 1.3333 | 132 | 2024-03-31 | 1248
Active | RT-6-012-004 | Threat | 6.12 PreOperations | BNL | A. Blednykh | RT-6-012-004 | A. Blednykh | COM | ARR Requirements May Change | If the ARR requirements change, then we will need to adjust our plans and timing, which would likely cost additional funds and take more time. | High (Risk is likely to occur with a probability of >40 to <65%) | 250 | Negligible | 0 | Negligible | None | 4 | 1 | 1 | 0 | 1 | 4 | Low |  | 52% | 130 | Mitigate | Have an up-to-date and comprehensive IRP plan. Work with BHSO. |  | Q2 FY30 |  | PO_0701_1120, Electron pre-injector - DOE BHSO approval to begin commiss. | 50% | 100 | 500 | 1000 | 0 | 0 | 1 | High | Significant | Negligible | Negligible | 4 | 3 | 1 | 1 | 3 | 12 | Moderate |  | Engineering judgement | 250 | 2024-01-25 | [5 empty] | 266.6667 |  |  | 2020-06-30 | 2020-10-30 |  | 258.3333 | 100 - 500 - 1000 | 0 - 0 - 1 | 266.6667 | 0.16667 | 39 | 2024-03-31 | 1248
Retired | 130 | Threat | 6.12 PreOperations | BNL | W. Fischer / T. Satogata |  | W. Fischer | COM | KPPs Change | If KPPs change compared to present assumptions, (low luminosity e-A collisions), then more comissioning beam time will be needed, resulting in schedule delay and additional cost. | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 30000 | Critical | 6 | Significant |  | 3 | 4 | 3 | 0 | 4 | 12 | Moderate |  | 32% | 9600 | Mitigate | Work with DOE on finalizing the KPPs. The KPPs should allow for expeditious commissioning. | [11 empty] | INSERT LIKELIHOOD | None |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Risk assumptions are no longer valid |  |  | 0 | NO | 2021-09-21 | 2020-06-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | 130
Retired | DOE | Threat | 6.12 PreOperations | BNL | W. Fischer / T. Satogata |  | J. Eng |  | Delay in Funding | If there is a delay in funding, there will be an impact on cost/schedule | Moderate (Risk is likely to occur with a probability of > 25% to < 40%) | 250 | Negligible |  |  |  | 3 | 1 | 0 | 0 | 1 | 3 | Low |  | 32% | 80 | Mitigate | [12 empty] | INSERT LIKELIHOOD | None |  | None | 0 | 0 | #N/A | 0 | #N/A | #N/A | Retired |  |  | Retired |  |  |  | Moved to management risk 174, "Full Year CR" |  |  | 0 | NO | 2021-09-21 | 2020-06-30 | 2020-10-30 |  | 0 | - - | - - | 0 | 0 | DOE
Note on N239: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost estimate is based on installing one set of DI system and cooling tower. The estimate of the DI and cooling tower cost at 4 O Clock location.
Note on P239: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on 6 months engineering and 6 months construciton
Note on N240: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on white paper
Note on N241: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on white paper
Note on N242: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost is based on RS MEans 2021 comparison of 1000 ton centrifugal chiller and absorption chiller and applying the factor to the CD-1 chilled water estimate.
Note on P242: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on 6 months engineering and 6 months construciton
Note on N243: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Costs are based on 4 inch header supply and return for magnet and ps based on RS MEans and LIRO estimate 2021
Note on N244: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New cost is a plug in number.
Note on N259: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost based on labor for installing 6000 feet of 8" pipe. and schedule based on 4 man crew for the same. Numbers are based on RS Means Adjusted for current conditions.
Note on P259: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost based on labor for installing 6000 feet of 8" pipe. and schedule based on 4 man crew for the same. Numbers are based on RS Means Adjusted for current conditions.
Note on N266: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cost estimate is based on installing one set of DI system and cooling tower. The estimate of the DI and cooling tower cost at 4 O Clock location.
Note on P266: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: based on 6 months engineering and 6 months construciton

## Risk Count
EIC Post-Mitigated Risk Profile
WBS L2 | WBS Description | High Active Threats | Moderate Active Threats | Low Active Threats | Total Active Threats | Active Opportunities | Total Active Risks | Retired Threats/ Opportunities | Grand Total (Threats/ Opportunities) |  |  | Heat Map: All Post-mitigated Risks
6.01 | Project Management | 3 | 9 | 6 | 18 | 2 | 20 | 7 | 27 |  |  |  | Overall Risk Impact
6.02 | Accelerator Devel. R&D | 0 | 2 | 0 | 2 | 0 | 2 | 9 | 11 |  | Category |  | Negligible | Marginal | Significant | Critical | Crisis
6.03 | Electron Injector | 0 | 1 | 3 | 4 | 0 | 4 | 9 | 13 |  |  | Score | 1 | 2 | 3 | 4 | 5
6.04 | Electron Storage Ring | 0 | 6 | 10 | 16 | 0 | 16 | 4 | 20 | Probability | Very High | 5 | 0 | 0 | 0 | 2 | 0
6.05 | Hadron Ring | 0 | 3 | 14 | 17 | 1 | 18 | 11 | 29 |  | High | 4 | 1 | 0 | 16 | 10 | 0
6.06 | Interaction Region & Detector I/F | 2 | 8 | 6 | 16 | 1 | 17 | 12 | 29 |  | Moderate | 3 | 1 | 4 | 25 | 13 | 4
6.07 | Accelerator Systems | 0 | 2 | 5 | 7 | 0 | 7 | 9 | 16 |  | Low | 2 | 9 | 7 | 34 | 13 | 3
6.08 | RF | 2 | 8 | 9 | 19 | 0 | 19 | 16 | 35 |  | Very Low | 1 | 3 | 3 | 13 | 10 | 3
6.09 | Cryogenics | 0 | 3 | 4 | 7 | 0 | 7 | 3 | 10
6.10 | Detector | 1 | 8 | 19 | 28 | 3 | 31 | 9 | 40 | [6 empty] | Total | 174
6.11 | Infrastructure | 5 | 12 | 10 | 27 | 2 | 29 | 9 | 38
6.12 | Pre-Operations | 1 | 3 | 0 | 4 | 0 | 4 | 2 | 6
| Total Project | 14 | 65 | 86 | 165 | 9 | 174 | 100 | 274 | [6 empty] | Total | 272
[12 empty] | Heat Map: Pre-mitigated LLP-CD3A Risks | [7 empty] | Heat Map: Pre-mitigated LLP-CD3B Risks
[13 empty] | Overall Risk Impact | [7 empty] | Overall Risk Impact
[11 empty] | Category |  | Negligible | Marginal | Significant | Critical | Crisis |  | Category |  | Negligible | Marginal | Significant | Critical | Crisis
[12 empty] | Score | 1 | 2 | 3 | 4 | 5 |  |  | Score | 1 | 2 | 3 | 4 | 5
[10 empty] | Probability | Very High | 5 | 0 | 0 | 1 | 1 | 0 | Probability | Very High | 5 | 0 | 0 | 0 | 0 | 0
[11 empty] | High | 4 | 2 | 1 | 4 | 4 | 2 |  | High | 4 | 0 | 1 | 6 | 3 | 0
[11 empty] | Moderate | 3 | 0 | 1 | 3 | 1 | 0 |  | Moderate | 3 | 0 | 0 | 0 | 3 | 0
[11 empty] | Low | 2 | 2 | 0 | 0 | 0 | 0 |  | Low | 2 | 1 | 0 | 0 | 1 | 2
[11 empty] | Very Low | 1 | 0 | 0 | 0 | 0 | 0 |  | Very Low | 1 | 0 | 0 | 0 | 0 | 0
[16 empty] | Total | 22 | [6 empty] | Total | 17
[12 empty] | Heat Map: Post-mitigated LLP-CD3A Risks | [7 empty] | Heat Map: Post-mitigated LLP-CD3B Risks
[13 empty] | Overall Risk Impact | [7 empty] | Overall Risk Impact
[11 empty] | Category |  | Negligible | Marginal | Significant | Critical | Crisis |  | Category |  | Negligible | Marginal | Significant | Critical | Crisis
[12 empty] | Score | 1 | 2 | 3 | 4 | 5 |  |  | Score | 1 | 2 | 3 | 4 | 5
[10 empty] | Probability | Very High | 5 | 0 | 0 | 0 | 1 | 0 |  | Very High | 5 | 0 | 0 | 0 | 0 | 0
[11 empty] | High | 4 | 0 | 0 | 3 | 2 | 0 | Probability | High | 4 | 0 | 0 | 0 | 0 | 0
[11 empty] | Moderate | 3 | 1 | 0 | 5 | 0 | 0 |  | Moderate | 3 | 0 | 0 | 3 | 0 | 0
[11 empty] | Low | 2 | 3 | 0 | 1 | 1 | 0 |  | Low | 2 | 1 | 4 | 9 | 0 | 0
[11 empty] | Very Low | 1 | 1 | 0 | 2 | 1 | 1 |  | Very Low | 1 | 0 | 0 | 0 | 0 | 0
[16 empty] | Total | 22 | [6 empty] | Total | 17
`
[6 empty] | Risk Category | 3A | Pre-mitigated | Post-mitigated
[6 empty] | High |  | 7 | 1
[6 empty] | Moderate |  | 9 | 7
[6 empty] | Low |  | 4 | 12
[7 empty] | Risk Category | Pre-mitigated | Post-mitigated
[7 empty] | High | 4 | 0
[7 empty] | Moderate | 12 | 2
[7 empty] | Low | 1 | 15

## CD-1 Retired Risks (hidden)
RETIRED Risk ID Number | System | Owner | Risk Title | IF/Then | Retired Date | Retired Note (If Applicable) | Likelihood of Impact | Cost Impact Estimate ($K) | Cost Impact Category | Schedule Impact Estimate (months) | Schedule Impact Category | Technical Impact Category | Likelihood Score (1-5) | Cost Score (1-5) | Schedule Score (1-5) | Technical Score (1-5) | Risk Consequence Weight (Max of Cost/Schedule/Technical) | Overall Impact Score | Overall Impact | Mitigations | Risk Handling Schedule (Triggers, Milestones, Due Dates) | Developed Likelihood of impact for Model | Expected Value (K$)
68 |  | V. Ptitsyn | In-Situ Pipe Coating Rate | If the In-situ pipe coating rate is longer than anticipated, the schedule will be impacted and/or the cost will go up. | 2020-08-05 | Risk Workshop #3 retired by WBS 6.05 | Very High (Risk is likely to occur with a probability of >65%) | 40000 | Crisis | 0 | Significant |  | 5 | 5 | 3 | 0 | 5 | 25 | High | Retired , consider new residual risks, Brainstorm new risk |  | 82% | 32800
13 | 6.03 Electron Injector | V. Ranjbar | Electron Ion Insufficiet Performance | The polarized electron gun, which is carried over from the corresponding R&R effort, might not deliver sufficient charge. Then an alternative method must be used and the cost for this is not taken into account. | 2020-10-30 | There is now money in the current budget to build a new gun since it was anticipated that the existing gun might not be able to deliver the full charge necessary I think it was designed under R&D during the linac-Ring days for 5 nC but now we need 7nC. So in the budget John and Erdong already have funds for the rebuild. | Low (Risk is likely to occur with a probability of > 10% to < 25%) | 7000 | Critical | 6 | Negligible |  | 2 | 4 | 1 | 0 | 4 | 8 | Moderate | Retired |  | 17% | 1190
71 | 6.05-Hadron Ring | V. Ptitsyn | Beam Current Increase | If the current increases to 1A, then without cooling, there is a performance risk that could impact the assumed KPPs. | 2020-10-30 | Initially it was introduced for a scope without hadron cooling. Present scope is fully based on strong hadron cooling and does not have this risk. | Low (Risk is likely to occur with a probability of > 10% to < 25%) |  |  |  |  | Significant | 2 | 0 | 0 | 3 | 3 | 6 | Low | Retired |  | 117% | 0
147 | 6.03-Electron Injector | V. Ranjbar | Pulsed Devices | Kicker Perfomance into the ESR | 2020-11-19 | If the fast kicker cannot inject bunches spaced at 10 ns THEN we increase our bunch spacing which decreases luminosity. | Very Low (There is a <10% chance that this event will occur) |  |  |  |  | Critical | 1 | 0 | 0 | 4 | 4 | 4 | Low | R&D for this area at BNL and other labs is in the project baseline.
40 | 6.02-Accelerator Development and R&D | M. Blaskiewicz | Accelerator Physics | Proton Emittance Growth Observed with Finite Crab Frequency | 2020-11-19 | If the simulations always show proton emittance growth, we will need to design and build different crab cavities which will take more R&D time and cost more money. | High (Risk is likely to occur with a probability of >40 to <65%) | 10000 | Critical |  | Negligible | Marginal | 4 | 4 | 1 | 2 | 4 | 16 | High | Task force has been assembled and is devoting 3FTEs to this problem. | CDR - Task Force complete by Sept, problem studied for additional year, should be addressed by CD-2. | 52% | 5200
84 | 6.02-Accelerator Development and R&D | M. Blaskiewicz | RF | 3rd Harmonic RF | 2020-12-22 | If predicted transient beam loading is too large at or before CD-2, a third harmonic system will not work which will impact the likely objective KPPs. | High (Risk is likely to occur with a probability of >40 to <65%) | 3000 | Significant |  | Negligible | Marginal | 4 | 3 | 1 | 2 | 3 | 12 | Moderate | Removing 3rd Harmonic system and increase complexity of vacuum components. (No longer have 3rd Hamonic systems) | Could cause additional impact or increase probability of risks in vacuum components | 52% | 1560
155 | 6.10 Detector | R. Ent | Location of detector not finalized | If detector location is in IP6, the layout of the collider hall introduces significantly more challenges to the integration of the detector, due to the limited door size to roll into maintenance position. Reuse of the existing sPHENIX magnet seems difficult as the magnet needs to be relocated after sPHENIX operations and modifications need to be made. | 2021-01-06 | We updated the risk mitigation text on validation of the collider Hall and assembly Hall that all first through the door, and since we carry the magnet risk contingency elsewhere, this one is complete | Very High (Risk is likely to occur with a probability of >65%) | 10000 | Critical | 12 | Crisis | Marginal | 5 | 4 | 5 | 2 | 5 | 25 | High | As part of OPC, model layout of the collider hall, door size and assembly Hall to study impact on detector integration and maintenance modes. Finalize IP location as IP6 and carry new central detector magnet risk/contingency. |  | 82% | 8200
Note on H1: kflick: What is the likelihood that this risk will actually impact the project, if we do NOT do any mitigation? (Drop-down Indicates odds)
Note on I1: kflick: To what degree might the risk impact the project cost IF LEFT UNMITIGATED This is an estimate of the most likely actual dollar cost (In $K) impact to the project if the risk occurs.
Note on K1: kflick: To what degree might the risk impact the Project Schedule IF LEFT UNMITIGATED This is an estimate of the most likely actual schedule impact to the affected activities if the risk occurs. (In Months)
Note on L1: kflick: To what degree might the risk impact the Project Schedule IF LEFT UNMITIGATED This is an estimate of the most likely actual schedule impact to the affected activities if the risk occurs. (In Months)
Note on N1: kflick: Risk Manager Use ONLY - Scoring
Note on O1: kflick: Risk Manager Use ONLY - Scoring
Note on P1: kflick: Risk Manager Use ONLY - Scoring
Note on Q1: kflick: Risk Manager Use ONLY - Scoring
Note on R1: kflick: Risk Manager Use ONLY - Scoring
Note on S1: kflick: Risk Manager Use ONLY - Scoring
Note on T1: kflick: Calculated Field DO NOT ALTER: This is the overall Risk Impact Score BEFORE mitigation is completed. The scoring is based on calculations as defined in the Project Risk Management Plan. Likelihood, Cost, Schedule, and Technical are scored based on Impact assessments, and the Likelihood score is multiplied by the greatest of the scores for Cost, Schedule, Technical Impact.
Note on U1: kflick: Document the steps that will be taken to mitigate the Likelihood, Cost, Schedule, and Scope impacts that the identified risk might have on the project. Try to provide as much relevant, specific detail as possible to assist the project in actively managing the outcome of the activities associated with the identified risk. Documented mitigations should be reasonable and not impact the project more than the risk, if fully realized might impact the project. Documented mitigations should be included in the baseline plan, and until the plan is updated, the estimated cost of mitigation should be included in the "Cost to Mitigate" column, after which the cost to mitigate should be removed. Some risks can not be mitigated. Include any information on monitoring, trigger events to watch for etc., so that the project can adequately manage related aspects of the overall project.
Note on V1: kflick: Document specific dates and/or circumstances for triggers, milestones, due dates, etc. for specific items listed in the Risk Handling Plan (Prior Column) Included may be things like: Report due dates, MOU due dates, inspections, studies, investigations, schedule milestones, Start-by dates, etc...

## Risk Matrices
Qualitative Risk Analysis Matrix
Impact
| Likelihood | Category |  | Negligible | Marginal | Significant | Critical | Crisis
|  | Cost |  | Minimal or no consequence. No impact to Project cost. (≤ $250k) | Small increase in meeting objectives. Marginal increases in costs. (> $250K ≤ $1M) | Significant degradation in meeting objectives significantly increases cost; (>$1M ≤ $5M) | Goals and objectives are not achievable. Additional funding may be required. (>$5M ≤ $30M) | Project stopped. Funding withdrawal; withdrawal of scope, or severe contractor cost performance issues. (> $30M)
|  | (less/equal than) [k$] |  | 250 | 1000 | 5000 | 30000 | over 30000
|  | Schedule (less/equal than) [mo] |  | 3 | 6 | 12 | 24 | over 24
|  | Technical |  | No impact to threshold or objective KPPs | Possible impact to objective KPPs but workarounds available. No impact to threshold KPPs | Possible impact to an objective KPP, but likely no workaround available. No impact to threshold KPPs. | Will impact objective KPP. Possible impact to threshold KPPs, but workaround available. | Impacts a threshold KPP
|  | Very High |  | Low | Moderate | High | High | High
|  | > | 65%
|  | High |  | Low | Moderate | Moderate | High | High
|  | <= | 65%
|  | > | 40%
|  | Moderate |  | Low | Low | Moderate | Moderate | High
|  | <= | 40%
|  | > | 25%
|  | Low |  | Low | Low | Low | Moderate | Moderate
|  | <= | 25%
|  | > | 10%
|  | Very Low |  | Low | Low | Low | Low | Low
|  | <= | 10%
Probability and Impact Scoring
Impact
Probability | Category |  | Negligible | Marginal | Significant | Critical | Crisis
|  | Score | 1 | 2 | 3 | 4 | 5
| Very High | 5 | 5 | 10 | 15 | 20 | 25 |  | 0 | 0 | 0 | 2 | 0
| High | 4 | 4 | 8 | 12 | 16 | 20 |  | 1 | 0 | 16 | 10 | 0
| Moderate | 3 | 3 | 6 | 9 | 12 | 15 |  | 1 | 4 | 25 | 13 | 4
| Low | 2 | 2 | 4 | 6 | 8 | 10 |  | 9 | 7 | 34 | 13 | 3
| Very Low | 1 | 1 | 2 | 3 | 4 | 5 |  | 3 | 3 | 13 | 10 | 3
Risk Matrix scoring
| High | ≥ | 15
| Moderate | ≤ | 14
| Low | ≤ | 6

## Presentation Template
Choose Row in Risks tab | 237
|  | Risk ID | Title | System | Owner | Overall Category
|  | Retired | DET | R. Ent | 0 | 800%
|  | Risk Statement (If/Then) |  | P6 Milestone affected | Residual Probability | L1_070, CD4-a
|  | Collaboration Formation Delayed |  | 0 | Residual Cost Category | Low
[5 empty] | Resid. Schedule Category | Critical
[5 empty] | Technical Category | Significant
|  | Risk Mitigations |  |  | Cost Impacts ($K) |  | Schedule Impacts (Months)
|  | Mitigate |  |  | Expected Value
Average EV
[5 empty] | Low Cost | 0.2 | Low | 30000
[5 empty] | Likely Cost | 5000 | Likely | 6
[5 empty] | High Cost | 10000 | High | 12
Basis of Impact Estimates (Cost & Sched.):
Risk Handling Schedule ( Triggers, Milestones, Due Dates)
Change History
44134

## Magnet Procurements
WBS ID | WBS Name | Activity Name | Original Duration | Start | Finish | Material Cost | Budgeted Total Cost | Column1
6 | EIC - Working File |  | 2224 | 2020-10-01 | 2029-08-24 | 161752852 | 179702389.48 | 16175285.2 | 32350570.4 | 48525855.6
6.02 | Accelerator Development and R&D |  | 704 | 2020-10-01 | 2023-07-27 | 3020620 | 3408079.26 | 3 | 30 | 3
6.02.03 | Accelerator Systems R&D |  | 704 | 2020-10-01 | 2023-07-27 | 3020620 | 3408079.26
6.02.03.03 | IR Design and Magnet Prototyping |  | 704 | 2020-10-01 | 2023-07-27 | 3020620 | 3408079.26
6.02.03.03.02 | IR Magnet Prototyping |  | 344 | 2022-03-16 | 2023-07-27 | 3020620 | 3119996.18 | 302062 | 604124 | 906186
6.03 | Electron Injector |  | 1112 | 2023-01-05 | 2027-06-15 | 42142514 | 46489569.68
6.03.02 | Rapid Cycling Synchrotron |  | 1112 | 2023-01-05 | 2027-06-15 | 42142514 | 46489569.68
6.03.02.01 | RCS Magnets |  | 1112 | 2023-01-05 | 2027-06-15 | 42142514 | 46489569.68 | 4214251.4 | 8428502.8 | 12642754.2
6.03.02.01.01 | RCS Dipole Magnets |  | 1072 | 2023-01-05 | 2027-04-19 | 15844402 | 17540463.9
6.03.02.01.02 | RCS Quad Magnets |  | 1072 | 2023-03-06 | 2027-06-15 | 8424412 | 9343514.9
6.03.02.01.03 | RCS Sextupole Magnets |  | 1012 | 2023-05-01 | 2027-05-17 | 7113300 | 7870854.81
6.03.02.01.04 | RCS Corrector Magnets |  | 520 | 2023-12-20 | 2026-01-20 | 1552500 | 1691340.98
6.03.02.01.05 | RCS Girders, Assembly and Integration |  | 500 | 2024-02-20 | 2026-02-18 | 8340000 | 9108751.21
6.03.02.01.06 | Magnet Measuring Stations |  | 250 | 2024-01-08 | 2025-01-06 | 867900 | 934643.89
6.04 | Electron Storage Ring |  | 1137 | 2022-08-26 | 2027-03-18 | 55333127 | 60898036.62
6.04.02 | Electron Storage Ring Magnets |  | 1137 | 2022-08-26 | 2027-03-18 | 55333127 | 60898036.62 | 5533312.7 | 11066625.4 | 16599938.1
6.04.02.01 | ESR Dipole Magnets |  | 1057 | 2022-08-26 | 2026-11-18 | 30779145 | 33809005
6.04.02.02 | ESR Quad Magnets |  | 1057 | 2022-10-25 | 2027-01-20 | 8456395 | 9316072.84
6.04.02.03 | ESR Sextupole Magnets |  | 1057 | 2022-12-23 | 2027-03-18 | 4982587 | 5504800.8
6.04.02.04 | ESR Corrector Magnets |  | 520 | 2023-10-06 | 2025-11-04 | 1235000 | 1339649.66
6.04.02.05 | ESR Girders and Integrated Assembly |  | 500 | 2024-09-06 | 2026-09-04 | 9880000 | 10928508.32
6.05 | Hadron Ring |  | 500 | 2026-12-09 | 2028-12-07 | 5251500 | 6108560.53
6.05.08 | Strong Hadron Cooling (SHC) |  | 500 | 2026-12-09 | 2028-12-07 | 5251500 | 6108560.53 | 525150 | 1050300 | 1575450
6.05.08.04 | SHC Beam Transport |  | 500 | 2026-12-09 | 2028-12-07 | 5251500 | 6108560.53
6.05.08.04.01 | SHC Beam Transport Magnets |  | 500 | 2026-12-09 | 2028-12-07 | 5251500 | 6108560.53
6.06 | Interaction Regions and Detector Interface |  | 1213 | 2023-08-17 | 2028-06-23 | 56005091 | 62798143.39
6.06.02 | Interaction Region (IR) |  | 1213 | 2023-08-17 | 2028-06-23 | 56005091 | 62798143.39 | 5600509.1 | 11201018.2 | 16801527.3
6.06.02.01 | IR Magnets |  | 1178 | 2023-10-06 | 2028-06-23 | 19407684 | 21525143.74
6.06.02.01.01 | Direct Wind Magnets |  | 700 | 2023-12-21 | 2026-10-06 | 5829510 | 6408054.17
6.06.02.01.02 | Collared Magnets |  | 770 | 2024-08-21 | 2027-09-20 | 10517000 | 11772807.78
6.06.02.01.03 | IR Warm Magnets |  | 250 | 2023-10-06 | 2024-10-04 | 2413369 | 2584701.27
6.06.02.01.04 | IR Cryostat Integration and Magnet Test |  | 100 | 2028-02-03 | 2028-06-23 | 647805 | 759580.51
6.06.02.02 | IR Spin Rotator Magnets |  | 845 | 2024-10-07 | 2028-02-28 | 30188464 | 34126449.22
6.06.02.07 | Matching Magnets |  | 930 | 2024-07-31 | 2028-04-20 | 4958943 | 5571083.23
6.06.02.08 | Cables |  | 792 | 2023-08-17 | 2026-10-16 | 1450000 | 1575467.2

## BOE 6_11
Risk ID | Risk Title | Basis of Estimates - Residual Risks
207 | Low Cooling Water Temperature for RF Power Amplifers | The cost is based on installing a total of 6600 tons of chillers at the 2, 4, 6, 10 o'clock locations. The chiller cost is based on a 77F CWIT. The $3.9 million net present value of additional electricity consumed by chiller compressors is not included in the cost impact.
208 | CW Performance for EIC Operation in the Summer Months | The cost is based on installing a total of 6600 tons of chillers at the 2, 4, 6, 10 o'clock locations. The chiller cost is based on a 77F CWIT. The $3.9 million net present value of additional electricity consumed by chiller compressors is not included in the cost impact.
212 | Preliminary cooling loads | Cost estimate is based on installation of a 2000 ton cooling system at a new location.
213 | Existing cooling water systems | Cost estimate is based on installation of a 2000 ton cooling system at a new location.
214 | Refrigerants in AC Systems | Assumed as roughly 50% of the cost of the chilled water system for the EIC.

## Risk BOE 6_01
Risk ID # | Title | Assumptions | Basis of Estimate | Cost | Schedule | Impact Category
3 | RHIC shut down date | Access to the tunnel milestone is June 2025 | If RHIC shut down is delayed, we assume here that we would not stick to the shutdown during the summer and we would go straight through. Assume an extra 6 months as most likely; 3 months as low; 9 months as high. Assume the hotel load per month plus some amount of other delays and the need to store material. If we saw this coming we could get ready with planning for multiple shifts. There would probably be a shift factor of 1.5x on some portion of the installation labor.
|  | Access to the tunnel is on the critical path | So…..there would be a day to day delay in the project.
|  | Cost per month is about $25M during the peak of the project | $2.2M/month x 3 months + $2M in extra costs | 8.6 | 3 mos | low
|  | Hotel load is about $2.2/month | $2.2M/month x 6 months + $5M in extra costs | 18.2 | 6 mos | likely
|  |  | $2.2M/month x 9 months + $8M in extra costs | 27.8 | 9 mos | high
116 | Limited magnet vendors | Ferdinand will need to verify this and provide some backup | See list of magnet procurements included as a separate tab in this spreadsheet | 10% |  | low
|  |  |  | 20% |  | likely
|  |  |  | 30% |  | high
4 | Reprioritized redirect funds | Assumes that this would become an overall reduction of funding issue or a slip in schedule. | Impact could be anywhere from zero to say 50% of the total redirection amount of $1,014M. Maybe $100M would be a good guess. We would need to descope, get more in kind or stretch the schedule out. A mitigation strategy could be to get more in-kind. Maybe $5M labor increase could fund a person to shake the trees. | $100M | 6 | low
[5 empty] | 12 | likely
[5 empty] | 24 | high
9 | Matrixed Labor | Applies to both BNL and TJ Labor | 25% of labor = TJ = $177.5M |  | 3 | low
|  | Assume all of TJ labor is matrixed | 75% of labor = BNL = $532.5M x 50% = 266.25 |  | 6 | likely
|  | Assume 50% of BNL labor is matrixed | Total matrixed labor = $443.75M |  | 12 | high
Total CD-1 labor = $710M
159 | Escalation | Current escalation rates could be low so assume the following | Need to just adjust the escalation in P6 accordingly. I would focus on materials since we have a good handle on labor and it is monitored by the labs.
|  | 1% above current escalation |  | 1% |  | low
|  | 2% above current escalation |  | 2% |  | likely
|  | 3% above current escalation |  | 3% |  | high
160 | TJ Labor rates < BNL | Total CD-1 labor = $710M | Low would be 60% more expensive in NY: 177.5/1.60 = 110.9 | 66.5625 |  | low
|  | TJ labor = 25% = $177.5M | Likely would be 75.4% more expensive in NY: 177.5/1.754 = 101.2 | 76.3027 |  | likely
|  | Assume labor rates are 75.4% more expensive in NY | High would be 80% more expensive in NY: 177.5/1.8 = 98.6 | 78.8889 |  | high
See details here:
175 | Additional In-Kind | Current in-kind is assumed at
|  | 5% for the accelerator ($50M) | For Accelerator assume 6% for low; 8% for likely; 10% for high | -10 |  | low
|  |  |  | -30 |  | likely
|  |  |  | -50 |  | high
|  | 30% for the detector ($100M) | For Detector assume 35% for low; 40% for likely; 45% for high | -16.6667 |  | low
|  |  |  | -33.3333 |  | likely
|  |  |  | -50 |  | high
|  |  | Overall | -26.6667 |  | low
|  |  |  | -63.3333 |  | likely
|  |  |  | -100 |  | high
176 | Decrease in Escalation | This is just the opposite of Risk ID#159 |  | 0% |  | low
|  |  |  | -1% |  | likely
|  |  |  | -2% |  | high
10 | ESH Issues | Includes "events" - accident, exposure, spill, violation. | Used NSLS-II as the basis of the likelihood, but added a factor of 30% assuming more stringent guidelines now ($5M additional cost for an ESH event plus 30% = $6,500). If this were to occur, it would mean also that the standing army cost would continue to address the issue but other work would get pushed out. Assume 50% of real work gets delayed. | $5.0M | 3 mos | low
|  |  |  | $6.5M | 6 mos | likely
|  |  |  | $8M | 9 mos | high
ICR-002 | Commodity Price Fluctuations | This impact could be more short-term -- say two years. | Spreadsheet attached (ICR-002) showing all procurements over $250K and which ones could be impacted by commodity price fluctuations. We are following this and will watch - see: https://economics.td.com/us-commodity-price-report
ICR-004 | Spares | We should assume that spares will be purchased with the larger quantity of items and then transferred to OPC funding at the end of the project. | Spares are targeted at $9M. Assume most likely increase is $1M. Point value for cost impact converted to a range based on a Class 5 cost ROM (-30% to +50%). No schedule impact. | 0 |  | low
|  |  |  | $1M |  | likely
|  |  |  | $1.5M |  | high
1 | Loss of Key Personnel | This risk would come to realization if we lost a number of key personnel all at one time. | The schedule risk here is a 3-6 month delay in having someone in place (depending on the level of the position) |  | 3 mos | low
[5 empty] | 4.5 mos | likely
[5 empty] | 6 mos | high
11 | Strong Hadron Cooling |  | We need to talk about this - no impact to KPPs so I don't think this is a project risk.
123 | NYS Funding Reduced or Delayed | This is already happening…..Tend to think this would be a delay instead of a reduction but OK to assume a 10% reduction for now. Once we start getting funds, we can reduce the probability of this. | The schedule delay would be a month to month delay on the A/E contract award which should push everything else out. I believe there is some float in between the A/E and the construction award, so we would need to use the float first. |  | 3 | low
[5 empty] | 6 | likely
[5 empty] | 12 | high
167 | COVID Delays | This is already happening….. | Schedule delays would be tied to R&D activities because that is the hands on work that is going on right now. |  | 3 | low
[5 empty] | 6 | likely
[5 empty] | 9 | high
174 | Full-Year CR in Ramp up Phase | This is already happening….. | This is probably only a schedule impact. I gave degrees of this with 3/6/12 month impacts. No cost impact. |  | 3
6
9
177 | G&A Increase | Assume that the Labs will hold the rates as best they can and that a 1% increase/decrease would be the most likely. | Probably best to use a 1.5% increase in Common Support (as that was the last increase we saw) as a likelly scenario. That increase resulted in a $1.5M increase in project cost (as calculated in the sensitivity analysis conducted for the CD-1 review (attached). I would say $1M low and $2M likely. | $1M |  | low
|  |  |  | $1.5M |  | likely
|  |  |  | $2M |  | high
178 | G&A Decrease | Assume that the Labs will hold the rates as best they can and that a 1% increase/decrease would be the most likely. | Use the opposite of Risk 177, but the likelihood is probably cut in half. | $1M |  | low
|  |  |  | $1.5M |  | likely
|  |  |  | $2M |  | high
ICR-001 | Foreign Exchange Rate Fluctuations |  | Spreadsheet attached (ICR-001, ICR-002) showing all procurements over $250K and which ones could be impacted by foreign exchange rate fluctuations.
ICR-003 | Lower Level of In Kind than Anticipated |  | Assume in-kind contributions are targeted at $242M, and contributions fall short by 10%. Point value for cost impact converted to a range based on a Class 5 cost ROM (-30% to +50%). No schedule impact. | $17M |  | low
|  |  |  | $24M |  | likely
|  |  |  | $36M |  | high
179 | Management of In Kind |  | 2.5M extra costs to replan and hire staff to address schedule impacts and loss of contributed labor. The cost would cover an additional dedicated individual for this. High estimate includes an additional person. Schedule risk associated with delays. | $1.5M | 3 | low
|  |  |  | $2.5M | 6 | likely
|  |  |  | $5.0M | 12 | high
5 | Supply Chain Issues | Assumes this is separate from Commodity Price Fluctuations and that this is a short term risk - FY2022 only would be a good estimate. | Given that we would not be procuring major material under CD-2/3A, this risk should be small |  | no impact | likely
[5 empty] | no impact | low
[5 empty] | 4 months delay | high

## ICR-001
EIC_Partner Scope | WBS | Activity ID | EIC_APP CODE | EIC CAM | Activity Name | EIC_PPM | Direct Material Cost | WS Dur | Start | BNL_PMC Rep | Foreign vs. Domestic
BNL | 6.05.06 | HR_0700_1040 | APP00139 | Anerella | Reconfiguring helical magnets in snakes - Non Labor | Alexander | 441487 | 500 | 2028-04-07 | Patil
JLAB | 6.08.05.09.01 | E03_00500 |  | Baggett | RCS Harmonic Injection Kicker Placeholder (includes Labor and Material) - Vendor Fabrication | Alexander | 3600000 | 400 | 2026-10-13 | Kessler
BNL | 6.10.05.02 | DE_0500_3002 | APP00019 | Bazilevsky | Barrel Electromagnetic Calorimetry - Prototyping In-Kind | Alexander | 540000 | 300 | 2023-03-01 | Lewis | Domestic
BNL | 6.10.05.02 | DE_0500_3080 | APP00019 | Bazilevsky | Barrel Electromagnetic Calorimetry - Material Procurement | Alexander | 11761249 | 100 | 2025-08-22 | Lewis
BNL | 6.10.05.03 | DE_0500_3240 | APP00019 | Bazilevsky | Forward (Hadronic Endcap) Electromagnetic Calorimetry - Purchase Material | Alexander | 632000 | 100 | 2025-08-21 | Lewis
BNL | 6.10.05.03 | DE_0500_3245 | APP00019 | Bazilevsky | Forward (Hadronic Endcap) Electromagnetic Calorimetry - Silicon Photomultipliers | Alexander | 833333 | 100 | 2025-08-21 | Lewis
BNL | 6.10.05.03 | DE_0500_3250 | APP00019 | Bazilevsky | Forward (Hadronic Endcap) Electromagnetic Calorimetry - Purchase Material In-Kind | Alexander | 3384708 | 100 | 2025-08-21 | Lewis
BNL | 6.10.05.01 | DE_0500_3380 | APP00019 | Bazilevsky | Backward (Electron Endcap) Electromagnetic Calorimetry - Material Procurement | Alexander | 1323707 | 100 | 2025-04-03 | Lewis
BNL | 6.10.05.01.01 | DE_0500_3385 | APP00019 | Bazilevsky | Backward (Electron Endcap) Electromagnetic Calorimetry - PbWO4 Crystals | Alexander | 4669574 | 100 | 2025-04-09 | Lewis
BNL | 6.10.05.01 | DE_0500_3390 | APP00021 | Bazilevsky | Backward (Electron Endcap) Electromagnetic Calorimetry - Material Procurement In-Kind | Alexander | 1997760 | 100 | 2025-04-03 | Lewis | Foreign | Czech Republic CRYTUR
BNL | 6.10.05.02 | DE_0500_3082 | APP00023 | Bazilevsky | Barrel Electromagnetic Calorimetry - Silicon Photomultipliers | Alexander | 1394805 | 100 | 2025-08-22 | Lewis | Foreign | Japan Hamamatzu
BNL | 6.03.02.03 | EJ_0202_1300 | APP00010 | Bruno | Corrector & Injection Bump Supplies - Vendor Fabrication | Alexander | 5772500 | 520 | 2026-10-14 | Patil | Foreign
BNL | 6.03.02.03 | EJ_0202_1460 | APP00011 | Bruno | Rest of RCS Supplies - Vendor Fabrication | Alexander | 8250000 | 520 | 2026-10-14 | Patil | Domestic
BNL | 6.03.02.03 | EJ_0202_1620 | APP00012 | Bruno | DC, AC power cables control and magnet interlock cables and cable trays - Materials Vendor Fabrication | Alexander | 7801220 | 260 | 2026-10-14 | Patil | Domestic
BNL | 6.03.02.03 | EJ_0202_1120 | APP00027 | Bruno | Main Dipole supply and the 2 Arc Quad supplies - Vendor Fabrication and ship | Alexander | 11250000 | 520 | 2026-10-14 | Patil | Foreign
BNL | 6.06.02.03 | IR_0203_1300 | APP00031 | Bruno | Bus/ Cable - Vendor Manufacturing | Alexander | 306320 | 180 | 2026-10-14 | Patil | Domestic
BNL | 6.04.04 | SR_0300_1080 | APP00031 | Bruno | Cable Bus - Manufacturing Vendor | Alexander | 8975521 | 180 | 2026-10-14 | Patil | Domestic
BNL | 6.04.04 | SR_0300_1085 | APP00031 | Bruno | Cable Bus - Mounting Brackets - Manufacturing Vendor | Alexander | 688525 | 180 | 2026-10-14 | Patil | Domestic
BNL | 6.03.04.01.01 | EJ_040102_1080 | APP00032 | Bruno | Dipole, Solenoid and Quad PS - Vendor Manufacturing | Alexander | 340494 | 180 | 2026-10-13 | Patil | Domestic
BNL | 6.05.07.07 | HR_0809_1260 | APP00032 | Bruno | Medium PS - Vendor Manufacturing | Alexander | 496727 | 120 | 2026-12-04 | Patil | Domestic
BNL | 6.04.04 | SR_0300_1660 | APP00032 | Bruno | Quades and Sextupoles - Manufacturing | Alexander | 1202370 | 300 | 2026-10-13 | Patil | Domestic
BNL | 6.05.02.02 | HR_0202_1080 | APP00040 | Bruno | New PS (medium PS/ Corrector PS) - Vendor Manufacturing - APS PS | Alexander | 360000 | 120 | 2026-10-14 | Patil | Domestic
BNL | 6.05.03.02 | HR_0402_2140 | APP00040 | Bruno | HR Inj Warm Line Septum APS - Vendor Manufacturing | Alexander | 1023827 | 180 | 2026-10-14 | Patil | Domestic
BNL | 6.04.04 | SR_0300_1460 | APP00040 | Bruno | Main Dipole/Quads/Sext - Vendor Manufacturing - APS | Alexander | 4770190 | 240 | 2026-10-14 | Patil | Domestic
BNL | 6.06.02.03 | IR_0203_1100 | APP00051 | Bruno | IR PS - Vendor Manufacturing - OCEM | Alexander | 824091 | 350 | 2026-10-13 | Patil | Foreign
BNL | 6.06.02.03 | IR_0203_1440 | APP00051 | Bruno | PED, Quench Protection - Vendor Manufacturing - OCEM | Alexander | 1200742 | 240 | 2026-10-14 | Patil | Foreign
BNL | 6.03.04.01.01 | EJ_040102_1280 | APP00060 | Bruno | Corrector PS - Vendor Manufacturing - CAEN-FAST PS | Alexander | 711360 | 250 | 2026-10-14 | Patil | Foreign
BNL | 6.05.07.07 | HR_0809_1460 | APP00060 | Bruno | Small PS - Manufacturing - CAEN | Alexander | 393120 | 60 | 2027-05-18 | Patil | Foreign
BNL | 6.04.04 | SR_0300_1260 | APP00060 | Bruno | Correctors - Vendor Manufacturing - CAEN | Alexander | 1131600 | 300 | 2026-10-14 | Patil | Foreign
BNL | 6.05.07.07 | HR_0809_1660 | APP00061 | Bruno | Cable - Manufacturing - DC Cable Order | Alexander | 346979 | 174 | 2027-03-05 | Patil | Domestic
BNL | 6.03.03.02 | IR_0302_3780 | APP00061 | Bruno | RCS-SR Cables - Vendor Manufacturing - DC Cable Order | Alexander | 257758 | 80 | 2026-10-14 | Patil | Domestic
BNL | 6.04.04 | SR_0300_1880 | APP00061 | Bruno | DC Cable - Manufacturing | Alexander | 2290077 | 60 | 2026-10-14 | Patil | Domestic
BNL | 6.03.02.03 | EJ_0202_2470 | APP00110 | Bruno | RCS-PSC/PSI/REG BTPs - Vendor Fabrication | Alexander | 1445963 | 63 | 2026-10-14 | Patil | Domestic
BNL | 6.04.04 | SR_0300_1790 | APP00111 | Bruno | Quads and Sextupoles-PDU+DCCT Chassis+PSC/PSI/REG BTPs - Vendor Maunufacturing | Alexander | 2065831 | 346 | 2026-10-14 | Patil | Domestic
BNL | 6.05.02.02 | HR_0202_1960 | APP00122 | Bruno | HR Straight DC Cables - Vendor Manufacturing | Alexander | 290416 | 240 | 2026-10-14 | Patil | Domestic
BNL | 6.03.04.01.01 | EJ_040102_1205 | APP00124 | Bruno | Dipole, Solenoid and Quad PS-PDU+DCCT Chassis+PSC/PSI/REG BTPs -Vendor Maunufacturing | Alexander | 613257 | 230 | 2026-10-13 | Patil | Domestic
BNL | 6.05.07.07 | HR_0809_9080 | APP00132 | Bruno | Medium PS - PDU+DCCT Chassis+PSC/PSI/REG BTPs - Vendor Maunufacturing | Alexander | 861112 | 215 | 2026-11-10 | Patil | Domestic
BNL | 6.04.04 | SR_0300_1760 | APP00135 | Bruno | Quades and Sextupoles - Purchase-Racks | Alexander | 330000 | 120 | 2028-03-08 | Patil | Domestic
BNL | 6.05.03.02 | HR_0402_2160 | APP00142 | Bruno | HR Inj Warm Line Septum/Quad/Dipole - DC, AC, Control Interlock Cable Order | Alexander | 410425 | 180 | 2027-03-30 | Patil | Domestic
BNL | 6.04.04 | SR_0300_2200 | APP00213 | Bruno | AC & Interlock Cable -Manufacturing | Alexander | 300000 | 60 | 2026-10-14 | Patil | Domestic
BNL | 6.11.02.02.02 | IF_0202_1100 | APP00004 | Dirul | New LINAC Tunnel 1002 - Installation of New 400 Mev LINAC Tunnel | Alexander | 7067161 | 90 | 2026-01-07 | Patil | Domestic
BNL | 6.11.02.02.02 | IF_0202_1120 | APP00004 | Dirul | New LINAC Tunnel 1002 - New 400 Mev LINAC - General & Systems | Alexander | 463347 | 60 | 2026-05-15 | Patil
BNL | 6.11.02.02.03 | IF_0202_1135 | APP00004 | Dirul | Energy Recovery LINAC Support Bldg 1002H - Excavation | Alexander | 438503 | 60 | 2026-01-07 | Patil
BNL | 6.11.02.02.03 | IF_0202_1145 | APP00004 | Dirul | Energy Recovery LINAC Support Bldg 1002H - Concrete Pad, Asphalt Pavings and markings | Alexander | 5603245 | 30 | 2026-04-03 | Patil
BNL | 6.11.02.02.03 | IF_0202_1155 | APP00004 | Dirul | Energy Recovery LINAC Support Bldg 1002H - Building Structural Work | Alexander | 1866932 | 30 | 2026-05-15 | Patil
BNL | 6.11.02.02.03 | IF_0202_1165 | APP00004 | Dirul | Energy Recovery LINAC Support Bldg 1002H - MEP and Interior | Alexander | 7274139 | 60 | 2026-06-29 | Patil
BNL | 6.11.02.02.04 | IF_0202_1195 | APP00004 | Dirul | 400MeV LINAC Support Bldg 1012D - Concrete Pad, Asphalt Pavings and markings | Alexander | 2759890 | 30 | 2026-05-15 | Patil
BNL | 6.11.02.02.04 | IF_0202_1205 | APP00004 | Dirul | 400MeV LINAC Support Bldg 1012D - Building Structural Work | Alexander | 1073347 | 30 | 2026-06-29 | Patil
BNL | 6.11.02.02.04 | IF_0202_1215 | APP00004 | Dirul | 400MeV LINAC Support Bldg 1012D - MEP and Interior | Alexander | 5177865 | 60 | 2026-08-11 | Patil
BNL | 6.11.02.02.04 | IF_0202_1217 | APP00004 | Dirul | 400MeV LINAC Support Bldg 1012D - Tunnel Modifications | Alexander | 362500 | 60 | 2026-11-05 | Patil
BNL | 6.11.02.03.01 | IF_0203_1020 | APP00004 | Dirul | Cryogenic 1002I - Concrete Pad, Asphalt Pavings and markings | Alexander | 255228 | 20 | 2026-02-05 | Patil
BNL | 6.11.02.03.01 | IF_0203_1040 | APP00004 | Dirul | Cryogenic 1002I - Building Structural Work | Alexander | 666196 | 30 | 2026-03-06 | Patil
BNL | 6.11.02.03.01 | IF_0203_1060 | APP00004 | Dirul | Cryogenic 1002I - MEP and Interior | Alexander | 1425882 | 60 | 2026-04-17 | Patil
BNL | 6.11.02.03.02 | IF_0203_1100 | APP00004 | Dirul | Cryogenic 1006 - Concrete Pad, Asphalt Pavings and markings | Alexander | 255228 | 20 | 2026-03-06 | Patil
BNL | 6.11.02.03.02 | IF_0203_1120 | APP00004 | Dirul | Cryogenic 1006 - Building Structural Work | Alexander | 666196 | 30 | 2026-04-03 | Patil
BNL | 6.11.02.03.02 | IF_0203_1140 | APP00004 | Dirul | Cryogenic 1006 - MEP and Interior | Alexander | 1425882 | 60 | 2026-05-15 | Patil
BNL | 6.11.02.03.03 | IF_0203_1180 | APP00004 | Dirul | Cryogenic 1010E – Concrete Pad, Asphalt Pavings and markings | Alexander | 284720 | 20 | 2026-04-17 | Patil
BNL | 6.11.02.03.03 | IF_0203_1200 | APP00004 | Dirul | Cryogenic 1010E – Building Structural Work | Alexander | 725264 | 30 | 2026-05-15 | Patil
BNL | 6.11.02.03.03 | IF_0203_1220 | APP00004 | Dirul | Cryogenic 1010E – MEP and Interior | Alexander | 1781251 | 30 | 2026-06-29 | Patil
BNL | 6.11.02.04.03 | IF_0204_1180 | APP00004 | Dirul | 1010D - EIC 10 O'Clock DI Pumphouse - Concrete Work/ slab/ Asphal Pavement | Alexander | 351288 | 30 | 2026-02-20 | Patil
BNL | 6.11.02.04.03 | IF_0204_1200 | APP00004 | Dirul | 1010D - EIC 10 O'Clock DI Pumphouse - Building Structural Work | Alexander | 557971 | 30 | 2026-04-03 | Patil
BNL | 6.11.02.04.03 | IF_0204_1220 | APP00004 | Dirul | 1010D - EIC 10 O'Clock DI Pumphouse - MEP and Interior | Alexander | 1730804 | 30 | 2026-05-15 | Patil
BNL | 6.11.02.04.04 | IF_0204_1240 | APP00004 | Dirul | 1010C EIC RF Power Amplifier Building - Excavation | Alexander | 882709 | 20 | 2026-01-07 | Patil
BNL | 6.11.02.04.04 | IF_0204_1260 | APP00004 | Dirul | 1010C EIC RF Power Amplifier Building - Concrete Work/ slab/ Asphal Pavement | Alexander | 5021704 | 60 | 2026-02-05 | Patil
BNL | 6.11.02.04.04 | IF_0204_1280 | APP00004 | Dirul | 1010C EIC RF Power Amplifier Building - Building Structural Work | Alexander | 2673417 | 60 | 2026-05-01 | Patil
BNL | 6.11.02.04.04 | IF_0204_1300 | APP00004 | Dirul | 1010C EIC RF Power Amplifier Building - MEP and Interior | Alexander | 10202800 | 60 | 2026-07-28 | Patil
BNL | 6.11.02.05.01 | IF_0205_1020 | APP00004 | Dirul | Alc-01 - Concrete Pad, Asphalt Pavings and markings | Alexander | 295439 | 10 | 2026-02-20 | Patil
BNL | 6.11.02.05.01 | IF_0205_1040 | APP00004 | Dirul | Alc-01 - Building Structural Work | Alexander | 391287 | 20 | 2026-03-06 | Patil
BNL | 6.11.02.05.01 | IF_0205_1060 | APP00004 | Dirul | Alc-01 - MEP and Interior Systems | Alexander | 2182264 | 30 | 2026-11-25 | Patil
BNL | 6.11.02.05.02 | IF_0205_1100 | APP00004 | Dirul | Alc-03 - Concrete Pad, Asphalt Pavings and markings | Alexander | 295439 | 10 | 2026-04-03 | Patil
BNL | 6.11.02.05.02 | IF_0205_1120 | APP00004 | Dirul | Alc-03 - Building Structural Work | Alexander | 391287 | 20 | 2026-04-17 | Patil
BNL | 6.11.02.05.02 | IF_0205_1140 | APP00004 | Dirul | Alc-03 - MEP and Interior Systems | Alexander | 2182264 | 30 | 2026-11-25 | Patil
BNL | 6.11.02.05.03 | IF_0205_1180 | APP00004 | Dirul | Alc-05 - Concrete Pad, Asphalt Pavings and markings | Alexander | 412401 | 10 | 2026-05-15 | Patil
BNL | 6.11.02.05.03 | IF_0205_1200 | APP00004 | Dirul | Alc-05 - Building Structural Work | Alexander | 806132 | 20 | 2026-06-01 | Patil
BNL | 6.11.02.05.03 | IF_0205_1220 | APP00004 | Dirul | Alc-05 - MEP and Interior Systems | Alexander | 3053563 | 30 | 2026-11-25 | Patil
BNL | 6.11.02.05.04 | IF_0205_1260 | APP00004 | Dirul | Alc-07 - Concrete Pad, Asphalt Pavings and markings | Alexander | 401498 | 10 | 2026-06-29 | Patil
BNL | 6.11.02.05.04 | IF_0205_1280 | APP00004 | Dirul | Alc-07 - Building Structural Work | Alexander | 1020619 | 20 | 2026-07-14 | Patil
BNL | 6.11.02.05.04 | IF_0205_1300 | APP00004 | Dirul | Alc-07 - MEP and Interior Systems | Alexander | 4107595 | 30 | 2026-11-25 | Patil
BNL | 6.11.02.05.05 | IF_0205_1340 | APP00004 | Dirul | Alc-09 - Concrete Pad, Asphalt Pavings and markings | Alexander | 295439 | 10 | 2026-08-11 | Patil
BNL | 6.11.02.05.05 | IF_0205_1360 | APP00004 | Dirul | Alc-09 - Building Structural Work | Alexander | 391287 | 20 | 2026-08-25 | Patil
BNL | 6.11.02.05.05 | IF_0205_1380 | APP00004 | Dirul | Alc-09 - MEP and Interior Systems | Alexander | 2182264 | 30 | 2026-11-25 | Patil
BNL | 6.11.02.06.01 | IF_0206_1040 | APP00004 | Dirul | 1004 Kicker - Building Structural Work | Alexander | 389212 | 20 | 2026-03-06 | Patil
BNL | 6.11.02.06.01 | IF_0206_1060 | APP00004 | Dirul | 1004 Kicker - MEP and Interior Systems | Alexander | 1569853 | 30 | 2026-11-25 | Patil
BNL | 6.11.02.06.02 | IF_0206_1100 | APP00004 | Dirul | EIC Kicker Power Supply Building - Concrete Pad, Asphalt Pavings and markings | Alexander | 630463 | 20 | 2026-04-03 | Patil
BNL | 6.11.02.06.02 | IF_0206_1120 | APP00004 | Dirul | EIC Kicker Power Supply Building - Building Structural Work | Alexander | 897750 | 30 | 2026-05-01 | Patil
BNL | 6.11.02.06.02 | IF_0206_1140 | APP00004 | Dirul | EIC Kicker Power Supply Building - MEP and Interior Systems | Alexander | 3019470 | 30 | 2026-11-25 | Patil
BNL | 6.11.02.07 | IF_0207_1000 | APP00004 | Dirul | Utility Ports Pipe Ports | Alexander | 2424404 | 150 | 2026-01-07 | Patil
BNL | 6.11.02.07 | IF_0207_1020 | APP00004 | Dirul | Excavated Penetrations- 1004 | Alexander | 1113464 | 30 | 2025-06-25 | Patil
BNL | 6.11.02.07 | IF_0207_1040 | APP00004 | Dirul | RF Waveguide Penetrations- Duct @ 1010 | Alexander | 2899148 | 160 | 2025-08-07 | Patil
BNL | 6.11.02.07 | IF_0207_1060 | APP00004 | Dirul | Excavated Penetrations- 1012 | Alexander | 1080188 | 100 | 2026-04-01 | Patil
BNL | 6.11.02.07 | IF_0207_1080 | APP00004 | Dirul | RHIC Tunnel HVAC | Alexander | 2552193 | 80 | 2026-08-21 | Patil
BNL | 6.11.02.08.01 | IF_0208_1000 | APP00004 | Dirul | Service piping to bldgs, water, sanitary, storm | Alexander | 1041602 | 90 | 2026-10-13 | Patil
BNL | 6.11.02.08.01 | IF_0208_1160 | APP00004 | Dirul | Road 1002 - Wearing Course, 3" thick | Alexander | 545389 | 20 | 2027-02-25 | Patil
BNL | 6.06.03.01.01 | EJ_0305_9100 | APP00063 | Drees | HR Machine Protection Beam Abort Kicker Electrical Components - Fabrication | Alexander | 2210800 | 150 | 2026-09-18 | Davis | Domestic
BNL | 6.06.03.01.01 | EJ_0305_9260 | APP00206 | Drees | HR Machine Protection Beam Abort Kicker Mechanical Components - Fabrication | Alexander | 531000 | 100 | 2026-11-17 | Davis | Domestic
BNL | 6.11.01.02 | IF_2102_1122 | APP00034 | Folz | A/E Design - Preliminary Design 30% Review Submittal | Alexander | 1448067 | 80 | 2022-08-02 | Patil | Domestic
BNL | 6.11.01.02 | IF_2102_1124 | APP00034 | Folz | A/E Design - Preliminary Design 60% Review Submittal/Conduct Value Engineering (VE) Study | Alexander | 1810084 | 100 | 2022-11-29 | Patil
BNL | 6.11.01.02 | IF_2102_1140 | APP00034 | Folz | A/E Design - Preliminary Design Report Final Including Comments | Alexander | 362017 | 20 | 2023-04-24 | Patil
BNL | 6.11.01.02 | IF_2102_1160 | APP00034 | Folz | A/E Design - Detailed Design Review 30% Submittal | Alexander | 1357563 | 75 | 2023-05-22 | Patil
BNL | 6.11.01.02 | IF_2102_1161 | APP00034 | Folz | A/E Design - Direct Award Subcontract Packages for (CD-2/3a approved) Long-Lead Electrical Contracts for Procurement | Alexander | 1357563 | 75 | 2023-09-07 | Patil
BNL | 6.11.01.02 | IF_2102_1162 | APP00034 | Folz | A/E Design - Detailed Design Review 60% Submittal | Alexander | 1357563 | 75 | 2023-09-07 | Patil
BNL | 6.11.01.02 | IF_2102_1164 | APP00034 | Folz | A/E Design - Detailed Design Review 90% Submittal/Conduct VE Study | Alexander | 1629076 | 90 | 2023-12-28 | Patil
BNL | 6.11.01.02 | IF_2102_1166 | APP00034 | Folz | A/E Design - Final Construction Bid Issue | Alexander | 633529 | 35 | 2024-05-07 | Patil
BNL | 6.11.01.02 | IF_2102_1180 | APP00034 | Folz | A/E Design - Conformed Set of Documents (Construction Documents modified to include any addenda) | Alexander | 724034 | 40 | 2024-06-26 | Patil
BNL | 6.11.01.02 | IF_2102_1200 | APP00034 | Folz | A/E Services Contract - Const - FY24 | Alexander | 703549 | 29 | 2024-08-22 | Patil
BNL | 6.11.01.02 | IF_2102_1220 | APP00034 | Folz | A/E Services Contract - Const - FY25 | Alexander | 925722 | 250 | 2024-10-03 | Patil
BNL | 6.11.01.02 | IF_2102_1240 | APP00034 | Folz | A/E Services Contract - Const - FY26 | Alexander | 925722 | 250 | 2025-10-03 | Patil
BNL | 6.11.01.02 | IF_2102_1260 | APP00034 | Folz | A/E Services Contract - Const - FY27 | Alexander | 925722 | 250 | 2026-10-05 | Patil
BNL | 6.11.01.02 | IF_2102_1280 | APP00034 | Folz | A/E Services Contract - Const - FY28 | Alexander | 925722 | 250 | 2027-10-05 | Patil
BNL | 6.11.01.02 | IF_2102_1300 | APP00034 | Folz | A/E Services Contract - Const - FY29 | Alexander | 922020 | 249 | 2028-10-04 | Patil
BNL | 6.11.01.02 | IF_2102_1320 | APP00034 | Folz | A/E Services Contract - Const - FY30 | Alexander | 925722 | 250 | 2029-10-03 | Patil
BNL | 6.11.01.02 | IF_2102_1340 | APP00034 | Folz | A/E Services Contract - Const - FY31 | Alexander | 555433 | 150 | 2030-10-03 | Patil
BNL | 6.11.01.03 | IF_0103_1300 | APP00050 | Folz | C/M Construction Mgt Services Contract - Const - FY24 | Alexander | 400000 | 190 | 2025-04-28 | Patil | Domestic
BNL | 6.11.01.03 | IF_0103_1320 | APP00050 | Folz | C/M Construction Mgt Services Contract - Const - FY25 | Alexander | 650000 | 250 | 2026-02-02 | Patil
BNL | 6.11.01.03 | IF_0103_1340 | APP00050 | Folz | C/M Construction Mgt Services Contract - Const - FY26 | Alexander | 650000 | 250 | 2027-02-02 | Patil
BNL | 6.11.01.03 | IF_0103_1360 | APP00050 | Folz | C/M Construction Mgt Services Contract - Const - FY27 | Alexander | 325000 | 250 | 2028-02-02 | Patil
BNL | 6.11.01.03 | IF_0103_1016 | APP00105 | Folz | C/M Preconstruction Services Contract- Design - FY23 - FY25 | Alexander | 800000 | 750 | 2022-10-28 | Patil | Domestic
BNL | 6.05.04 | HR_0500_2080 | APP00073 | Gallagher | Carbon Coating System Service Bldg 919B - Building Modification SubContract – Pit and service crane | Alexander | 2000000 | 250 | 2026-04-22 | Davis | Domestic (In-house), then Foreign | Would like to do it inhouse but if it won't work, may work with CERN
BNL | 6.05.04 | HR_0500_1100 | APP00128 | Gallagher | Bellows Upgrade - Shield inserts - Vendor Fabrication/Leadtime | Alexander | 330000 | 125 | 2025-06-03 | Davis | Domestic (In-house), then Foreign | VAT Vaccuum in Germany
BNL | 6.05.04 | HR_0500_1110 | APP00128 | Gallagher | Bellows Upgrade - BPM Bellows Housing - Vendor Fabrication/Leadtime | Alexander | 687740 | 125 | 2025-06-03 | Davis | Domestic (In-house), then Foreign
BNL | 6.05.04 | HR_0500_1460 | APP00138 | Gallagher | Beam Tube Sleeves - Vendor Fabrication/Leadtime | Alexander | 1719000 | 250 | 2025-09-18 | Davis | Domestic
BNL | 6.05.04 | HR_0500_1810 | APP00144 | Gallagher | Carbon Coating System - AC coating system material | Alexander | 546000 | 250 | 2025-04-10 | Davis | Domestic
BNL | 6.05.04 | HR_0500_1980 | APP00210 | Gallagher | Carbon Coating System Service Bldg - A/E Design | Alexander | 309338 | 250 | 2025-04-10 | Davis | Domestic
BNL | 6.05.04 | HR_0500_1750 | APP00245 | Gallagher | Carbon Coating System - Power Supplies & other equipment | Alexander | 500000 | 250 | 2025-04-10 | Davis | Domestic | Multiple Procurements / foreign procurements with Domestic distributors
BNL | 6.03.04.01.04.03 | EJ_0401_6960 | APP00159 | Gassner | Bunch Length Monitors - Construction - Vendor Fabrication including Delivery | Alexander | 463354 | 250 | 2027-08-19 | Layden | Foreign | Possibly Japan
BNL | 6.05.05.02 | HR_0602_1120 | APP00160 | Gassner | HR TL Material - Vendor Fabrication including Delivery | Alexander | 343563 | 250 | 2027-07-22 | Layden | Domestic
BNL | 6.03.02.05.04 | EJ_0205_8360 | APP00161 | Gassner | RCS SLM s-RAD - Vendor Fabrication including Delivery | Alexander | 348414 | 250 | 2027-07-22 | Layden | Domestic | Multiple
BNL | 6.05.05.01 | HR_0601_1300 | APP00162 | Gassner | BPM Buttons Material - Vendor Fabrication including Delivery | Alexander | 1116000 | 150 | 2026-10-19 | Layden | Domestic
BNL | 6.05.07.06.03 | HR_0807_4080 | APP00163 | Gassner | Profile Monitors Materials - Vendor Fabrication including Delivery | Alexander | 1502064 | 150 | 2026-10-14 | Layden | Domestic
BNL | 6.04.06.01 | SR_0601_1440 | APP00164 | Gassner | BPM Electronics - V301 module procurement (material) - Vendor Fabrication including Delivery | Alexander | 1419227 | 250 | 2027-07-22 | Layden | Domestic
BNL | 6.05.07.06.05 | HR_0807_8080 | APP00165 | Gassner | Synchrotron Radiation Monitors Materials - Vendor Fabrication including Delivery | Alexander | 813144 | 150 | 2026-10-14 | Layden | Foreign | Japan Hamamatzu
BNL | 6.03.02.05.01 | EJ_0205_1720 | APP00166 | Gassner | BPM System Misc Materials - Vendor Fabrication including Delivery | Alexander | 1352538 | 250 | 2027-01-15 | Layden | Domestic
BNL | 6.04.06.03 | SR_0603_1200 | APP00167 | Gassner | Longitudinal Feedback System - Vendor Fabrication including Delivery | Alexander | 1000000 | 250 | 2027-07-22 | Layden | Domestic
BNL | 6.03.02.05.01 | EJ_0205_1600 | APP00168 | Gassner | BPM Pick-up -Button Procurement - Vendor Fabrication including Delivery | Alexander | 889344 | 251 | 2027-07-22 | Layden | Domestic
BNL | 6.06.02.05.01 | IR_0206_1320 | APP00169 | Gassner | IR BPM Pick-up Materials - Vendor Fabrication including Delivery | Alexander | 906069 | 200 | 2028-06-09 | Layden | Domestic
BNL | 6.05.05.01 | HR_0601_1240 | APP00170 | Gassner | BPM Electronics Construction - Vendor Fabrication including Delivery | Alexander | 255518 | 350 | 2027-07-22 | Layden | Domestic
BNL | 6.03.03.04.03 | EJ_0304_7280 | APP00171 | Gassner | Profile Monitors Construction - Vendor Fabrication including Delivery | Alexander | 283000 | 250 | 2027-07-22 | Layden | Domestic
BNL | 6.03.04.01.04.02 | EJ_0401_5400 | APP00172 | Gassner | ICT Material - Vendor Fabrication including Delivery | Alexander | 298638 | 150 | 2026-10-14 | Layden | Foreign | France - Bergoz/GMW
BNL | 6.06.03.02.02 | HR_0603_2960 | APP00173 | Gassner | HSR Collimators Material - Vendor Fabrication including Delivery | Alexander | 304786 | 250 | 2027-07-22 | Layden | Domestic
BNL | 6.05.07.06.01 | HR_0807_0080 | APP00174 | Gassner | BPM System Materials - Vendor Fabrication including Delivery | Alexander | 936694 | 150 | 2026-10-14 | Layden | Domestic
BNL | 6.05.05.01 | HR_0601_1360 | APP00175 | Gassner | BPM Cryo Cables Material - Vendor Fabrication including Delivery | Alexander | 615570 | 250 | 2026-10-14 | Layden | Domestic
BNL | 6.05.07.06.02 | HR_0807_2080 | APP00176 | Gassner | Charge and Current Monitors Materials - Vendor Fabrication including Delivery | Alexander | 979593 | 150 | 2026-10-14 | Layden | Foreign | France - Bergoz/GMW
BNL | 6.04.06.04 | SR_0604_1360 | APP00177 | Gassner | SR SLM Materials s-Rad - Vendor Fabrication including Delivery | Alexander | 497900 | 100 | 2027-07-22 | Layden | Foreign | Japan Hamamatzu
BNL | 6.04.06.01 | SR_0601_1620 | APP00178 | Gassner | BPM Pick-up -Button & Housing Materials - Vendor Fabrication including Delivery | Alexander | 924412 | 250 | 2027-07-22 | Layden | Domestic
BNL | 6.04.06.01 | SR_0601_1760 | APP00179 | Gassner | BPM System - Signal cables, rack hardware, system connectors - Vendor Fabrication including Delivery | Alexander | 1109751 | 250 | 2027-07-22 | Layden | Domestic
BNL | 6.03.02.05.01 | EJ_0205_1440 | APP00180 | Gassner | BPM Electronics - V301 module - Vendor Fabrication | Alexander | 1654808 | 250 | 2027-06-23 | Layden | Domestic
BNL | 6.05.05.01 | HR_0601_1210 | APP00181 | Gassner | BPM Electronics - V301 Module - PCB Assy - Non Labor | Alexander | 598956 | 125 | 2027-01-19 | Layden | Domestic
BNL | 6.04.05.01 | SR_0401_1170 | APP00007 | Hetzel | ESR Vacuum Chamber and Bellows - ESR Vacuum Chambers 3/A Procurement | Alexander | 16800000 | 325 | 2025-08-11 | Lewis | Foreign | FMB Berlin and Saes Rial
BNL | 6.04.05.03 | SR_0403_1160 | APP00030 | Hetzel | ESR Vacuum Pumps - Procurement | Alexander | 7751396 | 430 | 2026-10-14 | Lewis | Domestic | Gamma
BNL | 6.06.02.04 | IR_0204_1160 | APP00041 | Hetzel | IR Vacuum - Procurement (NonLabor) | Alexander | 2262545 | 315 | 2026-10-14 | Lewis | Foreign | Brush Welmon (Canada)
BNL | 6.03.02.04.03 | EJ_0203_3000 | APP00044 | Hetzel | RCS Vacuum Pumps - Procurement | Alexander | 3105120 | 240 | 2026-10-14 | Lewis | Domestic | Gamma
BNL | 6.04.05.07 | SR_0407_1160 | APP00064 | Hetzel | Construction of Vacuum Fabrication Facility - Procurement | Alexander | 2080000 | 220 | 2026-10-14 | Lewis | Domestic
BNL | 6.03.02.04.01 | EJ_0203_1220 | APP00070 | Hetzel | RCS Vacuum Chambers and Bellows - Procurement | Alexander | 3960560 | 320 | 2025-06-27 | Lewis | Domestic
BNL | 6.06.03.02.03 | IR_0204_1380 | APP00141 | Hetzel | Movable ESR Collimators - Procurement Fabrication/leadtime | Alexander | 506630 | 360 | 2026-10-14 | Lewis | Domestic | Multiple Smaller Procurements - Built inhouse
BNL | 6.03.03.03 | EJ_0303_2300 | APP00148 | Hetzel | Transfer Lines Vacuum - Hardware Deliveries | Alexander | 890358 | 146 | 2026-10-14 | Lewis | Domestic
BNL | 6.03.02.04.04 | EJ_0203_1440 | APP00152 | Hetzel | RCS Vacuum Monitoring and Controls - Procurement | Alexander | 643710 | 280 | 2026-10-14 | Lewis | Foreign | NKS - maufacturing maybe in Mexico
BNL | 6.04.05.05 | SR_0405_1160 | APP00158 | Hetzel | ESR Vacuum Utilities (racks, cooling water) - Procurement | Alexander | 808376 | 250 | 2026-10-14 | Lewis | Domestic
BNL | 6.03.02.04.02 | EJ_0203_1560 | APP00200 | Hetzel | RCS Vacuum Valves - Procurement | Alexander | 867720 | 200 | 2026-10-14 | Lewis | Foreign | BAT Switzerland
BNL | 6.04.05.04 | SR_0404_1160 | APP00232 | Hetzel | ESR Vacuum Monitoring & Control - Procurement | Alexander | 1886310 | 260 | 2026-10-14 | Lewis | Foreign | NKS - maufacturing maybe in Mexico
BNL | 6.04.05.02 | SR_0402_1160 | APP00234 | Hetzel | ESR Vacuum Valves - Procurement | Alexander | 1244400 | 250 | 2026-10-14 | Lewis | Foreign | BAT Switzerland
BNL | 6.07.04.03.04 | AS_0502_4020 | APP00297 | Hetzel | ESR - Installation of vacuum system - Non Labor | Alexander | 520000 | 445 | 2028-10-31 | Golnar | Domestic | Multiple Smaller Procurements - Built inhouse
BNL | 6.07.04.02.04 | AS_0501_4040 | APP00424 | Hetzel | Injection System - RCS Vacuum System - Non Labor | Alexander | 370000 | 380 | 2028-12-08 | Golnar | Domestic | Multiple Smaller Procurements - Built inhouse
BNL | 6.04.05.01 | SR_0401_1265 | APP00498 | Hetzel | ESR Vacuum Chamber and Bellows - Bellows, Chamber Stands, etc. Procurement | Alexander | 6165500 | 300 | 2026-10-14 | Lewis | Domestic | Multiple Smaller Procurements - Built inhouse
BNL | 6.07.02.12 | AS_0302_1180 | APP00075 | Jamilkowski | Network Systems - Non Labor | Alexander | 3249650 | 60 | 2026-10-13 | Layden | Domestic
BNL | 6.07.02.12 | AS_0305_2220 | APP00125 | Jamilkowski | Instrumentation General Support - Non Labor | Alexander | 470600 | 60 | 2026-10-13 | Layden | ?
BNL | 6.07.02.12 | AS_0302_1480 | APP00140 | Jamilkowski | Beam Sync System - Non Labor | Alexander | 694200 | 60 | 2026-10-13 | Layden | Domestic | Multiple smaller procurements possible
BNL | 6.07.02.12 | AS_0307_1920 | APP00151 | Jamilkowski | Instrumentation BPM Support - Non Labor | Alexander | 1619200 | 60 | 2026-10-13 | Layden | Domestic | possible multiple procurements
BNL | 6.07.02.12 | AS_0307_1640 | APP00154 | Jamilkowski | Power Supply Controls - Non Labor | Alexander | 1628350 | 60 | 2026-10-13 | Layden | Domestic | possible multiple procurements
BNL | 6.07.02.12 | AS_0302_3290 | APP00211 | Jamilkowski | Data Management - Large High Availability Storage system (500TB+) - Delivery & Acceptance | Alexander | 532648 | 10 | 2026-10-13 | Layden | domestic
BNL | 6.07.02.12 | AS_0302_3350 | APP00211 | Jamilkowski | Data Management - Additional High Availability Storage Systems - Delivery & Acceptance | Alexander | 291904 | 10 | 2026-10-13 | Layden | Domestic
BNL | 6.07.02.12 | AS_0307_1540 | APP00233 | Jamilkowski | General Data I/O - Non Labor | Alexander | 991400 | 60 | 2026-10-13 | Layden | May go away
BNL | 6.10.14.03 | IR_0303_1010 | APP00006 | Jaroslav | Luminosity Monitor - Procurement and Fabrication - Materials In-Kind | Alexander | 602272 | 120 | 2024-01-16 | Lewis
BNL | 6.10.06.01 | DE_0600_3081 | APP00024 | Kiselev | Backward Hadronic Calorimetry - Fabrication In-Kind | Alexander | 3783690 | 1000 | 2025-01-14 | Lewis
BNL | 6.10.06.02 | DE_0600_3250 | APP00025 | Kiselev | Barrel Hadronic Calorimetry - Fabrication In-Kind | Alexander | 9675562 | 1000 | 2025-09-02 | Lewis
BNL | 6.10.06.02 | DE_0600_3230 | APP00038 | Kiselev | Barrel Hadronic Calorimetry - Long Lead Procurement - Steel for Hadronic Calorimeters | Alexander | 2418891 | 1000 | 2025-04-09 | Lewis
BNL | 6.10.06.01 | DE_0600_3074 | APP00092 | Kiselev | Backward Hadronic Calorimetry - Long Lead Procurement - Scintillators | Alexander | 420410 | 1000 | 2025-04-09 | Lewis
BNL | 6.10.06.03 | DE_0600_3390 | APP00092 | Kiselev | Forward Hadronic Calorimetry - Fabrication In-Kind | Alexander | 13038403 | 1000 | 2025-11-03 | Lewis
BNL | 6.05.03.01 | HR_0401_1080 | APP00119 | Mahler | AtR to Blue Transfer Line Magnet - Material and construction of the magnets | Alexander | 500000 | 80 | 2026-11-12 | Davis
BNL | 6.06.02.01.05 | IR_0215_1040 | APP00108 | Micolon | IR Magnet Cryostats, Forward Fabrication | Alexander | 1337062 | 500 | 2026-10-13 | Davis
BNL | 6.06.02.01.05 | IR_0215_1220 | APP00209 | Micolon | B0pF Cryostat Fabrication | Alexander | 279967 | 500 | 2026-07-10 | Davis
BNL | 6.06.02.01.05 | IR_0215_1280 | APP00261 | Micolon | IR Magnet Cryostats, Rear Fabrication | Alexander | 870903 | 500 | 2024-10-18 | Davis
BNL | 6.05.07.08 | HR_0810_3003 | APP00472 | Micolon | Procurement phase - SHC Chicane Feedbox |  | 500000 | 180 | 2026-09-23 | Davis
BNL | 6.11.03.01 | IF_0301_1520 | APP00008 | Nehring | 69kV /20 MVA Transformer x 2 - Fabrication | Alexander | 2340000 | 240 | 2026-10-14 | Patil | Domestic
BNL | 6.11.03.01 | IF_0301_1616 | APP00008 | Nehring | 15 kV switchgear - Fabrication | Alexander | 564000 | 200 | 2026-10-14 | Patil
BNL | 6.11.03.01 | IF_0301_1627 | APP00008 | Nehring | Main House Construction - PreFab Metal Building - Construction | Alexander | 518000 | 120 | 2026-10-14 | Patil
BNL | 6.11.03.01 | IF_0301_1628 | APP00008 | Nehring | Main House Construction - Low Voltage Underground Ductbank - Construction | Alexander | 286200 | 120 | 2026-10-14 | Patil
BNL | 6.11.03.01 | IF_0301_1629 | APP00008 | Nehring | Main House Construction - Hight Voltage Underground Ductbank - Construction | Alexander | 696100 | 120 | 2026-10-14 | Patil
BNL | 6.11.03.01 | IF_0301_1630 | APP00008 | Nehring | Main House Construction - Civil Work (road, sanitory, drainage, fencing etc) - Construction | Alexander | 386300 | 180 | 2026-10-14 | Patil
BNL | 6.11.03.01 | IF_0301_2005 | APP00008 | Nehring | Substation Installation Contract - Contract Cost (Rolled up Cost) | Alexander | 6514100 | 500 | 2027-11-30 | Patil
BNL | 6.11.03.01 | IF_0301_2015 | APP00008 | Nehring | Substation Installation Contract - 15kV Feeder to existing Pole lines | Alexander | 262700 | 50 | 2027-11-30 | Patil
BNL | 6.11.03.02 | IF_0302_1085 | APP00025 | Nehring | Overhead 13.8 kV lines - switch stations and duct bank- Mobilization and training | Alexander | 1799900 | 40 | 2026-10-14 | Patil | Domestic
BNL | 6.11.03.02 | IF_0302_1102 | APP00025 | Nehring | Overhead 13.8 kV lines - switch stations and duct bank- Construction - OH lines 9 (Material & Labor) | Alexander | 1903700 | 120 | 2027-01-13 | Patil
BNL | 6.11.03.02 | IF_0302_1104 | APP00025 | Nehring | Overhead 13.8 kV lines - switch stations and duct bank- Construction - OH lines 10 (Material & Labor) | Alexander | 3443100 | 160 | 2027-07-06 | Patil
BNL | 6.11.03.02 | IF_0302_1105 | APP00025 | Nehring | Overhead 13.8 kV lines - switch stations and duct bank- Construction - OH lines 8A (Material & Labor) | Alexander | 1425000 | 60 | 2028-02-28 | Patil
BNL | 6.11.03.07 | IF_0307_1080 | APP00026 | Nehring | 138kW Substation - PSEG Design Contract | Alexander | 1780801 | 119 | 2026-04-13 | Patil | Domestic | Labs Ops funds. PSEG will support - Per Tom, should disappear
BNL | 6.11.03.07 | IF_0307_1200 | APP00026 | Nehring | 138kW Substation - PSEG Design Title 1 | Alexander | 300000 | 120 | 2027-05-25 | Patil
BNL | 6.11.03.07 | IF_0307_1240 | APP00026 | Nehring | 138kW Substation - PSEG Design Title 2 | Alexander | 700000 | 200 | 2027-11-16 | Patil
BNL | 6.11.03.07 | IF_0307_1320 | APP00026 | Nehring | 138kW Substation - PSEG Construction | Alexander | 11872000 | 912 | 2029-12-18 | Patil
BNL | 6.11.03.05 | IF_0305_1060 | APP00074 | Nehring | 400 kW & 150 kW Standby Gen & 3-Position Auto Trans Switches - Vendor fabrication | Alexander | 1600000 | 140 | 2025-12-03 | Patil | Domestic
BNL | 6.11.03.05 | IF_0305_1380 | APP00074 | Nehring | 30 kVA 480V UPS - Vendor fabrication | Alexander | 1416800 | 60 | 2025-10-31 | Patil
BNL | 6.11.03.05 | IF_0305_1820 | APP00074 | Nehring | Standby/Emergency power - 400kW Diesel Generator - Vendor fabrication - 1002I | Alexander | 416200 | 120 | 2025-12-17 | Patil
BNL | 6.11.03.05 | IF_0305_1830 | APP00074 | Nehring | Standby/Emergency power - 400kW Diesel Generator - Vendor fabrication - 1006G | Alexander | 416200 | 120 | 2025-12-17 | Patil
BNL | 6.11.03.05 | IF_0305_1840 | APP00074 | Nehring | Standby/Emergency power - 400kW Diesel Generator - Vendor fabrication - 1010E | Alexander | 416200 | 120 | 2025-12-17 | Patil
BNL | 6.11.03.04 | AIF_0304_1460 | APP00078 | Nehring | Load centers 480V Switchboards & Panelborards - Vendor fabrication | Alexander | 1684350 | 100 | 2027-03-03 | Patil | Domestic
BNL | 6.11.03.04 | AIF_0304_1640 | APP00078 | Nehring | Load centers 480V Switchboards & Panelborards - Installation | Alexander | 1684350 | 100 | 2027-07-30 | Patil
BNL | 6.11.03.04 | AIF_0304_1820 | APP00078 | Nehring | Load centers 480V - Vendor fabrication | Alexander | 900000 | 100 | 2027-01-19 | Patil
BNL | 6.11.03.04 | AIF_0304_2100 | APP00078 | Nehring | Load centers 120/208V panelboard with Transformer - Vendor fabrication | Alexander | 274900 | 100 | 2027-02-02 | Patil
BNL | 6.11.03.04 | AIF_0304_2240 | APP00078 | Nehring | Load centers 120/208V panelboard with Transformer - Installation - Installation | Alexander | 335100 | 120 | 2027-06-24 | Patil
BNL | 6.11.03.03 | AIF_0303_1104 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1001A - 1500kVA | Alexander | 641542 | 360 | 2025-05-22 | Patil | Domestic
BNL | 6.11.03.03 | AIF_0303_1105 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1002H - 2500kVA | Alexander | 732050 | 360 | 2025-05-22 | Patil
BNL | 6.11.03.03 | AIF_0303_1106 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1002I Cryo [1002E] - 1500kVA | Alexander | 304799 | 360 | 2025-05-22 | Patil
BNL | 6.11.03.03 | AIF_0303_1107 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1002I Cryo [1002F] - 1500kVA | Alexander | 304799 | 360 | 2025-05-22 | Patil
BNL | 6.11.03.03 | AIF_0303_1108 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1003A - 1500kVA | Alexander | 641542 | 360 | 2025-06-20 | Patil
BNL | 6.11.03.03 | AIF_0303_1109 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1004G - 1500kVA | Alexander | 641542 | 360 | 2025-06-20 | Patil
BNL | 6.11.03.03 | AIF_0303_1110 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1005T - 2500kVA | Alexander | 732050 | 360 | 2025-06-20 | Patil
BNL | 6.11.03.03 | AIF_0303_1113 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1007 [1007A] - 1500kVA | Alexander | 641542 | 360 | 2025-07-21 | Patil
BNL | 6.11.03.03 | AIF_0303_1114 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1007 [1007B] - 1500kVA | Alexander | 641542 | 360 | 2025-07-21 | Patil
BNL | 6.11.03.03 | AIF_0303_1115 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1009A - 1500kVA | Alexander | 641542 | 360 | 2025-07-21 | Patil
BNL | 6.11.03.03 | AIF_0303_1116 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1010D [1010B] - 1500kVA | Alexander | 641542 | 360 | 2025-08-18 | Patil
BNL | 6.11.03.03 | AIF_0303_1117 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1010D [T 1010C] - 1500kVA | Alexander | 641542 | 360 | 2025-08-18 | Patil
BNL | 6.11.03.03 | AIF_0303_1118 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1010E Cryo [1010D] - 1500kVA | Alexander | 304799 | 360 | 2025-08-18 | Patil
BNL | 6.11.03.03 | AIF_0303_1119 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1010E Cryo [1010E] - 1500kVA | Alexander | 304799 | 360 | 2025-08-18 | Patil
BNL | 6.11.03.03 | AIF_0303_1120 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1011A - 1500kVA | Alexander | 641542 | 360 | 2025-09-16 | Patil
BNL | 6.11.03.03 | AIF_0303_1121 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1012A - 1500kVA | Alexander | 641542 | 360 | 2025-09-16 | Patil
BNL | 6.11.03.03 | AIF_0303_1122 | APP00091 | Nehring | Unit Substation Xfmrs for Buildings - Fabrication - Bldg 1012D - 2500kVA | Alexander | 732050 | 360 | 2025-09-16 | Patil
BNL | 6.11.03.03 | AIF_0303_1185 | APP00091 | Nehring | Unit Substation Xfmrs for Large PS - Fabrication - Bldg 1007A [1007C] - 2000kVA | Alexander | 548372 | 360 | 2026-10-14 | Patil
BNL | 6.11.03.03 | AIF_0303_1200 | APP00091 | Nehring | Unit Substation Xfmrs for Large PS - Fabrication - Bldg 1007A [1007D] - 2000kVA | Alexander | 548372 | 360 | 2026-10-14 | Patil
BNL | 6.11.03.03 | AIF_0303_1248 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-1] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1249 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-2] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1250 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-3] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1251 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-4] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1252 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-5] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1253 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-6] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1254 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-7] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1255 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-8] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1256 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-9] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1257 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-10] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1258 | APP00091 | Nehring | Unit Substation RF Amplifier Xfmrs - Fabrication - Bldg 1010C [1010RF-11] - 3000kVA | Alexander | 734712 | 360 | 2026-11-30 | Patil
BNL | 6.11.03.03 | AIF_0303_1420 | APP00091 | Nehring | UNIT Substations w/Distribution Installation - xfmrs for Buildings | Alexander | 8069655 | 220 | 2027-03-29 | Patil
BNL | 6.11.03.03 | AIF_0303_1440 | APP00091 | Nehring | UNIT Substations w/Distribution Installation - Xfmrs for Large PS | Alexander | 1182001 | 220 | 2028-05-08 | Patil
BNL | 6.11.03.03 | AIF_0303_1442 | APP00091 | Nehring | UNIT Substations w/Distribution Installation - RF Amplifier Xfmrs | Alexander | 5426687 | 220 | 2028-05-08 | Patil
BNL | 6.11.03.04 | AIF_0304_1120 | APP00130 | Nehring | Variable Frequency Drives - Vendor fabrication | Alexander | 22105500 | 100 | 2027-01-19 | Patil | Domestic
BNL | 6.11.03.06 | IF_0306_1080 | APP00134 | Nehring | Cable Trays Tunnel Material - Non Labor | Alexander | 1058200 | 250 | 2026-10-14 | Patil | Domestic
BNL | 6.11.03.06 | IF_0306_1370 | APP00134 | Nehring | Cable Trays Installation - Tunnel - Non Labor | Alexander | 2148600 | 250 | 2026-10-14 | Patil
BNL | 6.11.03.06 | IF_0306_1440 | APP00134 | Nehring | Cable Trays - Service Buildings - Non Labor | Alexander | 454500 | 360 | 2026-10-14 | Patil
BNL | 6.11.03.04 | AIF_0304_1260 | APP00201 | Nehring | Variable Frequency Drives - Installation - Installation | Alexander | 1200000 | 30 | 2027-06-17 | Patil | Domestic
BNL | 6.11.03.05 | IF_0305_1420 | APP00250 | Nehring | 30 kVA 480V UPS and Bypass Switch Installation - Installation | Alexander | 1286600 | 120 | 2026-02-02 | Patil | Domestic
BNL | 6.09.03.03.01 | E09_14450 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR02 Distribution | Alexander | 1200000 | 1 | 2029-01-04 | Layden | Domestic
BNL | 6.09.03.03.01 | E09_14470 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR04 Distribution | Alexander | 1800000 | 1 | 2029-01-04 | Layden
BNL | 6.09.03.03.01 | E09_14490 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR06 Detector Solenoid Distribution | Alexander | 1200000 | 1 | 2029-01-04 | Layden
BNL | 6.09.03.03.01 | E09_14510 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR06 IR magnets Tie-in & Crab Bypasses Distribution | Alexander | 1675000 | 1 | 2029-01-04 | Layden
BNL | 6.09.03.03.01 | E09_14530 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR06 eSR Solenoids IR06 Distribution | Alexander | 700000 | 1 | 2029-01-04 | Layden
BNL | 6.09.03.03.01 | E09_14550 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR06 Blue Injection Distribution | Alexander | 1200000 | 1 | 2029-01-04 | Layden
BNL | 6.09.03.03.01 | E09_14570 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR10 Distribution | Alexander | 1200000 | 1 | 2029-01-04 | Layden
BNL | 6.09.03.03.01 | E09_14590 | APP00201 | Orfin | RCV: 4K Distribution B&P - Procurement IR12 Distribution | Alexander | 800000 | 1 | 2029-01-04 | Layden
BNL | 6.09.03.04 | E09_15110 | APP00304 | Orfin | RCV: Cryo Installation - IR04 | Alexander | 1200000 | 1 | 2029-10-12 | Layden | Domestic
BNL | 6.09.03.04 | E09_15170 | APP00305 | Orfin | RCV: Cryo Installation - IR12 | Alexander | 1200000 | 1 | 2029-10-12 | Layden | Domestic
BNL | 6.09.03.04 | E09_15090 | APP00306 | Orfin | RCV: Cryo Installation - IR02 | Alexander | 1200000 | 1 | 2029-10-12 | Layden | Domestic
BNL | 6.09.03.04 | E09_15150 | APP00307 | Orfin | RCV: Cryo Installation - IR10 | Alexander | 1200000 | 1 | 2029-10-12 | Layden | Domestic
BNL | 6.09.03.04 | E09_15130 | APP00514 | Orfin | RCV: Cryo Installation - IR06 | Alexander | 1200000 | 1 | 2029-10-12 | Layden | Domestic
BNL | 6.11.04.01 | IF_0401_1520 | APP00004 | Ram | CHW - 1002H - System Installations | Alexander | 350000 | 80 | 2027-08-02 | Patil | Domestic
BNL | 6.11.04.01 | IF_0401_1546 | APP00004 | Ram | CHW - 1012C - System Installations | Alexander | 350000 | 120 | 2027-11-29 | Patil
BNL | 6.11.04.01 | IF_0401_1600 | APP00004 | Ram | CHW - 1007A - System Installations | Alexander | 700000 | 80 | 2028-11-09 | Patil
BNL | 6.11.04.02 | IF_0402_1360 | APP00004 | Ram | DI - 2 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | Alexander | 1469615 | 160 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1400 | APP00004 | Ram | DI - 2 O'clock Bldg - System Installation (Mobilization/ Safety Orientation/ Traning) | Alexander | 925945 | 120 | 2027-08-02 | Patil
BNL | 6.11.04.02 | IF_0402_1440 | APP00004 | Ram | 2 O'clock Bldg - Cryo SCW - Material Fabrication | Alexander | 436581 | 160 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1480 | APP00004 | Ram | 2 O'clock Bldg - Cryo SCW - System Installation | Alexander | 387166 | 60 | 2027-08-30 | Patil
BNL | 6.11.04.02 | IF_0402_1520 | APP00004 | Ram | DI - 10 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | Alexander | 3742165 | 160 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1560 | APP00004 | Ram | DI - 10 O'clock Bldg - System Installation | Alexander | 2286964 | 120 | 2028-01-27 | Patil
BNL | 6.11.04.02 | IF_0402_1600 | APP00004 | Ram | 10 O'clock Bldg - Cryo SCW - Material Fabrication | Alexander | 417553 | 140 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1680 | APP00004 | Ram | DI - 4 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | Alexander | 1176369 | 160 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1720 | APP00004 | Ram | DI - 4 O'clock Bldg - System Installation - Installations | Alexander | 634474 | 80 | 2028-07-18 | Patil
BNL | 6.11.04.02 | IF_0402_1760 | APP00004 | Ram | DI - 6 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | Alexander | 1278543 | 160 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1800 | APP00004 | Ram | DI - 6 O'clock Bldg - System Installation - Installations | Alexander | 707716 | 100 | 2028-11-09 | Patil
BNL | 6.11.04.02 | IF_0402_1840 | APP00004 | Ram | 6 O'clock Bldg - Cryo SCW - Material Fabrication | Alexander | 430160 | 160 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1920 | APP00004 | Ram | DI - 12 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | Alexander | 427991 | 160 | 2026-12-11 | Patil
BNL | 6.11.04.02 | IF_0402_1960 | APP00004 | Ram | DI - 12 O'clock Bldg - System Installation - Installations | Alexander | 257063 | 60 | 2029-04-09 | Patil
BNL | 6.11.04.02 | IF_0402_2140 | APP00004 | Ram | RHIC Tunnel DI Pipe - Pipe manufacturing [8" Vacuum/ Magnet/ PS] | Alexander | 4350661 | 150 | 2026-10-13 | Patil
BNL | 6.11.04.02 | IF_0402_2260 | APP00004 | Ram | RHIC Tunnel DI Pipe - Supply and Installation Arc 1/2 | Alexander | 1135432 | 70 | 2028-01-27 | Patil
BNL | 6.11.04.02 | IF_0402_2280 | APP00004 | Ram | RHIC Tunnel DI Pipe - Supply and Installation Arc 3/4 | Alexander | 1135432 | 70 | 2028-05-05 | Patil
BNL | 6.11.04.02 | IF_0402_2300 | APP00004 | Ram | RHIC Tunnel DI Pipe - Supply and Installation Arc 9/10 | Alexander | 1135432 | 70 | 2028-08-15 | Patil
BNL | 6.11.04.02 | IF_0402_2320 | APP00004 | Ram | RHIC Tunnel DI Pipe - Supply and Installation Arc 7/8 | Alexander | 1135432 | 70 | 2028-11-28 | Patil
BNL | 6.11.04.02 | IF_0402_2340 | APP00004 | Ram | RHIC Tunnel DI Pipe - Supply and Installation Arc 5/6 | Alexander | 1135432 | 70 | 2029-03-12 | Patil
BNL | 6.11.04.02 | IF_0402_2360 | APP00004 | Ram | RHIC Tunnel DI Pipe - Supply and Installation Arc 11/12 | Alexander | 1135432 | 70 | 2029-06-19 | Patil
BNL | 6.11.04.03 | IF_0403_1260 | APP00004 | Ram | TWR - 2 O'clock Bldg - Component manufacturing (Equipment and pump) | Alexander | 1866769 | 180 | 2026-10-13 | Patil
BNL | 6.11.04.03 | IF_0403_1300 | APP00004 | Ram | TWR - 2 O'clock Bldg - System Installations | Alexander | 900000 | 90 | 2027-08-02 | Patil
BNL | 6.11.04.03 | IF_0403_1322 | APP00004 | Ram | TWR - 10 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | Alexander | 2270521 | 180 | 2026-10-13 | Patil
BNL | 6.11.04.03 | IF_0403_1326 | APP00004 | Ram | TWR - 10 O'clock Bldg - System Installations | Alexander | 900000 | 145 | 2028-01-27 | Patil
BNL | 6.11.04.03 | IF_0403_1420 | APP00004 | Ram | TWR - 4 O'clock Bldg - Component manufacturing (Equipment and pump) | Alexander | 1409512 | 180 | 2026-10-13 | Patil
BNL | 6.11.04.03 | IF_0403_1460 | APP00004 | Ram | TWR - 4 O'clock Bldg - System Installations | Alexander | 900000 | 90 | 2028-08-22 | Patil
BNL | 6.11.04.03 | IF_0403_1520 | APP00004 | Ram | TWR - 6 O'clock Bldg - Component manufacturing (Equipment and pump) | Alexander | 1698858 | 180 | 2026-10-13 | Patil
BNL | 6.11.04.03 | IF_0403_1560 | APP00004 | Ram | TWR - 6 O'clock Bldg - System Installations | Alexander | 900000 | 90 | 2029-01-04 | Patil
BNL | 6.11.04.03 | IF_0403_1660 | APP00004 | Ram | TWR - 12 O'clock Bldg - System Installations | Alexander | 900000 | 90 | 2029-05-14 | Patil
BNL | 6.03.03.05.05 | EJ_0305_5080 | APP00182 | Ranjbar | RCS Extraction Septum - Electrical Components - Fabrication | Alexander | 392950 | 300 | 2026-10-14 | Layden
BNL | 6.03.03.05.05 | EJ_0305_5220 | APP00183 | Ranjbar | RCS Extraction Septum - Mechanical Components - Fabrication | Alexander | 674000 | 100 | 2026-10-14 | Layden
BNL | 6.03.03.05.01 | EJ_0305_1080 | APP00184 | Ranjbar | RCS Injection Pulsed Bump - Kicker Magnet - Fabrication | Alexander | 270893 | 300 | 2026-10-14 | Layden
BNL | 6.03.03.05.04 | EJ_0305_4100 | APP00191 | Ranjbar | RCS Extraction Kicker - Fabrication | Alexander | 270893 | 300 | 2026-10-14 | Layden
BNL | 6.03.03.05.06 | EJ_0305_6100 | APP00192 | Ranjbar | ESR Stripline Kickers Electrical Components - Fabrication | Alexander | 1193893 | 300 | 2026-10-14 | Layden
BNL | 6.03.03.05.06 | EJ_0305_6260 | APP00193 | Ranjbar | ESR Stripline Kickers Mechanical Components - Fabrication | Alexander | 636187 | 100 | 2026-10-14 | Layden
BNL | 6.03.03.05.08 | EJ_0305_8100 | APP00196 | Ranjbar | ESR Injection ESR Injection Electrical Components - Fabrication | Alexander | 357072 | 150 | 2026-10-14 | Layden
BNL | 6.03.03.05.08 | EJ_0305_8260 | APP00197 | Ranjbar | ESR Injection ESR Injection Mechanical Components - Fabrication | Alexander | 686000 | 100 | 2026-11-17 | Layden
BNL | 6.05.03.04 | HR_0404_2000 | APP00072 | Sandberg | Construction - Material | Alexander | 2995807 | 500 | 2026-10-13 | Patil
BNL | 6.05.03.04 | HR_0404_1820 | APP00109 | Sandberg | Long Lead Procurement - Material | Alexander | 1528473 | 499 | 2025-12-05 | Patil
BNL | 6.10.10 | DE_1000_3150 | APP00017 | Sharma | Detector Infrastructure: Fabrication - Material | Alexander | 9576557 | 750 | 2025-10-01 | Lewis
BNL | 6.10.10 | DE_1000_3160 | APP00026 | Sharma | Detector Infrastructure: Fabrication - Material In-Kind | Alexander | 3192186 | 750 | 2025-10-01 | Lewis
BNL | 6.03.04.01.03 | EJ_0401_2270 | APP00001 | Skaritka | 400 MeV Linac - Vendor Design | Alexander | 1831233 | 250 | 2025-04-10 | Davis | Foreign
BNL | 6.03.04.01.03 | EJ_0401_2280 | APP00001 | Skaritka | 400 MeV Linac - Fabrication and ship | Alexander | 16481096 | 500 | 2026-04-10 | Davis
BNL | 6.03.04.01.02 | EJ_0401_1150 | APP00104 | Skaritka | XHV pumping systems - Fabrication and ship | Alexander | 890121 | 120 | 2026-11-20 | Davis | Foreign
BNL | 6.03.04.01.02 | EJ_0401_1680 | APP00131 | Skaritka | Transport line vacuum cmpts. - material | Alexander | 350000 | 120 | 2026-12-29 | Davis | Foreign and Domestic | Mix of Procurements
BNL | 6.03.04.01.02 | EJ_0401_1500 | APP00136 | Skaritka | XHV ion pumps diag. line - material | Alexander | 398000 | 160 | 2027-02-10 | Davis | Domestic | Domestic company may purchase from foreign supplier
BNL | 6.03.04.01.02 | EJ_0401_1040 | APP00207 | Skaritka | XHV Diag.Cal.& purging systems - Fabrication and ship | Alexander | 500164 | 160 | 2027-04-14 | Davis | Domestic
BNL | 6.03.04.01.02 | EJ_0401_1380 | APP00214 | Skaritka | Valves and beam line isolation - material | Alexander | 458000 | 160 | 2027-02-10 | Davis | Foreign and Domestic | Mix of Procurements
BNL | 6.03.04.01.03 | EJ_0401_2580 | APP00230 | Skaritka | Installation Support - Material | Alexander | 750000 | 121 | 2027-10-21 | Davis | Domestic
BNL | 6.03.04.02.03 | EJ_0402_4060 | APP00235 | Skaritka | Laser System - Procurements - Material | Alexander | 610000 | 250 | 2026-11-25 | Davis | Foreign and Domestic | Mix of Procurements
BNL | 6.08.07.07.03 | IR_0205_2320 | APP00041 | Smith | RF-CRAB-1-CTRL: Materials (Production) | Alexander | 502131 | 147 | 2025-07-21 | Golnar
BNL | 6.08.07.07.03 | IR_0205_5320 | APP00120 | Smith | RF-CRAB-2-CTRL: Materials (Production) | Alexander | 334754 | 147 | 2026-01-27 | Golnar
BNL | 6.08.07.06.03 | HR_0805_6320 | APP00153 | Smith | RF-ERL-3-CTRL: Materials (Production) | Alexander | 334754 | 60 | 2029-06-01 | Golnar
BNL | 6.08.07.04.03 | SR_0501_1660 | APP00251 | Smith | RF-ESR-1-CTRL: Materials (Production) | Alexander | 1004261 | 233 | 2025-10-28 | Golnar
BNL | 6.08.07.05.03 | HR_0304_1640 | APP00254 | Smith | RF-HR-4-CTRL: Materials (Production) | Alexander | 334754 | 275 | 2027-05-19 | Golnar
BNL | 6.08.07.06.03 | HR_0805_1420 | APP00259 | Smith | RF-ERL-1-CTRL: Materials (Production) | Alexander | 557923 | 168 | 2028-05-18 | Golnar
BNL | 6.09.05.03 | E09_17550 | APP00311 | Tallerico | RCV: Lakeshore temperature controllers | Alexander | 260000 | 1 | 2024-10-07 | Layden
BNL | 6.09.05.03 | E09_17510 | APP00312 | Tallerico | RCV: PLC hardware cards | Alexander | 600000 | 1 | 2025-04-03 | Layden
BNL | 6.09.05.03 | E09_17610 | APP00313 | Tallerico | RCV: Heater Controllers Chromalox | Alexander | 527000 | 1 | 2025-06-27 | Layden
BNL | 6.09.05.03 | E09_17930 | APP00314 | Tallerico | RCV: Multiconductor Cables | Alexander | 573000 | 1 | 2027-03-08 | Layden
BNL | 6.09.02.04.01 | E09_12730 | APP00198 | Than | RCV: Cryogenics System Installation Contract - IR02 | Alexander | 5119500 | 1 | 2028-09-29 | Layden | Domestic
BNL | 6.09.02.04.02 | E09_12780 | APP00199 | Than | RCV: Cryogenics System Installation Contract - IR06 | Alexander | 5119500 | 1 | 2028-11-14 | Layden | Domestic
BNL | 6.09.02.04.03 | E09_12830 | APP00200 | Than | RCV: Cryogenics System Installation Contract - IR10 | Alexander | 5520000 | 1 | 2028-09-15 | Layden | Domestic
BNL | 6.09.04.04 | E09_16430 | APP00308 | Than | RCV: 2K Distribution System Installation Contract - NonLabor, OnSite - IR02 | Alexander | 802800 | 1 | 2029-11-06 | Layden | Domestic
BNL | 6.09.04.04 | E09_16510 | APP00309 | Than | RCV: 2K Distribution System Installation Contract - NonLabor, OnSite - IR10 | Alexander | 1225200 | 1 | 2029-05-16 | Layden | Domestic
BNL | 6.09.04.04 | E09_16470 | APP00310 | Than | RCV: 2K Distribution System Installation Contract - NonLabor, OnSite - IR06 | Alexander | 956400 | 1 | 2028-09-15 | Layden | Domestic
BNL | 6.03.03.01 | EJ_0301_1120 | APP00106 | Tsoupas | Linac to RCS Transfer line magnets - Material and Construction | Alexander | 500000 | 120 | 2026-10-14 | Davis
BNL | 6.03.03.01 | EJ_0301_1340 | APP00127 | Tsoupas | RCS to SR Transfer line magnets - Material and Construction | Alexander | 400000 | 160 | 2026-10-14 | Davis
BNL | 6.03.03.01 | EJ_0301_1530 | APP00270 | Tsoupas | Transfer Line Magnets - Girders - Vendor Delivery | Alexander | 265000 | 20 | 2027-03-30 | Davis
BNL | 6.10.02 | DE_0200_2040 | APP00048 | Ullrich | Detector R&D Material Purchase FY23 - Procurement(s) BNL | Alexander | 1593250 | 160 | 2023-02-08 | Lewis
BNL | 6.10.02 | DE_0200_2110 | APP00048 | Ullrich | Detector R&D Material Purchase FY24 - Procurement(s) BNL | Alexander | 1166500 | 160 | 2023-12-14 | Lewis
BNL | 6.10.02 | DE_0200_2345 | APP00048 | Ullrich | Detector R&D Material Purchase FY25 - Procurement(s) BNL | Alexander | 689500 | 160 | 2024-10-18 | Lewis
BNL | 6.02.03.07 | RD1_0307_1780 | APP00059 | Wang | HV DC Gun PS 600 kV - Vendor Manufacturing - Final Design Review | Alexander | 312000 | 20 | 2022-11-21 | Patil
BNL | 6.02.03.07 | RD1_0307_1800 | APP00059 | Wang | HV DC Gun PS 600 kV - Vendor Manufacturing - Confirm 95% of PS Drawings and 80% Long Lead Items | Alexander | 708000 | 180 | 2022-12-21 | Patil
BNL | 6.02.03.07 | RD1_0307_1820 | APP00059 | Wang | HV DC Gun PS 600 kV - Vendor Manufacturing - Fabrication and Factory Acceptance | Alexander | 975000 | 240 | 2023-09-08 | Patil
BNL | 6.02.03.07 | RD1_0307_6880 | APP00100 | Wang | Laser procurement - Vendor Fabrication | Alexander | 400000 | 200 | 2023-07-31 | Patil
BNL | 6.05.07.03 | HR_0801_1510 | APP00101 | Wang | Hadron Cooling Design - Physics Design - LBNL [0.5 FTE] | Alexander | 300000 | 250 | 03-Jan-2022* | Patil
BNL | 6.05.02.03 | HR_0203_1540 | APP00065 | Weiss | HR SS Mod Vacuum - valves and pumps - Vendor Fabrication | Alexander | 2020410 | 120 | 2026-10-14 | Lewis
BNL | 6.05.02.03 | HR_0203_1420 | APP00129 | Weiss | HR SS Mod Vacuum - I&C systems - Vendor Fabrication | Alexander | 320610 | 250 | 2026-10-14 | Lewis
BNL | 6.05.02.03 | HR_0203_1200 | APP00237 | Weiss | HR SS Mod Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | Alexander | 1675350 | 250 | 2027-03-30 | Lewis
BNL | 6.05.03.03 | HR_0403_1200 | APP00238 | Weiss | HR Inj-Sys Upgrade Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | Alexander | 259150 | 250 | 2026-10-14 | Lewis
BNL | 6.05.07.05 | HR_0804_4800 | APP00239 | Weiss | e-beamlines Baked Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | Alexander | 531600 | 250 | 2027-08-24 | Lewis
BNL | 6.05.07.05 | HR_0804_5400 | APP00240 | Weiss | e-loop Return Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | Alexander | 277875 | 250 | 2027-08-24 | Lewis
BNL | 6.05.07.05 | HR_0804_6000 | APP00241 | Weiss | DC-Gun LINAC Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | Alexander | 387800 | 250 | 2027-08-24 | Lewis
BNL | 6.05.07.05 | HR_0804_5740 | APP00242 | Weiss | e-loop Return Vacuum - valves and pumps - Vendor Fabrication | Alexander | 257400 | 120 | 2027-11-19 | Lewis
BNL | 6.06.02.02 | IR_0202_1140 | APP00005 | Witte | Spin Rotator - Fabrication-Manufacturing (Cost Module 1-4=$9.45/ 5-16=$19.85) | Alexander | 29310000 | 750 | 2026-10-14 | Davis | Foreign
BNL | 6.04.02.01 | SR_0200_1320 | APP00023 | Witte | ESR Dipole - Magnet II - Fabrication | Alexander | 15306239 | 750 | 2026-03-16 | Davis | Foreign
BNL | 6.04.02.01 | SR_0200_1220 | APP00024 | Witte | ESR Dipole - Magnet I - Fabrication | Alexander | 15306239 | 750 | 2026-03-16 | Davis | Foreign
BNL | 6.04.02.03 | SR_0200_2700 | APP00035 | Witte | eSR Girders: 5 Types - Fabrication [$20K per Girder, 494 Girders] | Alexander | 9880000 | 500 | 2025-11-17 | Davis | Domestic
BNL | 6.03.02.01.04 | EJ_0201_2840 | APP00036 | Witte | RCS Girder: 5 types - Vendor Fabrication - Long Dipole [$20K per Girder, #334] | Alexander | 7680000 | 500 | 2026-10-14 | Davis | Domestic
BNL | 6.03.02.01.04 | EJ_0201_2845 | APP00036 | Witte | RCS Girder: 5 types - Vendor Fabrication - Short Dipole [$5K per Girder, #132] | Alexander | 660000 | 500 | 2026-10-14 | Davis
BNL | 6.06.02.01.03 | IR_0213_1080 | APP00043 | Witte | IR Magnets Warm - Vendor Manufacturing / Fabrication | Alexander | 2413369 | 250 | 2026-10-14 | Davis | Foreign
BNL | 6.03.02.01.01 | EJ_0201_1820 | APP00047 | Witte | RCS Quad - Magnet I - Fabrication | Alexander | 3962206 | 750 | 2025-11-14 | Davis | Foreign
BNL | 6.04.02.02 | SR_0200_2120 | APP00049 | Witte | ESR Sextupole - Magnet I - Fabrication | Alexander | 2407960 | 750 | 2026-03-16 | Davis | Foreign
BNL | 6.04.02.02 | SR_0200_2220 | APP00049 | Witte | ESR Sextupole - Magnet II - Fabrication | Alexander | 2407960 | 750 | 2026-03-16 | Davis
BNL | 6.06.02.01.02 | IR_0212_1080 | APP00052 | Witte | Collared Magnet 1 - Q1ApF - Fabrication/ Manufacturing | Alexander | 3715000 | 750 | 2026-11-02 | Davis | Foreign | Tesla/ELYTT
BNL | 6.06.02.01.02 | IR_0212_1260 | APP00054 | Witte | Collared Magnet 2 - Q1BpF - Fabrication/ Manufacturing | Alexander | 3715000 | 750 | 2026-11-02 | Davis | Foreign | Tesla/ELYTT
BNL | 6.06.02.01.02 | IR_0212_1440 | APP00055 | Witte | Collared Magnet 3 - Q2pF - Fabrication/ Manufacturing | Alexander | 3715000 | 750 | 2026-11-02 | Davis | Foreign | Tesla/ELYTT
BNL | 6.06.02.01.02 | IR_0212_1620 | APP00056 | Witte | Collared Magnet 4 - B1pF - Fabrication/ Manufacturing | Alexander | 3318000 | 750 | 2026-11-02 | Davis | Foreign | Tesla/ELYTT
BNL | 6.06.02.01.02 | IR_0212_1800 | APP00057 | Witte | Collared Magnet 5 - B1ApF - Fabrication/ Manufacturing | Alexander | 3318000 | 750 | 2026-11-02 | Davis | Foreign | Tesla/ELYTT
BNL | 6.03.02.01.02 | EJ_0201_2380 | APP00067 | Witte | RCS Sextupole - Magnet II - Fabrication | Alexander | 3306650 | 750 | 2025-11-14 | Davis | Foreign
BNL | 6.05.07.04 | HR_0804_1080 | APP00069 | Witte | SHC Beam Transport Magnets - Fabrication | Alexander | 6569583 | 500 | 2028-07-10 | Davis | Foreign | JLAB Scope?
BNL | 6.06.02.06 | IR_0207_1100 | APP00076 | Witte | Collared Dipole - Fabrication Dipole 1 | Alexander | 3318000 | 750 | 2026-10-13 | Davis | foreign
BNL | 6.06.02.06 | IR_0207_1120 | APP00076 | Witte | Collared Dipole - Fabrication Dipole 2 | Alexander | 3318000 | 750 | 2027-02-25 | Davis
BNL | 6.06.02.06 | IR_0207_1140 | APP00076 | Witte | Collared Dipole - Cryostat 1 | Alexander | 350000 | 750 | 2026-10-13 | Davis
BNL | 6.06.02.06 | IR_0207_1160 | APP00076 | Witte | Collared Dipole - Cryostat 2 | Alexander | 350000 | 750 | 2027-02-25 | Davis
BNL | 6.03.02.01.01 | EJ_0201_1920 | APP00079 | Witte | RCS Quad - Magnet II - Fabrication | Alexander | 3962206 | 750 | 2025-11-14 | Davis | Foreign
BNL | 6.02.03.03.02 | RD_0303_2060 | APP00089 | Witte | Coil Assembly + Yoke Material - Vendor Fabrication | Alexander | 773330 | 60 | 2023-08-24 | Davis | Domestic
BNL | 6.02.03.03.02 | RD_0303_3323 | APP00090 | Witte | B1pF Prototype - Tooling Materials - Vendor Manufacturing/ Fabrication | Alexander | 1605568 | 100 | 2023-06-14 | Davis | Domestic
BNL | 6.02.03.03.02 | RD_0303_3328 | APP00090 | Witte | B1pF Prototype - Prototype Material - Vendor Manufacturing/ Fabrication | Alexander | 1068943 | 100 | 2023-08-14 | Davis
BNL | 6.06.02.01.01 | IR_0211_2620 | APP00112 | Witte | Direct Wind Magnets 5 - B2eR - Coil Assembly - Coil Parts Fabrication | Alexander | 683109 | 80 | 2026-03-19 | Davis | Domestic
BNL | 6.06.02.01.01 | IR_0211_2800 | APP00113 | Witte | Direct Wind Magnets 5 - B2eR - Cold Mass Assembly - Parts Fabrication | Alexander | 800214 | 120 | 2026-08-10 | Davis | domestic
BNL | 6.06.02.01.01 | IR_0211_2940 | APP00114 | Witte | Direct Wind Magnets 5 - B2eR - Vertical Cold Test - Material | Alexander | 495248 | 60 | 2026-08-24 | Davis | domestic | in house
BNL | 6.06.02.01.01 | IR_0211_6120 | APP00115 | Witte | Direct Wind Magnets 12 - Q2BpR - Coil Assembly - Coil Parts Fabrication | Alexander | 338039 | 80 | 2027-04-30 | Davis | Domestic
BNL | 6.06.02.01.01 | IR_0211_6300 | APP00116 | Witte | Direct Wind Magnets 12 - Q2BpR - Cold Mass Assembly - Parts Fabrication | Alexander | 280325 | 120 | 2027-09-22 | Davis | Domestic
BNL | 6.05.07.04 | HR_0804_1200 | APP00117 | Witte | Girder - Vendor Fabrication [$5K per Girder, 530 Girders] | Alexander | 2650000 | 250 | 2028-08-07 | Davis | Domestic
BNL | 6.03.02.01.03 | EJ_0201_2620 | APP00118 | Witte | RCS Corrector - Fabrication | Alexander | 1552500 | 520 | 2025-04-10 | Davis | domestic
BNL | 6.06.02.02 | IR_0202_1380 | APP00118 | Witte | Spin Rotator Quad - Fabrication Manufacturing | Alexander | 748464 | 750 | 2026-09-18 | Davis | Foreign
BNL | 6.03.02.01.05 | EJ_0201_2980 | APP00126 | Witte | Magnet Measuring Station - Vendor Fabrication | Alexander | 867900 | 250 | 2026-10-14 | Davis | Foreign
BNL | 6.03.02.01.02 | EJ_0201_2280 | APP00205 | Witte | RCS Sextupole - Magnet I - Fabrication | Alexander | 3306650 | 750 | 2025-11-14 | Davis | Domestic
BNL | 6.06.02.07 | RD_0303_7200 | APP00289 | Witte | SC Strand - Production Magnets - Fabrication | Alexander | 880848 | 250 | 2024-08-21 | Davis | Domestic
BNL | 6.02.03.03.02 | RD_0303_7090 | APP00290 | Witte | Vendor Delivery - Cabeling Machine | Alexander | 450000 | 60 | 2023-07-13 | Davis | Foreign | Bilfinger
JLAB | 6.06.04 | E06_00000 | APP00470 | Wittmer | IR #2 Development (Planning Package) | Alexander | 1500000 | 293 | 02-May-2022* | Kessler
BNL | 6.08.06.01 | SR_0501_1328 | APP00002 | Zaltsman | RF-ESR-1 TEST PWR: (4) Option 1: Design of 200 kW Amplifier and Fabrication of the 1st Unit | Alexander | 1000000 | 125 | 2023-08-02 | Golnar | foreign
BNL | 6.08.06.01 | SR_0501_1332 | APP00002 | Zaltsman | RF-ESR-1 TEST PWR: (4) Option 2: Begin Fabrication of the 2nd 200 kW Unit | Alexander | 1500000 | 170 | 2024-02-06 | Golnar
BNL | 6.08.06.01 | SR_0501_1336 | APP00002 | Zaltsman | RF-ESR-1 TEST PWR: (4) Option 3: Complete Fabrication of the 2nd 200 kW Unit | Alexander | 700000 | 170 | 2024-10-08 | Golnar
BNL | 6.08.06.01 | SR_0501_1340 | APP00002 | Zaltsman | RF-ESR-1 TEST PWR: (4) Option 4: Fabrication of 2 each of the 400 kW | Alexander | 6000000 | 250 | 2025-06-17 | Golnar
BNL | 6.08.06.01 | SR_0501_1790 | APP00002 | Zaltsman | RF-ESR-1 TEST PWR: (4) Circulators and Loads Fabrication | Alexander | 1000000 | 250 | 2023-11-14 | Golnar
BNL | 6.08.05.03 | E08_51310 | APP00008 | Zaltsman | 591 MHz FPC Couplers: Fabrication (60 units) | Alexander | 13200000 | 500 | 2027-12-23 | Golnar | domestic | in house
BNL | 6.08.05.07.02 | E08_10965 | APP00018 | Zaltsman | 197 MHz Cavity (HSR Store 1) - Window Manufacturing Materials | Alexander | 600000 | 200 | 2026-10-13 | Golnar | Domestic
BNL | 6.08.05.07.02 | E08_10985 | APP00020 | Zaltsman | 197 MHz Cavity (HSR Store 1) - Damper Manufacturing Materials | Alexander | 322500 | 200 | 2026-10-13 | Golnar | Domestic
BNL | 6.08.05.07.02 | E08_10959 | APP00021 | Zaltsman | 197 MHz Cavity (HSR Store 1) - Tuner Manufacturing Materials | Alexander | 322500 | 200 | 2026-10-13 | Golnar | Domestic
BNL | 6.08.05.03 | E08_51360 | APP00028 | Zaltsman | 197 MHz FPC Couplers: Fabrication (10 units) | Alexander | 2200000 | 500 | 2028-03-29 | Golnar | Domestic
BNL | 6.08.05.03 | E08_51410 | APP00029 | Zaltsman | 394 MHz FPC Couplers: Fabrication (60 units) | Alexander | 1760000 | 500 | 2028-03-29 | Golnar | Domestic
BNL | 6.08.06.02.01 | HR_0805_6170 | APP00039 | Zaltsman | RF-ERL-3-PWR: Materials (First Article) | Alexander | 956580 | 222 | 2027-12-20 | Golnar | Foreign
BNL | 6.08.06.02.01 | HR_0805_6200 | APP00039 | Zaltsman | RF-ERL-3-PWR: Materials (Production) | Alexander | 5739480 | 60 | 2029-01-08 | Golnar
BNL | 6.08.06.03.02 | IR_0205_5170 | APP00062 | Zaltsman | RF-CRAB-2-PWR: Materials (First Article) | Alexander | 563771 | 222 | 2026-10-14 | Golnar | Foreign
BNL | 6.08.06.03.02 | IR_0205_5200 | APP00062 | Zaltsman | RF-CRAB-2-PWR: Materials (Production) | Alexander | 2818857 | 61 | 2027-11-01 | Golnar | Foreign
BNL | 6.08.05.05.02 | E08_10598 | APP00066 | Zaltsman | 49.2 MHz Cavity Components: Cavity Manufacturing Materials | Alexander | 1202000 | 190 | 2027-03-30 | Golnar | Foreign | RI
BNL | 6.08.06.03.01 | IR_0205_2170 | APP00071 | Zaltsman | RF-CRAB-1-PWR: Materials (First Article) | Alexander | 563771 | 222 | 2025-04-10 | Golnar | Foreign
BNL | 6.08.06.03.01 | IR_0205_2200 | APP00071 | Zaltsman | RF-CRAB-1-PWR: Materials (Production) | Alexander | 3946400 | 61 | 2026-04-28 | Golnar
BNL | 6.08.05.03 | E08_51460 | APP00077 | Zaltsman | 1.773 GHz MHz FPC Couplers: Fabrication (60 units) | Alexander | 500000 | 500 | 2028-09-25 | Golnar | Domestic
BNL | 6.08.06.02.02 | HR_0805_1150 | APP00080 | Zaltsman | RF-ERL-1-PWR: Materials (First Article) | Alexander | 453095 | 125 | 2028-06-12 | Golnar | Foreign
BNL | 6.08.06.02.02 | HR_0805_1180 | APP00080 | Zaltsman | RF-ERL-1-PWR: Materials (Production) | Alexander | 3171665 | 336 | 2029-01-19 | Golnar
BNL | 6.08.05.06.02 | E08_10775 | APP00082 | Zaltsman | 98.4 MHz Cavity - Cavity Manufacturing Materials | Alexander | 1102000 | 190 | 2027-03-30 | Golnar | Foreign
BNL | 6.08.06.01 | SR_0501_1420 | APP00101 | Zaltsman | RF 200KW PWR: (32) Amplifier Fabrication | Alexander | 41312603 | 750 | 2028-01-14 | Golnar | Foreign
BNL | 6.08.06.01 | SR_0501_1482 | APP00101 | Zaltsman | RF-400KW PWR: Upgrade: (32) Amplifier Upgrade Fabrication | Alexander | 22000000 | 500 | 2031-08-18 | Golnar
BNL | 6.08.05.01.02 | E08_10087 | APP00215 | Zaltsman | 295 MHz Cavity - Cavity Manufacturing Materials | Alexander | 1202000 | 190 | 2027-03-30 | Golnar | Foreign
BNL | 6.08.05.02.02 | E08_10268 | APP00216 | Zaltsman | 148 MHz Cavity - Cavity Manufacturing Materials | Alexander | 602000 | 190 | 2027-03-30 | Golnar | Foreign
BNL | 6.08.06.03.03 | EJ_0204_2170 | APP00218 | Zaltsman | RF-RCS-2-PWR: Materials (First Article) | Alexander | 324246 | 375 | 2026-10-14 | Golnar | Foreign
BNL | 6.08.06.03.03 | EJ_0204_2200 | APP00218 | Zaltsman | RF-RCS-2-PWR: Materials (Production) | Alexander | 324246 | 125 | 2028-09-14 | Golnar
BNL | 6.08.06.03.04 | EJ_0204_2530 | APP00219 | Zaltsman | RF-RCS-3-PWR: Materials (First Article) | Alexander | 324246 | 375 | 2026-10-14 | Golnar | Foreign
BNL | 6.08.06.04.02 | HR_0805_6530 | APP00222 | Zaltsman | RF-ERL-4-PWR: Materials (First Article) | Alexander | 456178 | 375 | 2028-03-24 | Golnar | foreign
BNL | 6.08.02.03.01 | HR_0305_1530 | APP00223 | Zaltsman | 591 MHz - 600 kW CW Klystron: Fabrication | Alexander | 1900000 | 380 | 2023-02-14 | Golnar | Domestic | CPI
BNL | 6.08.02.03.01 | HR_0305_1610 | APP00224 | Zaltsman | 591 MHz - 600 kW Circulator with Load: Fabrication | Alexander | 800000 | 250 | 2023-06-14 | Golnar | Foreign
BNL | 6.08.02.03.01 | RF_0802_3705 | APP00226 | Zaltsman | 591 MHz FPC conditioning box: Fabrication | Alexander | 400000 | 200 | 2024-02-06 | Golnar | Domestic | IN House
BNL | 6.08.06.02.04 | HR_0305_1162 | APP00243 | Zaltsman | RF-HR-5-PWR: Materials (First Article) | Alexander | 648928 | 125 | 2028-06-12 | Golnar | Domestic
BNL | 6.08.06.02.03 | EJ_0204_1360 | APP00249 | Zaltsman | RF-RCS-1-PWR: Materials (First Article) | Alexander | 648928 | 222 | 2028-03-17 | Golnar | Foreign
BNL | 6.08.06.02.03 | EJ_0204_1420 | APP00249 | Zaltsman | RF-RCS-1-PWR: Materials (Production) | Alexander | 1297856 | 61 | 2029-04-04 | Golnar
BNL | 6.08.06.03.06 | HR_0303_1340 | APP00252 | Zaltsman | RF-HR-3-PWR: Materials (First Article) | Alexander | 525440 | 375 | 2026-10-14 | Golnar | Foreign
BNL | 6.08.06.03.06 | HR_0303_1400 | APP00252 | Zaltsman | RF-HR-3-PWR: Materials (Production) | Alexander | 525440 | 125 | 2028-07-19 | Golnar
BNL | 6.08.06.04.01 | HR_0805_5340 | APP00253 | Zaltsman | RF-ERL-2-PWR: Materials (First Article) | Alexander | 425518 | 375 | 2028-03-24 | Golnar | Foreign
BNL | 6.08.06.04.01 | HR_0805_5400 | APP00253 | Zaltsman | RF-ERL-2-PWR: Materials (Production) | Alexander | 851036 | 232 | 2029-12-27 | Golnar
BNL | 6.08.06.03.05 | HR_0302_1340 | APP00258 | Zaltsman | RF-HR-2-PWR: Materials (First Article) | Alexander | 525440 | 375 | 2026-10-14 | Golnar | Foreign
BNL | 6.08.06.03.05 | HR_0302_1400 | APP00258 | Zaltsman | RF-HR-2-PWR: Materials (Production) | Alexander | 525440 | 125 | 2028-07-19 | Golnar
BNL Scope | [6 empty] | 841210464 | 2907 | 2022-01-03
APP00001 400 MeV Linac | [6 empty] | 18312329 | 750 | 2025-04-10
APP00002 eSR H1 Test Power Aplifier - 4 Units | [6 empty] | 10200000 | 718 | 2023-08-02
APP00004 Main CM/GC | [6 empty] | 136452601 | 1065 | 2025-06-25
APP00005 (New Code Value) | [6 empty] | 29310000 | 750 | 2026-10-14
APP00006 | [6 empty] | 602272 | 120 | 2024-01-16
APP00007 (New Code Value) | [6 empty] | 16800000 | 325 | 2025-08-11
APP00008 (New Code Value) | [6 empty] | 24767400 | 797 | 2026-10-14
APP00010 Roman Pots Fabrication | [6 empty] | 5772500 | 520 | 2026-10-14
APP00011 B0 Fabrication | [6 empty] | 8250000 | 520 | 2026-10-14
APP00012 (New Code Value) | [6 empty] | 7801220 | 260 | 2026-10-14
APP00017 (New Code Value) | [6 empty] | 9576557 | 750 | 2025-10-01
APP00018 (New Code Value) | [6 empty] | 600000 | 200 | 2026-10-13
APP00019 (New Code Value) | [6 empty] | 23144571 | 723 | 2023-03-01
APP00020 (New Code Value) | [6 empty] | 322500 | 200 | 2026-10-13
APP00021 Backward (Electron Endcap) EMCal Material | [6 empty] | 2320260 | 583 | 2025-04-03
APP00023 EMCal Silicon Photomultipliers | [6 empty] | 16701044 | 887 | 2025-08-22
APP00024 Backward Hadronic Calorimetry | [6 empty] | 19089929 | 1041 | 2025-01-14
APP00025 Barrel Hadronic Calorimetry | [6 empty] | 18247262 | 1000 | 2025-09-02
APP00026 Detector Infrastructure: Fabrication | [6 empty] | 17844987 | 1963 | 2025-10-01
APP00027 (New Code Value) | [6 empty] | 11250000 | 520 | 2026-10-14
APP00028 (New Code Value) | [6 empty] | 2200000 | 500 | 2028-03-29
APP00029 (New Code Value) | [6 empty] | 1760000 | 500 | 2028-03-29
APP00030 (New Code Value) | [6 empty] | 7751396 | 430 | 2026-10-14
APP00031 (New Code Value) | [6 empty] | 9970366 | 180 | 2026-10-14
APP00032 (New Code Value) | [6 empty] | 2039591 | 300 | 2026-10-13
APP00034 (New Code Value) | [6 empty] | 17489110 | 2193 | 2022-08-02
APP00035 (New Code Value) | [6 empty] | 9880000 | 500 | 2025-11-17
APP00036 (New Code Value) | [6 empty] | 8340000 | 500 | 2026-10-14
APP00038 FTTL Fabrication | [6 empty] | 2418891 | 1000 | 2025-04-09
APP00039 (New Code Value) | [6 empty] | 6696060 | 322 | 2027-12-20
APP00040 (New Code Value) | [6 empty] | 6154017 | 240 | 2026-10-14
APP00041 (New Code Value) | [6 empty] | 2764676 | 624 | 2025-07-21
APP00043 (New Code Value) | [6 empty] | 2413369 | 250 | 2026-10-14
APP00044 (New Code Value) | [6 empty] | 3105120 | 240 | 2026-10-14
APP00047 (New Code Value) | [6 empty] | 3962206 | 750 | 2025-11-14
APP00048 (New Code Value) | [6 empty] | 3449250 | 586 | 2023-02-08
APP00049 (New Code Value) | [6 empty] | 4815920 | 750 | 2026-03-16
APP00050 (New Code Value) | [6 empty] | 2025000 | 940 | 2025-04-28
APP00051 (New Code Value) | [6 empty] | 2024833 | 350 | 2026-10-13
APP00052 (New Code Value) | [6 empty] | 3715000 | 750 | 2026-11-02
APP00054 (New Code Value) | [6 empty] | 3715000 | 750 | 2026-11-02
APP00055 (New Code Value) | [6 empty] | 3715000 | 750 | 2026-11-02
APP00056 (New Code Value) | [6 empty] | 3318000 | 750 | 2026-11-02
APP00057 (New Code Value) | [6 empty] | 3318000 | 750 | 2026-11-02
APP00059 (New Code Value) | [6 empty] | 1995000 | 440 | 2022-11-21
APP00060 (New Code Value) | [6 empty] | 2236080 | 300 | 2026-10-14
APP00061 (New Code Value) | [6 empty] | 2894814 | 269 | 2026-10-14
APP00062 (New Code Value) | [6 empty] | 3382628 | 323 | 2026-10-14
APP00063 (New Code Value) | [6 empty] | 2210800 | 150 | 2026-09-18
APP00064 (New Code Value) | [6 empty] | 2080000 | 220 | 2026-10-14
APP00065 (New Code Value) | [6 empty] | 2020410 | 120 | 2026-10-14
APP00066 (New Code Value) | [6 empty] | 1202000 | 190 | 2027-03-30
APP00067 (New Code Value) | [6 empty] | 3306650 | 750 | 2025-11-14
APP00069 (New Code Value) | [6 empty] | 6569583 | 500 | 2028-07-10
APP00070 RCS Vacuum Chambers and Bellows | [6 empty] | 3960560 | 320 | 2025-06-27
APP00071 (New Code Value) | [6 empty] | 4510171 | 323 | 2025-04-10
APP00072 (New Code Value) | [6 empty] | 2995807 | 500 | 2026-10-13
APP00073 (New Code Value) | [6 empty] | 2000000 | 250 | 2026-04-22
APP00074 (New Code Value) | [6 empty] | 4265400 | 160 | 2025-10-31
APP00075 (New Code Value) | [6 empty] | 3249650 | 60 | 2026-10-13
APP00076 (New Code Value) | [6 empty] | 7336000 | 840 | 2026-10-13
APP00077 (New Code Value) | [6 empty] | 500000 | 500 | 2028-09-25
APP00078 (New Code Value) | [6 empty] | 4878700 | 235 | 2027-01-19
APP00079 (New Code Value) | [6 empty] | 3962206 | 750 | 2025-11-14
APP00080 (New Code Value) | [6 empty] | 3624760 | 486 | 2028-06-12
APP00082 (New Code Value) | [6 empty] | 1102000 | 190 | 2027-03-30
APP00089 (New Code Value) | [6 empty] | 773330 | 60 | 2023-08-24
APP00090 (New Code Value) | [6 empty] | 2674511 | 142 | 2023-06-14
APP00091 (New Code Value) | [6 empty] | 33687685 | 959 | 2025-05-22
APP00092 (New Code Value) | [6 empty] | 13458813 | 1144 | 2025-04-09
APP00100 (New Code Value) | [6 empty] | 400000 | 200 | 2023-07-31
APP00101 (New Code Value) | [6 empty] | 63612603 | 2907 | 2022-01-03
APP00104 (New Code Value) | [6 empty] | 890121 | 120 | 2026-11-20
APP00105 (New Code Value) | [6 empty] | 800000 | 750 | 2022-10-28
APP00106 (New Code Value) | [6 empty] | 500000 | 120 | 2026-10-14
APP00108 (New Code Value) | [6 empty] | 1337062 | 500 | 2026-10-13
APP00109 (New Code Value) | [6 empty] | 1528473 | 499 | 2025-12-05
APP00110 (New Code Value) | [6 empty] | 1445963 | 63 | 2026-10-14
APP00111 (New Code Value) | [6 empty] | 2065831 | 346 | 2026-10-14
APP00112 (New Code Value) | [6 empty] | 683109 | 80 | 2026-03-19
APP00113 (New Code Value) | [6 empty] | 800214 | 120 | 2026-08-10
APP00114 (New Code Value) | [6 empty] | 495248 | 60 | 2026-08-24
APP00115 (New Code Value) | [6 empty] | 338039 | 80 | 2027-04-30
APP00116 (New Code Value) | [6 empty] | 280325 | 120 | 2027-09-22
APP00117 (New Code Value) | [6 empty] | 2650000 | 250 | 2028-08-07
APP00118 (New Code Value) | [6 empty] | 2300964 | 1112 | 2025-04-10
APP00119 (New Code Value) | [6 empty] | 500000 | 80 | 2026-11-12
APP00120 (New Code Value) | [6 empty] | 334754 | 147 | 2026-01-27
APP00122 HR Straight DC Cables | [6 empty] | 290416 | 240 | 2026-10-14
APP00124 (New Code Value) | [6 empty] | 613257 | 230 | 2026-10-13
APP00125 (New Code Value) | [6 empty] | 470600 | 60 | 2026-10-13
APP00126 (New Code Value) | [6 empty] | 867900 | 250 | 2026-10-14
APP00127 (New Code Value) | [6 empty] | 400000 | 160 | 2026-10-14
APP00128 (New Code Value) | [6 empty] | 1017740 | 125 | 2025-06-03
APP00129 (New Code Value) | [6 empty] | 320610 | 250 | 2026-10-14
APP00130 (New Code Value) | [6 empty] | 22105500 | 100 | 2027-01-19
APP00131 (New Code Value) | [6 empty] | 350000 | 120 | 2026-12-29
APP00132 (New Code Value) | [6 empty] | 861112 | 215 | 2026-11-10
APP00134 (New Code Value) | [6 empty] | 3661300 | 360 | 2026-10-14
APP00135 (New Code Value) | [6 empty] | 330000 | 120 | 2028-03-08
APP00136 (New Code Value) | [6 empty] | 398000 | 160 | 2027-02-10
APP00138 (New Code Value) | [6 empty] | 1719000 | 250 | 2025-09-18
APP00139 (New Code Value) | [6 empty] | 441487 | 500 | 2028-04-07
APP00140 (New Code Value) | [6 empty] | 694200 | 60 | 2026-10-13
APP00141 (New Code Value) | [6 empty] | 506630 | 360 | 2026-10-14
APP00142 (New Code Value) | [6 empty] | 410425 | 180 | 2027-03-30
APP00144 (New Code Value) | [6 empty] | 546000 | 250 | 2025-04-10
APP00148 (New Code Value) | [6 empty] | 890358 | 146 | 2026-10-14
APP00151 (New Code Value) | [6 empty] | 1619200 | 60 | 2026-10-13
APP00152 (New Code Value) | [6 empty] | 643710 | 280 | 2026-10-14
APP00153 (New Code Value) | [6 empty] | 334754 | 60 | 2029-06-01
APP00154 (New Code Value) | [6 empty] | 1628350 | 60 | 2026-10-13
APP00158 (New Code Value) | [6 empty] | 808376 | 250 | 2026-10-14
APP00159 Streak Camera | [6 empty] | 463354 | 250 | 2027-08-19
APP00160 AtR Material | [6 empty] | 343563 | 250 | 2027-07-22
APP00161 RCS SLM s-RAD | [6 empty] | 348414 | 250 | 2027-07-22
APP00162 BPM Buttons and Housing Material | [6 empty] | 1116000 | 150 | 2026-10-19
APP00163 Profile Monitors Materials | [6 empty] | 1502064 | 150 | 2026-10-14
APP00164 BPM Electronics - V301 Module Procurement | [6 empty] | 1419227 | 250 | 2027-07-22
APP00165 Synchrotron Radiation Monitors Materials | [6 empty] | 813144 | 150 | 2026-10-14
APP00166 BPM System Misc Materials | [6 empty] | 1352538 | 250 | 2027-01-15
APP00167 Longitudinal Feedback System | [6 empty] | 1000000 | 250 | 2027-07-22
APP00168 BPM Pick-up -Button Procurement | [6 empty] | 889344 | 251 | 2027-07-22
APP00169 BPM Pick-up Materials | [6 empty] | 906069 | 200 | 2028-06-09
APP00170 BPM Electronics Construction | [6 empty] | 255518 | 350 | 2027-07-22
APP00171 Profile Monitors Construction | [6 empty] | 283000 | 250 | 2027-07-22
APP00172 ICT Material | [6 empty] | 298638 | 150 | 2026-10-14
APP00173 HSR Collimators | [6 empty] | 304786 | 250 | 2027-07-22
APP00174 BPM System Materials | [6 empty] | 936694 | 150 | 2026-10-14
APP00175 BPM Cables Material | [6 empty] | 615570 | 250 | 2026-10-14
APP00176 Charge and Current Monitors Materials | [6 empty] | 979593 | 150 | 2026-10-14
APP00177 SR SLM Materials s-Rad | [6 empty] | 497900 | 100 | 2027-07-22
APP00178 BPM Pick-up - Button & Housing Materials | [6 empty] | 924412 | 250 | 2027-07-22
APP00179 BPM System - Signal Cables, Rack Hardware, System Connectors | [6 empty] | 1109751 | 250 | 2027-07-22
APP00180 RCS Beam Position Monitors | [6 empty] | 1654808 | 250 | 2027-06-23
APP00181 Hadron Ring BPM Upgrade | [6 empty] | 598956 | 125 | 2027-01-19
APP00182 Pulsed Spectrum - Electrical Components | [6 empty] | 392950 | 300 | 2026-10-14
APP00183 Pulsed Spectrum - Mechanical Components | [6 empty] | 674000 | 100 | 2026-10-14
APP00184 RCS Injection Pulsed Bump - Kicker Magnet | [6 empty] | 270893 | 300 | 2026-10-14
APP00191 RCS Extraction Kicker | [6 empty] | 270893 | 300 | 2026-10-14
APP00192 ESR Stripline Kickers - Electrical Components | [6 empty] | 1193893 | 300 | 2026-10-14
APP00193 ESR Stripline Kickers - Mechanical Components | [6 empty] | 636187 | 100 | 2026-10-14
APP00196 ESR Injection Slow Pulsed Septum - Electrical Components | [6 empty] | 357072 | 150 | 2026-10-14
APP00197 ESR Injection Slow Pulsed Septum - Mechanical Components | [6 empty] | 686000 | 100 | 2026-11-17
APP00198 Cryogenics System Installation Contract - IR02 | [6 empty] | 5119500 | 1 | 2028-09-29
APP00199 Cryogenics System Installation Contract - IR06 | [6 empty] | 5119500 | 1 | 2028-11-14
APP00200 Cryogenics System Installation Contract - IR10 | [6 empty] | 6387720 | 482 | 2026-10-14
APP00201 4K Distribution B&P - Procurement | [6 empty] | 10975000 | 387 | 2027-06-17
APP00205 (New Code Value) | [6 empty] | 3306650 | 750 | 2025-11-14
APP00206 (New Code Value) | [6 empty] | 531000 | 100 | 2026-11-17
APP00207 (New Code Value) | [6 empty] | 500164 | 160 | 2027-04-14
APP00209 (New Code Value) | [6 empty] | 279967 | 500 | 2026-07-10
APP00210 (New Code Value) | [6 empty] | 309338 | 250 | 2025-04-10
APP00211 (New Code Value) | [6 empty] | 824552 | 10 | 2026-10-13
APP00213 (New Code Value) | [6 empty] | 300000 | 60 | 2026-10-14
APP00214 (New Code Value) | [6 empty] | 458000 | 160 | 2027-02-10
APP00215 (New Code Value) | [6 empty] | 1202000 | 190 | 2027-03-30
APP00216 (New Code Value) | [6 empty] | 602000 | 190 | 2027-03-30
APP00218 (New Code Value) | [6 empty] | 648492 | 605 | 2026-10-14
APP00219 (New Code Value) | [6 empty] | 324246 | 375 | 2026-10-14
APP00222 (New Code Value) | [6 empty] | 456178 | 375 | 2028-03-24
APP00223 (New Code Value) | [6 empty] | 1900000 | 380 | 2023-02-14
APP00224 (New Code Value) | [6 empty] | 800000 | 250 | 2023-06-14
APP00226 (New Code Value) | [6 empty] | 400000 | 200 | 2024-02-06
APP00230 (New Code Value) | [6 empty] | 750000 | 121 | 2027-10-21
APP00232 (New Code Value) | [6 empty] | 1886310 | 260 | 2026-10-14
APP00233 (New Code Value) | [6 empty] | 991400 | 60 | 2026-10-13
APP00234 (New Code Value) | [6 empty] | 1244400 | 250 | 2026-10-14
APP00235 (New Code Value) | [6 empty] | 610000 | 250 | 2026-11-25
APP00237 (New Code Value) | [6 empty] | 1675350 | 250 | 2027-03-30
APP00238 (New Code Value) | [6 empty] | 259150 | 250 | 2026-10-14
APP00239 (New Code Value) | [6 empty] | 531600 | 250 | 2027-08-24
APP00240 (New Code Value) | [6 empty] | 277875 | 250 | 2027-08-24
APP00241 (New Code Value) | [6 empty] | 387800 | 250 | 2027-08-24
APP00242 (New Code Value) | [6 empty] | 257400 | 120 | 2027-11-19
APP00243 (New Code Value) | [6 empty] | 648928 | 125 | 2028-06-12
APP00245 (New Code Value) | [6 empty] | 500000 | 250 | 2025-04-10
APP00249 (New Code Value) | [6 empty] | 1946784 | 323 | 2028-03-17
APP00250 (New Code Value) | [6 empty] | 1286600 | 120 | 2026-02-02
APP00251 (New Code Value) | [6 empty] | 1004261 | 233 | 2025-10-28
APP00252 (New Code Value) | [6 empty] | 1050880 | 565 | 2026-10-14
APP00253 (New Code Value) | [6 empty] | 1276554 | 672 | 2028-03-24
APP00254 (New Code Value) | [6 empty] | 334754 | 275 | 2027-05-19
APP00258 (New Code Value) | [6 empty] | 1050880 | 565 | 2026-10-14
APP00259 (New Code Value) | [6 empty] | 557923 | 168 | 2028-05-18
APP00261 (New Code Value) | [6 empty] | 870903 | 500 | 2024-10-18
APP00270 (New Code Value) | [6 empty] | 265000 | 20 | 2027-03-30
APP00289 (New Code Value) | [6 empty] | 880848 | 250 | 2024-08-21
APP00290 (New Code Value) | [6 empty] | 450000 | 60 | 2023-07-13
APP00297 ESR - Installation of Vacuum System | [6 empty] | 520000 | 445 | 2028-10-31
APP00304 (New Code Value) | [6 empty] | 1200000 | 1 | 2029-10-12
APP00305 (New Code Value) | [6 empty] | 1200000 | 1 | 2029-10-12
APP00306 (New Code Value) | [6 empty] | 1200000 | 1 | 2029-10-12
APP00307 (New Code Value) | [6 empty] | 1200000 | 1 | 2029-10-12
APP00308 (New Code Value) | [6 empty] | 802800 | 1 | 2029-11-06
APP00309 (New Code Value) | [6 empty] | 1225200 | 1 | 2029-05-16
APP00310 (New Code Value) | [6 empty] | 956400 | 1 | 2028-09-15
APP00311 (New Code Value) | [6 empty] | 260000 | 1 | 2024-10-07
APP00312 (New Code Value) | [6 empty] | 600000 | 1 | 2025-04-03
APP00313 (New Code Value) | [6 empty] | 527000 | 1 | 2025-06-27
APP00314 (New Code Value) | [6 empty] | 573000 | 1 | 2027-03-08
APP00424 Injection System - RCS Vacuum | [6 empty] | 370000 | 380 | 2028-12-08
APP00472 SHC Chicane Feedbox Procurement | [6 empty] | 500000 | 180 | 2026-09-23
APP00498 (New Code Value) | [6 empty] | 6165500 | 300 | 2026-10-14
APP00514 Cryo Installation - IR06 | [6 empty] | 1200000 | 1 | 2029-10-12
JLab Scope | [6 empty] | 5100000 | 1513 | 2022-05-02
APP00470 (New Code Value) | [6 empty] | 1500000 | 293 | 2022-05-02
No EIC_APP CODE | [6 empty] | 3600000 | 400 | 2026-10-13

## ICR-002
Sum of Budgeted Material Cost |  |  |  | Subject to Commodity Price Fluctuations? | Likely Foreign Supplier? | 0 | 0
Procurement Code | WBS Name | Activity ID | Total
A.PP001.A | Crab: Production Procurement, Assembly, Test | IR_0205_2290 | 62510.08 |  | x | IR_0205_2290 | 0
A.PP001.B | Crab: Production Procurement, Assembly, Test | IR_0205_2320 | 569900.31 |  |  | 0 | 0
| IR Vacuum | IR_0204_1160 | 2614119.1 |  | x | IR_0204_1160 | 0
A.PP002 | DAQ / Computing | DE_0900_3101 | 3751144.22 |  |  | 0 | 0
A.PP003 | Cooling R&D | RD_0310_1680 | 423040.48 |  |  | 0 | 0
| IR Warm Magnets | IR_0213_1080 | 2707204.01 |  | x | IR_0213_1080 | 0
A.PP004 | RCS Vacuum Pumps | EJ_0203_1660 | 3480017.05 |  |  | 0 | 0
A.PP005 | IR Integration & Auxiliary Detectors | DE_1100_3080 | 2921805.49 |  |  | 0 | 0
A.PP006 | Tracking | DE_0300_3150 | 3590010.69 |  | x | DE_0300_3150 | 0
A.PP007.A | CS: 591 MHz 5-Cell Procurement | EJ_0204_1120 | 2228465.98 |  |  | 0 | 0
A.PP007.B | CM: 591 MHz 5-Cell Procurement | EJ_0204_1180 | 3334145.49 |  |  | 0 | 0
A.PP008 | Detector R&D and Physics Design | DE_0200_2110 | 1057855.48 |  |  | 0 | 0
|  | DE_0200_2120 | 1057856.63 |  | x | DE_0200_2120 | 0
|  | DE_0200_2130 | 1057856.63 |  |  | 0 | 0
A.PP009 | ESR Sextupole Magnets | SR_0200_2120 | 2741819.16 |  | x | SR_0200_2120 | 0
|  | SR_0200_2220 | 2741819.16 |  |  | 0 | 0
A.PP011 | Infrastructure Construction Management & Inspection | IF_0103_1300 | 434875.12 |  | x | IF_0103_1300 | 0
|  | IF_0103_1320 | 720278.18 |  |  | 0 | 0
|  | IF_0103_1340 | 736844.71 |  | x | IF_0103_1340 | 0
|  | IF_0103_1360 | 376896.11 |  |  | 0 | 0
A.PP012 | IR Power Supplies | IR_0203_1100 | 930178.73 |  | x | IR_0203_1100 | 0
|  | IR_0203_1440 | 1345713.74 |  |  | 0 | 0
A.PP013 | Collared Magnets | IR_0212_1080 | 2364060.39 |  |  | 0 | 0
A.PP014 | Main Substation #9 | IF_0301_1620 | 45847.32 | X | X
|  | IF_0301_2005 | 3879697.47 |  |  | 0 | 0
|  | IF_0301_2015 | 22408.26 |  |  | 0 | 0
A.PP016 | Collared Magnets | IR_0212_1260 | 2368382.41 |  |  | 0 | 0
A.PP017 | Collared Magnets | IR_0212_1440 | 2368382.41 |  |  | 0 | 0
A.PP018 | Collared Magnets | IR_0212_1620 | 2525581.05 |  | x | IR_0212_1620 | 0
A.PP019 | Collared Magnets | IR_0212_1800 | 2525581.05 |  |  | 0 | 0
A.PP020 | Main Substation #9 | IF_0301_1520 | 2622520.19 |  |  | 0 | 0
A.PP021 | Cooling R&D | RD_0310_1185 | 204600 |  |  | 0 | 0
|  | RD_0310_1186 | 306900 |  | x | RD_0310_1186 | 0
|  | RD_0310_1187 | 624937.06 |  |  | 0 | 0
|  | RD_0310_1193 | 880750.13 |  | x | RD_0310_1193 | 0
|  | RD_0310_1194 | 234461.18 |  |  | 0 | 0
|  | RD_0310_1195 | 53529.95 |  | x | RD_0310_1195 | 0
A.PP022 | 400 MeV Injector Power Supplies | EJ_040102_1280 | 837074.55 |  |  | 0 | 0
| Electron Storage Ring Power Supplies | SR_0300_1260 | 1857610.76 |  | x | SR_0300_1260 | 0
| Hadron Ring Straight Sections Modifications Power Supplies | HR_0202_1100 | 33612.39 |  |  | 0 | 0
| HR Injection System Upgrade Power Supplies | HR_0402_2620 | 14726.71 |  |  | 0 | 0
| SHC Power Supplies and Cables | HR_0809_1460 | 440456.76 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_3580 | 151748.74 |  |  | 0 | 0
|  | IR_0302_4220 | 39057.6 |  |  | 0 | 0
A.PP023 | 400 MeV Injector Power Supplies | EJ_040102_1500 | 42171.77 |  |  | 0 | 0
| Electron Storage Ring Power Supplies | SR_0300_1880 | 2565832.04 |  |  | 0 | 0
| HR Injection System Upgrade Power Supplies | HR_0402_2360 | 106900.09 |  |  | 0 | 0
|  | HR_0402_2800 | 185244.6 |  |  | 0 | 0
| SHC Power Supplies and Cables | HR_0809_1660 | 390095.89 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_3780 | 288795.41 |  |  | 0 | 0
A.PP024.A | SSA: Crab: 394 MHz | IR_0205_5170 | 639378.65 |  |  | 0 | 0
A.PP024.B | SSA: Crab: 394 MHz | IR_0205_5200 | 3230925.97 |  |  | 0 | 0
A.PP025 | ESR Machine Protection - Single Turn Extraction Kicker | EJ_0305_9100 | 2477009.06 |  |  | 0 | 0
A.PP026 | Construction of Vacuum Fabrication Facility | SR_0407_1160 | 2330459.04 |  |  | 0 | 0
A.PP027 | Hadron Ring Straight Sections Modifications Vacuum System | HR_0203_1540 | 2270201.88 |  |  | 0 | 0
A.PP028 | RCS Sextupole Magnets | EJ_0201_2280 | 3744656.71 |  |  | 0 | 0
A.PP029 | RCS Sextupole Magnets | EJ_0201_2380 | 3744656.71 |  |  | 0 | 0
A.PP030 | Particle Identification | DE_0400_4244 | 2073827.18 |  | x | DE_0400_4244 | 0
|  | DE_0400_4261 | 464110.6 |  |  | 0 | 0
A.PP042 | SHC Beam Transport Magnets | HR_0804_1080 | 7693616.31 |  | x | HR_0804_1080 | 0
A.PP048 | RCS Vacuum Chamber and Bellows | EJ_0203_1220 | 4463935.67 |  |  | 0 | 0
A.PP054.A | SSA: Crab: 197 MHz | IR_0205_2170 | 623020.38 |  |  | 0 | 0
A.PP054.B | SSA: Crab: 197 MHz | IR_0205_2200 | 4421597.86 |  |  | 0 | 0
A.PP057 | HR Injection System Upgrade Pulsed Devices | HR_0404_2000 | 3474713.91 |  |  | 0 | 0
A.PP064 | HR SC Magnet Beam Pipe Upgrade | HR_0500_2080 | 2264534.4 |  |  | 0 | 0
A.PP068 | Standby Power | IF_0305_1060 | 1867334.88 |  |  | 0 | 0
|  | IF_0305_1380 | 1630759.52 |  |  | 0 | 0
A.PP069 | Controls - Hardware Procurements - Network | AS_0302_1180 | 3640950.11 |  | x | AS_0302_1180 | 0
A.PP071 | Matching Magnets | IR_0207_1100 | 2331783.33 |  |  | 0 | 0
|  | IR_0207_1120 | 2350962.17 |  | x | IR_0207_1120 | 0
|  | IR_0207_1140 | 408062.08 |  |  | 0 | 0
|  | IR_0207_1160 | 411418.38 |  | x | IR_0207_1160 | 0
A.PP080.A | CS: 1773 MHz 5-Cell Procurement | HR_0805_5100 | 1602446.52 |  |  | 0 | 0
A.PP080.B | CM: 1773 MHz 5-Cell Procurement | HR_0805_5160 | 2641489.44 |  |  | 0 | 0
A.PP082 | Motor Control & Load Centers | IF_0304_1360 | 1199513 | X | X
|  | IF_0304_1460 | 2020399.72 |  |  | 0 | 0
|  | IF_0304_1580 | 1079561.7 |  |  | 0 | 0
|  | IF_0304_1620 | 299878.25 |  |  | 0 | 0
|  | IF_0304_1740 | 329746.12 |  |  | 0 | 0
|  | IF_0304_1780 | 402110.89 |  |  | 0 | 0
A.PP088 | RCS Quad Magnets | EJ_0201_1820 | 4511558.47 |  |  | 0 | 0
A.PP093 | SSA: ERL Main Linac Fundamental | HR_0805_1180 | 3665169.73 |  | x | HR_0805_1180 | 0
A.PP097 | New LINAC Tunnel 1002 | IF_0202_1080 | 742352.93 |  |  | 0 | 0
|  | IF_0202_1100 | 1420352.27 |  |  | 0 | 0
|  | IF_0202_1120 | 922527.17 |  |  | 0 | 0
A.PP107 | RCS Quad Magnets | EJ_0201_1920 | 4511558.47 |  |  | 0 | 0
A.PP112 | ESR Magnet Quad #1 | SR_0200_1680 | 4693902.52 |  |  | 0 | 0
A.PP113 | ESR Magnet Quad #2 | SR_0200_1780 | 4693902.52 |  |  | 0 | 0
A.PP129 | Tracking | DE_0300_3171 | 3817885.63 |  |  | 0 | 0
|  | DE_0300_3172 | 833530.05 |  | x | DE_0300_3172 | 0
A.PP142 | Detector Magnets | DE_0700_3560 | 5664490.69 | X
D.APP01 | RCS Power Supplies | EJ_0202_1300 | 6687017.32 |  |  | 0 | 0
D.APP02 | RCS Power Supplies | EJ_0202_1460 | 6872561.99 |  |  | 0 | 0
D.APP03 | RCS Power Supplies | EJ_0202_1620 | 8758372.39 |  |  | 0 | 0
D.APP04 | CM: 591 MHz 5-Cell Procurement | HR_0805_1000 | 13680970.66 |  |  | 0 | 0
D.APP05 | Direct Wind Magnets | IR_0211_1120 | 167646.28 |  |  | 0 | 0
|  | IR_0211_1300 | 196385.99 |  |  | 0 | 0
|  | IR_0211_1440 | 121541.28 |  | x | IR_0211_1440 | 0
|  | IR_0211_1620 | 156869.02 |  |  | 0 | 0
|  | IR_0211_1800 | 183761.18 |  |  | 0 | 0
|  | IR_0211_1940 | 113728.64 |  |  | 0 | 0
|  | IR_0211_2120 | 131266.47 |  |  | 0 | 0
|  | IR_0211_2300 | 153769.96 |  |  | 0 | 0
|  | IR_0211_2440 | 95166.76 |  | x | IR_0211_2440 | 0
|  | IR_0211_2620 | 765364.2 |  |  | 0 | 0
|  | IR_0211_2800 | 911177.07 |  | x | IR_0211_2800 | 0
|  | IR_0211_2940 | 562327.11 |  |  | 0 | 0
|  | IR_0211_3120 | 92420.91 |  | x | IR_0211_3120 | 0
|  | IR_0211_3300 | 110754.62 |  |  | 0 | 0
|  | IR_0211_3440 | 68545.4 |  |  | 0 | 0
|  | IR_0211_3620 | 163641.13 |  |  | 0 | 0
|  | IR_0211_3800 | 194703.25 |  |  | 0 | 0
|  | IR_0211_3940 | 120500.51 | X | X
|  | IR_0211_4120 | 193956.64 |  |  | 0 | 0
|  | IR_0211_4300 | 228167.21 |  |  | 0 | 0
|  | IR_0211_4440 | 141212.04 |  |  | 0 | 0
|  | IR_0211_4620 | 83583.1 |  |  | 0 | 0
|  | IR_0211_4800 | 97911.54 |  |  | 0 | 0
|  | IR_0211_4940 | 60596.4 |  |  | 0 | 0
|  | IR_0211_5120 | 82513.48 |  |  | 0 | 0
|  | IR_0211_5300 | 68884.84 |  |  | 0 | 0
|  | IR_0211_5440 | 51067.13 |  |  | 0 | 0
|  | IR_0211_5620 | 143502.11 | X
|  | IR_0211_5800 | 120711.93 |  |  | 0 | 0
|  | IR_0211_5940 | 89663.1 | X
|  | IR_0211_6120 | 387454.56 |  |  | 0 | 0
|  | IR_0211_6300 | 328385.76 | X
|  | IR_0211_6440 | 245308.14 |  |  | 0 | 0
D.APP06 | Tower Water Systems | IF_0403_1100 | 2543921.25 | X
|  | IF_0403_1140 | 1023302.19 |  | x | IF_0403_1140 | 0
|  | IF_0403_1260 | 2091552.26 |  | x | IF_0403_1260 | 0
|  | IF_0403_1300 | 1023302.19 |  |  | 0 | 0
|  | IF_0403_1420 | 1579235.57 |  |  | 0 | 0
|  | IF_0403_1460 | 1023302.19 |  |  | 0 | 0
|  | IF_0403_1520 | 1903422.07 |  |  | 0 | 0
|  | IF_0403_1560 | 1023302.19 |  |  | 0 | 0
|  | IF_0403_1620 | 252115.33 |  |  | 0 | 0
|  | IF_0403_1660 | 1023302.19 |  |  | 0 | 0
D.APP07 | Electronics | DE_0800_3080 | 10219967.4 |  |  | 0 | 0
D.APP08 | Detector Infrastructure | DE_1000_3150 | 14841184.05 |  |  | 0 | 0
D.APP09.A | 400 MeV Injector RF Systems | EJ_0401_2270 | 2006162.05 |  |  | 0 | 0
D.APP09.B | 400 MeV Injector RF Systems | EJ_0401_2280 | 18683148.29 |  |  | 0 | 0
D.APP10.A | CM: 394 MHz Crab Procurement | IR_0205_5050 | 2260028.99 |  |  | 0 | 0
D.APP10.B | CM: 394 MHz Crab Procurement | IR_0205_5080 | 9082129.03 |  |  | 0 | 0
D.APP11 | Electromagnetic Calorimetry | DE_0500_3080 | 1128333.57 | X
|  | DE_0500_3082 | 2908402.76 |  | x | DE_0500_3082 | 0
|  | DE_0500_3375 | 2084316.97 | X
|  | DE_0500_3380 | 1405125.22 |  | x | DE_0500_3380 | 0
D.APP12.A | CS: 197 MHz Crab FA Procurement | IR_0205_2050 | 4401888.26 | X
D.APP12.B | CM: 197 MHz Crab Procurement | IR_0205_2080 | 10838512.22 |  | x | IR_0205_2080 | 0
D.APP14 | Tunnel Modifications | IF_0207_1000 | 2757151.99 | X
|  | IF_0207_1020 | 1276233.51 |  |  | 0 | 0
|  | IF_0207_1040 | 3332029.9 |  |  | 0 | 0
|  | IF_0207_1060 | 1266569.04 | X
|  | IF_0207_1080 | 2992561.14 |  |  | 0 | 0
D.APP15 | RCS Dipole Magnets | EJ_0201_1360 | 8969230.05 | X
D.APP16 | ESR Dipole Magnets | SR_0200_1320 | 17278509.32 |  |  | 0 | 0
D.APP18 | ESR Dipole Magnets | SR_0200_1220 | 17278509.32 |  |  | 0 | 0
D.APP19 | Overhead 13.8kV & Switching | IF_0302_1100 | 4830316.92 |  |  | 0 | 0
| Unit Substations | IF_0303_1240 | 3804532.11 |  |  | 0 | 0
|  | IF_0303_1245 | 759528.48 |  |  | 0 | 0
D.APP20 | 138kV Substation | IF_0307_1080 | 1995232.59 |  |  | 0 | 0
|  | IF_0307_1120 | 56020.65 |  |  | 0 | 0
|  | IF_0307_1200 | 343854.9 | X
|  | IF_0307_1240 | 812754.27 |  |  | 0 | 0
|  | IF_0307_1320 | 14893464.56 |  |  | 0 | 0
|  | IF_0307_1340 | 225810.62 |  |  | 0 | 0
D.APP23 | RCS Power Supplies | EJ_0202_1120 | 11879550.95 |  |  | 0 | 0
D.APP24 | Procurement - Distribution Lines | AS_0201_1160 | 198908.48 | X
|  | AS_0207_1080 | 1208688.55 |  |  | 0 | 0
| Procurement - IR02 | HR_0808_1200 | 3351644.47 |  |  | 0 | 0
| Procurement - IR06 | AS_0204_1200 | 4055557.04 |  |  | 0 | 0
| Procurement - IR10 | AS_0205_1200 | 4207555.72 |  |  | 0 | 0
| Reconfiguration Existing and New 4k Distribution - Installation | AS_0203_1260 | 2015824.86 |  |  | 0 | 0
D.APP25 | Installation - IR02 | HR_0808_1260 | 3393864.58 |  |  | 0 | 0
| Installation - IR06 | AS_0204_1320 | 5401194.42 |  |  | 0 | 0
| Installation - IR10 | AS_0205_1260 | 4455699.15 |  |  | 0 | 0
| Reconfiguration Existing and New 4k Distribution - Installation | AS_0201_1180 | 45645.85 |  |  | 0 | 0
|  | AS_0203_1280 | 527011.86 |  |  | 0 | 0
|  | AS_0207_1100 | 205766.25 |  |  | 0 | 0
D.APP27 | ESR Vacuum Pumps | SR_0403_1160 | 8836611.38 |  |  | 0 | 0
D.APP29 | Electron Storage Ring Power Supplies | SR_0300_1080 | 10056290.41 |  | x | SR_0300_1080 | 0
|  | SR_0300_1085 | 771432.36 | X
|  | SR_0300_1086 | 51493.06 |  |  | 0 | 0
| IR Power Supplies | IR_0203_1300 | 343204.91 |  |  | 0 | 0
D.APP30 | 400 MeV Injector Power Supplies | EJ_040102_1080 | 1293244.55 |  |  | 0 | 0
| Electron Storage Ring Power Supplies | SR_0300_1660 | 3432175.67 |  |  | 0 | 0
| HR Injection System Upgrade Power Supplies | HR_0402_1940 | 70312.64 |  |  | 0 | 0
|  | HR_0402_2600 | 116891.57 |  |  | 0 | 0
| IR Power Supplies | IR_0203_1080 | 448577.69 |  | x | IR_0203_1080 | 0
| SHC Power Supplies and Cables | HR_0809_1260 | 1674571.51 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_3120 | 129026.76 |  | x | IR_0302_3120 | 0
|  | IR_0302_3980 | 260045.62 |  |  | 0 | 0
D.APP33 | RCS Dipole Magnets | EJ_0201_1460 | 8969230.05 |  |  | 0 | 0
D.APP34 | Infrastructure Engineering | IF_2102_1140 | 5451225.29 |  |  | 0 | 0
|  | IF_2102_1160 | 4122119.87 |  |  | 0 | 0
|  | IF_2102_1180 | 836892.59 |  |  | 0 | 0
|  | IF_2102_1200 | 1025894.89 |  |  | 0 | 0
|  | IF_2102_1220 | 1570432.69 |  |  | 0 | 0
|  | IF_2102_1240 | 1606552.76 |  |  | 0 | 0
|  | IF_2102_1260 | 821751.35 |  |  | 0 | 0
|  | IF_2102_1280 | 840651.4 |  |  | 0 | 0
|  | IF_2102_1300 | 860012.67 |  |  | 0 | 0
|  | IF_2102_1320 | 879765.87 |  |  | 0 | 0
|  | IF_2102_1340 | 520974.94 |  |  | 0 | 0
D.APP35 | ESR Girders and Integrated Assembly | SR_0200_2700 | 11061043.34 |  |  | 0 | 0
D.APP36 | RCS Girders, Assembly and Integration | EJ_0201_2840 | 8714138.36 |  |  | 0 | 0
|  | EJ_0201_2845 | 748871.27 |  |  | 0 | 0
D.APP37 | Particle Identification | DE_0400_4161 | 6412812.38 |  |  | 0 | 0
D.APP38 | Hadronic Calorimetry | DE_0600_3072 | 2062668.16 |  |  | 0 | 0
|  | DE_0600_3073 | 7947152.73 |  |  | 0 | 0
|  | DE_0600_3074 | 8324676.29 | X
D.APP41.A | SSA: ERL Injector: Fundamental | HR_0805_6170 | 1113908.86 |  |  | 0 | 0
D.APP41.B | SSA: ERL Injector: Fundamental | HR_0805_6200 | 6879421.46 |  |  | 0 | 0
D.APP42 | Electron Storage Ring Power Supplies | SR_0300_1460 | 5346119.49 |  |  | 0 | 0
| Hadron Ring Straight Sections Modifications Power Supplies | HR_0202_1080 | 403348.68 |  |  | 0 | 0
|  | HR_0202_1420 | 229357.5 |  |  | 0 | 0
|  | HR_0202_1720 | 184141.38 |  |  | 0 | 0
| HR Injection System Upgrade Power Supplies | HR_0402_1080 | 134449.56 |  |  | 0 | 0
|  | HR_0402_1420 | 57790.9 |  |  | 0 | 0
|  | HR_0402_2140 | 1147109.08 | X
|  | HR_0402_3040 | 168061.95 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_3400 | 84030.98 |  |  | 0 | 0
D25.APP01.A | 1002 Pre-injector & SHC Bldg | IF_0204_1140 | 4942938.81 |  |  | 0 | 0
| 1002H - EIC Injection LINAC Building | IF_0204_1060 | 3997824.41 |  |  | 0 | 0
| 1002I - EIC Cryogenics Building | IF_0203_1060 | 262290.23 |  |  | 0 | 0
| 1006G - EIC 6 O’Clock Cryo Facility | IF_0203_1140 | 160706.32 |  |  | 0 | 0
| 1010C - EIC RF Power Amplifier Building | IF_0204_1300 | 4949850.89 |  |  | 0 | 0
| 1010D - EIC 10 O'Clock DI Pumphouse | IF_0204_1220 | 311419.07 |  |  | 0 | 0
| 1010E - EIC 10 O'Clock Cryo Facility | IF_0203_1220 | 324940.59 |  |  | 0 | 0
| Access Roads, Paving and Sitework | IF_0208_1000 | 1167024.42 | X
| CRYO1002 - Cryogenic Plant (A-106, S-105) | IF_0202_1060 | 3864171.45 |  |  | 0 | 0
D25.APP01.B | 1001A - EIC 1 O-Clock Power Supply Building | IF_0205_1060 | 2501273.9 |  |  | 0 | 0
| 1003A - EIC 3 O-Clock Power Supply Building | IF_0205_1140 | 2501273.9 |  |  | 0 | 0
| 1005T - EIC 5 O-Clock Power Supply Building | IF_0205_1220 | 3499942 |  |  | 0 | 0
| 1007A - EIC 7 O-Clock Power Supply Building | IF_0205_1300 | 4708055.56 |  |  | 0 | 0
| 1009A - EIC 9 O-Clock Power Supply Building | IF_0205_1380 | 2501273.9 |  |  | 0 | 0
| 1012C - EIC Kicker Power Supply Building | IF_0206_1140 | 2541963.39 |  |  | 0 | 0
| Alcove Building | IF_0205_1460 | 198205 |  |  | 0 | 0
| B1004 - Kicker Power (A-103, S-103) | IF_0206_1060 | 1367584.29 |  |  | 0 | 0
D25.APP02.A | 1002 Pre-injector & SHC Bldg | IF_0204_1080 | 369942.59 | X
|  | IF_0204_1100 | 3514287.63 |  |  | 0 | 0
|  | IF_0204_1120 | 5274371.97 | X | X
| 1002H - EIC Injection LINAC Building | IF_0204_1000 | 160676.19 |  |  | 0 | 0
|  | IF_0204_1020 | 4092050.79 |  |  | 0 | 0
|  | IF_0204_1040 | 2668670.59 |  |  | 0 | 0
| 1002I - EIC Cryogenics Building | IF_0203_1000 | 16426.37 |  |  | 0 | 0
|  | IF_0203_1020 | 89043.7 |  |  | 0 | 0
|  | IF_0203_1040 | 157643.55 |  |  | 0 | 0
| 1006G - EIC 6 O’Clock Cryo Facility | IF_0203_1080 | 11831.56 |  | x | IF_0203_1080 | 0
|  | IF_0203_1100 | 47872.47 |  |  | 0 | 0
|  | IF_0203_1120 | 114017.7 |  |  | 0 | 0
| 1010C - EIC RF Power Amplifier Building | IF_0204_1240 | 39360.11 |  |  | 0 | 0
|  | IF_0204_1260 | 3711057.62 |  |  | 0 | 0
|  | IF_0204_1280 | 1993546.92 |  |  | 0 | 0
| 1010D - EIC 10 O'Clock DI Pumphouse | IF_0204_1160 | 22400.42 |  |  | 0 | 0
|  | IF_0204_1180 | 180451.23 |  |  | 0 | 0
|  | IF_0204_1200 | 169379.49 |  |  | 0 | 0
| 1010E - EIC 10 O'Clock Cryo Facility | IF_0203_1160 | 8817.8 |  |  | 0 | 0
|  | IF_0203_1180 | 16809.92 |  |  | 0 | 0
|  | IF_0203_1200 | 134685.67 |  |  | 0 | 0
| Concrete Foundations for Externally Mounted Equipment | IF_0204_1320 | 69960 |  | x | IF_0204_1320 | 0
|  | IF_0204_1340 | 103013.29 |  |  | 0 | 0
|  | IF_0204_1360 | 22352.55 |  | x | IF_0204_1360 | 0
| CRYO1002 - Cryogenic Plant (A-106, S-105) | IF_0202_1000 | 76320.29 |  |  | 0 | 0
|  | IF_0202_1020 | 4684985.19 |  |  | 0 | 0
|  | IF_0202_1040 | 2322001.71 |  |  | 0 | 0
D25.APP02.B | 1001A - EIC 1 O-Clock Power Supply Building | IF_0205_1000 | 37167.46 |  |  | 0 | 0
|  | IF_0205_1020 | 331013.7 |  |  | 0 | 0
|  | IF_0205_1040 | 442436.43 |  |  | 0 | 0
| 1003A - EIC 3 O-Clock Power Supply Building | IF_0205_1080 | 37395.43 |  |  | 0 | 0
|  | IF_0205_1100 | 338627.16 |  |  | 0 | 0
|  | IF_0205_1120 | 448486.51 |  |  | 0 | 0
| 1005T - EIC 5 O-Clock Power Supply Building | IF_0205_1160 | 124119.01 |  |  | 0 | 0
|  | IF_0205_1180 | 472687.02 |  |  | 0 | 0
|  | IF_0205_1200 | 923974.79 |  |  | 0 | 0
| 1007A - EIC 7 O-Clock Power Supply Building | IF_0205_1240 | 70288.53 |  |  | 0 | 0
|  | IF_0205_1260 | 460190.18 |  |  | 0 | 0
|  | IF_0205_1280 | 1169816.15 |  |  | 0 | 0
| 1009A - EIC 9 O-Clock Power Supply Building | IF_0205_1320 | 38022.33 |  |  | 0 | 0
|  | IF_0205_1340 | 338627.16 |  |  | 0 | 0
|  | IF_0205_1360 | 448486.51 |  |  | 0 | 0
| 1012C - EIC Kicker Power Supply Building | IF_0206_1080 | 50452.68 |  |  | 0 | 0
|  | IF_0206_1100 | 727455.99 |  |  | 0 | 0
|  | IF_0206_1120 | 920834.25 |  |  | 0 | 0
| Access Roads, Paving and Sitework | IF_0208_1160 | 611060.93 |  |  | 0 | 0
|  | IF_0208_1180 | 12041.08 |  |  | 0 | 0
|  | IF_0208_1200 | 9617.63 |  |  | 0 | 0
|  | IF_0208_1240 | 941680.24 |  |  | 0 | 0
|  | IF_0208_1260 | 12041.08 |  |  | 0 | 0
|  | IF_0208_1280 | 14398.43 |  |  | 0 | 0
| Alcove Building | IF_0205_1400 | 17906.82 |  |  | 0 | 0
|  | IF_0205_1420 | 80526.23 |  |  | 0 | 0
|  | IF_0205_1440 | 194667.72 |  |  | 0 | 0
| B1004 - Kicker Power (A-103, S-103) | IF_0206_1000 | 48240.55 |  |  | 0 | 0
|  | IF_0206_1020 | 354300.07 |  |  | 0 | 0
|  | IF_0206_1040 | 577226.93 |  |  | 0 | 0
D25.APP03 | IR Spin Rotator Magnets | IR_0202_1140 | 34249565.45 |  |  | 0 | 0
D25.APP04.A | CS: 591 MHz FA Procurement | SR_0501_1120 | 2003743.65 |  |  | 0 | 0
D25.APP04.B | CM: 591 MHz 1-Cell Procurement | SR_0501_1180 | 23790368.94 |  |  | 0 | 0
D25.APP05 | ESR Vacuum Chamber and Bellows | SR_0401_1180 | 26417734.41 |  |  | 0 | 0
D25.APP06 | Procurement - Satellite Refrigerators | AS_0204_1260 | 9849103.62 |  |  | 0 | 0
|  | AS_0205_1220 | 11389693.24 |  |  | 0 | 0
|  | HR_0808_1220 | 11694967 |  |  | 0 | 0
D25.APP07 | Low Conductivity Water Systems | IF_0402_1081 | 1646575.75 |  |  | 0 | 0
|  | IF_0402_1083 | 1061302.42 |  |  | 0 | 0
|  | IF_0402_1085 | 497800 |  |  | 0 | 0
|  | IF_0402_1088 | 450397.29 |  |  | 0 | 0
|  | IF_0402_1100 | 4309552.67 |  |  | 0 | 0
|  | IF_0402_1140 | 2681568.2 |  |  | 0 | 0
|  | IF_0402_1162 | 489599.68 |  |  | 0 | 0
|  | IF_0402_1166 | 234929.94 |  |  | 0 | 0
|  | IF_0402_1420 | 1379345.59 |  | x | IF_0402_1420 | 0
|  | IF_0402_1460 | 757423.83 |  |  | 0 | 0
|  | IF_0402_1620 | 1457825.01 |  |  | 0 | 0
|  | IF_0402_1740 | 848914.54 |  |  | 0 | 0
|  | IF_0402_1762 | 495380.93 |  |  | 0 | 0
|  | IF_0402_1766 | 262070.8 |  |  | 0 | 0
|  | IF_0402_1880 | 501838.71 |  |  | 0 | 0
|  | IF_0402_2000 | 308350.41 |  |  | 0 | 0
|  | IF_5000_5120 | 4895027.41 |  |  | 0 | 0
|  | IF_5000_5600 | 1301412.86 |  |  | 0 | 0
|  | IF_5000_5606 | 1301412.86 |  |  | 0 | 0
|  | IF_5000_5640 | 1306971.7 |  |  | 0 | 0
|  | IF_5000_5660 | 1331345.11 |  |  | 0 | 0
|  | IF_5000_5710 | 1331345.11 |  |  | 0 | 0
|  | IF_5000_5730 | 1331345.11 |  |  | 0 | 0
D50.APP01.A | SSA: 591 MHz, 400 kW with 200 kW Variant | SR_0501_1360 | 11018953.51 |  |  | 0 | 0
D50.APP01.B | SSA: 591 MHz, 400 kW with 200 kW Variant | SR_0501_1420 | 26649271.63 |  |  | 0 | 0
D50.APP01.C | SSA: 591 MHz, 400 kW with 200 kW Variant | SR_0501_1482 | 48362472.12 |  |  | 0 | 0
S.P001 | RCS Beam Position Monitors | EJ_0205_1440 | 1885625.25 |  |  | 0 | 0
S.P002 | RCS Dipole Magnets | EJ_0201_1240 | 273805.75 |  |  | 0 | 0
S.P003 | RCS Quad Magnets | EJ_0201_1700 | 264941.88 |  |  | 0 | 0
S.P004 | 400 MeV Injector Vacuum | EJ_0401_1150 | 1002655.44 |  |  | 0 | 0
S.P005 | Transfer Lines Magnets | EJ_0301_1120 | 560206.5 |  |  | 0 | 0
S.P006 | Detector R&D and Physics Design | DE_0200_2260 | 1490472.75 |  |  | 0 | 0
| SHC Design | HR_0801_1510 | 308594.09 |  |  | 0 | 0
S.P007 | IR Magnet Cryostats | IR_0215_1040 | 1520726.58 |  |  | 0 | 0
S.P008 | HR Injection System Upgrade Pulsed Devices | HR_0404_1820 | 1734171.07 |  |  | 0 | 0
S.P009 | SHC Beam Transport Magnets | HR_0804_1200 | 3096066.76 |  |  | 0 | 0
S.P010 | RCS Corrector Magnets | EJ_0201_2620 | 1739674.95 |  |  | 0 | 0
S.P012 | IR Spin Rotator Magnets | IR_0202_1380 | 867102.28 |  |  | 0 | 0
S.P013 | HR Injection System Upgrade Magnets | HR_0401_1080 | 560206.5 |  |  | 0 | 0
S.P015 | Cables | IR_0208_1720 | 689906.63 |  |  | 0 | 0
S.P016.A | Crab: Production Procurement, Assembly, Test | IR_0205_5290 | 63947.84 |  |  | 0 | 0
S.P016.B | Crab: Production Procurement, Assembly, Test | IR_0205_5320 | 390533.05 |  |  | 0 | 0
S.P017 | Chilled Water Systems | IF_0401_1100 | 112041.3 |  |  | 0 | 0
|  | IF_0401_1140 | 410390.75 |  |  | 0 | 0
|  | IF_0401_1200 | 224082.6 |  |  | 0 | 0
|  | IF_0401_1240 | 839659.1 |  |  | 0 | 0
|  | IF_0401_1280 | 112041.3 |  |  | 0 | 0
|  | IF_0401_1320 | 413222.39 |  |  | 0 | 0
S.P018 | Hadron Ring Straight Sections Modifications Power Supplies | HR_0202_1960 | 321270.85 |  |  | 0 | 0
S.P019 | SHC Chicanes | HR_0810_1020 | 795060.09 |  |  | 0 | 0
S.P021 | Controls - Hardware Procurements - Diagnostics | AS_0305_2220 | 527266.36 |  | x | AS_0305_2220 | 0
S.P022 | RCS Injection - Pulsed Bump | EJ_0305_1080 | 302261.01 |  |  | 0 | 0
S.P023 | RCS Extraction - Kicker | EJ_0305_4100 | 306886.15 |  |  | 0 | 0
S.P024 | RCS Extraction - Pulsed Septum | EJ_0305_5080 | 438451.13 |  | x | EJ_0305_5080 | 0
S.P025 | RCS Magnet Measuring Stations | EJ_0201_2980 | 973569.46 |  |  | 0 | 0
S.P026 | Transfer Lines Magnets | EJ_0301_1340 | 448165.2 |  |  | 0 | 0
S.P027 | HR SC Magnet Beam Pipe Upgrade | HR_0500_1100 | 361423.59 |  |  | 0 | 0
S.P028 | Hadron Ring Straight Sections Modifications Vacuum System | HR_0203_1420 | 363346.67 |  | x | HR_0203_1420 | 0
S.P029 | RCS Extraction - Pulsed Septum | EJ_0305_5220 | 755158.36 |  |  | 0 | 0
S.P030 | Motor Control & Load Centers | IF_0304_1120 | 1439415.6 |  |  | 0 | 0
S.P031 | 400 MeV Injector Vacuum | EJ_0401_1680 | 396128.16 |  |  | 0 | 0
S.P032 | ESR Injection & Extraction - Strip-line Kickers | EJ_0305_6100 | 1352523.77 |  |  | 0 | 0
S.P038 | ESR Injection & Extraction - Strip-line Kickers | EJ_0305_6260 | 713611.54 |  |  | 0 | 0
S.P040 | Main Substation #9 | IF_0301_1780 | 894599.36 |  |  | 0 | 0
S.P041 | Unit Substations | IF_0303_1120 | 1644646.26 |  |  | 0 | 0
S.P042 | Cable Plant | IF_0306_1080 | 81790.28 |  |  | 0 | 0
|  | IF_0306_1370 | 289256.02 |  |  | 0 | 0
|  | IF_0306_1440 | 456415.43 |  |  | 0 | 0
S.P043 | 400 MeV Injector Power Supplies | EJ_040102_1180 | 159540.67 |  |  | 0 | 0
| Electron Storage Ring Power Supplies | SR_0300_1360 | 137541.96 |  |  | 0 | 0
|  | SR_0300_1560 | 68770.98 |  |  | 0 | 0
|  | SR_0300_1760 | 378240.39 |  |  | 0 | 0
| Hadron Ring Straight Sections Modifications Power Supplies | HR_0202_1200 | 3363.17 |  |  | 0 | 0
|  | HR_0202_1480 | 4481.65 |  |  | 0 | 0
|  | HR_0202_1620 | 3361.24 |  |  | 0 | 0
| HR Injection System Upgrade Power Supplies | HR_0402_1200 | 4484.23 |  |  | 0 | 0
|  | HR_0402_1480 | 3361.24 |  |  | 0 | 0
|  | HR_0402_1620 | 3361.24 |  |  | 0 | 0
|  | HR_0402_1960 | 6722.48 |  |  | 0 | 0
|  | HR_0402_2700 | 6730.21 |  |  | 0 | 0
| IR Power Supplies | IR_0203_1200 | 59143.04 |  |  | 0 | 0
|  | IR_0203_1645 | 3318.73 |  |  | 0 | 0
| SHC Power Supplies and Cables | HR_0809_1360 | 147894.52 |  |  | 0 | 0
|  | HR_0809_1560 | 16960.82 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_3280 | 30550.34 |  |  | 0 | 0
|  | IR_0302_3660 | 13577.93 |  | x | IR_0302_3660 | 0
|  | IR_0302_4020 | 56020.65 |  |  | 0 | 0
S.P044 | 400 MeV Profile and Emittance Monitors | EJ_0401_6960 | 298232.31 |  | x | EJ_0401_6960 | 0
S.P045 | Hadron Ring Injection Transfer Line Instrumentation | HR_0602_1120 | 389824.94 |  |  | 0 | 0
S.P046 | RCS Synchrotron Radiation Monitor | EJ_0205_8360 | 394091.4 |  |  | 0 | 0
S.P047 | 400 MeV Injector Vacuum | EJ_0401_1500 | 446116.68 |  |  | 0 | 0
S.P048 | ESR Injection - Slow Pulsed Septum | EJ_0305_8100 | 400068.33 |  | x | EJ_0305_8100 | 0
S.P049 | ESR Magnet Correctors Design | SR_0200_2460 | 1383896.02 |  |  | 0 | 0
S.P050 | HR SC Magnet Beam Pipe Upgrade | HR_0500_1460 | 1902607.08 |  | x | HR_0500_1460 | 0
S.P051 | Hadron Ring Additional Snakes | HR_0700_1040 | 523737.09 |  |  | 0 | 0
S.P052 | Controls - Hardware Procurements - Global Controls - Timing, Common Platform FECs MCHINE Protection | AS_0302_1480 | 777790.7 |  |  | 0 | 0
S.P053 | Electromagnetic Calorimetry | DE_0500_3240 | 812635.13 |  |  | 0 | 0
| Hadron Ring BPM Upgrade | HR_0601_1210 | 691060.61 |  |  | 0 | 0
S.P054 | Particle Identification | DE_0400_4150 | 696602.41 |  |  | 0 | 0
S.P055 | Collimation System Design and Integration | IR_0204_1380 | 372480.48 |  |  | 0 | 0
S.P056 | Tracking | DE_0300_3220 | 538589.8 |  |  | 0 | 0
S.P057 | Hadron Ring Straight Sections Modifications Power Supplies | HR_0202_1725 | 16139.45 |  |  | 0 | 0
| HR Injection System Upgrade Power Supplies | HR_0402_1980 | 13045.88 |  |  | 0 | 0
|  | HR_0402_2160 | 459845.51 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_4000 | 92371.33 |  |  | 0 | 0
S.P058 | Procurement - 2K Satellite Plant Auxiliary Systems | AS_0204_1240 | 357393.8 |  |  | 0 | 0
|  | AS_0205_1240 | 357393.8 |  |  | 0 | 0
|  | HR_0808_1240 | 568925.35 |  |  | 0 | 0
S.P059 | HR SC Magnet Beam Pipe Upgrade | HR_0500_1810 | 598156.8 |  |  | 0 | 0
S.P060.A | RCS: Production Procurement, Assembly, Test | EJ_0204_1600 | 61104.68 |  |  | 0 | 0
S.P060.B | RCS: Production Procurement, Assembly, Test | EJ_0204_1660 | 246331.94 |  |  | 0 | 0
S.P061 | Hadron Polarimetry at IP12 | IR_0302_1143 | 286888.46 |  |  | 0 | 0
S.P062 | Transfer Lines Vacuum | EJ_0303_2300 | 997568.68 |  |  | 0 | 0
S.P063 | Particle Identification | DE_0400_4263 | 453053.28 |  |  | 0 | 0
S.P065.A | 24.6 MHz Cavity Components | HR_0301_1100 | 158611.3 |  |  | 0 | 0
S.P065.B | 24.6 MHz Cavity Assembly and Test | HR_0301_1160 | 171927.45 |  |  | 0 | 0
S.P066 | Controls - Hardware Procurements - Diagnostics | AS_0307_1920 | 1814172.73 |  |  | 0 | 0
S.P067 | RCS Vacuum Monitoring and Control | EJ_0203_1440 | 723768.56 |  |  | 0 | 0
S.P068.A | ERL: Production Procurement, Assembly, Test | HR_0805_6290 | 65418.63 |  |  | 0 | 0
S.P068.B | ERL: Production Procurement, Assembly, Test | HR_0805_6320 | 401541.77 |  |  | 0 | 0
S.P069 | Controls - Hardware Procurements - Power Supply | AS_0307_1640 | 1824424.51 |  |  | 0 | 0
S.P070.A | HSR: Production Procurement, Assembly, Test | HR_0301_1580 | 63947.84 |  |  | 0 | 0
S.P070.B | HSR: Production Procurement, Assembly, Test | HR_0301_1640 | 261675.7 |  |  | 0 | 0
S.P071 | 197 MHz Crab Cavity R&D | RD_0305_1680 | 306900 |  |  | 0 | 0
S.P072 | 197 MHz Crab Cavity R&D | RD_0305_1220 | 313958.7 |  |  | 0 | 0
S.P073 | Electron Storage Ring Vacuum Development | RD_0309_1360 | 308939.18 |  |  | 0 | 0
S.P074 | IR Magnet Prototyping | RD_0303_1160 | 1698562.61 |  |  | 0 | 0
S.P075 | ESR Vacuum Utilities (racks, cooling water) | SR_0405_1160 | 911964.53 |  |  | 0 | 0
S.P076 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | AS_0203_1160 | 162241.95 |  |  | 0 | 0
|  | AS_0204_1160 | 392633.06 |  |  | 0 | 0
|  | AS_0205_1160 | 203755.29 |  |  | 0 | 0
|  | HR_0808_1160 | 282428.15 |  |  | 0 | 0
S.P077 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | AS_0203_1100 | 113890.02 |  |  | 0 | 0
|  | AS_0204_1100 | 455560.07 |  |  | 0 | 0
|  | AS_0205_1100 | 535055.3 |  |  | 0 | 0
|  | HR_0808_1100 | 472066.56 |  |  | 0 | 0
S.P078 | RCS Vacuum Valves | EJ_0203_1560 | 972204.77 |  |  | 0 | 0
S.P079 | IR Magnet Prototyping | RD_0303_1360 | 1143415.79 |  |  | 0 | 0
S.P080 | ESR Injection - Slow Pulsed Septum | EJ_0305_8260 | 769487.23 |  |  | 0 | 0
S.P081 | Motor Control & Load Centers | IF_0304_1220 | 1439415.6 |  |  | 0 | 0
S.P082 | Infrastructure Construction Management & Inspection | IF_0103_1540 | 42513.22 |  |  | 0 | 0
|  | IF_0103_1560 | 20073.73 |  |  | 0 | 0
|  | IF_0103_1580 | 61154.31 |  |  | 0 | 0
|  | IF_0103_1600 | 66487.22 |  |  | 0 | 0
|  | IF_0103_1620 | 68016.43 |  |  | 0 | 0
|  | IF_0103_1640 | 34790.41 |  |  | 0 | 0
|  | IF_0103_1641 | 35590.58 |  |  | 0 | 0
|  | IF_0103_1642 | 36412.47 |  |  | 0 | 0
|  | IF_0103_1643 | 37249.95 |  |  | 0 | 0
|  | IF_0103_1644 | 25218.14 |  |  | 0 | 0
S.P083 | Infrastructure Construction Management & Inspection | IF_0103_1380 | 40334.87 |  |  | 0 | 0
|  | IF_0103_1400 | 54056.9 |  |  | 0 | 0
|  | IF_0103_1420 | 55300.23 |  |  | 0 | 0
|  | IF_0103_1440 | 56572.12 |  |  | 0 | 0
|  | IF_0103_1441 | 57878.56 |  |  | 0 | 0
|  | IF_0103_1442 | 59209.77 |  |  | 0 | 0
|  | IF_0103_1443 | 60571.59 |  |  | 0 | 0
|  | IF_0103_1444 | 26968.16 |  |  | 0 | 0
S.P084 | Infrastructure Construction Management & Inspection | IF_0103_1460 | 5602.06 |  |  | 0 | 0
|  | IF_0103_1480 | 75079.41 |  |  | 0 | 0
|  | IF_0103_1500 | 76806.26 |  |  | 0 | 0
|  | IF_0103_1520 | 39286.98 |  |  | 0 | 0
|  | IF_0103_1521 | 40194.25 |  |  | 0 | 0
|  | IF_0103_1522 | 41118.72 |  | x | IF_0103_1522 | 0
|  | IF_0103_1523 | 42064.44 |  |  | 0 | 0
|  | IF_0103_1524 | 21402.44 |  |  | 0 | 0
S.P085 | RCS Sextupole Magnets | EJ_0201_2160 | 266205.55 |  |  | 0 | 0
S.P086 | Cables | IR_0208_1080 | 336123.9 |  | x | IR_0208_1080 | 0
S.P089 | ESR Machine Protection - Single Turn Extraction Kicker | EJ_0305_9260 | 595623.5 |  |  | 0 | 0
S.P090 | 400 MeV Injector Vacuum | EJ_0401_1040 | 573279.47 |  |  | 0 | 0
S.P091 | 400 MeV Injector Power Supplies | EJ_040102_1315 | 45797.55 |  |  | 0 | 0
| Electron Storage Ring Power Supplies | SR_0300_2040 | 85207.26 |  |  | 0 | 0
| Hadron Ring Straight Sections Modifications Power Supplies | HR_0202_1730 | 39020.64 |  |  | 0 | 0
| HR Injection System Upgrade Power Supplies | HR_0402_2180 | 161444.79 |  |  | 0 | 0
|  | HR_0402_2920 | 80752.65 |  |  | 0 | 0
| SHC Power Supplies and Cables | HR_0809_1685 | 80999.83 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_3800 | 80722.4 |  |  | 0 | 0
|  | IR_0302_4040 | 80722.4 |  |  | 0 | 0
S.P092 | IR Magnet Cryostats | IR_0215_1220 | 325748.25 |  |  | 0 | 0
S.P093 | HR SC Magnet Beam Pipe Upgrade | HR_0500_1980 | 342378.52 |  |  | 0 | 0
S.P094 | Controls - Hardware Procurements - Global Controls - Timing, Common Platform FECs MCHINE Protection | AS_0302_2440 | 280103.25 |  |  | 0 | 0
| Controls - Hardware Procurements - Network | AS_0302_3290 | 596785.74 |  |  | 0 | 0
|  | AS_0302_3350 | 327053.04 |  |  | 0 | 0
S.P095 | 400 MeV Injector Power Supplies | EJ_040102_1680 | 141364.28 |  |  | 0 | 0
| Electron Storage Ring Power Supplies | SR_0300_2200 | 328566.9 |  |  | 0 | 0
| Transfer Lines Power Supplies | IR_0302_4400 | 65060.14 |  |  | 0 | 0
S.P096 | 400 MeV Injector Vacuum | EJ_0401_1380 | 513370.45 |  |  | 0 | 0
S.P097.A | 295 MHz Cavity Components | EJ_0204_2050 | 816902.85 |  |  | 0 | 0
S.P098.A | 148 MHz Cavity Components | EJ_0204_2410 | 443846.91 |  |  | 0 | 0
S.P099 | ESR 1-Cell Cavity R&D | RD_0308_1160 | 523328.52 |  |  | 0 | 0
S.P100.A | SSA: RCS Bunch Merge 1: 296 MHz | EJ_0204_2170 | 362769.99 |  |  | 0 | 0
S.P100.B | SSA: RCS Bunch Merge 1: 296 MHz | EJ_0204_2200 | 373696.72 |  |  | 0 | 0
S.P101.A | SSA: RCS Bunch Merge 2: 148 MHz | EJ_0204_2530 | 362769.99 |  |  | 0 | 0
S.P102.B | 197 MHz Cavity (ERL Inj) Assembly and Test | HR_0805_6080 | 1073714.25 |  |  | 0 | 0
S.P103.A | CS: ERL Inj Procurement | HR_0805_6410 | 774101.14 |  |  | 0 | 0
S.P104.A | SSA: ERL Injector Third Harmonic: 1773 MHz | HR_0805_6530 | 507773.32 |  |  | 0 | 0
S.P105 | 400 MeV Injector RF Systems | EJ_0401_2580 | 860944.46 |  |  | 0 | 0
S.P106 | HP HOM Absorber Prototype | RD_0304_2200 | 347042.48 |  |  | 0 | 0
S.P107 | ESR Vacuum Monitoring and Control | SR_0404_1160 | 2132703.37 |  |  | 0 | 0
S.P108 | Controls - Hardware Procurements - Water and Cryo | AS_0307_1540 | 1110777.45 |  |  | 0 | 0
S.P110 | HP FPC Prototype | RD_0304_2020 | 1170910.97 |  |  | 0 | 0
S.P111 | ESR Vacuum Valves | SR_0402_1160 | 1413482.85 |  |  | 0 | 0
S.P112 | Polarized Electron Source Laser | EJ_0402_4060 | 686155.72 |  |  | 0 | 0
S.P113 | Lepton Polarimetry in the RCS | IR_0301_3120 | 336727.83 |  |  | 0 | 0
|  | IR_0301_3140 | 353653.14 |  |  | 0 | 0
|  | IR_0301_3160 | 380570.25 |  |  | 0 | 0
| Lepton Polarimetry in the Storage Ring | IR_0301_1120 | 336727.83 |  |  | 0 | 0
|  | IR_0301_1140 | 353653.14 |  |  | 0 | 0
|  | IR_0301_1160 | 380570.25 |  |  | 0 | 0
S.P114 | Hadron Ring Straight Sections Modifications Vacuum System | HR_0203_1200 | 1898670.8 |  |  | 0 | 0
S.P115 | HR Injection System Upgrade Vacuum System | HR_0403_1200 | 293694.18 |  |  | 0 | 0
S.P116 | SHC Beam Transport Vacuum Systems | HR_0804_4800 | 607776.56 |  |  | 0 | 0
S.P117 | SHC Beam Transport Vacuum Systems | HR_0804_5400 | 317693.59 |  |  | 0 | 0
S.P118 | SHC Beam Transport Vacuum Systems | HR_0804_6000 | 443370.48 |  |  | 0 | 0
S.P120 | SHC Beam Transport Vacuum Systems | HR_0804_5740 | 295027.5 |  |  | 0 | 0
S.P121 | SSA: HSR: Store 2 | HR_0305_1162 | 727067.37 |  |  | 0 | 0
S.P122 | Electronics | DE_0800_3031 | 484322.49 |  |  | 0 | 0
S.P123 | HR SC Magnet Beam Pipe Upgrade | HR_0500_1750 | 547762.64 |  |  | 0 | 0
S.P124 | SHC Electron Source | HR_0802_1260 | 291488.63 |  |  | 0 | 0
S.P125 | Hadron Ring BPM Upgrade | HR_0601_1240 | 286628.5 |  |  | 0 | 0
S.P126 | TL Profile and Emittance Monitors | EJ_0304_7280 | 321106.92 |  |  | 0 | 0
S.P127 | 400 MeV Current and Charge Monitors | EJ_0401_5400 | 338573.64 |  |  | 0 | 0
S.P128 | Collimation System Design and Integration | HR_0603_2960 | 342973.96 |  |  | 0 | 0
S.P129 | SHC Beam Position Monitors | HR_0807_0080 | 990724.11 |  |  | 0 | 0
S.P130 | Hadron Ring BPM Upgrade | HR_0601_1360 | 690517.52 |  |  | 0 | 0
S.P131 | SHC Charge and Current Monitors | HR_0807_2080 | 1103802.84 |  |  | 0 | 0
S.P132 | ESR Synchrotron and X-ray Radiation Monitors | SR_0604_1360 | 564943.94 |  |  | 0 | 0
S.P133 | ESR Beam Position Monitors | SR_0601_1620 | 1045068.81 |  |  | 0 | 0
S.P134 | ESR Beam Position Monitors | SR_0601_1760 | 930931.63 |  |  | 0 | 0
S.P135 | IR Beam Position Monitors | IR_0206_1320 | 1018786.84 |  |  | 0 | 0
S.P136 | RCS Beam Position Monitors | EJ_0205_1600 | 997710.9 |  |  | 0 | 0
S.P137 | ESR Tune Meter and Bunch-by-Bunch Longitudinal Feedback Systems | SR_0603_1200 | 1134653.43 |  |  | 0 | 0
S.P138 | RCS Beam Position Monitors | EJ_0205_1720 | 1139931.42 |  |  | 0 | 0
S.P139 | SHC Synchrotron Radiation Monitors | HR_0807_8080 | 918128.29 |  |  | 0 | 0
S.P140 | ESR Beam Position Monitors | SR_0601_1440 | 1592022.2 |  |  | 0 | 0
S.P141 | SHC Profile and Emittance Monitors | HR_0807_4080 | 1698406.53 |  |  | 0 | 0
S.P142 | Hadron Ring BPM Upgrade | HR_0601_1300 | 1702942.62 |  |  | 0 | 0
S.P143 | Tracking | DE_0300_3180 | 2305463.9 |  |  | 0 | 0
S.P144 | Tracking | DE_0300_3230 | 2305463.9 |  |  | 0 | 0
S.P146.A | SSA: RCS: Fundamental | EJ_0204_1360 | 719115.02 |  |  | 0 | 0
S.P146.B | SSA: RCS: Fundamental | EJ_0204_1420 | 1454134.73 |  |  | 0 | 0
S.P147 | Standby Power | IF_0305_1420 | 1508596.4 |  |  | 0 | 0
S.P148.A | ESR: Production Procurement, Assembly, Test | SR_0501_1600 | 61104.68 |  |  | 0 | 0
S.P148.B | ESR: Production Procurement, Assembly, Test | SR_0501_1660 | 1120084.18 |  |  | 0 | 0
S.P149.A | SSA: HSR Bunch Split 2: 98 MHz | HR_0303_1340 | 570678.13 |  |  | 0 | 0
S.P149.B | SSA: HSR Bunch Split 2: 98 MHz | HR_0303_1400 | 588709.81 |  |  | 0 | 0
S.P150.A | SSA: ERL Main Linac Third Harmonic: 1773 MHz | HR_0805_5340 | 481814.7 |  | x | HR_0805_5340 | 0
S.P150.B | SSA: ERL Main Linac Third Harmonic: 1773 MHz | HR_0805_5400 | 998867.26 |  | x | HR_0805_5400 | 0
S.P151.A | HSR: Production Procurement, Assembly, Test | HR_0304_1580 | 62510.08 |  |  | 0 | 0
S.P151.B | HSR: Production Procurement, Assembly, Test | HR_0304_1640 | 385454.3 |  |  | 0 | 0
S.P154.A | 49.2 MHz Cavity Components | HR_0302_1100 | 759050.02 |  |  | 0 | 0
S.P154.B | 49.2 MHz Cavity Assembly and Test | HR_0302_1160 | 784289.1 |  |  | 0 | 0
S.P155.A | 98.4 MHz Cavity Components | HR_0303_1100 | 768744.89 |  |  | 0 | 0
S.P155.B | 98.4 MHz Cavity Assembly and Test | HR_0303_1160 | 794827.67 |  |  | 0 | 0
S.P156.A | 197 MHz Cavity (HSR Store 1) Components | HR_0304_1100 | 139107 |  |  | 0 | 0
S.P156.B | 197 MHz Cavity (HSR Store 1) Assembly and Test | HR_0304_1160 | 870500.71 |  |  | 0 | 0
S.P157.A | SSA: HSR Bunch Split 1: 49 MHz | HR_0302_1340 | 582568.38 |  |  | 0 | 0
S.P157.B | SSA: HSR Bunch Split 1: 49 MHz | HR_0302_1400 | 602250.4 |  |  | 0 | 0
S.P158.A | ERL: Production Procurement, Assembly, Test | HR_0805_1360 | 63947.84 |  |  | 0 | 0
| SSA: ERL Main Linac Fundamental | HR_0805_1150 | 507653.53 |  |  | 0 | 0
S.P158.B | ERL: Production Procurement, Assembly, Test | HR_0805_1420 | 654727.18 |  | x | HR_0805_1420 | 0
S.P159 | CM: 591 MHz 5-Cell Procurement | HR_0305_1000 | 1679520.16 |  |  | 0 | 0
S.P160 | Electron Storage Ring Vacuum Development | RD_0309_1185 | 320918.83 |  | x | RD_0309_1185 | 0
S.P161 | Electron Storage Ring Vacuum Development | RD_0309_1260 | 503683 |  |  | 0 | 0
S.P162 | IR Magnet Prototyping | RD_0303_2060 | 833591.74 |  |  | 0 | 0
S.P163 | Detector Interface Vacuum Development | RD_0309_5180 | 456273.75 |  |  | 0 | 0
S.P164 | Cooling R&D | RD_0310_1106 | 120147.09 |  |  | 0 | 0
|  | RD_0310_1107 | 122418.85 |  |  | 0 | 0
|  | RD_0310_1108 | 125737.4 |  |  | 0 | 0
S.P165 | Cooling R&D | RD_0310_1240 | 518652.82 |  |  | 0 | 0
S.P166 | Cooling R&D | RD_0310_1290 | 462718.01 |  |  | 0 | 0
S.P167 | Cooling R&D | RD_0310_1488 | 318724.56 |  |  | 0 | 0
S.P168 | Cooling R&D | RD_0310_1700 | 355819.86 |  |  | 0 | 0
S.P169 | Cooling R&D | RD_0310_1940 | 422125.82 |  |  | 0 | 0
S.P183 | HP FPC Prototype | HR_0305_1530 | 1992532.26 |  |  | 0 | 0
S.P184 | HP FPC Prototype | HR_0305_1610 | 835792.64 |  |  | 0 | 0
| IR Magnet Cryostats | IR_0215_1280 | 974477.12 |  |  | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[5 empty] | x | 0 | 0
[6 empty] | 0 | 0
[5 empty] | x | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
0

## over $250K P6 Data
Activity ID | Procurement Code | BNL_Estimator | BNL_WBS_Hierarchical | WBS Name | Activity Name | Direct Material Cost | Budgeted Material Cost | Start | Finish
RD_0303_1160 | S.P074 | Witte | 6.02.03.03.02 | IR Magnet Prototyping | Tooling Materials - Vendor Manufacturing/ Fabrication | 1623044 | 1698562.61 | 2023-02-16 | 2023-07-10
RD_0303_1360 | S.P079 | Witte | 6.02.03.03.02 | IR Magnet Prototyping | Prototype Material - Vendor Manufacturing/ Fabrication | 1068015 | 1143415.79 | 2023-12-13 | 2024-05-06
RD_0303_2060 | S.P162 | Witte | 6.02.03.03.02 | IR Magnet Prototyping | Coil Assembly + Yoke Material - Vendor Fabrication | 773330 | 833591.74 | 2023-04-21 | 2023-07-17
RD_0309_1360 | S.P073 | Hetzel | 6.02.03.06.01 | Electron Storage Ring Vacuum Development | PROC: RF shielded bellows - Non Labor | 300000 | 308939.18 | 2022-04-01 | 2022-12-19
RD_0309_1185 | S.P160 | Hetzel | 6.02.03.06.01 | Electron Storage Ring Vacuum Development | PROC: Vacuum chamber cross sections - Non Labor | 312094 | 320918.83 | 2022-04-01 | 2022-11-28
RD_0309_1260 | S.P161 | Hetzel | 6.02.03.06.01 | Electron Storage Ring Vacuum Development | PROC: Vacuum chamber welding and tooling development - Non Labor | 487500 | 503683 | 2022-06-27 | 2022-12-19
RD_0309_5180 | S.P163 | Hetzel | 6.02.03.06.02 | Detector Interface Vacuum Development | PROC: Prototype Detector Chamber - Non Labor | 433000 | 456273.75 | 2023-03-15 | 2023-12-29
RD_0310_1680 | A.PP003 | Wang | 6.02.03.07 | Cooling R&D | PROC: Procurement, beamline | 400000 | 423040.48 | 2023-03-22 | 2024-03-20
RD_0310_1193 | A.PP021 | Wang | 6.02.03.07 | Cooling R&D | HV DC Gun PS 600 kV - Vendor Manufacturing - Factory Acceptance | 831000 | 880750.13 | 2023-05-01 | 2024-04-15
RD_0310_1187 | A.PP021 | Wang | 6.02.03.07 | Cooling R&D | HV DC Gun PS 600 kV - Vendor Manufacturing - Confirm 95% of PS Drawings and 80% Long Lead Items | 600000 | 624937.06 | 2022-08-09 | 2023-04-28
RD_0310_1186 | A.PP021 | Wang | 6.02.03.07 | Cooling R&D | HV DC Gun PS 600 kV - Vendor Manufacturing - Final Design Review | 300000 | 306900 | 2022-07-12 | 2022-08-08
RD_0310_1194 | A.PP021 | Wang | 6.02.03.07 | Cooling R&D | HV DC Gun PS 600 kV - Vendor Manufacturing - Final Acceptance | 219000 | 234461.18 | 2024-04-16 | 2024-05-13
RD_0310_1185 | A.PP021 | Wang | 6.02.03.07 | Cooling R&D | HV DC Gun PS 600 kV - Vendor Manufacturing - Preliminary Design review | 200000 | 204600 | 2022-06-13 | 2022-07-11
RD_0310_1195 | A.PP021 | Wang | 6.02.03.07 | Cooling R&D | HV DC Gun PS 600 kV - Vendor Manufacturing - Operating Manual and Parts List | 50000 | 53529.95 | 2024-04-16 | 2024-05-13
RD_0310_1108 | S.P164 | Wang | 6.02.03.07 | Cooling R&D | PROC: Cooler R&D Miscellaneous Materials - FY24 | 114025.09 | 125737.4 | 2023-10-02 | 2024-09-30
RD_0310_1107 | S.P164 | Wang | 6.02.03.07 | Cooling R&D | PROC: Cooler R&D Miscellaneous Materials - FY23 | 113568.99 | 122418.85 | 2022-10-03 | 2023-09-29
RD_0310_1106 | S.P164 | Wang | 6.02.03.07 | Cooling R&D | PROC: Cooler R&D Miscellaneous Materials - FY22 | 114025.09 | 120147.09 | 2021-10-01 | 2022-09-30
RD_0310_1240 | S.P165 | Wang | 6.02.03.07 | Cooling R&D | Gun Electrodes and Feedthru - Vendor Fabrication | 500000 | 518652.82 | 2022-05-13 | 2023-05-12
RD_0310_1290 | S.P166 | Wang | 6.02.03.07 | Cooling R&D | PROC: Procurement, diagnostic | 440000 | 462718.01 | 2022-12-20 | 2023-12-19
RD_0310_1488 | S.P167 | Wang | 6.02.03.07 | Cooling R&D | PROC: Procurement, photocathode material | 300000 | 318724.56 | 01-Jun-23* | 2024-05-30
RD_0310_1700 | S.P168 | Wang | 6.02.03.07 | Cooling R&D | PROC: Procurement, vacuum | 340000 | 355819.86 | 2023-03-22 | 2023-08-10
RD_0310_1940 | S.P169 | Wang | 6.02.03.07 | Cooling R&D | Laser procurement - Vendor Fabrication | 400000 | 422125.82 | 2023-04-03 | 2024-01-19
EJ_0201_1820 | A.PP088 | Witte | 6.03.02.01.01 | RCS Quad Magnets | RCS Quad - Magnet I - Fabrication | 3962206 | 4511558.47 | 2025-06-16 | 2028-06-14
EJ_0201_1920 | A.PP107 | Witte | 6.03.02.01.01 | RCS Quad Magnets | RCS Quad - Magnet II - Fabrication | 3962206 | 4511558.47 | 2025-06-16 | 2028-06-14
EJ_0201_1700 | S.P003 | Witte | 6.03.02.01.01 | RCS Quad Magnets | RCS Quad Prototype - Fabrication | 250000 | 264941.88 | 2023-07-28 | 2023-12-21
EJ_0201_2280 | A.PP028 | Witte | 6.03.02.01.02 | RCS Sextupole Magnets | RCS Sextupole - Magnet I - Fabrication | 3306650 | 3744656.71 | 2025-03-21 | 2028-03-21
EJ_0201_2380 | A.PP029 | Witte | 6.03.02.01.02 | RCS Sextupole Magnets | RCS Sextupole - Magnet II - Fabrication | 3306650 | 3744656.71 | 2025-03-21 | 2028-03-21
EJ_0201_2160 | S.P085 | Witte | 6.03.02.01.02 | RCS Sextupole Magnets | RCS Sextupole Prototype - Fabrcation | 250000 | 266205.55 | 2023-08-28 | 2024-01-24
EJ_0201_2620 | S.P010 | Witte | 6.03.02.01.03 | RCS Corrector Magnets | RCS Corrector - Fabrication | 1552500 | 1739674.95 | 2025-03-21 | 2027-04-19
EJ_0201_2840 | D.APP36 | Witte | 6.03.02.01.04 | RCS Girders, Assembly and Integration | RCS Girder: 5 types - Vendor Fabrication - Long Dipole [$20K per Girder, #334] | 7680000 | 8714138.36 | 2025-10-21 | 2027-10-20
EJ_0201_2845 | D.APP36 | Witte | 6.03.02.01.04 | RCS Girders, Assembly and Integration | RCS Girder: 5 types - Vendor Fabrication - Short Dipole [$5K per Girder, #132] | 660000 | 748871.27 | 2025-10-21 | 2027-10-20
EJ_0201_2980 | S.P025 | Witte | 6.03.02.01.05 | RCS Magnet Measuring Stations | Magnet Measuring Station - Vendor Fabrication | 867900 | 973569.46 | 2025-10-21 | 2026-10-20
EJ_0201_1360 | D.APP15 | TBD | 6.03.02.02.01 | RCS Dipole Magnets | RCS Dipole - Magnet I - Manufacturing/Fabrication | 7672201 | 8969230.05 | 2026-08-12 | 2029-08-10
EJ_0201_1460 | D.APP33 | TBD | 6.03.02.02.01 | RCS Dipole Magnets | RCS Dipole - Magnet II - Manufacturing/Fabrication | 7672201 | 8969230.05 | 2026-08-12 | 2029-08-10
EJ_0201_1240 | S.P002 | TBD | 6.03.02.02.01 | RCS Dipole Magnets | RCS Dipole Prototype - Fabrication | 250000 | 273805.75 | 2024-10-04 | 2025-09-19
EJ_0202_1300 | D.APP01 | Bruno | 6.03.02.03 | RCS Power Supplies | Corrector Supplies - Vendor Fabrication | 5859000 | 6687017.32 | 2026-01-08 | 2028-02-07
EJ_0202_1460 | D.APP02 | Bruno | 6.03.02.03 | RCS Power Supplies | Rest of RCS Supplies - Vendor Fabrication | 5990000 | 6872561.99 | 2026-04-06 | 2028-05-02
EJ_0202_1620 | D.APP03 | Bruno | 6.03.02.03 | RCS Power Supplies | DC, AC power cables control and magnet interlock cables and cable trays - Materials Vendor Fabrication | 7801220 | 8758372.39 | 2025-10-21 | 2026-11-03
EJ_0202_1120 | D.APP23 | Bruno | 6.03.02.03 | RCS Power Supplies | Main Dipole supply and the 2 Arc Quad supplies - Vendor Fabrication and ship | 10300000 | 11879550.95 | 2026-06-30 | 2028-07-27
EJ_0203_1220 | A.PP048 | Hetzel | 6.03.02.04.01 | RCS Vacuum Chamber and Bellows | RCS Vacuum Chambers and Bellows - Procurement | 3960560 | 4463935.67 | 2025-10-21 | 2027-02-03
EJ_0203_1560 | S.P078 | Hetzel | 6.03.02.04.02 | RCS Vacuum Valves | RCS Vacuum Valves - Procurement | 867720 | 972204.77 | 2025-10-21 | 2026-08-07
EJ_0203_1660 | A.PP004 | Hetzel | 6.03.02.04.03 | RCS Vacuum Pumps | RCS Vacuum Pumps - Procurement | 3105120 | 3480017.05 | 2025-10-21 | 2026-10-05
EJ_0203_1440 | S.P067 | Hetzel | 6.03.02.04.04 | RCS Vacuum Monitoring and Control | RCS Vacuum Monitoring and Controls - Procurement | 643710 | 723768.56 | 2025-10-21 | 2026-12-04
EJ_0205_1440 | S.P001 | Gassner | 6.03.02.05.01 | RCS Beam Position Monitors | BPM Electronics - V301 module - Vendor Fabrication | 1654808 | 1885625.25 | 2026-06-30 | 2027-06-29
EJ_0205_1600 | S.P136 | Gassner | 6.03.02.05.01 | RCS Beam Position Monitors | BPM Pick-up -Button Procurement - materials | 889344 | 997710.9 | 2025-10-21 | 2026-10-21
EJ_0205_1720 | S.P138 | Gassner | 6.03.02.05.01 | RCS Beam Position Monitors | BPM System - Miscellaneous materials | 1017140 | 1139931.42 | 2025-10-06 | 2026-10-05
EJ_0205_8360 | S.P046 | Gassner | 6.03.02.05.04 | RCS Synchrotron Radiation Monitor | RCS SLM Material - s-RAD | 347300 | 394091.4 | 2025-10-21 | 2027-10-21
EJ_0301_1120 | S.P005 | Tsoupas | 6.03.03.01 | Transfer Lines Magnets | Linac to RCS Transfer line magnets - Material and Construction | 500000 | 560206.5 | 2025-11-19 | 2026-05-13
EJ_0301_1340 | S.P026 | Tsoupas | 6.03.03.01 | Transfer Lines Magnets | RCS to SR Transfer line magnets - Material and Construction | 400000 | 448165.2 | 2025-10-21 | 2026-06-11
IR_0302_3580 | A.PP022 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | RCS-SR H,V Corrector - Vendor Manufacturing - CAEN-FAST PS | 135440 | 151748.74 | 2025-10-21 | 2026-07-10
IR_0302_4220 | A.PP022 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | 400MeV-RCS Correctors CAEN - Vendor Maunufacturing | 34860 | 39057.6 | 2025-10-21 | 2026-07-10
IR_0302_3780 | A.PP023 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | RCS-SR Cables - Vendor Manufacturing - DC Cable Order | 257758 | 288795.41 | 2025-10-21 | 2026-02-18
IR_0302_3980 | D.APP30 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | 400MeV-RCS Quad/Dipole Lambda - Vendor Maunufacturing | 232098 | 260045.62 | 2025-10-21 | 2026-07-10
IR_0302_3120 | D.APP30 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | RCS-SR Quad, Small Dipole - Vendor Manufacturing | 115160 | 129026.76 | 2025-10-21 | 2026-07-10
IR_0302_3400 | D.APP42 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | RCS-SR Large Dipole - Vendor Manufacturing | 75000 | 84030.98 | 2025-10-21 | 2026-07-10
IR_0302_4020 | S.P043 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | 400MeV-RCS Quad/Dipole/Corr - Purchase Racks | 50000 | 56020.65 | 2025-10-21 | 2026-07-10
IR_0302_3280 | S.P043 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | RCS-SR Quad, Small Dipole, Large Dipole - Purchase-Racks | 27000 | 30550.34 | 2026-07-13 | 2026-12-04
IR_0302_3660 | S.P043 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | RCS-SR H,V Corrector - Purchase-Racks | 12000 | 13577.93 | 2026-07-13 | 2026-12-04
IR_0302_4000 | S.P057 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | 400MeV-RCS Quad/Dipole - DC, AC, Control Interlock Cable Order | 82444 | 92371.33 | 2025-10-21 | 2026-07-10
IR_0302_3800 | S.P091 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | RCS-SR Cables - Vendor Manufacturing - DC Cable Tray Order | 72047 | 80722.4 | 2025-10-21 | 2026-02-18
IR_0302_4040 | S.P091 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | 400MeV-RCS Quad/Dipole/Corr - Cable Tray Order | 72047 | 80722.4 | 2025-10-21 | 2026-07-10
IR_0302_4400 | S.P095 | Bruno | 6.03.03.02 | Transfer Lines Power Supplies | AC, Control, Interlock Cable & Cable Tray - Vendor Maunufacturing | 58068 | 65060.14 | 2025-10-21 | 2026-07-10
EJ_0303_2300 | S.P062 | Hetzel | 6.03.03.03 | Transfer Lines Vacuum | Hardware Deliveries | 890358 | 997568.68 | 2025-10-21 | 2026-05-21
EJ_0304_7280 | S.P126 | Gassner | 6.03.03.04.03 | TL Profile and Emittance Monitors | Profile Monitors - Construction - Non Labor | 283000 | 321106.92 | 2025-10-21 | 2027-10-20
EJ_0305_1080 | S.P022 | Ranjbar | 6.03.03.05.01 | RCS Injection - Pulsed Bump | RCS Injection Pulsed Bump - Kicker Magnet - Fabrication | 270893 | 302261.01 | 2025-07-15 | 2026-09-23
EJ_0305_4100 | S.P023 | Ranjbar | 6.03.03.05.04 | RCS Extraction - Kicker | RCS Extraction Kicker - Fabrication | 270893 | 306886.15 | 2026-02-23 | 2027-05-03
EJ_0305_5080 | S.P024 | Ranjbar | 6.03.03.05.05 | RCS Extraction - Pulsed Septum | RCS Extraction Septum - Electrical Components - Fabrication | 392949.6 | 438451.13 | 2025-07-15 | 2026-09-23
EJ_0305_5220 | S.P029 | Ranjbar | 6.03.03.05.05 | RCS Extraction - Pulsed Septum | RCS Extraction Septum - Mechanical Components - Fabrication | 674000 | 755158.36 | 2025-11-06 | 2026-04-03
EJ_0305_6100 | S.P032 | Ranjbar | 6.03.03.05.06 | ESR Injection & Extraction - Strip-line Kickers | ESR Stripline Kickers Electrical Components - Fabrication | 1193893 | 1352523.77 | 2026-02-23 | 2027-05-03
EJ_0305_6260 | S.P038 | Ranjbar | 6.03.03.05.06 | ESR Injection & Extraction - Strip-line Kickers | ESR Stripline Kickers Mechanical Components - Fabrication | 636186.67 | 713611.54 | 2026-05-18 | 2026-10-07
EJ_0305_8100 | S.P048 | Ranjbar | 6.03.03.05.08 | ESR Injection - Slow Pulsed Septum | ESR Injection ESR Injection Electrical Components - Fabrication | 357072.2 | 400068.33 | 2026-02-23 | 2026-09-23
EJ_0305_8260 | S.P080 | Ranjbar | 6.03.03.05.08 | ESR Injection - Slow Pulsed Septum | ESR Injection ESR Injection Mechanical Components - Fabrication | 686000 | 769487.23 | 2026-05-18 | 2026-10-07
EJ_040102_1280 | A.PP022 | Bruno | 6.03.04.01.01 | 400 MeV Injector Power Supplies | Corrector PS - Vendor Manufacturing - CAEN-FAST PS | 746220 | 837074.55 | 2025-10-21 | 2026-10-20
EJ_040102_1500 | A.PP023 | Bruno | 6.03.04.01.01 | 400 MeV Injector Power Supplies | Cable - Vendor Manufacturing - DC Cable Order | 37000 | 42171.77 | 2026-04-06 | 2027-11-05
EJ_040102_1080 | D.APP30 | Bruno | 6.03.04.01.01 | 400 MeV Injector Power Supplies | Dipole, Solenoid and Quad PS - Vendor Manufacturing | 1154257 | 1293244.55 | 2025-10-21 | 2026-07-10
EJ_040102_1180 | S.P043 | Bruno | 6.03.04.01.01 | 400 MeV Injector Power Supplies | Dipole, Solenoid and Quad PS Purchase-Racks | 141000 | 159540.67 | 2026-07-13 | 2026-12-04
EJ_040102_1315 | S.P091 | Bruno | 6.03.04.01.01 | 400 MeV Injector Power Supplies | Corrector PS - Vendor Manufacturing - Cable Tray | 40826.77 | 45797.55 | 2025-10-21 | 2026-10-20
EJ_040102_1680 | S.P095 | Bruno | 6.03.04.01.01 | 400 MeV Injector Power Supplies | AC, Control & Interlock Cable - Vendor Manufacturing - DC Cable Order | 125000 | 141364.28 | 2025-10-21 | 2027-05-27
EJ_0401_1150 | S.P004 | Skaritka | 6.03.04.01.02 | 400 MeV Injector Vacuum | XHV pumping systems - Fabrication and ship | 890121 | 1002655.44 | 2026-05-21 | 2026-11-10
EJ_0401_1680 | S.P031 | Skaritka | 6.03.04.01.02 | 400 MeV Injector Vacuum | Transport line vacuum cmpts. - material | 350000 | 396128.16 | 2026-06-26 | 2026-12-18
EJ_0401_1500 | S.P047 | Skaritka | 6.03.04.01.02 | 400 MeV Injector Vacuum | XHV ion pumps diag. line - material | 398000 | 446116.68 | 2026-02-19 | 2026-10-05
EJ_0401_1040 | S.P090 | Skaritka | 6.03.04.01.02 | 400 MeV Injector Vacuum | XHV Diag.Cal.& purging systems - Fabrication and ship | 500164 | 573279.47 | 2026-10-08 | 2027-06-01
EJ_0401_1380 | S.P096 | Skaritka | 6.03.04.01.02 | 400 MeV Injector Vacuum | Valves and beam line isolation - material | 458000 | 513370.45 | 2026-02-19 | 2026-10-05
EJ_0401_2270 | D.APP09.A | Skaritka | 6.03.04.01.03 | 400 MeV Injector RF Systems | 400 MeV Linac - Vendor Design | 1831233 | 2006162.05 | 2024-10-04 | 2025-10-03
EJ_0401_2280 | D.APP09.B | Skaritka | 6.03.04.01.03 | 400 MeV Injector RF Systems | 400 MeV Linac - Fabrication and ship | 16481096 | 18683148.29 | 2025-10-06 | 2027-10-05
EJ_0401_2580 | S.P105 | Skaritka | 6.03.04.01.03 | 400 MeV Injector RF Systems | Installation Support - Material | 750000 | 860944.46 | 2027-04-22 | 2027-10-13
EJ_0401_5400 | S.P127 | Gassner | 6.03.04.01.04.02 | 400 MeV Current and Charge Monitors | ICT, Material | 298638 | 338573.64 | 2026-03-27 | 2027-04-26
EJ_0401_6960 | S.P044 | Gassner | 6.03.04.01.04.03 | 400 MeV Profile and Emittance Monitors | Streak Camera - Construction - Non Labor | 262840 | 298232.31 | 2025-10-21 | 2027-10-20
EJ_0402_4060 | S.P112 | Skaritka | 6.03.04.02.03 | Polarized Electron Source Laser | Laser System - Procurements - Material | 610000 | 686155.72 | 2025-12-05 | 2026-12-04
SR_0200_1320 | D.APP16 | Witte | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole - Magnet II - Fabrication | 15306239 | 17278509.32 | 2025-01-30 | 2028-01-31
SR_0200_1220 | D.APP18 | Witte | 6.04.02.01 | ESR Dipole Magnets | ESR Dipole - Magnet I - Fabrication | 15306239 | 17278509.32 | 2025-01-30 | 2028-01-31
SR_0200_2120 | A.PP009 | Witte | 6.04.02.02 | ESR Sextupole Magnets | ESR Sextupole - Magnet I - Fabrication | 2407960 | 2741819.16 | 2025-06-16 | 2028-06-14
SR_0200_2220 | A.PP009 | Witte | 6.04.02.02 | ESR Sextupole Magnets | ESR Sextupole - Magnet II - Fabrication | 2407960 | 2741819.16 | 2025-06-16 | 2028-06-14
SR_0200_2700 | D.APP35 | Witte | 6.04.02.03 | ESR Girders and Integrated Assembly | eSR Girders: 5 Types - Fabrication [$20K per Girder, 494 Girders] | 9880000 | 11061043.34 | 2025-03-21 | 2027-03-22
SR_0200_1680 | A.PP112 | TBD | 6.04.03.02.01 | ESR Magnet Quad #1 | ESR Quad - Magnet I - Fabrication | 4144864 | 4693902.52 | 2025-03-21 | 2028-03-21
SR_0200_1780 | A.PP113 | TBD | 6.04.03.02.02 | ESR Magnet Quad #2 | ESR Quad - Magnet II - Fabrication | 4144864 | 4693902.52 | 2025-03-21 | 2028-03-21
SR_0200_2460 | S.P049 | TBD | 6.04.03.03.01 | ESR Magnet Correctors Design | ESR Corrector - Fabrication (#247) | 1235000 | 1383896.02 | 2025-03-21 | 2027-04-19
SR_0300_1260 | A.PP022 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Correctors - Vendor Manufacturing - CAEN | 1650000 | 1857610.76 | 2025-10-21 | 2027-01-05
SR_0300_1880 | A.PP023 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | DC Cable - Manufacturing | 2290077 | 2565832.04 | 2025-10-21 | 2026-01-20
SR_0300_1080 | D.APP29 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Cable Bus - Manufacturing Vendor | 8975521 | 10056290.41 | 2025-10-21 | 2026-07-10
SR_0300_1085 | D.APP29 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Cable Bus - Mounting Brackets - Manufacturing Vendor | 688525 | 771432.36 | 2025-10-21 | 2026-07-10
SR_0300_1086 | D.APP29 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Cable Bus - Water Hoses - Manufacturing Vendor | 45959 | 51493.06 | 2025-10-21 | 2026-07-10
SR_0300_1660 | D.APP30 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Quades and Sextupoles - Manufacturing | 3048588 | 3432175.67 | 2025-10-21 | 2027-01-05
SR_0300_1460 | D.APP42 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Main Dipole/Quads/Sext - Vendor Manufacturing - APS | 4770190 | 5346119.49 | 2025-10-21 | 2026-10-05
SR_0300_1760 | S.P043 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Quades and Sextupoles - Purchase-Racks | 330000 | 378240.39 | 2027-01-22 | 2027-07-13
SR_0300_1360 | S.P043 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Correctors - Purchase-Racks | 120000 | 137541.96 | 2027-01-22 | 2027-07-13
SR_0300_1560 | S.P043 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Main Dipole/Quads/Sext - - Purchase-Racks | 60000 | 68770.98 | 2027-01-22 | 2027-04-16
SR_0300_2040 | S.P091 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | Cable Tray - Manufacturing | 76049.87 | 85207.26 | 2025-10-21 | 2026-02-18
SR_0300_2200 | S.P095 | Bruno | 6.04.04 | Electron Storage Ring Power Supplies | AC & Interlock Cable -Manufacturing | 300000 | 328566.9 | 2025-02-10 | 2025-05-05
SR_0401_1180 | D25.APP05 | Hetzel | 6.04.05.01 | ESR Vacuum Chamber and Bellows | ESR Vacuum Chamber and Bellows - Procurement | 22965500 | 26417734.41 | 2026-03-16 | 2028-09-08
SR_0402_1160 | S.P111 | Hetzel | 6.04.05.02 | ESR Vacuum Valves | ESR Vacuum Valves - Procurement | 1244400 | 1413482.85 | 2026-05-11 | 2027-05-10
SR_0403_1160 | D.APP27 | Hetzel | 6.04.05.03 | ESR Vacuum Pumps | ESR Vacuum Pumps - Procurement | 7751396 | 8836611.38 | 2026-03-12 | 2027-11-29
SR_0404_1160 | S.P107 | Hetzel | 6.04.05.04 | ESR Vacuum Monitoring and Control | ESR Vacuum Monitoring & Control - Procurement | 1886310 | 2132703.37 | 2026-02-19 | 2027-03-04
SR_0405_1160 | S.P075 | Hetzel | 6.04.05.05 | ESR Vacuum Utilities (racks, cooling water) | ESR Vacuum Utilities (racks, cooling water) - Procurement | 808376 | 911964.53 | 2026-01-23 | 2027-01-22
SR_0407_1160 | A.PP026 | Hetzel | 6.04.05.07 | Construction of Vacuum Fabrication Facility | Construction of Vacuum Fabrication Facility - Procurement | 2080000 | 2330459.04 | 2025-10-21 | 2026-09-04
SR_0601_1620 | S.P133 | Gassner | 6.04.06.01 | ESR Beam Position Monitors | BPM Pick-up -Button & Housing Procurement - materials | 924412 | 1045068.81 | 2025-10-21 | 2027-05-13
SR_0601_1760 | S.P134 | Gassner | 6.04.06.01 | ESR Beam Position Monitors | BPM System - Signal cables, rack hardware, system connectors | 829890 | 930931.63 | 2025-10-21 | 2026-10-20
SR_0601_1440 | S.P140 | Gassner | 6.04.06.01 | ESR Beam Position Monitors | BPM Electronics - V301 module procurement (material) | 1419227 | 1592022.2 | 2025-10-21 | 2026-10-20
SR_0603_1200 | S.P137 | Gassner | 6.04.06.03 | ESR Tune Meter and Bunch-by-Bunch Longitudinal Feedback Systems | Longitudinal Feedback System | 1000000 | 1134653.43 | 2025-10-21 | 2027-10-20
SR_0604_1360 | S.P132 | Gassner | 6.04.06.04 | ESR Synchrotron and X-ray Radiation Monitors | SR SLM Materials - s-Rad | 497900 | 564943.94 | 2025-10-21 | 2027-10-20
HR_0202_1100 | A.PP022 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | New PS (medium PS/ Corrector PS) - Vendor Manufacturing - CAEN | 30000 | 33612.39 | 2025-10-21 | 2026-04-15
HR_0202_1080 | D.APP42 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | New PS (medium PS/ Corrector PS) - Vendor Manufacturing - APS PS | 360000 | 403348.68 | 2025-10-21 | 2026-04-15
HR_0202_1420 | D.APP42 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | Quench Protection - Vendor Manufacturing - QPAs - APS | 204708 | 229357.5 | 2025-10-21 | 2026-02-18
HR_0202_1720 | D.APP42 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | HR Straight Sw Mag APS - Vendor Manufacturing | 170000 | 184141.38 | 2024-05-28 | 2025-02-14
HR_0202_1960 | S.P018 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | HR Straight DC Cables - Vendor Manufacturing | 290416 | 321270.85 | 2025-03-21 | 2026-03-06
HR_0202_1480 | S.P043 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | Quench Protection - QPAs - Purchase-Racks | 4000 | 4481.65 | 2026-02-19 | 2026-08-14
HR_0202_1200 | S.P043 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | New PS (medium PS/ Corrector PS) - Purchase-Racks | 3000 | 3363.17 | 2026-04-16 | 2026-10-05
HR_0202_1620 | S.P043 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | Quench Detection - QDs - Purchase-Racks | 3000 | 3361.24 | 2025-10-21 | 2025-11-18
HR_0202_1725 | S.P057 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | HR Straight Sw Mag APS - DC, AC, Control Interlock Cable Order | 14900 | 16139.45 | 2024-05-28 | 2025-02-14
HR_0202_1730 | S.P091 | Bruno | 6.05.02.02 | Hadron Ring Straight Sections Modifications Power Supplies | HR Straight Sw Mag APS - Cable Tray Order | 36024 | 39020.64 | 2024-05-28 | 2025-02-14
HR_0203_1540 | A.PP027 | Weiss | 6.05.02.03 | Hadron Ring Straight Sections Modifications Vacuum System | HR SS Mod Vacuum - valves and pumps - Vendor Fabrication | 2020410 | 2270201.88 | 2026-05-04 | 2026-10-22
HR_0203_1420 | S.P028 | Weiss | 6.05.02.03 | Hadron Ring Straight Sections Modifications Vacuum System | HR SS Mod Vacuum - I&C systems - Vendor Fabrication | 320610 | 363346.67 | 2026-04-06 | 2027-04-05
HR_0203_1200 | S.P114 | Weiss | 6.05.02.03 | Hadron Ring Straight Sections Modifications Vacuum System | HR SS Mod Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | 1675350 | 1898670.8 | 2026-04-06 | 2027-04-05
HR_0401_1080 | S.P013 | Mahler | 6.05.03.01 | HR Injection System Upgrade Magnets | AtR to Blue Transfer Line Magnet - Material and construction of the magnets | 500000 | 560206.5 | 2025-11-19 | 2026-03-18
HR_0402_2620 | A.PP022 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | Corr H/V - Vendor Manufacturing - CAEN Corr H/V | 13144 | 14726.71 | 2025-10-21 | 2026-07-10
HR_0402_2800 | A.PP023 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | ATR Quad Cables/Corr H/V - Vendor Maunufacturing - DC Cable Order | 165336 | 185244.6 | 2025-10-21 | 2026-02-18
HR_0402_2360 | A.PP023 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | HR Injection DC Cables - Vendor Manufacturing - DC Cable | 96633.41 | 106900.09 | 2025-03-21 | 2026-03-06
HR_0402_2600 | D.APP30 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | ATR Quad/Dipole- Vendor Manufacturing - BiGen | 104329 | 116891.57 | 2025-10-21 | 2026-07-10
HR_0402_1940 | D.APP30 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | HR Inj Warm Line Quad/Dipole BiGen - Vendor Manufacturing | 62756 | 70312.64 | 2025-10-21 | 2026-07-10
HR_0402_2140 | D.APP42 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | HR Inj Warm Line Septum APS - Vendor Manufacturing | 1023827 | 1147109.08 | 2025-10-21 | 2026-07-10
HR_0402_3040 | D.APP42 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | ATR Dipole - Vendor Maunufacturing - APS | 150000 | 168061.95 | 2025-10-21 | 2026-02-18
HR_0402_1080 | D.APP42 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | New PS (medium PS/ Corrector PS) - Vendor Manufacturing - APS PS | 120000 | 134449.56 | 2025-10-21 | 2026-04-15
HR_0402_1420 | D.APP42 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | Quench Protection - Vendor Manufacturing - QPAs - APS | 51580 | 57790.9 | 2025-10-21 | 2026-02-18
HR_0402_2700 | S.P043 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | ATR Quad/Dipole/Corr H/V - Purchase-Racks | 6000 | 6730.21 | 2026-07-13 | 2026-10-05
HR_0402_1960 | S.P043 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | HR Inj Warm Line Quad/Dipole BiGen - Installation Racks Vendor Manufacturing | 6000 | 6722.48 | 2025-10-21 | 2026-07-10
HR_0402_1200 | S.P043 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | New PS (medium PS/ Corrector PS) - Purchase-Racks | 4000 | 4484.23 | 2026-04-16 | 2026-10-05
HR_0402_1480 | S.P043 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | Quench Protection - QPAs - Purchase-Racks | 3000 | 3361.24 | 2026-02-19 | 2026-08-14
HR_0402_1620 | S.P043 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | Quench Detection - QDs - Purchase-Racks | 3000 | 3361.24 | 2026-02-19 | 2026-07-28
HR_0402_2160 | S.P057 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | HR Inj Warm Line Septum/Quad/Dipole - DC, AC, Control Interlock Cable Order | 410425 | 459845.51 | 2025-10-21 | 2026-07-10
HR_0402_1980 | S.P057 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | HR Inj Warm Line Quad/Dipole BiGen - Travel | 9000 | 13045.88 | 2025-10-21 | 2026-07-10
HR_0402_2180 | S.P091 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | HR Inj Warm Line Septum/Quad/Dipole - Cable Tray Order | 144094 | 161444.79 | 2025-10-21 | 2026-07-10
HR_0402_2920 | S.P091 | Bruno | 6.05.03.02 | HR Injection System Upgrade Power Supplies | ATR Quad Cables/Corr H/V - Cable Tray - Vendor Maunufacturing - DC Cable Tray Order | 72074 | 80752.65 | 2025-10-21 | 2026-02-18
HR_0403_1200 | S.P115 | Weiss | 6.05.03.03 | HR Injection System Upgrade Vacuum System | HR Inj-Sys Upgrade Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | 259150 | 293694.18 | 2026-04-06 | 2027-04-05
HR_0404_2000 | A.PP057 | Sandberg | 6.05.03.04 | HR Injection System Upgrade Pulsed Devices | Construction - Material | 2995807 | 3474713.91 | 2025-10-21 | 2029-09-19
HR_0404_1820 | S.P008 | Sandberg | 6.05.03.04 | HR Injection System Upgrade Pulsed Devices | Long Lead Procurement - Material | 1528473 | 1734171.07 | 2025-10-21 | 2027-10-19
HR_0500_2080 | A.PP064 | Tuozzolo | 6.05.04 | HR SC Magnet Beam Pipe Upgrade | Carbon Coating System Service Bldg 919B - Building Modification SubContract – Pit and service crane | 2000000 | 2264534.4 | 2026-03-23 | 2027-03-22
HR_0500_1100 | S.P027 | Tuozzolo | 6.05.04 | HR SC Magnet Beam Pipe Upgrade | Bellows Upgrade - Shield inserts - Vendor Fabrication/Leadtime | 330000 | 361423.59 | 2024-10-04 | 2025-04-08
HR_0500_1460 | S.P050 | Tuozzolo | 6.05.04 | HR SC Magnet Beam Pipe Upgrade | Beam Tube Sleeves - Vendor Fabrication/Leadtime | 1719000 | 1902607.08 | 2025-03-21 | 2026-03-20
HR_0500_1810 | S.P059 | Tuozzolo | 6.05.04 | HR SC Magnet Beam Pipe Upgrade | Carbon Coating System - AC coating system material | 546000 | 598156.8 | 2024-10-04 | 2025-10-03
HR_0500_1980 | S.P093 | Tuozzolo | 6.05.04 | HR SC Magnet Beam Pipe Upgrade | Carbon Coating System Service Bldg - A/E Design | 309338 | 342378.52 | 2025-03-21 | 2026-03-20
HR_0500_1750 | S.P123 | Tuozzolo | 6.05.04 | HR SC Magnet Beam Pipe Upgrade | Carbon Coating System - Power Supplies & other equipment | 500000 | 547762.64 | 2024-10-04 | 2025-10-03
HR_0601_1210 | S.P053 | Gassner | 6.05.05.01 | Hadron Ring BPM Upgrade | BPM Electronics - V301 Module - PCB Assy - Non Labor | 598956 | 691060.61 | 2027-05-26 | 2027-11-23
HR_0601_1240 | S.P125 | Gassner | 6.05.05.01 | Hadron Ring BPM Upgrade | BPM Electronics - Construction - Non Labor | 255518.36 | 286628.5 | 2025-10-21 | 2026-10-20
HR_0601_1360 | S.P130 | Gassner | 6.05.05.01 | Hadron Ring BPM Upgrade | BPM Cables procure - Material | 615570 | 690517.52 | 2025-10-21 | 2026-10-20
HR_0601_1300 | S.P142 | Gassner | 6.05.05.01 | Hadron Ring BPM Upgrade | BPM Buttons and Housing procure- Material | 1471000 | 1702942.62 | 2027-03-15 | 2028-03-13
HR_0602_1120 | S.P045 | Gassner | 6.05.05.02 | Hadron Ring Injection Transfer Line Instrumentation | AtR Material - Construction | 343563 | 389824.94 | 2025-10-21 | 2027-10-20
HR_0700_1040 | S.P051 | Anerella | 6.05.06 | Hadron Ring Additional Snakes | Reconfiguring helical magnets in snakes - Non Labor | 441487 | 523737.09 | 2027-10-05 | 2029-10-03
HR_0802_1260 | S.P124 | Skaritka | 6.05.07.02 | SHC Electron Source | High Current HCeS - Procurements - materials/equipment for refurbishment, upgrade, and reassembly of systems | 250000 | 291488.63 | 2027-07-22 | 2028-05-09
HR_0801_1510 | S.P006 | Wang | 6.05.07.03 | SHC Design | Partner Lab Resources - LBNL [0.5 FTE] | 300000 | 308594.09 | 03-Jan-22* | 2022-12-30
HR_0804_1080 | A.PP042 | Witte | 6.05.07.04 | SHC Beam Transport Magnets | SHC Beam Transport Magnets - Fabrication | 6569583 | 7693616.31 | 2027-03-16 | 2029-03-14
HR_0804_1200 | S.P009 | Witte | 6.05.07.04 | SHC Beam Transport Magnets | Girder - Vendor Fabrication [$5K per Girder, 530 Girders] | 2650000 | 3096066.76 | 2027-08-05 | 2028-08-03
HR_0804_4800 | S.P116 | Weiss | 6.05.07.05 | SHC Beam Transport Vacuum Systems | e-beamlines Baked Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | 531600 | 607776.56 | 2026-08-21 | 2027-08-20
HR_0804_5400 | S.P117 | Weiss | 6.05.07.05 | SHC Beam Transport Vacuum Systems | e-loop Return Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | 277875 | 317693.59 | 2026-08-21 | 2027-08-20
HR_0804_6000 | S.P118 | Weiss | 6.05.07.05 | SHC Beam Transport Vacuum Systems | DC-Gun LINAC Vacuum - Chambers, Bellows, Supports - Vendor Fabrication | 387800 | 443370.48 | 2026-08-21 | 2027-08-20
HR_0804_5740 | S.P120 | Weiss | 6.05.07.05 | SHC Beam Transport Vacuum Systems | e-loop Return Vacuum - valves and pumps - Vendor Fabrication | 257400 | 295027.5 | 2027-01-19 | 2027-07-08
HR_0807_0080 | S.P129 | Gassner | 6.05.07.06.01 | SHC Beam Position Monitors | BPM System - Materials | 874726 | 990724.11 | 2025-10-21 | 2027-08-09
HR_0807_2080 | S.P131 | Gassner | 6.05.07.06.02 | SHC Charge and Current Monitors | Charge and Current Monitors - Materials | 974565 | 1103802.84 | 2025-10-21 | 2027-08-09
HR_0807_4080 | S.P141 | Gassner | 6.05.07.06.03 | SHC Profile and Emittance Monitors | Profile Monitors - Materials | 1499550 | 1698406.53 | 2025-10-21 | 2027-08-09
HR_0807_8080 | S.P139 | Gassner | 6.05.07.06.05 | SHC Synchrotron Radiation Monitors | Synchrotron Radiation Monitors - Synchrotron Radiation Monitors - Materials | 810630 | 918128.29 | 2025-10-21 | 2027-08-09
HR_0809_1460 | A.PP022 | Bruno | 6.05.07.07 | SHC Power Supplies and Cables | Small PS - Manufacturing - CAEN | 393120 | 440456.76 | 2026-05-15 | 2026-08-10
HR_0809_1660 | A.PP023 | Bruno | 6.05.07.07 | SHC Power Supplies and Cables | Cable - Manufacturing - DC Cable Order | 346979 | 390095.89 | 2026-03-04 | 2026-11-06
HR_0809_1260 | D.APP30 | Bruno | 6.05.07.07 | SHC Power Supplies and Cables | Medium PS - Vendor Manufacturing | 1494602 | 1674571.51 | 2025-12-04 | 2026-05-27
HR_0809_1360 | S.P043 | Bruno | 6.05.07.07 | SHC Power Supplies and Cables | Medium PS - Installation Racks | 132000 | 147894.52 | 2026-05-28 | 2026-07-23
HR_0809_1560 | S.P043 | Bruno | 6.05.07.07 | SHC Power Supplies and Cables | Small PS - Installation Racks | 15000 | 16960.82 | 2026-08-11 | 2026-11-04
HR_0809_1685 | S.P091 | Bruno | 6.05.07.07 | SHC Power Supplies and Cables | Cable Tray - Manufacturing - Cable Tray Order | 72047 | 80999.83 | 2026-03-04 | 2026-11-06
HR_0810_1020 | S.P019 | Tuozzolo | 6.05.07.08 | SHC Chicanes | Hadron Chicane magnet layout / interconnect Fabrication | 698243 | 795060.09 | 2026-06-18 | 2027-06-17
IR_0211_2800 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 5 - B2eR - Cold Mass Assembly - Parts Fabrication | 800214 | 911177.07 | 2026-08-12 | 2027-02-05
IR_0211_2620 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 5 - B2eR - Coil Assembly - Coil Parts Fabrication | 683109 | 765364.2 | 2026-03-23 | 2026-07-14
IR_0211_2940 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 5 - B2eR - Vertical Cold Test - Material | 495248 | 562327.11 | 2026-08-26 | 2026-11-20
IR_0211_6120 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 12 - Q2BpR - Coil Assembly - Coil Parts Fabrication | 338039 | 387454.56 | 2027-05-04 | 2027-08-25
IR_0211_6300 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 12 - Q2BpR - Cold Mass Assembly - Parts Fabrication | 280325 | 328385.76 | 2027-09-24 | 2028-03-21
IR_0211_6440 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 12 - Q2BpR - Vertical Cold Test - Material | 209210 | 245308.14 | 2027-10-08 | 2028-01-07
IR_0211_4300 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 8 - B0pF - Quad - Cold Mass Assembly - Parts Fabrication | 199067 | 228167.21 | 2027-02-08 | 2027-07-28
IR_0211_1300 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 2 - Q2eF -Cold Mass Assembly - Parts Fabrication | 175280 | 196385.99 | 2025-10-23 | 2026-04-17
IR_0211_3800 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 7 - B0pF - Dipole - Cold Mass Assembly - Parts Fabrication | 169871 | 194703.25 | 2026-12-09 | 2027-06-01
IR_0211_4120 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 8 - B0pF - Quad - Coil Assembly - Coil Parts Fabrication | 169936 | 193956.64 | 2026-09-10 | 2027-01-07
IR_0211_1800 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 3 - Q1eR - Cold Mass Assembly - Parts Fabrication | 164012 | 183761.18 | 2025-12-23 | 2026-06-15
IR_0211_1120 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 2 - Q2eF -Coil Assembly - Coil Parts Fabrication | 149629 | 167646.28 | 2025-10-21 | 2026-02-18
IR_0211_3620 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 7 - B0pF - Dipole - Coil Assembly - Coil Parts Fabrication | 145012 | 163641.13 | 2026-07-15 | 2026-11-05
IR_0211_1620 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 3 - Q1eR - Coil Assembly - Coil Parts Fabrication | 140010 | 156869.02 | 2025-10-21 | 2026-02-18
IR_0211_2300 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 4 - Q2eR - Cold Mass Assembly - Parts Fabrication | 137244 | 153769.96 | 2026-02-23 | 2026-08-11
IR_0211_5620 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 11 - Q1BpR - Coil Assembly - Coil Parts Fabrication | 125200 | 143502.11 | 2027-03-09 | 2027-06-29
IR_0211_4440 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 8 - B0pF - Quad - Vertical Cold Test - Material | 123202 | 141212.04 | 2027-02-23 | 2027-05-17
IR_0211_2120 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 4 - Q2eR - Coil Assembly - Coil Parts Fabrication | 117159 | 131266.47 | 2025-10-21 | 2026-02-18
IR_0211_1440 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 2 - Q2eF -Vertical Cold Test - Material | 108479 | 121541.28 | 2025-11-06 | 2026-02-05
IR_0211_5800 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 11 - Q1BpR - Cold Mass Assembly - Parts Fabrication | 103824 | 120711.93 | 2027-07-29 | 2028-01-24
IR_0211_3940 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 7 - B0pF - Dipole - Vertical Cold Test - Material | 105132 | 120500.51 | 2026-12-23 | 2027-03-22
IR_0211_1940 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 3 - Q1eR - Vertical Cold Test - Material | 101506 | 113728.64 | 2026-01-08 | 2026-04-03
IR_0211_3300 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 6 - B0ApF - Cold Mass Assembly - Parts Fabrication | 96629.09 | 110754.62 | 2026-10-08 | 2027-04-05
IR_0211_4800 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 9 - Q0eF - Cold Mass Assembly - Parts Fabrication | 85424 | 97911.54 | 2027-04-06 | 2027-09-23
IR_0211_2440 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 4 - Q2eR - Vertical Cold Test - Material | 84939 | 95166.76 | 2026-03-09 | 2026-06-01
IR_0211_3120 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 6 - B0ApF - Coil Assembly - Coil Parts Fabrication | 82488.25 | 92420.91 | 2026-05-18 | 2026-09-09
IR_0211_5940 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 11 - Q1BpR - Vertical Cold Test - Material | 77485 | 89663.1 | 2027-08-12 | 2027-11-05
IR_0211_4620 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 9 - Q0eF - Coil Assembly - Coil Parts Fabrication | 72923 | 83583.1 | 2026-11-06 | 2027-03-08
IR_0211_5120 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 10 - Q1ApR - Coil Assembly - Coil Parts Fabrication | 71989.8 | 82513.48 | 2027-01-08 | 2027-05-03
IR_0211_5300 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 10 - Q1ApR - Cold Mass Assembly - Parts Fabrication | 59698.86 | 68884.84 | 2027-06-02 | 2027-11-22
IR_0211_3440 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 6 - B0ApF - Vertical Cold Test - Material | 59803.19 | 68545.4 | 2026-10-23 | 2027-01-22
IR_0211_4940 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 9 - Q0eF - Vertical Cold Test - Material | 52868 | 60596.4 | 2027-04-20 | 2027-07-14
IR_0211_5440 | D.APP05 | Witte | 6.06.02.01.01 | Direct Wind Magnets | Direct Wind Magnets 10 - Q1ApR - Vertical Cold Test - Material | 44554.08 | 51067.13 | 2027-06-16 | 2027-09-09
IR_0212_1080 | A.PP013 | Witte | 6.06.02.01.02 | Collared Magnets | Collared Magnet 1 - Q1ApF - Fabrication/ Manufacturing | 2049000 | 2364060.39 | 2026-01-15 | 2029-01-16
IR_0212_1260 | A.PP016 | Witte | 6.06.02.01.02 | Collared Magnets | Collared Magnet 2 - Q1BpF - Fabrication/ Manufacturing | 2049000 | 2368382.41 | 2026-02-13 | 2029-02-13
IR_0212_1440 | A.PP017 | Witte | 6.06.02.01.02 | Collared Magnets | Collared Magnet 3 - Q2pF - Fabrication/ Manufacturing | 2049000 | 2368382.41 | 2026-02-13 | 2029-02-13
IR_0212_1620 | A.PP018 | Witte | 6.06.02.01.02 | Collared Magnets | Collared Magnet 4 - B1pF - Fabrication/ Manufacturing | 2185000 | 2525581.05 | 2026-02-13 | 2029-02-13
IR_0212_1800 | A.PP019 | Witte | 6.06.02.01.02 | Collared Magnets | Collared Magnet 5 - B1ApF - Fabrication/ Manufacturing | 2185000 | 2525581.05 | 2026-02-13 | 2029-02-13
IR_0213_1080 | A.PP003 | Witte | 6.06.02.01.03 | IR Warm Magnets | IR Magnets Warm - Vendor Manufacturing / Fabrication | 2413369 | 2707204.01 | 2025-10-21 | 2026-10-20
IR_0215_1040 | S.P007 | Tuozzolo | 6.06.02.01.05 | IR Magnet Cryostats | IR Magnet Cryostats, Forward Fabrication | 1337062 | 1520726.58 | 2025-12-01 | 2027-11-30
IR_0215_1220 | S.P092 | Tuozzolo | 6.06.02.01.05 | IR Magnet Cryostats | B0pF Cryostat Fabrication | 279967 | 325748.25 | 2026-12-01 | 2028-11-29
IR_0215_1280 | S.P184 | Tuozzolo | 6.06.02.01.05 | IR Magnet Cryostats | IR Magnet Cryostats, Rear Fabrication | 870903 | 974477.12 | 2025-03-13 | 2027-03-12
IR_0202_1140 | D25.APP03 | Witte | 6.06.02.02 | IR Spin Rotator Magnets | Spin Rotator - Fabrication-Manufacturing (Cost Module 1-4=$9.45/ 5-16=$19.85) | 29310000 | 34249565.45 | 2026-08-05 | 2029-08-03
IR_0202_1380 | S.P012 | Witte | 6.06.02.02 | IR Spin Rotator Magnets | Spin Rotator Quad - Fabrication Manufacturing | 748464 | 867102.28 | 2026-03-23 | 2029-03-21
IR_0203_1440 | A.PP012 | Bruno | 6.06.02.03 | IR Power Supplies | PED, Quench Protection - Vendor Manufacturing - OCEM | 1200742 | 1345713.74 | 2025-10-21 | 2026-10-05
IR_0203_1100 | A.PP012 | Bruno | 6.06.02.03 | IR Power Supplies | IR PS - Vendor Manufacturing - OCEM | 824091 | 930178.73 | 2025-10-21 | 2027-03-18
IR_0203_1300 | D.APP29 | Bruno | 6.06.02.03 | IR Power Supplies | Bus/ Cable - Vendor Manufacturing | 306320 | 343204.91 | 2025-10-21 | 2026-07-10
IR_0203_1080 | D.APP30 | Bruno | 6.06.02.03 | IR Power Supplies | IR PS - Vendor Manufacturing - BiGen | 397417 | 448577.69 | 2025-10-21 | 2027-03-18
IR_0203_1200 | S.P043 | Bruno | 6.06.02.03 | IR Power Supplies | IR PS - Purchase-Racks | 51600 | 59143.04 | 2027-03-19 | 2027-06-11
IR_0203_1645 | S.P043 | Bruno | 6.06.02.03 | IR Power Supplies | Quench Detection QD BNL - Vendor Manufacturing - Purchasing Racks | 3000 | 3318.73 | 2025-03-21 | 2026-03-06
IR_0204_1160 | A.PP001.B | Hetzel | 6.06.02.04 | IR Vacuum | IR Vacuum - Procurement (NonLabor) | 2262545 | 2614119.1 | 2026-12-09 | 2028-03-14
IR_0206_1320 | S.P135 | Gassner | 6.06.02.05.01 | IR Beam Position Monitors | BPM Pick-up - Materials | 861015 | 1018786.84 | 2027-09-08 | 2029-07-25
IR_0207_1120 | A.PP071 | Witte | 6.06.02.06 | Matching Magnets | Collared Dipole - Fabrication Dipole 2 | 2000000 | 2350962.17 | 2026-11-06 | 2029-11-06
IR_0207_1100 | A.PP071 | Witte | 6.06.02.06 | Matching Magnets | Collared Dipole - Fabrication Dipole 1 | 2000000 | 2331783.33 | 2026-06-30 | 2029-06-28
IR_0207_1160 | A.PP071 | Witte | 6.06.02.06 | Matching Magnets | Collared Dipole - Cryostat 2 | 350000 | 411418.38 | 2026-11-06 | 2029-11-06
IR_0207_1140 | A.PP071 | Witte | 6.06.02.06 | Matching Magnets | Collared Dipole - Cryostat 1 | 350000 | 408062.08 | 2026-06-30 | 2029-06-28
IR_0208_1720 | S.P015 | Witte | 6.06.02.07 | Cables | Cable - SC strand NbTi Matching Magnets - Fabrication | 600000 | 689906.63 | 2027-02-23 | 2027-11-05
IR_0208_1080 | S.P086 | Witte | 6.06.02.07 | Cables | Cable - SC Strand NbTi IR Magnets - Fabrication | 300000 | 336123.9 | 2025-10-21 | 2026-07-10
EJ_0305_9100 | A.PP025 | Ranjbar | 6.06.03.01.01 | ESR Machine Protection - Single Turn Extraction Kicker | HR Machine Protection Beam Abort Kicker Electrical Components - Fabrication | 2210800 | 2477009.06 | 2026-02-23 | 2026-09-23
EJ_0305_9260 | S.P089 | Ranjbar | 6.06.03.01.01 | ESR Machine Protection - Single Turn Extraction Kicker | HR Machine Protection Beam Abort Kicker Mechanical Components - Fabrication | 531000 | 595623.5 | 2026-05-18 | 2026-10-07
IR_0204_1380 | S.P055 | Hetzel | 6.06.03.02 | Collimation System Design and Integration | Movable ESR Collimators - Procurement Fabrication/leadtime | 322400 | 372480.48 | 2026-10-23 | 2028-04-04
HR_0603_2960 | S.P128 | Gassner | 6.06.03.02 | Collimation System Design and Integration | HSR Collimators - Material | 302272 | 342973.96 | 2025-10-21 | 2027-10-20
AS_0302_1480 | S.P052 | Dalesio | 6.07.02.12.01 | Controls - Hardware Procurements - Global Controls - Timing, Common Platform FECs MCHINE Protection | Beam Sync System - Non Labor | 694200 | 777790.7 | 2025-10-21 | 2026-01-20
AS_0302_2440 | S.P094 | Dalesio | 6.07.02.12.01 | Controls - Hardware Procurements - Global Controls - Timing, Common Platform FECs MCHINE Protection | Legacy Equipment Expansion - Non Labor | 250000 | 280103.25 | 2025-10-21 | 2026-01-20
AS_0305_2220 | S.P021 | Dalesio | 6.07.02.12.03 | Controls - Hardware Procurements - Diagnostics | Instrumentation General Support - Non Labor | 470600 | 527266.36 | 2025-10-21 | 2026-01-20
AS_0307_1920 | S.P066 | Dalesio | 6.07.02.12.03 | Controls - Hardware Procurements - Diagnostics | Instrumentation BPM Support - Non Labor | 1619200 | 1814172.73 | 2025-10-21 | 2026-01-20
AS_0307_1640 | S.P069 | Dalesio | 6.07.02.12.05 | Controls - Hardware Procurements - Power Supply | Power Supply Controls - Non Labor | 1628350 | 1824424.51 | 2025-10-21 | 2026-01-20
AS_0307_1540 | S.P108 | Dalesio | 6.07.02.12.07 | Controls - Hardware Procurements - Water and Cryo | General Data I/O - Non Labor | 991400 | 1110777.45 | 2025-10-21 | 2026-01-20
AS_0302_1180 | A.PP069 | Dalesio | 6.07.02.12.10 | Controls - Hardware Procurements - Network | Network Systems - Non Labor | 3249650 | 3640950.11 | 2025-10-21 | 2026-01-20
AS_0302_3290 | S.P094 | Dalesio | 6.07.02.12.10 | Controls - Hardware Procurements - Network | Data Management – Large High Availability Storage system (500TB+) - Delivery & Acceptance | 532648 | 596785.74 | 2025-10-21 | 2025-11-03
AS_0302_3350 | S.P094 | Dalesio | 6.07.02.12.10 | Controls - Hardware Procurements - Network | Data Management – Additional High Availability Storage Systems - Delivery & Acceptance | 291904 | 327053.04 | 2025-10-21 | 2025-11-03
RD_0305_1680 | S.P071 | TBD | 6.08.02.01 | 197 MHz Crab Cavity R&D | Crab Cavity Prototype - Fabrication - FPC conditioning hardware (include amplifier) | 300000 | 306900 | 2022-07-05 | 2022-08-31
RD_0305_1220 | S.P072 | TBD | 6.08.02.01 | 197 MHz Crab Cavity R&D | Crab Cavity Prototype - Fabrication - Cavity | 300000 | 313958.7 | 2022-12-09 | 2023-06-08
RD_0308_1160 | S.P099 | TBD | 6.08.02.02 | ESR 1-Cell Cavity R&D | Nb Cavity - Fabrication (Incl. Tooling & Cu Model) | 500000 | 523328.52 | 2023-01-05 | 2023-10-02
RD_0304_2020 | S.P110 | Zaltsman | 6.08.02.03.01 | HP FPC Prototype | FPC: Component Fabrications - Material | 1112608 | 1170910.97 | 2023-01-03 | 2024-01-02
HR_0305_1530 | S.P183 | Zaltsman | 6.08.02.03.01 | HP FPC Prototype | 591 MHz - 600 kW CW Klystron: Fabrication | 1900000 | 1992532.26 | 2022-09-06 | 2023-12-11
HR_0305_1610 | S.P184 | Zaltsman | 6.08.02.03.01 | HP FPC Prototype | 591 MHz - 600 kW Circulator with Load: Fabrication | 800000 | 835792.64 | 2022-09-06 | 2023-09-05
RD_0304_2200 | S.P106 | Zaltsman | 6.08.02.03.02 | HP HOM Absorber Prototype | BLA: Component Fabrications - Material | 330000 | 347042.48 | 2023-01-03 | 2023-12-15
IR_0205_2050 | D.APP12.A | TBD | 6.08.03.01.01.02 | CS: 197 MHz Crab FA Procurement | RF-CRAB-1-CM: Materials (Prototype) | 3938449 | 4401888.26 | 2025-06-16 | 2026-11-20
SR_0501_1120 | D25.APP04.A | TBD | 6.08.03.02.01.02 | CS: 591 MHz FA Procurement | RF-ESR-1-CM: Materials (Prototype) | 1774379 | 2003743.65 | 2025-10-21 | 2027-04-02
SR_0501_1180 | D25.APP04.B | TBD | 6.08.04.01.02.02 | CM: 591 MHz 1-Cell Procurement | RF-ESR-1-CM: Materials (Production) | 20507918 | 23790368.94 | 2027-04-05 | 2028-04-25
EJ_0204_1120 | A.PP007.A | TBD | 6.08.04.02.01.02 | CS: 591 MHz 5-Cell Procurement | RF-RCS-1-CM: Materials (Prototype) | 2005880 | 2228465.98 | 2025-03-21 | 2026-08-25
EJ_0204_1180 | A.PP007.B | TBD | 6.08.04.02.02.02 | CM: 591 MHz 5-Cell Procurement | RF-RCS-1-CM: Materials (Production) | 2916101 | 3334145.49 | 2026-08-26 | 2027-07-26
HR_0805_1000 | D.APP04 | TBD | 6.08.04.02.02.02 | CM: 591 MHz 5-Cell Procurement | RF-ERL-1-CM: Materials (Production) | 11664404 | 13680970.66 | 2027-10-21 | 2028-10-04
HR_0305_1000 | S.P159 | TBD | 6.08.04.02.02.02 | CM: 591 MHz 5-Cell Procurement | RF-HR-5-CM: Materials (Production) | 1458050 | 1679520.16 | 2027-07-27 | 2027-10-20
HR_0805_5100 | A.PP080.A | TBD | 6.08.04.03.01.02 | CS: 1773 MHz 5-Cell Procurement | RF-ERL-2-CM: Materials (Prototype) | 1388339 | 1602446.52 | 2027-03-30 | 2027-12-27
HR_0805_5160 | A.PP080.B | TBD | 6.08.04.03.02.02 | CM: 1773 MHz 5-Cell Procurement | RF-ERL-2-CM: Materials (Production) | 2252783 | 2641489.44 | 2027-12-28 | 2028-08-15
IR_0205_2080 | D.APP12.B | TBD | 6.08.04.04.02.02 | CM: 197 MHz Crab Procurement | RF-CRAB-1-CM: Materials (Production) | 9443795 | 10838512.22 | 2026-11-23 | 2027-10-20
IR_0205_5050 | D.APP10.A | TBD | 6.08.04.05.02.02 | CM: 394 MHz Crab Procurement | RF-CRAB-2-CM: Materials (Prototype) | 1991815 | 2260028.99 | 2026-02-12 | 2027-07-20
IR_0205_5080 | D.APP10.B | TBD | 6.08.04.05.02.02 | CM: 394 MHz Crab Procurement | RF-CRAB-2-CM: Materials (Production) | 7784805 | 9082129.03 | 2027-07-21 | 2028-06-16
HR_0805_6410 | S.P103.A | TBD | 6.08.04.06.01.02 | CS: ERL Inj Procurement | RF-ERL-4-CAV: Materials (First Article) | 700000 | 774101.14 | 2025-01-13 | 2026-04-15
EJ_0204_2050 | S.P097.A | Zaltsman | 6.08.05.01.01 | 295 MHz Cavity Components | RF-RCS-2-CAV: Fabrication - 2 Cavities | 750000 | 816902.85 | 2024-06-12 | 2025-09-12
EJ_0204_2410 | S.P098.A | Zaltsman | 6.08.05.02.01 | 148 MHz Cavity Components | RF-RCS-3-CAV: Fabrication | 400000 | 443846.91 | 2025-03-21 | 2026-06-22
HR_0301_1100 | S.P065.A | Zaltsman | 6.08.05.04.01 | 24.6 MHz Cavity Components | RF-HR-1-CAV: Materials (First Article) | 150000 | 158611.3 | 2023-03-20 | 2024-03-18
HR_0301_1160 | S.P065.B | Zaltsman | 6.08.05.04.02 | 24.6 MHz Cavity Assembly and Test | RF-HR-1-CAV: Materials (Production) | 150000 | 171927.45 | 2026-10-28 | 2027-04-29
HR_0302_1100 | S.P154.A | Zaltsman | 6.08.05.05.01 | 49.2 MHz Cavity Components | RF-HR-2-CAV: Materials (First Article) | 700000 | 759050.02 | 2024-03-15 | 2025-06-16
HR_0302_1160 | S.P154.B | Zaltsman | 6.08.05.05.02 | 49.2 MHz Cavity Assembly and Test | RF-HR-2-CAV: Materials (Production) | 700000 | 784289.1 | 2025-12-10 | 2026-09-10
HR_0303_1100 | S.P155.A | Zaltsman | 6.08.05.06.01 | 98.4 MHz Cavity Components | RF-HR-3-CAV: Materials (First Article) | 700000 | 768744.89 | 2024-09-11 | 2025-12-16
HR_0303_1160 | S.P155.B | Zaltsman | 6.08.05.06.02 | 98.4 MHz Cavity Assembly and Test | RF-HR-3-CAV: Materials (Production) | 700000 | 794827.67 | 2026-06-10 | 2027-03-16
HR_0304_1100 | S.P156.A | Zaltsman | 6.08.05.07.01 | 197 MHz Cavity (HSR Store 1) Components | RF-HR-4-CAV: Materials (First Article) | 125000 | 139107 | 2025-06-16 | 2026-06-15
HR_0304_1160 | S.P156.B | Zaltsman | 6.08.05.07.02 | 197 MHz Cavity (HSR Store 1) Assembly and Test | RF-HR-4-CAV: Materials (Production) | 750000 | 870500.71 | 2026-12-09 | 2028-09-29
HR_0805_6080 | S.P102.B | Zaltsman | 6.08.05.08.02 | 197 MHz Cavity (ERL Inj) Assembly and Test | RF-ERL-3-CAV: Materials (Production) | 875000 | 1073714.25 | 2029-10-11 | 1930-07-16
SR_0501_1360 | D50.APP01.A | Zaltsman | 6.08.06.01 | SSA: 591 MHz, 400 kW with 200 kW Variant | RF-ESR-1-PWR: Materials (Prototype) | 10000000 | 11018953.51 | 2024-10-04 | 2026-02-11
SR_0501_1420 | D50.APP01.B | Zaltsman | 6.08.06.01 | SSA: 591 MHz, 400 kW with 200 kW Variant | RF-ESR-1-PWR: Materials (Production) - Phase 3 | 23457190 | 26649271.63 | 2026-05-13 | 2027-05-12
SR_0501_1482 | D50.APP01.C | Zaltsman | 6.08.06.01 | SSA: 591 MHz, 400 kW with 200 kW Variant | RF-ESR-1-PWR: Materials (Production) - Phase 4 | 41312603 | 48362472.12 | 2027-09-07 | 2028-09-05
HR_0805_6170 | D.APP41.A | Zaltsman | 6.08.06.02.01 | SSA: ERL Injector: Fundamental | RF-ERL-3-PWR: Materials (First Article) | 956580 | 1113908.86 | 2027-06-25 | 2028-05-15
HR_0805_6200 | D.APP41.B | Zaltsman | 6.08.06.02.01 | SSA: ERL Injector: Fundamental | RF-ERL-3-PWR: Materials (Production) | 5739480 | 6879421.46 | 2028-09-28 | 2028-12-27
HR_0805_1180 | A.PP093 | Zaltsman | 6.08.06.02.02 | SSA: ERL Main Linac Fundamental | RF-ERL-1-PWR: Materials (Production) | 3171665 | 3665169.73 | 2026-11-20 | 2028-03-28
HR_0805_1150 | S.P158.A | Zaltsman | 6.08.06.02.02 | SSA: ERL Main Linac Fundamental | RF-ERL-1-PWR: Materials (First Article) | 453095 | 507653.53 | 2026-03-13 | 2026-09-08
EJ_0204_1360 | S.P146.A | Zaltsman | 6.08.06.02.03 | SSA: RCS: Fundamental | RF-RCS-1-PWR: Materials (Prototype) | 648928 | 719115.02 | 2025-04-29 | 2026-03-19
EJ_0204_1420 | S.P146.B | Zaltsman | 6.08.06.02.03 | SSA: RCS: Fundamental | RF-RCS-1-PWR: Materials (Production) | 1297856 | 1454134.73 | 2026-06-15 | 2026-09-09
HR_0305_1162 | S.P121 | Zaltsman | 6.08.06.02.04 | SSA: HSR: Store 2 | RF-HR-5-PWR: Materials (First Article) | 648928 | 727067.37 | 2025-12-12 | 2026-06-11
IR_0205_2170 | A.PP054.A | Zaltsman | 6.08.06.03.01 | SSA: Crab: 197 MHz | RF-CRAB-1-PWR: Materials (Prototype) | 563771 | 623020.38 | 2025-03-21 | 2026-02-09
IR_0205_2200 | A.PP054.B | Zaltsman | 6.08.06.03.01 | SSA: Crab: 197 MHz | RF-CRAB-1-PWR: Materials (Production) | 3946400 | 4421597.86 | 2026-05-06 | 2026-07-31
IR_0205_5170 | A.PP024.A | Zaltsman | 6.08.06.03.02 | SSA: Crab: 394 MHz | RF-CRAB-2-PWR: Materials (Prototype) | 563771 | 639378.65 | 2026-05-05 | 2027-03-25
IR_0205_5200 | A.PP024.B | Zaltsman | 6.08.06.03.02 | SSA: Crab: 394 MHz | RF-CRAB-2-PWR: Materials (Production) | 2818857 | 3230925.97 | 2027-06-21 | 2027-09-15
EJ_0204_2170 | S.P100.A | Zaltsman | 6.08.06.03.03 | SSA: RCS Bunch Merge 1: 296 MHz | RF-RCS-2-PWR: Materials (Prototype) | 324246 | 362769.99 | 2025-06-16 | 2026-12-15
EJ_0204_2200 | S.P100.B | Zaltsman | 6.08.06.03.03 | SSA: RCS Bunch Merge 1: 296 MHz | RF-RCS-2-PWR: Materials (Production) | 324246 | 373696.72 | 2027-05-18 | 2027-11-15
EJ_0204_2530 | S.P101.A | Zaltsman | 6.08.06.03.04 | SSA: RCS Bunch Merge 2: 148 MHz | RF-RCS-3-PWR: Materials (First Article) | 324246 | 362769.99 | 2025-06-16 | 2026-12-15
HR_0302_1340 | S.P157.A | Zaltsman | 6.08.06.03.05 | SSA: HSR Bunch Split 1: 49 MHz | RF-HR-2-PWR: Materials (First Article) | 525440 | 582568.38 | 2025-01-24 | 2026-07-22
HR_0302_1400 | S.P157.B | Zaltsman | 6.08.06.03.05 | SSA: HSR Bunch Split 1: 49 MHz | RF-HR-2-PWR: Materials (Production) | 525440 | 602250.4 | 2027-01-26 | 2027-07-22
HR_0303_1340 | S.P149.A | Zaltsman | 6.08.06.03.06 | SSA: HSR Bunch Split 2: 98 MHz | RF-HR-3-PWR: Materials (First Article) | 525440 | 570678.13 | 2024-03-15 | 2025-09-10
HR_0303_1400 | S.P149.B | Zaltsman | 6.08.06.03.06 | SSA: HSR Bunch Split 2: 98 MHz | RF-HR-3-PWR: Materials (Production) | 525440 | 588709.81 | 2026-03-17 | 2026-09-10
HR_0805_5340 | S.P150.A | Zaltsman | 6.08.06.04.01 | SSA: ERL Main Linac Third Harmonic: 1773 MHz | RF-ERL-2-PWR: Materials (Prototype) | 425518 | 481814.7 | 2025-12-12 | 2027-06-11
HR_0805_5400 | S.P150.B | Zaltsman | 6.08.06.04.01 | SSA: ERL Main Linac Third Harmonic: 1773 MHz | RF-ERL-2-PWR: Materials (Production) | 851036 | 998867.26 | 2027-11-12 | 2028-10-16
HR_0805_6530 | S.P104.A | Zaltsman | 6.08.06.04.02 | SSA: ERL Injector Third Harmonic: 1773 MHz | RF-ERL-4-PWR: Materials (First Article) | 456178 | 507773.32 | 2025-04-16 | 2026-10-13
EJ_0204_1600 | S.P060.A | TBD | 6.08.07.03.03 | RCS: Production Procurement, Assembly, Test | RF-RCS-1-CTRL: Materials (Prototype) | 55792 | 61104.68 | 2025-01-29 | 2025-04-22
EJ_0204_1660 | S.P060.B | TBD | 6.08.07.03.03 | RCS: Production Procurement, Assembly, Test | RF-RCS-1-CTRL: Materials (Production) | 223169 | 246331.94 | 2025-05-14 | 2025-12-15
SR_0501_1600 | S.P148.A | TBD | 6.08.07.04.03 | ESR: Production Procurement, Assembly, Test | RF-ESR-1-CTRL: Materials (Prototype) | 55792 | 61104.68 | 2025-03-06 | 2025-05-28
SR_0501_1660 | S.P148.B | TBD | 6.08.07.04.03 | ESR: Production Procurement, Assembly, Test | RF-ESR-1-CTRL: Materials (Production) | 1004261 | 1120084.18 | 2025-07-25 | 2026-06-30
HR_0301_1580 | S.P070.A | TBD | 6.08.07.05.03 | HSR: Production Procurement, Assembly, Test | RF-HR-1-CTRL: Materials (First Article) | 55792 | 63947.84 | 2026-12-16 | 2027-06-15
HR_0301_1640 | S.P070.B | TBD | 6.08.07.05.03 | HSR: Production Procurement, Assembly, Test | RF-HR-1-CTRL: Materials (Production) | 223169 | 261675.7 | 2028-02-15 | 2028-08-15
HR_0304_1580 | S.P151.A | TBD | 6.08.07.05.03 | HSR: Production Procurement, Assembly, Test | RF-HR-4-CTRL: Materials (First Article) | 55792 | 62510.08 | 2025-10-16 | 2026-04-17
HR_0304_1640 | S.P151.B | TBD | 6.08.07.05.03 | HSR: Production Procurement, Assembly, Test | RF-HR-4-CTRL: Materials (Production) | 334754 | 385454.3 | 2026-11-16 | 2027-12-22
HR_0805_6290 | S.P068.A | TBD | 6.08.07.06.03 | ERL: Production Procurement, Assembly, Test | RF-ERL-3-CTRL: Materials (First Article) | 55792 | 65418.63 | 2027-11-01 | 2028-06-07
HR_0805_6320 | S.P068.B | TBD | 6.08.07.06.03 | ERL: Production Procurement, Assembly, Test | RF-ERL-3-CTRL: Materials (Production) | 334754 | 401541.77 | 2029-01-09 | 2029-04-04
HR_0805_1360 | S.P158.A | TBD | 6.08.07.06.03 | ERL: Production Procurement, Assembly, Test | RF-ERL-1-CTRL: Materials (First Article) | 55792 | 63947.84 | 2027-03-12 | 2027-09-07
HR_0805_1420 | S.P158.B | TBD | 6.08.07.06.03 | ERL: Production Procurement, Assembly, Test | RF-ERL-1-CTRL: Materials (Production) | 557923 | 654727.18 | 2028-02-11 | 2028-10-10
IR_0205_2290 | A.PP001.A | TBD | 6.08.07.07.03 | Crab: Production Procurement, Assembly, Test | RF-CRAB-1-CTRL: Materials (Prototype) | 55792 | 62510.08 | 2026-01-20 | 2026-04-13
IR_0205_2320 | A.PP001.B | TBD | 6.08.07.07.03 | Crab: Production Procurement, Assembly, Test | RF-CRAB-1-CTRL: Materials (Production) | 502131 | 569900.31 | 2026-07-01 | 2027-02-03
IR_0205_5290 | S.P016.A | TBD | 6.08.07.07.03 | Crab: Production Procurement, Assembly, Test | RF-CRAB-2-CTRL: Materials (Prototype) | 55792 | 63947.84 | 2027-03-05 | 2027-05-26
IR_0205_5320 | S.P016.B | TBD | 6.08.07.07.03 | Crab: Production Procurement, Assembly, Test | RF-CRAB-2-CTRL: Materials (Production) | 334754 | 390533.05 | 2027-08-16 | 2028-03-20
HR_0808_1220 | D25.APP06 | TBD | 6.09.02.03.01 | Procurement - Satellite Refrigerators | Satellite Cryoplant - Procurement - Vendor Fabrication and Delivery - IR02 SHC | 10000000 | 11694967 | 2027-02-23 | 2029-02-21
AS_0205_1220 | D25.APP06 | TBD | 6.09.02.03.01 | Procurement - Satellite Refrigerators | Satellite Cryoplant - Procurement - Vendor Fabrication and Delivery - IR10 | 10100000 | 11389693.24 | 2025-07-15 | 2027-07-14
AS_0204_1260 | D25.APP06 | TBD | 6.09.02.03.01 | Procurement - Satellite Refrigerators | Satellite Cryoplant - Procurement - Vendor Fabrication and Delivery - IR02 SHC,IR06,IR10 | 8600000 | 9849103.62 | 2025-07-15 | 2028-11-21
HR_0808_1240 | S.P058 | TBD | 6.09.02.03.02 | Procurement - 2K Satellite Plant Auxiliary Systems | LN2 Storage Dewar System - Procurement - Vendor Fabrication and Delivery - IR02 SHC | 500000 | 568925.35 | 2026-05-14 | 2027-07-26
AS_0204_1240 | S.P058 | TBD | 6.09.02.03.02 | Procurement - 2K Satellite Plant Auxiliary Systems | LN2 Storage Dewar System - Procurement - Vendor Fabrication and Delivery - IR06 | 325000 | 357393.8 | 2024-10-04 | 2025-12-18
AS_0205_1240 | S.P058 | TBD | 6.09.02.03.02 | Procurement - 2K Satellite Plant Auxiliary Systems | LN2 Storage Dewar System - Procurement - Vendor Fabrication and Delivery - IR10 | 325000 | 357393.8 | 2024-10-04 | 2025-12-18
HR_0808_1260 | D.APP25 | TBD | 6.09.02.04.01 | Installation - IR02 | Cryogenics System Installation Contract - NonLabor, OnSite - IR02 SHC | 2820000 | 3393864.58 | 2029-02-22 | 2029-11-06
AS_0204_1320 | D.APP25 | TBD | 6.09.02.04.02 | Installation - IR06 | Cryogenics System Installation Contract - NonLabor, OnSite - IR02 SHC,IR06,IR10 | 4500000 | 5401194.42 | 2028-11-22 | 2029-10-09
AS_0205_1260 | D.APP25 | TBD | 6.09.02.04.03 | Installation - IR10 | Cryogenics System Installation Contract - NonLabor, OnSite - IR10 | 3750000 | 4455699.15 | 2028-05-03 | 2029-05-02
AS_0207_1080 | D.APP24 | TBD | 6.09.03.03.01 | Procurement - Distribution Lines | Cryogenic Distribution System - Procurement - Vendor Fabrication and Delivery - IR02 HSR Mods SHC | 1090000 | 1208688.55 | 2025-01-10 | 2026-08-13
AS_0201_1160 | D.APP24 | TBD | 6.09.03.03.01 | Procurement - Distribution Lines | Cryogenic Distribution System - Procurement - Vendor Fabrication and Delivery - IR12 | 180000 | 198908.48 | 2025-01-10 | 2026-03-24
AS_0203_1260 | D.APP24 | TBD | 6.09.03.04 | Reconfiguration Existing and New 4k Distribution - Installation | Cryogenic Distribution System - Procurement - Vendor Fabrication and Delivery - IR04 | 1800000 | 2015824.86 | 2025-01-10 | 2027-06-03
AS_0203_1280 | D.APP25 | TBD | 6.09.03.04 | Reconfiguration Existing and New 4k Distribution - Installation | Cryogenics System Installation Contract - NonLabor, OnSite - IR04 | 440000 | 527011.86 | 2028-09-11 | 2029-08-10
AS_0207_1100 | D.APP25 | TBD | 6.09.03.04 | Reconfiguration Existing and New 4k Distribution - Installation | Cryogenics System Installation Contract - NonLabor, OnSite - IR02 HSR Mods SHC | 180000 | 205766.25 | 2026-08-14 | 2027-09-27
AS_0201_1180 | D.APP25 | TBD | 6.09.03.04 | Reconfiguration Existing and New 4k Distribution - Installation | Cryogenics System Installation Contract - NonLabor, OnSite - IR12 | 40000 | 45645.85 | 2026-07-31 | 2027-06-17
HR_0808_1200 | D.APP24 | TBD | 6.09.04.03.01 | Procurement - IR02 | Cryogenic Distribution System - Procurement - Vendor Fabrication and Delivery - IR02 SHC | 2910000 | 3351644.47 | 2026-08-14 | 2028-03-23
AS_0204_1200 | D.APP24 | TBD | 6.09.04.03.02 | Procurement - IR06 | Cryogenic Distribution System - Procurement - Vendor Fabrication and Delivery - IR06 | 3657317 | 4055557.04 | 2025-01-10 | 2026-08-13
AS_0205_1200 | D.APP24 | TBD | 6.09.04.03.03 | Procurement - IR10 | Cryogenic Distribution System - Procurement - Vendor Fabrication and Delivery - IR10 | 3794390 | 4207555.72 | 2025-01-10 | 2026-08-13
AS_0204_1160 | S.P076 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Cable and Tray Procurement - Vendor Fabrication and Delivery - IR06 | 358496 | 392633.06 | 2024-10-04 | 2025-09-05
HR_0808_1160 | S.P076 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Cable and Tray Procurement - Vendor Fabrication and Delivery - IR02 SHC | 250000 | 282428.15 | 2026-03-05 | 2027-02-03
AS_0205_1160 | S.P076 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Cable and Tray Procurement - Vendor Fabrication and Delivery - IR10 | 186040 | 203755.29 | 2024-10-04 | 2025-09-05
AS_0203_1160 | S.P076 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Cable and Tray Procurement - Vendor Fabrication and Delivery - IR04 | 148136 | 162241.95 | 2024-10-04 | 2025-09-05
AS_0205_1100 | S.P077 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Hardware Procurement - Vendor Fabrication and Delivery - IR10 | 469800 | 535055.3 | 2026-06-30 | 2027-06-01
HR_0808_1100 | S.P077 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Hardware Procurement - Vendor Fabrication and Delivery - IR02 SHC | 400000 | 472066.56 | 2028-02-08 | 2029-01-08
AS_0204_1100 | S.P077 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Hardware Procurement - Vendor Fabrication and Delivery - IR06 | 400000 | 455560.07 | 2026-06-30 | 2027-06-01
AS_0203_1100 | S.P077 | TBD | 6.09.05.03 | Cryogenics Controls - Controls & Instrumentation Hardware Procurement | Cryogenic Controls and Instr. System - Hardware Procurement - Vendor Fabrication and Delivery - IR04 | 100000 | 113890.02 | 2026-06-30 | 2027-06-01
DE_0200_2120 | A.PP008 | Ullrich | 6.10.02 | Detector R&D and Physics Design | Systems Engineering & Design - R&D - FY23 - Phase 2 | 916667 | 1057856.63 | 2025-11-19 | 2025-12-18
DE_0200_2130 | A.PP008 | Ullrich | 6.10.02 | Detector R&D and Physics Design | Systems Engineering & Design - R&D - FY23 - Phase 3 | 916667 | 1057856.63 | 2025-12-19 | 2026-01-20
DE_0200_2110 | A.PP008 | Ullrich | 6.10.02 | Detector R&D and Physics Design | Systems Engineering & Design - R&D - FY23 - Phase 1 | 916666 | 1057855.48 | 2025-10-21 | 2025-11-18
DE_0200_2260 | S.P006 | Ullrich | 6.10.02 | Detector R&D and Physics Design | Systems Engineering & Design - R&D - FY24 - Phase 1 | 1290000 | 1490472.75 | 2025-10-21 | 2026-10-20
DE_0300_3150 | A.PP006 | Eng | 6.10.03 | Tracking | Tracking: Mu Vertex - Material - Construction | 3097084 | 3590010.69 | 2025-10-21 | 2029-08-24
DE_0300_3171 | A.PP129 | Eng | 6.10.03 | Tracking | Tracking: TPC - Material - Construction | 3220000 | 3817885.63 | 2027-10-21 | 2029-08-24
DE_0300_3172 | A.PP129 | Eng | 6.10.03 | Tracking | Tracking: Long Lead Procurement - GEM foils for MPGDs | 753000 | 833530.05 | 2024-10-04 | 2026-08-11
DE_0300_3220 | S.P056 | Eng | 6.10.03 | Tracking | Tracking: Lepton Endcap - Material - Construction | 470000 | 538589.8 | 2025-10-21 | 2028-08-24
DE_0300_3180 | S.P143 | Eng | 6.10.03 | Tracking | Tracking: Hadron Endcap Low-rapidity Si - Material - Construction | 1988912 | 2305463.9 | 2025-10-21 | 2029-08-24
DE_0300_3230 | S.P144 | Eng | 6.10.03 | Tracking | Tracking: Lepton Endcap Low-rapidity Si - Material - Construction | 1988912 | 2305463.9 | 2025-10-21 | 2029-08-24
DE_0400_4244 | A.PP030 | Zilhmann | 6.10.04 | Particle Identification | PID: Long Lead Procurement - Silicon Photomultipliers | 1830333 | 2073827.18 | 2024-10-04 | 2028-09-06
DE_0400_4261 | A.PP030 | Zilhmann | 6.10.04 | Particle Identification | PID: Hadron Endcap Construction - Materials | 400130 | 464110.6 | 2025-10-21 | 2029-09-20
DE_0400_4161 | D.APP37 | Zilhmann | 6.10.04 | Particle Identification | PID: Barrel Construction - Materials | 5473602 | 6412812.38 | 2026-06-16 | 2029-12-19
DE_0400_4150 | S.P054 | Zilhmann | 6.10.04 | Particle Identification | PID: Barrel First Article | 612750 | 696602.41 | 2026-06-16 | 2027-04-14
DE_0400_4263 | S.P063 | Zilhmann | 6.10.04 | Particle Identification | PID: Lepton Endcap Construction - Materials | 390597 | 453053.28 | 2025-10-21 | 2029-09-20
DE_0500_3082 | D.APP11 | Bazilevsky | 6.10.05 | Electromagnetic Calorimetry | EMCal - Long Lead Procurement - PbWO4 Crystals | 2554000 | 2908402.76 | 2024-10-04 | 2029-02-02
DE_0500_3375 | D.APP11 | Bazilevsky | 6.10.05 | Electromagnetic Calorimetry | EMCal - Long Lead Procurement - Silicon Photomultipliers | 1830333 | 2084316.97 | 2024-10-04 | 2029-02-02
DE_0500_3380 | D.APP11 | Bazilevsky | 6.10.05 | Electromagnetic Calorimetry | EMCal- Lepton: Purchase Material | 1205114 | 1405125.22 | 2025-10-21 | 1930-02-19
DE_0500_3080 | D.APP11 | Bazilevsky | 6.10.05 | Electromagnetic Calorimetry | EMCal- Central: Purchase Material | 967722 | 1128333.57 | 2025-10-21 | 1930-02-19
DE_0500_3240 | S.P053 | Bazilevsky | 6.10.05 | Electromagnetic Calorimetry | EMCal- Hadron: Purchase Material | 694666 | 812635.13 | 2025-12-18 | 1930-04-15
DE_0600_3074 | D.APP38 | Kiselev | 6.10.06 | Hadronic Calorimetry | HCAL: Long Lead Procurement - Scintillators | 7387000 | 8324676.29 | 2024-10-04 | 2028-03-02
DE_0600_3073 | D.APP38 | Kiselev | 6.10.06 | Hadronic Calorimetry | HCAL: Long Lead Procurement - Steel for Hadronic Calorimeters | 7052000 | 7947152.73 | 2024-10-04 | 2028-03-02
DE_0600_3072 | D.APP38 | Kiselev | 6.10.06 | Hadronic Calorimetry | HCAL: Long Lead Procurement - Silicon Photomultipliers | 1830333 | 2062668.16 | 2024-10-04 | 2028-03-02
DE_0700_3560 | A.PP142 | Rajput-Ghoshal | 6.10.07 | Detector Magnets | Long Lead Procurement - Materials | 4974000 | 5664490.69 | 2024-10-04 | 2029-02-05
DE_0800_3080 | D.APP07 | Barbosa | 6.10.08 | Electronics | CD-1 Electronics: Construction Material | 8718360 | 10219967.4 | 2026-09-18 | 2029-10-02
DE_0800_3031 | S.P122 | Barbosa | 6.10.08 | Electronics | CD-1 Electronics: Final Design - Material | 429800 | 484322.49 | 2025-10-21 | 2027-01-28
DE_0900_3101 | A.PP002 | Barbosa | 6.10.09 | DAQ / Computing | CD-1 DAQ/Computing: Construction - Material | 3211941 | 3751144.22 | 2026-09-01 | 2029-06-01
DE_1000_3150 | D.APP08 | Aschenauer | 6.10.10 | Detector Infrastructure | Detector Infrastructure: Fabrication - Material | 12768743 | 14841184.05 | 2026-05-12 | 2029-05-10
DE_1100_3080 | A.PP005 | Furletova | 6.10.11 | IR Integration & Auxiliary Detectors | Zero Degree Calorimeter: Production | 2465637 | 2921805.49 | 2027-03-09 | 1930-03-29
IR_0301_1160 | S.P113 | Gaskell | 6.10.14.01.01 | Lepton Polarimetry in the Storage Ring | Position detectors - FY 26 | 324180 | 380570.25 | 2027-10-21 | 2028-10-19
IR_0301_1140 | S.P113 | Gaskell | 6.10.14.01.01 | Lepton Polarimetry in the Storage Ring | Position detectors - FY 25 | 308180 | 353653.14 | 2026-10-21 | 2027-10-20
IR_0301_1120 | S.P113 | Gaskell | 6.10.14.01.01 | Lepton Polarimetry in the Storage Ring | Position detectors - FY 24 | 300180 | 336727.83 | 2025-10-21 | 2026-10-20
IR_0301_3160 | S.P113 | Gaskell | 6.10.14.01.02 | Lepton Polarimetry in the RCS | Position detectors - FY 26 | 324180 | 380570.25 | 2027-10-21 | 2028-10-19
IR_0301_3140 | S.P113 | Gaskell | 6.10.14.01.02 | Lepton Polarimetry in the RCS | Position detectors - FY 25 | 308180 | 353653.14 | 2026-10-21 | 2027-10-20
IR_0301_3120 | S.P113 | Gaskell | 6.10.14.01.02 | Lepton Polarimetry in the RCS | Position detectors - FY 24 | 300180 | 336727.83 | 2025-10-21 | 2026-10-20
IR_0302_1143 | S.P061 | Schmidke | 6.10.14.02.01 | Hadron Polarimetry at IP12 | Polarized Atomic HJET and readout electronics - material - FY25 | 250000 | 286888.46 | 2026-10-21 | 2027-10-20
IF_2102_1140 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Design - FY22 | 5269134 | 5451225.29 | 2022-05-31 | 2023-02-06
IF_2102_1160 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Design - FY23 | 3908523 | 4122119.87 | 2023-02-07 | 2024-02-05
IF_2102_1240 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY26 | 1422897 | 1606552.76 | 2026-02-05 | 2027-02-04
IF_2102_1220 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY25 | 1422897 | 1570432.69 | 2025-02-05 | 2026-02-04
IF_2102_1200 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY24 | 948598 | 1025894.89 | 2024-05-01 | 2025-02-04
IF_2102_1320 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY30 | 711448 | 879765.87 | 1930-02-05 | 1931-02-04
IF_2102_1300 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY29 | 711448 | 860012.67 | 2029-02-06 | 1930-02-04
IF_2102_1280 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY28 | 711448 | 840651.4 | 2028-02-07 | 2029-02-05
IF_2102_1180 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Design - FY24 | 781705 | 836892.59 | 2024-02-06 | 2024-04-30
IF_2102_1260 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY27 | 711448 | 821751.35 | 2027-02-05 | 2028-02-04
IF_2102_1340 | D.APP34 | Folz | 6.11.01.02 | Infrastructure Engineering | A/E Services Contract - Const - FY31 | 415012 | 520974.94 | 1931-02-05 | 1931-09-08
IF_0103_1340 | A.PP011 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | C/M Construction Mgt Services Contract - Const - FY26 | 650000 | 736844.71 | 2026-04-09 | 2027-04-08
IF_0103_1320 | A.PP011 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | C/M Construction Mgt Services Contract - Const - FY25 | 650000 | 720278.18 | 2025-04-09 | 2026-04-08
IF_0103_1300 | A.PP011 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | C/M Construction Mgt Services Contract - Const - FY24 | 400000 | 434875.12 | 2024-07-03 | 2025-04-08
IF_0103_1360 | A.PP011 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | C/M Construction Mgt Services Contract - Const - FY27 | 325000 | 376896.11 | 2027-04-09 | 2028-04-07
IF_0103_1620 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY26 | 60000 | 68016.43 | 2026-04-09 | 2027-04-08
IF_0103_1600 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY25 | 60000 | 66487.22 | 2025-04-09 | 2026-04-08
IF_0103_1580 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY24 | 56250 | 61154.31 | 2024-07-03 | 2025-04-08
IF_0103_1540 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Design - FY23 | 40000 | 42513.22 | 2023-07-06 | 2024-04-08
IF_0103_1643 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY30 | 30000 | 37249.95 | 1930-04-10 | 1931-04-09
IF_0103_1642 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY29 | 30000 | 36412.47 | 2029-04-10 | 1930-04-09
IF_0103_1641 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY28 | 30000 | 35590.58 | 2028-04-10 | 2029-04-09
IF_0103_1640 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY27 | 30000 | 34790.41 | 2027-04-09 | 2028-04-07
IF_0103_1644 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Const - FY31 | 20000 | 25218.14 | 1931-04-10 | 1931-11-10
IF_0103_1560 | S.P082 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Commissioning Contract - Design - FY24 | 18750 | 20073.73 | 2024-04-09 | 2024-07-02
IF_0103_1443 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY30 | 48000 | 60571.59 | 1930-12-26 | 1931-12-18
IF_0103_1442 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY29 | 48000 | 59209.77 | 2029-12-26 | 1930-12-24
IF_0103_1441 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY28 | 48000 | 57878.56 | 2028-12-26 | 2029-12-24
IF_0103_1440 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY27 | 48000 | 56572.12 | 2027-12-27 | 2028-12-22
IF_0103_1420 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY26 | 48000 | 55300.23 | 2026-12-24 | 2027-12-23
IF_0103_1400 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY25 | 48000 | 54056.9 | 2025-12-24 | 2026-12-23
IF_0103_1380 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY24 | 36000 | 40334.87 | 2025-10-21 | 2025-12-23
IF_0103_1444 | S.P083 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Field Office Trailer Rental - FY31 | 21000 | 26968.16 | 1931-12-19 | 1932-07-15
IF_0103_1500 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY26 | 66667 | 76806.26 | 2026-12-24 | 2027-12-23
IF_0103_1480 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY25 | 66667 | 75079.41 | 2025-12-24 | 2026-12-23
IF_0103_1523 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY30 | 33334 | 42064.44 | 1930-12-26 | 1931-12-18
IF_0103_1522 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY29 | 33334 | 41118.72 | 2029-12-26 | 1930-12-24
IF_0103_1521 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY28 | 33334 | 40194.25 | 2028-12-26 | 2029-12-24
IF_0103_1520 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY27 | 33334 | 39286.98 | 2027-12-27 | 2028-12-22
IF_0103_1524 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY31 | 16666 | 21402.44 | 1931-12-19 | 1932-07-15
IF_0103_1460 | S.P084 | Folz | 6.11.01.03 | Infrastructure Construction Management & Inspection | Testing Contracts - FY24 | 5000 | 5602.06 | 2025-10-21 | 2025-12-23
IF_0202_1060 | D25.APP01.A | Dirul | 6.11.02.02.01 | CRYO1002 - Cryogenic Plant (A-106, S-105) | RF Building@ 1002 Pre-injector - MEP and Interior | 3371339 | 3864171.45 | 2026-11-30 | 2027-02-25
IF_0202_1020 | D25.APP02.A | Dirul | 6.11.02.02.01 | CRYO1002 - Cryogenic Plant (A-106, S-105) | RF Building@ 1002 Pre-injector - Concrete Pad, Asphalt Pavings and markings | 4155990 | 4684985.19 | 2026-08-31 | 2026-10-13
IF_0202_1040 | D25.APP02.A | Dirul | 6.11.02.02.01 | CRYO1002 - Cryogenic Plant (A-106, S-105) | RF Building@ 1002 Pre-injector - Building Structural Work | 2025856 | 2322001.71 | 2026-10-14 | 2026-11-25
IF_0202_1000 | D25.APP02.A | Dirul | 6.11.02.02.01 | CRYO1002 - Cryogenic Plant (A-106, S-105) | RF Building@ 1002 Pre-injector - Excavation | 68118 | 76320.29 | 2026-07-20 | 2026-08-28
IF_0202_1100 | A.PP097 | Dirul | 6.11.02.02.02 | New LINAC Tunnel 1002 | New LINAC Tunnel 1002 - Installation of New 400 Mev LINAC Tunnel | 1239202 | 1420352.27 | 2027-04-30 | 2027-07-26
IF_0202_1120 | A.PP097 | Dirul | 6.11.02.02.02 | New LINAC Tunnel 1002 | New LINAC Tunnel 1002 - New 400 Mev LINAC - General & Systems | 804869 | 922527.17 | 2027-07-27 | 2027-09-28
IF_0202_1080 | A.PP097 | Dirul | 6.11.02.02.02 | New LINAC Tunnel 1002 | New LINAC Tunnel 1002 - Demolition of existing spectrometer tunnel | 647674 | 742352.93 | 2027-02-26 | 2027-04-29
IF_0203_1060 | D25.APP01.A | Dirul | 6.11.02.03.01 | 1002I - EIC Cryogenics Building | Cryogenic 1002I - MEP and Interior | 228838 | 262290.23 | 2026-10-28 | 2027-01-27
IF_0203_1040 | D25.APP02.A | Dirul | 6.11.02.03.01 | 1002I - EIC Cryogenics Building | Cryogenic 1002I - Building Structural Work | 138786 | 157643.55 | 2026-09-15 | 2026-10-27
IF_0203_1020 | D25.APP02.A | Dirul | 6.11.02.03.01 | 1002I - EIC Cryogenics Building | Cryogenic 1002I - Concrete Pad, Asphalt Pavings and markings | 79474 | 89043.7 | 2026-08-17 | 2026-09-14
IF_0203_1000 | D25.APP02.A | Dirul | 6.11.02.03.01 | 1002I - EIC Cryogenics Building | Cryogenic 1002I – Excavation | 14661 | 16426.37 | 2026-07-20 | 2026-08-14
IF_0203_1140 | D25.APP01.A | Dirul | 6.11.02.03.02 | 1006G - EIC 6 O’Clock Cryo Facility | Cryogenic 1006 - MEP and Interior | 140210 | 160706.32 | 2026-11-30 | 2027-02-25
IF_0203_1120 | D25.APP02.A | Dirul | 6.11.02.03.02 | 1006G - EIC 6 O’Clock Cryo Facility | Cryogenic 1006 - Building Structural Work | 99476 | 114017.7 | 2026-10-14 | 2026-11-25
IF_0203_1100 | D25.APP02.A | Dirul | 6.11.02.03.02 | 1006G - EIC 6 O’Clock Cryo Facility | Cryogenic 1006 - Concrete Pad, Asphalt Pavings and markings | 42338 | 47872.47 | 2026-09-15 | 2026-10-13
IF_0203_1080 | D25.APP02.A | Dirul | 6.11.02.03.02 | 1006G - EIC 6 O’Clock Cryo Facility | Cryogenic 1006 - Excavation | 10560 | 11831.56 | 2026-08-17 | 2026-09-14
IF_0203_1220 | D25.APP01.A | Dirul | 6.11.02.03.03 | 1010E - EIC 10 O'Clock Cryo Facility | Cryogenic 1010E – MEP and Interior | 283498 | 324940.59 | 2027-01-13 | 2027-02-25
IF_0203_1200 | D25.APP02.A | Dirul | 6.11.02.03.03 | 1010E - EIC 10 O'Clock Cryo Facility | Cryogenic 1010E – Building Structural Work | 117508 | 134685.67 | 2026-11-30 | 2027-01-12
IF_0203_1180 | D25.APP02.A | Dirul | 6.11.02.03.03 | 1010E - EIC 10 O'Clock Cryo Facility | Cryogenic 1010E – Concrete Pad, Asphalt Pavings and markings | 14666 | 16809.92 | 2026-10-28 | 2026-11-25
IF_0203_1160 | D25.APP02.A | Dirul | 6.11.02.03.03 | 1010E - EIC 10 O'Clock Cryo Facility | Cryogenic 1010E – Excavation | 7763 | 8817.8 | 2026-09-15 | 2026-10-27
IF_0204_1060 | D25.APP01.A | Dirul | 6.11.02.04.01 | 1002H - EIC Injection LINAC Building | 1002H - EIC Injection LINAC Building - MEP and Interior | 3487946 | 3997824.41 | 2026-12-07 | 2027-02-10
IF_0204_1020 | D25.APP02.A | Dirul | 6.11.02.04.01 | 1002H - EIC Injection LINAC Building | 1002H - EIC Injection LINAC Building - Concrete Work/ slab/ Asphal Pavement | 3652270 | 4092050.79 | 2026-08-17 | 2026-09-28
IF_0204_1040 | D25.APP02.A | Dirul | 6.11.02.04.01 | 1002H - EIC Injection LINAC Building | 1002H - EIC Injection LINAC Building - Structural Work | 2330640 | 2668670.59 | 2026-09-29 | 2026-12-04
IF_0204_1000 | D25.APP02.A | Dirul | 6.11.02.04.01 | 1002H - EIC Injection LINAC Building | 1002H - EIC Injection LINAC Building - Excavation | 143408 | 160676.19 | 2026-07-20 | 2026-08-14
IF_0204_1140 | D25.APP01.A | Dirul | 6.11.02.04.02 | 1002 Pre-injector & SHC Bldg | 1002 Pre-injector & SHC Bldg - MEP and Interior Systems | 4228875 | 4942938.81 | 2027-09-13 | 2028-02-08
IF_0204_1120 | D25.APP02.A | Dirul | 6.11.02.04.02 | 1002 Pre-injector & SHC Bldg | 1002 Pre-injector & SHC Bldg - Building Structural Work | 4601684 | 5274371.97 | 2027-03-24 | 2027-09-10
IF_0204_1100 | D25.APP02.A | Dirul | 6.11.02.04.02 | 1002 Pre-injector & SHC Bldg | 1002 Pre-injector & SHC Bldg - Concrete Work/ slab/ Asphal Pavement | 3066079 | 3514287.63 | 2026-11-12 | 2027-03-23
IF_0204_1080 | D25.APP02.A | Dirul | 6.11.02.04.02 | 1002 Pre-injector & SHC Bldg | 1002 Pre-injector & SHC Bldg - Excavation | 323245 | 369942.59 | 2026-09-29 | 2026-11-10
IF_0204_1220 | D25.APP01.A | Dirul | 6.11.02.04.03 | 1010D - EIC 10 O'Clock DI Pumphouse | 1010D - EIC 10 O'Clock DI Pumphouse - MEP and Interior | 271701 | 311419.07 | 2026-12-29 | 2027-02-10
IF_0204_1180 | D25.APP02.A | Dirul | 6.11.02.04.03 | 1010D - EIC 10 O'Clock DI Pumphouse | 1010D - EIC 10 O'Clock DI Pumphouse - Concrete Work/ slab/ Asphal Pavement | 157673 | 180451.23 | 2026-09-29 | 2026-11-10
IF_0204_1200 | D25.APP02.A | Dirul | 6.11.02.04.03 | 1010D - EIC 10 O'Clock DI Pumphouse | 1010D - EIC 10 O'Clock DI Pumphouse - Building Structural Work | 147777 | 169379.49 | 2026-11-12 | 2026-12-28
IF_0204_1160 | D25.APP02.A | Dirul | 6.11.02.04.03 | 1010D - EIC 10 O'Clock DI Pumphouse | 1010D - EIC 10 O'Clock DI Pumphouse - Excavation | 19993 | 22400.42 | 2026-08-17 | 2026-09-28
IF_0204_1300 | D25.APP01.A | Dirul | 6.11.02.04.04 | 1010C - EIC RF Power Amplifier Building | 1010C EIC RF Power Amplifier Building - MEP and Interior | 4318552 | 4949850.89 | 2027-03-12 | 2027-06-04
IF_0204_1260 | D25.APP02.A | Dirul | 6.11.02.04.04 | 1010C - EIC RF Power Amplifier Building | 1010C EIC RF Power Amplifier Building - Concrete Work/ slab/ Asphal Pavement | 3252378 | 3711057.62 | 2026-09-15 | 2026-12-11
IF_0204_1280 | D25.APP02.A | Dirul | 6.11.02.04.04 | 1010C - EIC RF Power Amplifier Building | 1010C EIC RF Power Amplifier Building - Building Structural Work | 1739292 | 1993546.92 | 2026-12-14 | 2027-03-11
IF_0204_1240 | D25.APP02.A | Dirul | 6.11.02.04.04 | 1010C - EIC RF Power Amplifier Building | 1010C EIC RF Power Amplifier Building - Excavation | 35130 | 39360.11 | 2026-08-17 | 2026-09-14
IF_0204_1340 | D25.APP02.A | Dirul | 6.11.02.04.05 | Concrete Foundations for Externally Mounted Equipment | Packaged HVAC and Mechanical Misc Foundations | 90010 | 103013.29 | 2026-09-29 | 2026-11-10
IF_0204_1320 | D25.APP02.A | Dirul | 6.11.02.04.05 | Concrete Foundations for Externally Mounted Equipment | Electrical Equipment Foundations | 61129 | 69960 | 2026-09-29 | 2026-11-10
IF_0204_1360 | D25.APP02.A | Dirul | 6.11.02.04.05 | Concrete Foundations for Externally Mounted Equipment | Cooling Water Towers Foundations | 19531 | 22352.55 | 2026-09-29 | 2026-11-10
IF_0205_1060 | D25.APP01.B | Dirul | 6.11.02.05.01 | 1001A - EIC 1 O-Clock Power Supply Building | Alc-01 - MEP and Interior Systems | 2182264 | 2501273.9 | 2026-10-14 | 2026-11-25
IF_0205_1040 | D25.APP02.B | Dirul | 6.11.02.05.01 | 1001A - EIC 1 O-Clock Power Supply Building | Alc-01 - Building Structural Work | 391287 | 442436.43 | 2026-09-15 | 2026-10-13
IF_0205_1020 | D25.APP02.B | Dirul | 6.11.02.05.01 | 1001A - EIC 1 O-Clock Power Supply Building | Alc-01 - Concrete Pad, Asphalt Pavings and markings | 295439 | 331013.7 | 2026-08-31 | 2026-09-14
IF_0205_1000 | D25.APP02.B | Dirul | 6.11.02.05.01 | 1001A - EIC 1 O-Clock Power Supply Building | Alc-01 - Excavation | 33173 | 37167.46 | 2026-07-20 | 2026-08-28
IF_0205_1140 | D25.APP01.B | Dirul | 6.11.02.05.02 | 1003A - EIC 3 O-Clock Power Supply Building | Alc-03 - MEP and Interior Systems | 2182264 | 2501273.9 | 2026-11-30 | 2027-01-12
IF_0205_1120 | D25.APP02.B | Dirul | 6.11.02.05.02 | 1003A - EIC 3 O-Clock Power Supply Building | Alc-03 - Building Structural Work | 391287 | 448486.51 | 2026-10-28 | 2026-11-25
IF_0205_1100 | D25.APP02.B | Dirul | 6.11.02.05.02 | 1003A - EIC 3 O-Clock Power Supply Building | Alc-03 - Concrete Pad, Asphalt Pavings and markings | 295439 | 338627.16 | 2026-10-14 | 2026-10-27
IF_0205_1080 | D25.APP02.B | Dirul | 6.11.02.05.02 | 1003A - EIC 3 O-Clock Power Supply Building | Alc-03 - Excavation | 33173 | 37395.43 | 2026-08-31 | 2026-10-13
IF_0205_1220 | D25.APP01.B | Dirul | 6.11.02.05.03 | 1005T - EIC 5 O-Clock Power Supply Building | Alc-05 - MEP and Interior Systems | 3053563 | 3499942 | 2027-01-13 | 2027-02-25
IF_0205_1200 | D25.APP02.B | Dirul | 6.11.02.05.03 | 1005T - EIC 5 O-Clock Power Supply Building | Alc-05 - Building Structural Work | 806132 | 923974.79 | 2026-12-14 | 2027-01-12
IF_0205_1180 | D25.APP02.B | Dirul | 6.11.02.05.03 | 1005T - EIC 5 O-Clock Power Supply Building | Alc-05 - Concrete Pad, Asphalt Pavings and markings | 412401 | 472687.02 | 2026-11-30 | 2026-12-11
IF_0205_1160 | D25.APP02.B | Dirul | 6.11.02.05.03 | 1005T - EIC 5 O-Clock Power Supply Building | Alc-05 - Excavation | 108289 | 124119.01 | 2026-10-14 | 2026-11-25
IF_0205_1300 | D25.APP01.B | Dirul | 6.11.02.05.04 | 1007A - EIC 7 O-Clock Power Supply Building | Alc-07 - MEP and Interior Systems | 4107595 | 4708055.56 | 2027-02-26 | 2027-04-08
IF_0205_1280 | D25.APP02.B | Dirul | 6.11.02.05.04 | 1007A - EIC 7 O-Clock Power Supply Building | Alc-07 - Building Structural Work | 1020619 | 1169816.15 | 2027-01-28 | 2027-02-25
IF_0205_1260 | D25.APP02.B | Dirul | 6.11.02.05.04 | 1007A - EIC 7 O-Clock Power Supply Building | Alc-07 - Concrete Pad, Asphalt Pavings and markings | 401498 | 460190.18 | 2027-01-13 | 2027-01-27
IF_0205_1240 | D25.APP02.B | Dirul | 6.11.02.05.04 | 1007A - EIC 7 O-Clock Power Supply Building | Alc-07 - Excavation | 61324 | 70288.53 | 2026-11-30 | 2027-01-12
IF_0205_1380 | D25.APP01.B | Dirul | 6.11.02.05.05 | 1009A - EIC 9 O-Clock Power Supply Building | Alc-09 - MEP and Interior Systems | 2182264 | 2501273.9 | 2027-04-09 | 2027-05-20
IF_0205_1360 | D25.APP02.B | Dirul | 6.11.02.05.05 | 1009A - EIC 9 O-Clock Power Supply Building | Alc-09 - Building Structural Work | 391287 | 448486.51 | 2027-03-12 | 2027-04-08
IF_0205_1340 | D25.APP02.B | Dirul | 6.11.02.05.05 | 1009A - EIC 9 O-Clock Power Supply Building | Alc-09 - Concrete Pad, Asphalt Pavings and markings | 295439 | 338627.16 | 2027-02-26 | 2027-03-11
IF_0205_1320 | D25.APP02.B | Dirul | 6.11.02.05.05 | 1009A - EIC 9 O-Clock Power Supply Building | Alc-09 - Excavation | 33173 | 38022.33 | 2027-01-13 | 2027-02-25
IF_0205_1460 | D25.APP01.B | Dirul | 6.11.02.05.06 | Alcove Building | Alc-11 - MEP and Interior Systems | 171263 | 198205 | 2027-07-20 | 2027-11-29
IF_0205_1440 | D25.APP02.B | Dirul | 6.11.02.05.06 | Alcove Building | Alc-11 - Building Structural Work | 169840 | 194667.72 | 2027-04-23 | 2027-07-19
IF_0205_1420 | D25.APP02.B | Dirul | 6.11.02.05.06 | Alcove Building | Alc-11 - Concrete Pad, Asphalt Pavings and markings | 70256 | 80526.23 | 2027-03-26 | 2027-04-22
IF_0205_1400 | D25.APP02.B | Dirul | 6.11.02.05.06 | Alcove Building | Alc-11 - Excavation | 15623 | 17906.82 | 2027-02-26 | 2027-03-25
IF_0206_1060 | D25.APP01.B | Dirul | 6.11.02.06.01 | B1004 - Kicker Power (A-103, S-103) | 1004 Kicker - MEP and Interior Systems | 1193164 | 1367584.29 | 2027-04-26 | 2027-06-07
IF_0206_1040 | D25.APP02.B | Dirul | 6.11.02.06.01 | B1004 - Kicker Power (A-103, S-103) | 1004 Kicker - Building Structural Work | 503608 | 577226.93 | 2027-03-29 | 2027-04-23
IF_0206_1020 | D25.APP02.B | Dirul | 6.11.02.06.01 | B1004 - Kicker Power (A-103, S-103) | 1004 Kicker - Concrete Pad, Asphalt Pavings and markings | 309113 | 354300.07 | 2027-03-15 | 2027-03-26
IF_0206_1000 | D25.APP02.B | Dirul | 6.11.02.06.01 | B1004 - Kicker Power (A-103, S-103) | 1004 Kicker - Excavation | 42088 | 48240.55 | 2027-01-29 | 2027-03-12
IF_0206_1140 | D25.APP01.B | Dirul | 6.11.02.06.02 | 1012C - EIC Kicker Power Supply Building | EIC Kicker Power Supply Building - MEP and Interior Systems | 2217764 | 2541963.39 | 2027-07-07 | 2027-08-17
IF_0206_1120 | D25.APP02.B | Dirul | 6.11.02.06.02 | 1012C - EIC Kicker Power Supply Building | EIC Kicker Power Supply Building - Building Structural Work | 803392 | 920834.25 | 2027-05-24 | 2027-07-06
IF_0206_1100 | D25.APP02.B | Dirul | 6.11.02.06.02 | 1012C - EIC Kicker Power Supply Building | EIC Kicker Power Supply Building - Concrete Pad, Asphalt Pavings and markings | 634677 | 727455.99 | 2027-04-26 | 2027-05-21
IF_0206_1080 | D25.APP02.B | Dirul | 6.11.02.06.02 | 1012C - EIC Kicker Power Supply Building | EIC Kicker Power Supply Building - Excavation | 44018 | 50452.68 | 2027-03-15 | 2027-04-23
IF_0207_1040 | D.APP14 | Dirul | 6.11.02.07 | Tunnel Modifications | RF Waveguide Penetrations- Duct @ 1010 | 2899148 | 3332029.9 | 2027-03-15 | 2027-10-28
IF_0207_1080 | D.APP14 | Dirul | 6.11.02.07 | Tunnel Modifications | RHIC Tunnel HVAC | 2552193 | 2992561.14 | 2028-03-28 | 2028-07-19
IF_0207_1000 | D.APP14 | Dirul | 6.11.02.07 | Tunnel Modifications | Utility Ports Pipe Ports | 2424404 | 2757151.99 | 2026-07-20 | 2027-02-25
IF_0207_1020 | D.APP14 | Dirul | 6.11.02.07 | Tunnel Modifications | Excavated Penetrations- 1004 | 1113464 | 1276233.51 | 2027-01-29 | 2027-03-12
IF_0207_1060 | D.APP14 | Dirul | 6.11.02.07 | Tunnel Modifications | Excavated Penetrations- 1012 | 1080188 | 1266569.04 | 2027-10-29 | 2028-03-27
IF_0208_1000 | D25.APP01.A | Dirul | 6.11.02.08 | Access Roads, Paving and Sitework | Service piping to bldgs, water, sanitary, storm | 1041602 | 1167024.42 | 2025-10-21 | 2026-03-04
IF_0208_1240 | D25.APP02.B | Dirul | 6.11.02.08 | Access Roads, Paving and Sitework | Road 1010 - Wearing Course, 3" thick | 840476 | 941680.24 | 2026-04-30 | 2026-05-28
IF_0208_1160 | D25.APP02.B | Dirul | 6.11.02.08 | Access Roads, Paving and Sitework | Road 1002 - Wearing Course, 3" thick | 545389 | 611060.93 | 2026-03-05 | 2026-04-01
IF_0208_1280 | D25.APP02.B | Dirul | 6.11.02.08 | Access Roads, Paving and Sitework | Road 1010 - Finish Grading | 12851 | 14398.43 | 2026-06-12 | 2026-06-25
IF_0208_1180 | D25.APP02.B | Dirul | 6.11.02.08 | Access Roads, Paving and Sitework | Road 1002 - Rough Grading, 7510-10000 SF | 10747 | 12041.08 | 2026-04-02 | 2026-04-15
IF_0208_1260 | D25.APP02.B | Dirul | 6.11.02.08 | Access Roads, Paving and Sitework | Road 1010 - Rough Grading, 7510-10000 SF | 10747 | 12041.08 | 2026-05-29 | 2026-06-11
IF_0208_1200 | D25.APP02.B | Dirul | 6.11.02.08 | Access Roads, Paving and Sitework | Road 1002 - Finish Grading | 8584 | 9617.63 | 2026-04-16 | 2026-04-29
IF_0301_2005 | A.PP014 | Nehring | 6.11.03.01 | Main Substation #9 | Substation Installation Contract - Contract Cost (Rolled up Cost) | 3356968 | 3879697.47 | 2026-08-12 | 2028-08-10
IF_0301_1620 | A.PP014 | Nehring | 6.11.03.01 | Main Substation #9 | 20 MVA transformer with OLTC - Installation by Contractor | 40000 | 45847.32 | 2026-10-21 | 2026-11-18
IF_0301_2015 | A.PP014 | Nehring | 6.11.03.01 | Main Substation #9 | Substation Installation Contract - Mobilization | 20000 | 22408.26 | 2026-08-12 | 2026-09-09
IF_0301_1520 | A.PP020 | Nehring | 6.11.03.01 | Main Substation #9 | 20 MVA transformer with OLTC - Fabrication | 2340000 | 2622520.19 | 2025-10-21 | 2026-10-05
IF_0301_1780 | S.P040 | Nehring | 6.11.03.01 | Main Substation #9 | 13.8 kV switchgear - Fabrication | 798455 | 894599.36 | 2025-10-21 | 2026-08-07
IF_0302_1100 | D.APP19 | Nehring | 6.11.03.02 | Overhead 13.8kV & Switching | Overhead 13.8 kV lines, switch stations and duct bank- Electrical Construction - Overhead Lines (Material & Labor) | 4348563 | 4830316.92 | 2024-12-05 | 2026-11-03
IF_0303_1240 | D.APP19 | Nehring | 6.11.03.03 | Unit Substations | UNIT Substations w/Distribution Installation - Contract Cost, NonLabor | 3319306 | 3804532.11 | 2026-11-04 | 2027-09-21
IF_0303_1245 | D.APP19 | Nehring | 6.11.03.03 | Unit Substations | UNIT Substations w/Distribution Installation - Distribution to Alcoves [1,3,5,9,11] | 662659 | 759528.48 | 2026-11-04 | 2027-09-21
IF_0303_1120 | S.P041 | Nehring | 6.11.03.03 | Unit Substations | UNIT Substations w/Distribution Unit substation - Fabrication (NYS Funded) | 1484172 | 1644646.26 | 2024-10-04 | 2026-10-05
IF_0304_1460 | A.PP082 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Load centers 480V Switchboards & Panelborards - Installation | 1684350 | 2020399.72 | 2029-04-20 | 2029-09-11
IF_0304_1360 | A.PP082 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Load centers 480V Switchboards & Panelborards - Vendor fabrication | 1000000 | 1199513 | 2028-11-16 | 2029-04-12
IF_0304_1580 | A.PP082 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Load centers 480V - Vendor fabrication | 900000 | 1079561.7 | 2028-11-01 | 2029-03-29
IF_0304_1780 | A.PP082 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Load centers 120/208V panelboard with Transformer - Installation - Installation | 335100 | 402110.89 | 2029-04-13 | 2029-10-02
IF_0304_1740 | A.PP082 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Load centers 120/208V panelboard with Transformer - Vendor fabrication | 274900 | 329746.12 | 2028-11-16 | 2029-04-12
IF_0304_1620 | A.PP082 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Load centers 480V - Installation - Installation | 250000 | 299878.25 | 2029-03-30 | 2029-09-18
IF_0304_1120 | S.P030 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Variable Frequency Drives - Vendor fabrication | 1200000 | 1439415.6 | 2028-11-01 | 2029-03-29
IF_0304_1220 | S.P081 | Nehring | 6.11.03.04 | Motor Control & Load Centers | Variable Frequency Drives - Installation - Installation | 1200000 | 1439415.6 | 2029-04-06 | 2029-05-17
IF_0305_1060 | A.PP068 | Nehring | 6.11.03.05 | Standby Power | 400 kW & 150 kW Standby Gen & 3-Position Auto Trans Switches - Vendor fabrication | 1600000 | 1867334.88 | 2027-08-20 | 2028-03-15
IF_0305_1380 | A.PP068 | Nehring | 6.11.03.05 | Standby Power | 30 kVA 480V UPS - Vendor fabrication | 1416800 | 1630759.52 | 2027-07-23 | 2027-10-18
IF_0305_1420 | S.P147 | Nehring | 6.11.03.05 | Standby Power | 30 kVA 480V UPS and Bypass Switch Installation - Installation | 1286600 | 1508596.4 | 2027-10-19 | 2028-04-12
IF_0306_1440 | S.P042 | Nehring | 6.11.03.06 | Cable Plant | Cable Trays - Service Buildings - Non Labor | 386511 | 456415.43 | 2027-10-04 | 2029-03-15
IF_0306_1370 | S.P042 | Nehring | 6.11.03.06 | Cable Plant | Cable Trays Installation - Tunnel - Non Labor | 247113 | 289256.02 | 2027-09-03 | 2028-09-01
IF_0306_1080 | S.P042 | Nehring | 6.11.03.06 | Cable Plant | Cable Trays Tunnel Material - Non Labor | 70000 | 81790.28 | 2027-08-06 | 2028-08-04
IF_0307_1320 | D.APP20 | Nehring | 6.11.03.07 | 138kV Substation | 138kW Substation - PSEG Construction | 11872000 | 14893464.56 | 2029-06-27 | 1933-01-26
IF_0307_1080 | D.APP20 | Nehring | 6.11.03.07 | 138kV Substation | 138kW Substation - PSEG Design Contract | 1780801 | 1995232.59 | 2025-10-21 | 2026-04-14
IF_0307_1240 | D.APP20 | Nehring | 6.11.03.07 | 138kV Substation | 138kW Substation - PSEG Design Title 2 | 700000 | 812754.27 | 2027-05-28 | 2028-03-17
IF_0307_1200 | D.APP20 | Nehring | 6.11.03.07 | 138kV Substation | 138kW Substation - PSEG Design Title 1 | 300000 | 343854.9 | 2026-12-07 | 2027-05-27
IF_0307_1340 | D.APP20 | Nehring | 6.11.03.07 | 138kV Substation | 138kW Substation - PSEG Construction Engineering | 180000 | 225810.62 | 2029-06-27 | 1933-01-26
IF_0307_1120 | D.APP20 | Nehring | 6.11.03.07 | 138kV Substation | 138kW Substation - PSEG Conceptual Design & Cost Report | 50000 | 56020.65 | 2025-11-19 | 2026-08-07
IF_0401_1240 | S.P017 | Ram | 6.11.04.01 | Chilled Water Systems | 1007A - System Installations | 700000 | 839659.1 | 2029-01-05 | 2029-04-30
IF_0401_1320 | S.P017 | Ram | 6.11.04.01 | Chilled Water Systems | 1012C - System Installations | 350000 | 413222.39 | 2028-06-02 | 2028-11-22
IF_0401_1140 | S.P017 | Ram | 6.11.04.01 | Chilled Water Systems | 1002H - System Installations | 350000 | 410390.75 | 2028-02-09 | 2028-06-01
IF_0401_1200 | S.P017 | Ram | 6.11.04.01 | Chilled Water Systems | 1007A - Component manufacturing (Equipment and pump) | 200000 | 224082.6 | 2025-10-21 | 2025-12-04
IF_0401_1100 | S.P017 | Ram | 6.11.04.01 | Chilled Water Systems | 1002H - Component manufacturing (Equipment and pump) | 100000 | 112041.3 | 2025-10-21 | 2025-12-04
IF_0401_1280 | S.P017 | Ram | 6.11.04.01 | Chilled Water Systems | 1012C - Component manufacturing (Equipment and pump) | 100000 | 112041.3 | 2025-10-21 | 2025-12-04
IF_5000_5120 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | RHIC Tunnel DI Pipe - Pipe manufacturing [8" Vacuum/ Magnet/ PS] | 4350661 | 4895027.41 | 2025-10-21 | 2026-12-18
IF_0402_1100 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 10 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | 3742165 | 4309552.67 | 2027-04-02 | 2027-11-18
IF_0402_1140 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 10 O'clock Bldg - System Installation | 2286964 | 2681568.2 | 2028-01-28 | 2028-07-18
IF_0402_1081 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 2 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | 1469615 | 1646575.75 | 2025-12-19 | 2026-08-07
IF_0402_1620 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 6 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | 1278543 | 1457825.01 | 2026-08-10 | 2027-04-01
IF_0402_1420 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 4 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | 1176369 | 1379345.59 | 2027-11-19 | 2028-07-11
IF_5000_5660 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | RHIC Tunnel DI Pipe - Supply and Installation Arc 3/4 | 1135432 | 1331345.11 | 2027-10-21 | 2028-02-03
IF_5000_5710 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | RHIC Tunnel DI Pipe - Supply and Installation Arc 7/8 | 1135432 | 1331345.11 | 2028-02-04 | 2028-05-12
IF_5000_5730 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | RHIC Tunnel DI Pipe - Supply and Installation Arc 11/12 | 1135432 | 1331345.11 | 2028-05-15 | 2028-08-22
IF_5000_5640 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | RHIC Tunnel DI Pipe - Supply and Installation Arc 1/2 | 1135432 | 1306971.7 | 2027-07-13 | 2027-10-20
IF_5000_5600 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | RHIC Tunnel DI Pipe - Supply and Installation Arc 5/6 | 1135432 | 1301412.86 | 2026-12-21 | 2027-04-01
IF_5000_5606 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | RHIC Tunnel DI Pipe - Supply and Installation Arc 9/10 | 1135432 | 1301412.86 | 2027-04-02 | 2027-07-12
IF_0402_1083 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 2 O'clock Bldg - System Installation (Mobilization/ Safety Orientation/ Traning) | 925945 | 1061302.42 | 2027-02-11 | 2027-08-02
IF_0402_1740 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 6 O'clock Bldg - System Installation - Installations | 707716 | 848914.54 | 2028-11-03 | 2029-04-02
IF_0402_1460 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 4 O'clock Bldg - System Installation - Installations | 634474 | 757423.83 | 2028-09-07 | 2029-01-04
IF_0402_1880 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 12 O'clock Bldg - Material Supply and Fabrication (Equipment and Piping) | 427991 | 501838.71 | 2027-11-19 | 2028-07-11
IF_0402_1085 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 2 O'clock Bldg - Cryo SCW - Material Fabrication | 436581 | 497800 | 2026-08-10 | 2027-04-01
IF_0402_1762 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 6 O'clock Bldg - Cryo SCW - Material Fabrication | 430160 | 495380.93 | 2027-04-02 | 2027-11-18
IF_0402_1162 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 10 O'clock Bldg - Cryo SCW - Material Fabrication | 417553 | 489599.68 | 2027-11-19 | 2028-06-12
IF_0402_1088 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 2 O'clock Bldg - Cryo SCW - Installation | 387166 | 450397.29 | 2027-08-03 | 2028-01-27
IF_0402_2000 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 12 O'clock Bldg - System Installation - Installations | 257063 | 308350.41 | 2029-02-05 | 2029-04-30
IF_0402_1766 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 6 O'clock Bldg - Cryo SCW - Installation | 218481 | 262070.8 | 2028-11-03 | 2029-02-02
IF_0402_1166 | D25.APP07 | Ram | 6.11.04.02 | Low Conductivity Water Systems | 10 O'clock Bldg - Cryo SCW - Installation | 200359 | 234929.94 | 2028-06-13 | 2028-09-06
IF_0403_1100 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 10 O'clock Bldg - Component manufacturing (Equipment and pump) | 2270521 | 2543921.25 | 2025-10-21 | 2026-07-10
IF_0403_1260 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 2 O'clock Bldg - Component manufacturing (Equipment and pump) | 1866769 | 2091552.26 | 2025-10-21 | 2026-07-10
IF_0403_1520 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 6 O'clock Bldg - Component manufacturing (Equipment and pump) | 1698857.54 | 1903422.07 | 2025-10-21 | 2026-07-10
IF_0403_1420 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 4 O'clock Bldg - Component manufacturing (Equipment and pump) | 1409512 | 1579235.57 | 2025-10-21 | 2026-07-10
IF_0403_1140 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 10 O'clock Bldg System Installations - Contract | 900000 | 1023302.19 | 2026-07-13 | 2027-03-04
IF_0403_1300 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 2 O'clock Bldg - System Installations - Contract | 900000 | 1023302.19 | 2026-07-13 | 2027-03-04
IF_0403_1460 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 4 O'clock Bldg - System Installations | 900000 | 1023302.19 | 2026-07-13 | 2027-03-04
IF_0403_1560 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 6 O'clock Bldg - System Installations | 900000 | 1023302.19 | 2026-07-13 | 2027-03-04
IF_0403_1660 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 12 O'clock Bldg - System Installations | 900000 | 1023302.19 | 2026-07-13 | 2027-03-04
IF_0403_1620 | D.APP06 | Ram | 6.11.04.03 | Tower Water Systems | 12 O'clock Bldg - Component manufacturing (Equipment and pump) | 225020 | 252115.33 | 2025-10-21 | 2026-07-10