## Slide 1
Status of Ancillary ASIC Design
Iain Sedgwick
ePIC SVT WP1 Co-convener
10th EIC DAC Review
June 11th – 13th, 2025
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 2
Introduction
SVT Silicon Scheme
  Plans
  Why AncASIC?
Design Overview
  Technology Selection
  Shunt LDO
  Negative Voltage Generator
  AncBrain
  Overview
Progress, Next Steps and Ongoing Challenges
  Progress to date
  Current work and future plans
  Ongoing challenges

## Slide 3
Introduction
  Thinned silicon bent around beampipe
  Use wafer-scale MOSAIX from ITS3
  Smaller Version of MOSAIX with minimum necessary changes (EIC-LAS)
  Supporting AncASIC
Inner Barrel
Outer Barrel and Discs
SVT Silicon Scheme

## Slide 4
Ancillary ASIC
Why AncASIC?
  Some MOSAIX/LAS features require adaptation to stave/disc operation:
    Point-to-point slow control
    Point-to-point powering
    Precise negative back bias
  May be technically unfeasible to integrate these features in the LAS
  Limited prototyping
  MOSAIX schedule is an external dependency
  For these reasons, develop supporting ASIC instead
https://ep-news.web.cern.ch/content/alice-its3-clears-major-milestone
https://indico.cern.ch/event/1381495/contributions/5988486/attachments/2869319/5164357/TWEPP2024.PVL.v11.pdf

## Slide 5
Why AncASIC?
  Some MOSAIX/LAS features require adaptation to stave/disc operation:
    Point-to-point slow control
    Point-to-point powering
    Precise negative sensor bias
  May be technically unfeasible to integrate these features in the LAS
  Limited prototyping
  MOSAIX schedule is an external dependency
  For these reasons, develop supporting ASIC instead
Ancillary ASIC
SLDO for serial powering
Serialised Slow Control interface from EIC-LAS to lpGBT
Local Negative Voltage Generator
Develop independent supporting chip
  Development decoupled from MOSAIX availability
  No modification of MOSAIX needed
  110nm XFAB process
    4 MPW runs a year
    Cost effective

## Slide 6
Ancillary ASIC
Why AncASIC?
  Some MOSAIX/LAS features require adaptation to stave/disc operation:
    Point-to-point slow control
    Point-to-point powering
    Precise negative back bias
  May be technically unfeasible to integrate these features in the LAS
  Limited prototyping
  MOSAIX schedule is an external dependency
  For these reasons, develop supporting ASIC instead

## Slide 7
Design Overview
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 8
Technology Selection
XFAB XT011
  110nm BCD-on-SOI Technology
    SOI – permits floating grounds for negative voltage generation
    Thick copper top layer – very low resistance for power dissipation
    High gate density – suitable for AncBrain
    All design sites have experience with XFAB
    Radiation hardness untested
      ePIC radiation requirement low [1]
      Derived from a previously tested technology [2]
      Test structures in fabrication

## Slide 9
Shunt LDO
SLDO
  Serial powering required for services reduction
  Reviewed with external participants
  SLDO test structure (including pre-regulator) submitted March 2025 (UK funded, submitted via Europractice)
  Expected back September 2025
  Test system in preparation
Prototype currently in fabrication!
SLDO Test System Plan, courtesy of Andrew Hill, UKRI-STFC Daresbury Laboratory

## Slide 10
Negative Voltage Generator
NVG
  Local generation of sensor bias voltage needed due to combination of serial powering and low bias level (~1V)
  Reviewed with external participants
  Test structure submitted March 2025
  Also included transistor test structures and other blocks
  Expected back September 2025
  Test system in preparation
Prototype currently in fabrication!
NVG test structure layout, courtesy of Praful Purohit, BNL

## Slide 11
AncBrain
AncBrain
  Required for services reduction and control of NVG and SLDO
  Core modules complete, working on tests with MOSAIX emulator
  Plan to submit as part of first AncASIC
  Hardware emulator in preparation between LBNL, ORNL and BNL
Hardware mockup, courtesy of Zhengwei Xue, LBNL
AncBrain Plan, courtesy of Arif Iqbal, BNL

## Slide 12
AncASIC Overview
PADS
PADS
SLDO
2500um
800um
SLDO
SLDO
SLDO
SLDO
NVG
Slow Control
1130um
500um
500um
500um
500um
~15mm
>1.5mm
Preliminary
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
PAD
15 pads IIn
15 pads IOut
3 pads
GAVDD
7 pads
GDVDD
1 pad GSVDD
3 pads TXVDD
32 pads Slow Control
1 pad
PSUB
2 pads
SCin
2 pads
SCout
2 pads
CL_in
Pads: 47
Pads: 40
4 pads R3
FPC Trace
FPC Trace
10µF
4x 100nF (sub-divided?)
4x 1-100k
AC-coupling caps?
530um

## Slide 13
Progress, Next Steps and Ongoing Challenges
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 14
Progress, Next Steps and Challenges
Progress and Next Steps
  AncASIC requires three main blocks. Prototypes for 2 have already been submitted:
    MPW1 (NVG) March 2025
    MPW2 (SLDO) March 2025
    Work has started on the next components, and planning for further phases:
    Complete MPW1/2 Test Systems September 2025 (to match out-of-fab date)
    Complete MPW1/2 Testing March 2026
    Complete AncBrain Design and Validation Q3 CY2025
    Submit AncASIC V1 September/November 2025
    Complete AncASIC V1 Test System March/June 2026
    Complete AncASIC V1 Testing Aug/December 2026
    Complete AncASIC V2 Design Modifications Q1 CY2027
    AncASIC V2 Production Q1 CY2027
Complete
In Progress
Not started

## Slide 15
Progress, Next Steps and Challenges
Ongoing Challenges
  Lack of Design Sharing Agreement
    Condition of academic licences
    Cannot transfer designs from RAL to BNL
    Process ongoing for more than a year
    As a result, exploring workarounds:
      MPW2: Fully UK submission (Infrastructure Fund, submitted via Europractice)
      Future: Visiting scientists, commercial licencing, US re-design, still pursuing DSA
    All time consuming, key reason for uncertainty in MPW3 timeline
  Other (more usual) challenges
    Long fab times, MPW cancellation, some specifications still evolving
    Complex design

## Slide 16
Conclusion
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 17
Conclusion
AncASIC Status
  Design progressing well
    First test structures in fabrication
    AncBrain design under way
  Next steps are testing, AncBrain completion and full integration
  Technical progress is good. Challenges remain around schedule and agreements. Working to mitigate.

## Slide 18
Notes: The abstract pattern can be removed or repositioned if required. Be careful to ‘Send to Back’ so that it does not obscure any important information.

## Slide 19
[1] Radiation and Rate Environment, Gonella L., ePIC Collaboration Meeting, Argonne, Jan 9 2024, https://indico.bnl.gov/event/20473/contributions/84983/
[2] S. Fernandez-Perez, M. Backhaus, H. Pernegger, T. Hemperek, T. Kishishita, H. Krüger, N. Wermes,
Radiation hardness of a 180nm SOI monolithic active pixel sensor, Nuclear Instruments and Methods in Physics Research Section A: Accelerators, Spectrometers, Detectors and Associated Equipment, Volume 796,
2015, Pages 13-18, ISSN 0168-9002, https://doi.org/10.1016/j.nima.2015.02.066.
References