## Slide 1
Agenda
(https://indico.bnl.gov/conferenceDisplay.py?confId=2666)
Schedule (Milestones for the Full-Field Test …)
AOB
Jon Hock (Return steel construction)
2/10/2017 Complete flame cutting of return steel
2/23/2017 Return steel 60% complete
2/24/2017 Install solenoid
  Sometime in Mar., Cryo can start working for the Test
4/14/2017 Complete return steel enclosure

## Slide 2
  Cryo Milestones for Full-Field Test
Prerequisites :
  Platform completed and ready for use (Riggers)
  Cable tray installed to route (Electricians)
  480V Power and motor control for vacuum pumps (Electricians)
Assuming 8-week schedule (4-week schedule would be half ?):
  Routed electrical cables in tray (3 weeks)
  Check out PLC controls complete (2 weeks)
  Installed previous unmodified mechanical components (3 weeks)
  Complete new warm return piping to plant (3 weeks)
  Pressure and Leak test completed (1 week)
  Restart of the 1660 plant completed (1 week)

## Slide 3
  DAQ/quench protection Milestones for Full-Field Test
Task Complete
Isolation and Anti-aliasing Filter Board Design......Jan. 15, 2017
Board Fabrication and Assembly………………….Mar. 15, 2017
Rack Design ………………………………………Jan. 20, 2017
Rack Assembly………………………………….....Mar. 15, 2017
Cable Tray………………………………………....Feb. 15, 2017
Power Connections………………………………...Mar. 1, 2017
Quench Detector Software…………………….…..Mar. 15, 2017
DAQ Software……………………………………..Mar. 15, 2017
System Assembly…………………………………..Mar. 20, 2017
System Test …..…………………………………….Apr. 1, 2017