## Slide 1: 27th Accelerator Test Facility (ATF) Users' Meeting New Conduct of Operations and Accelerator Readiness Review
Karl Kusche
April 29, 2025
Accelerator Facilities Division

## Slide 2: Recent history
ATF shut down operations starting July 2024 in preparation for:
  Completion of legacy facility Accelerator Readiness Review (ARR) process
  Transition to the new Accelerator Facilities Division (AFD) Conduct of Operations (ConOps) Program
No operations for Users FY25-Q1 thru FY25-Q3

## Slide 3: Why?
As a DOE User facility and an accelerator (>10MeV) facility, ATF is one of several BNL legacy facilities recently required by DOE to undergo a formal review (ARR) process
ATF was formally reviewed and approved (~1990) when it first began operations, but this was prior to the current ARR process requirements
ATF has always operated with approved safety documentation and procedures

## Slide 4: Review Requirements
IRR = Internal Readiness Review
  Determines readiness of facilities, procedures and documentation in advance of the ARR
  Includes resolution of facility and procedural deficiencies that may have been identified during the IRR
ARR = Accelerator Readiness Review
  Formal review of facilities, procedures and documentation
  Includes resolution of facility and procedural deficiencies that may have been identified during the ARR
  Completion of commissioning of Capabilities prior to start of User operations

## Slide 5: Sequence
New ConOps, procedures, and safety basis documentation are ready prior to IRR
Successful completion of the IRR is required prior to the ARR
Successful completion of the ARR is required prior to resumption of ATF Capability operations
New ConOps & Procedures
ARR
Commissioning
User Operations
IRR

## Slide 6: Conduct of Operations
Conduct of Operations (ConOps) = DOE-defined procedural guidelines that are tailored to fit the ATF style of operations
ATF now has 3 distinct Capabilities:
Operators, control stations & expectations more clearly defined
Operations checklists refined & reporting formalized
E-beam
LWIR
NIR

## Slide 7: Staff Impact
ATF operations staff impacted the most
New training definitions (JTA) for staff & User tailored to AFD/ATF
Operations procedures (SOP) have been reformatted to new standard
SOPs have been created, and existing ones revised, to ensure compliance with new Conduct of Operations and safety basis documentation

## Slide 8: User Impact
Each Experiment Safety Review (ESR) requires two separate safety processes to ensure compliance
Duty Operator training for Users will follow the new ConOps guidelines
ATF staff will continue the same close collaboration with Users during prep, review, training, compliance, execution …

## Slide 9: For Users, mostly business as usual…
PI contacts ATF Experiment Review Coordinator (ERC), provides experiment details
ERC initiates Experiment Safety Review (ESR) process
  Define hazards and mitigating controls
  Identify experimental team, and set training requirements based on hazards
  Prepare/submit ESR package for safety committee review (simple vs. complex)
  Prepare/submit USI screening for review (no User intervention)
ATF ESH Manager (ESHM) expedites User training
  Online training assigned for completion prior to arrival
  ATF Awareness class/tour scheduled for the morning of the team’s arrival to ATF
  All electrical devices require safety inspection prior to installation/use

## Slide 10: Status
ConOps complete
Procedures (SOPs) and Safety basis documents nearing completion
ATF Corrective Action Plans (facility infrastructure) – need final review
Working toward holding first review (IRR) sometime in May
*ATF staff and select Users must prepare for interviews by the ARR cmte*
we are looking for volunteers that intend to become Duty Operators!

## Slide 11: FY25 Running Plans
Begin Return to Operations process in the July 2025 timeframe
Provide User Operations during FY25-Q4
Target delivery of 1500 user hours
Plan 6-day/week operations schedule, with an extended number of hours available for users on each day

## Slide 12: Questions?