## Slide 1
Agenda
(https://indico.bnl.gov/conferenceDisplay.py?confId=2803)
Cable Jacket (TEFZEL …) to wrap non-thermal wires ?
  Piyush/Sonny can use Kapton/TEFZEL. But probably Kapton is too difficult to work with other signals connected with D-connectors
Voltage tap locations (Paul Giannotti)
Schedule update
  P. Rosas’ crew still haven’t started working on power supply again. Probably he’ll get back to sPHENIX next week or the week after …
  C. Schultheiss suddenly has had a RHIC “crisis” and is not able to report today and spend much time in the sPHENIX Magnet project.
  When will FSU deliver the brackets (at least 4 at the bottom) ?
Working on the project file and dictionary files for 5 WBS branches.
AOB

## Slide 2
Legacy flat ribbon, also PVC
Teflon for thermal sensors

## Slide 3
Changed from
WBS 1.8.2 Engineering & Design
  Mechanical …
  Cryo …
  Power Supply/Quench Protection …
  Magnetic Measurement …
WBS 1.8.3 Fabrication
  Mechanical …
  Cryo …
  Power Supply/Quench Protection …
  Magnetic Measurement …
WBS 1.8.4 Installation & Testing
  Mechanical …
  Cryo …
  Power Supply/Quench Protection …
  Magnetic Measurement …

## Slide 4
1.9 SC-Magnet
1.9.1 Project Management
1.9.2 Mechanical
1.9.3 Cryogenic Systems
1.9.4 Power Supply
1.9.5 Magnet Measurements
WBS 1.9.3.1 RHIC Lines S/R/H/U-Line Taps and Valvebox
WBS 1.9.3.3 LN2 Cooling System
WBS 1.9.3.4 Coldbox with Heatexchangers, Valve Box Upgrade, 500L Dewar
WBS 1.9.3.5 Cryo Controls –Hardware/Software
WBS 1.9.3.2 Helium Transfer Line Bundle System
WBS 1.9.4.1 AC/DC Power Distribution
WBS 1.9.4.2 Power Supply
WBS 1.9.4.3 Quench Detection and Dump Resistor
WBS Level 2
WBS Level 3
Level 3 Manager
WBS Level 4 – Work Packages
Control Accounts
And Reporting
Level 2 Manager
CAM
1.9 SC- Magnet
Proposed DOE Reporting Levels (Control Accounts)
To
for CD1