{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Input","Lists"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":5,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Input","index":0,"n_rows":16,"n_cols":45,"rows_kept":16,"cut":false,"hidden":false,"merged":[[0,0,0,4],[1,21,1,22],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,23,1,24],[1,25,1,26],[0,21,0,26],[0,5,0,10],[1,17,1,18],[1,19,1,20],[0,15,0,20],[0,11,0,14],[1,11,1,12],[1,13,1,14],[1,15,1,16],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,37,1,38],[0,27,0,28],[0,29,0,31],[0,32,0,38],[1,27,2,27],[1,28,2,28],[1,29,2,29],[1,30,2,30],[1,31,2,31],[1,32,2,32],[1,33,2,33],[1,34,1,36],[0,42,0,44],[1,42,2,42],[1,43,2,43],[1,44,2,44],[0,39,0,41],[1,39,2,39],[1,40,2,40],[1,41,2,41]]}
["Component Information",null,null,null,null,"In-House Inspection & Test",null,null,null,null,null,"Outsourced Inspection & Test",null,null,null,"Travelers, Procedures & Checklists",null,null,null,null,null,"Verification",null,null,null,null,null,"Associated Equipment",null,"Calibration Plans",null,null,"Serialization",null,null,null,null,null,null,"Partner/Vendor Communications & Visits",null,null,"Packaging/Transportation/Shipping"]
["WBS","System Name","Component","Sub-Component/ Activity","Provider","In-Process Inspections",null,"In-Process Tests",null,"Documentation Deliverables",null,"Inspection & Tests",null,"Acceptance Testing",null,"Material Records",null,"Fabrication Records",null,"Other Documentation",null,"Assembly Verification",null,"Internal Verification\n(In-House Components)",null,"External Verification\n(Outsourced Components)",null,"Required","Reference","Required","Required By","Reference","Serializable","Required","Contractual Serialization",null,null,"Special Serialization",null,"Required","Required By","Reference","Required","Required By","Reference"]
[null,null,null,null,null,"Required","Reference","Required","Reference","Required","Reference","Required","Reference","Required","Reference","Required","Reference","Required","Reference","Required","Reference","Required","Reference","Required","Reference","Required","Reference",null,null,null,null,null,null,null,"Required","Required By","Reference","Required","Reference"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Aerogel","Material Purchase","Vendor Contract","Yes",null,"Yes",null,"Yes",null,"Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes",null,"Yes","Aerogel Test Stand QA Procedures","No",null,"No",null,null,"No",null,null,null,null,null,null,"No",null,null,"Yes","Formal Agreement","Aerogel Test Stand QA Procedures"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Aerogel","Material Tests","In-Kind Labor",null,null,null,null,null,null,"Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures","Yes","Aerogel Test Stand QA Procedures",null,null,"Yes","Aerogel Test Stand QA Procedures","No",null,"No",null,null,"No",null,null,null,null,null,null,"No",null,null,"Yes","Formal Agreement","Aerogel Test Stand QA Procedures"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Mirrors","Material Purchase","Service Agreement",null,null,null,null,null,null,"Yes","Mirror System","Yes","Mirror System","No",null,"Yes","Mirror System","Yes","Mirror System","Yes","Mirror System",null,null,"Yes","Mirror System","Yes","Mirror System","Yes","Statement of Work","Mirror System","Yes","No",null,null,null,null,null,"No",null,null,"Yes","Statement of Work","Mirror System"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Mirrors","Mirror Assembly & Tests","In-Kind Labor",null,null,null,null,null,null,"Yes","Mirror System","Yes","Mirror System","No",null,"Yes","Mirror System","Yes","Mirror System","Yes","Mirror System",null,null,"Yes","Mirror System","Yes","Mirror System","Yes","Statement of Work","Mirror System","Yes","No",null,null,null,null,null,"No",null,null,"Yes","Statement of Work","Mirror System"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Photosensors (HRPPDs)","Material Purchase","Vendor Contract",null,null,null,null,null,null,"Yes","High Rate Picosecond Photodetector ","Yes","High Rate Picosecond Photodetector ","No",null,"No",null,"Yes","High Rate Picosecond Photodetector ","Yes","High Rate Picosecond Photodetector ",null,null,"Yes","High Rate Picosecond Photodetector ","No",null,"Yes","Formal Agreement","High Rate Picosecond Photodetector ","Yes","Yes","Yes","Formal Agreement","High Rate Picosecond Photodetector ","No",null,"No",null,null,"Yes","Formal Agreement","High Rate Picosecond Photodetector "]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Photosensors (HRPPDs)","Material Tests & Assembly","Service Agreement",null,null,null,null,null,null,"Yes","High Rate Picosecond Photodetector ","Yes","High Rate Picosecond Photodetector ","No",null,"No",null,"Yes","High Rate Picosecond Photodetector ","Yes","High Rate Picosecond Photodetector ",null,null,"Yes","High Rate Picosecond Photodetector ","No",null,"Yes","Formal Agreement","High Rate Picosecond Photodetector ","Yes","Yes","Yes","Formal Agreement","High Rate Picosecond Photodetector ","No",null,"No",null,null,"Yes","Formal Agreement","High Rate Picosecond Photodetector "]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Photosensors (HRPPDs)","Material Tests","In-Kind Labor",null,null,null,null,null,null,"Yes","High Rate Picosecond Photodetector ","Yes","High Rate Picosecond Photodetector ","No",null,"No",null,"Yes","High Rate Picosecond Photodetector ","Yes","High Rate Picosecond Photodetector ",null,null,"Yes","High Rate Picosecond Photodetector ","No",null,"Yes","Formal Agreement","High Rate Picosecond Photodetector ","Yes","Yes","Yes","Formal Agreement","High Rate Picosecond Photodetector ","No",null,"No",null,null,"Yes","Formal Agreement","High Rate Picosecond Photodetector "]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Vessel","Material Purchase","Vendor Contract",null,null,null,null,null,null,"Yes","pfRICH Vessel","Yes","pfRICH Vessel","No",null,"No",null,"No",null,"Yes","pfRICH Vessel",null,null,"Yes","pfRICH Vessel","No",null,"No",null,null,"Yes","Yes","No",null,null,"Yes","pfRICH Vessel","Yes","Statement of Work","pfRICH Vessel","Yes","Formal Agreement","pfRICH Vessel"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Laser Monitoring System","Material Purchase","Vendor Contract",null,null,null,null,null,null,"Yes","Laser Monitoring System","Yes","Laser Monitoring System","No",null,"No",null,"No",null,"No",null,null,null,"No",null,"No",null,"No",null,null,"Yes","Yes","No",null,null,"Yes","Laser Monitoring System","No",null,null,"No"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Laser Monitoring System","Assembly & Tests","Built In House","No",null,"No",null,"No",null,null,null,null,null,"No",null,"No",null,"No",null,"No",null,"Yes",null,null,null,"No",null,"No",null,null,"Yes","Yes","No",null,null,"Yes","Laser Monitoring System",null,null,null,"No"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Laser Monitoring System","Laser","Built In House","No",null,"No",null,"No",null,null,null,null,null,"No",null,"No",null,"No",null,"Yes","Laser Monitoring System","Yes",null,null,null,"Yes","Laser Monitoring System","No",null,null,"Yes","Yes","Yes","Statement of Work","Laser Monitoring System","No",null,null,null,null,"Yes","Statement of Work","Laser Monitoring System"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Laser Monitoring System","Support Stand","Built In House","Yes","Laser Monitoring System","Yes","Laser Monitoring System","Yes","Laser Monitoring System",null,null,null,null,"Yes","Laser Monitoring System","Yes","Laser Monitoring System","No",null,"No",null,"Yes","Laser Monitoring System",null,null,"No",null,"No",null,null,"Yes","No",null,null,null,null,null,null,null,null,"No"]
["6.10.04.03","Proximity Focusing Ring Imaging Cherenkov","Laser Monitoring System","Control System","Vendor Contract",null,null,null,null,null,null,"Yes",null,"Yes",null,"No",null,"No",null,"No",null,"Yes","Laser Monitoring System",null,null,"Yes",null,"No",null,"No",null,null,"No",null,null,null,null,null,null,"Yes",null,null,"No"]

{"sheet":"Lists","index":1,"n_rows":8,"n_cols":8,"rows_kept":8,"cut":false,"hidden":false,"merged":[[0,4,0,5]]}
["Source",null,"Options",null,"References",null,null,"Contracts"]
["Built In House",null,"Yes",null,"Name","URL",null,"Contract"]
["Vendor Contract",null,"No",null,"EIC Detector Web Portal","https://eic.jlab.org/Detector",null,"Formal Agreement"]
["In-Kind Contribution",null,null,null,"Aerogel Test Stand QA Procedures","https://eic.jlab.org/Documents/DET/PID/pfRICH/Aerogel/Aerogel_Test_Stand_Q_A_Prodedures.pdf",null,"Statement of Work"]
["Service Agreement",null,null,null,"High Rate Picosecond Photodetector","https://eic.jlab.org/Documents/DET/PID/pfRICH/HRPPD/",null,"Project Planning Document"]
["In-Kind Labor",null,null,null,"Laser Monitoring System","https://eic.jlab.org/Documents/DET/PID/pfRICH/Laser/"]
[null,null,null,null,"Mirror System","https://eic.jlab.org/Documents/DET/PID/pfRICH/Mirror/"]
[null,null,null,null,"pfRICH Vessel","https://eic.jlab.org/Documents/DET/PID/pfRICH/Vessel/"]