## Slide 1
ePIC Electronics and DAQ WG – 5/14/2025 – PicoDAQ
News / Announcements
  Schedule
    May 19th – TIC meeting dedicated to the preTDR (discussion of standardization of scenarios)
    May 20 – RHIC / AGS user meeting: full day parallel session focused on ePIC (I’ll be giving ePIC DAQ talk at 3:30)
    May 22 – WG Meeting: Further Discussion towards developing PICO-DAQ
    May 29 – WG Meeting: GTU / Timing Synchronization
  June 2-3 - Project meeting with ASIC developers
  June 4 – ASIC updates (probably just a short summary of the ASIC developer meetings early in the week)
  June 12-13 – DAC Review
  July 14-18 – collaboration meeting:
  1. Requested electronics & DAQ meeting offset from detector meetings: test beds & PICO-DAQ
  2. Calorimeter session focusing on SiPM dark currents, thresholds required & resulting
  3. ASIC summary
  Other Announcements?
Agenda
  Intro
  BHCAL Test Setup – Norbert Novitzky (ORNL)
  FELIX-Lite – Tonko Ljubicic (Rice)
  JLAB Test Setups – Ben Raydo (JLAB)
  Miniature DAQ setup - William Gu (JLAB)

## Slide 2
Detector Install: FY29Q2 - FY31Q2
Cosmics: FY31Q3
Early CD-4: FY32Q4
DAQ Releases:
PicoDAQ FY26Q1
  Readout test setups
MicroDAQ: FY26Q4
  Readout detector data in test stand using engineering articles
MiniDAQ: FY28Q1
  Readout detector data using full hardware and timing chain
Full DAQ-v1: FY29Q2
  Full functionality DAQ ready for full system integration & testing
Production DAQ: FY31Q3
Ready for cosmics
MiniDAQ
Production
DAQ
PicoDAQ
MicroDAQ
PDR2
Full DAQ-V1
PDR1
PDR3
PicoDAQ development --- Streaming DAQ Milestones

## Slide 3
Detector Install: FY29Q2 - FY31Q2
Cosmics: FY31Q3
Early CD-4: FY32Q4
DAQ Releases:
PicoDAQ FY26Q1
  Readout test setups
MicroDAQ: FY26Q4
  Readout detector data in test stand using engineering articles
MiniDAQ: FY28Q1
  Readout detector data using full hardware and timing chain
Full DAQ-v1: FY29Q2
  Full functionality DAQ ready for full system integration & testing
Production DAQ: FY31Q3
Ready for cosmics
MiniDAQ
Production
DAQ
PicoDAQ
MicroDAQ
PDR2
Full DAQ-V1
PDR1
PDR3
PicoDAQ development --- Streaming DAQ Milestones
PicoDAQ Milestone - 7 months away!
Need it to be well defined and show progress by PDR3
Will help the collaboration develop test stands consistent with our eventual plans for epicDAQ
Will help avoid duplication of effort when possible
What is it?
Documented, source control tagged software / firmware
Support existing hardware (FELIX, GTU prototype, Dev Boards)
Need to specify details

## Slide 4: Hear about test stands / early hardware partially to prime discussion of common software:
How to make this useful for collaboration?
  Common tools
  Instructions
  Helpers?
How to develop towards an integrated ePIC DAQ?
  Present common model for data to collaboration:
    Data formats: decide on one existing format? / implement standard readers handling all existing formats?
  Define messaging / data transfer scheme
    Node Identification
    Common headers for data transfer
    Common transfer mechanisms
  Streaming Readout:
    Time based data even for triggered events?
  Consider schemes to easily incorporate aggregation / GTU distribution of clock & fast commands as the new ASICs/hardware becomes available.
Will discuss in coming week(s)