## Foglio1
Subsystem | Performance studies | Hits/Rates/Bandwidth | Doses/Fluences | Planning | Missing | Notes
June 2026, after the second report at TIC
el/r-o/DAQ |  | table template ready (shared sheet) |  |  |  | including background and noise is requested
SVT | performed: efficiency, purity, spatial and angular resolutions and primary vertexing | very advanced study |  | use the most recent simulation files; hit rate fluctuations; sensor response function; insert noise in simulation; track chi^2 studies |  | 10u Au coating used and needed! noise was included for the second report; noise rates similar or larger than SR in several layers/disks
MPGD |  | studies performed w/o clustering (multiply by 3 or 4 the rates); fully compatible with SALSA |  | repeat studies introducing threshold (100 e?)
pfRICH |  | detailed hit occupancy (maximum, average) performed |  |  | full ITR2 implementation in EICrecon for performance studies; hit maps used to estimate HRPPD QE ageing challenge | for performance the completion of the reconstruction software is needed
hpDIRC | report postponed |  |  |  |  | for performance the completion of the reconstruction software is needed
dRICH |  | extremely detailed analysis: DCR remains dominant; ALCOR shutter and external "trigger" needed for compatibility of the avilable bandwidth |  |  | full ITR2 implementation in EICrecon for performance studies | for performance the completion of the reconstruction software is needed
TOF |  | dominat SR rate for low En. Deposition in both BTOF and FTOF; controlled with 80keV cut |  | repeat studies with ePIC simulation files; PID performance; angular resolution |  | SRO simulation files used so far
EEEMCAL | modest background impact within available statistics | rates dominated by background, but still in r-o/DAQ capabilities | n fluence evaluated: Noise from dark current in SiPMs evaluated to be below expected threshold after 150 fb^-1 | refine the performance studies with different simulated files to enhance the background role | refine the performance studies with different simulated files to enhance the background role (e/pi separation) | simulated files with enhanced background
BIC | Energy resolution is not affected by the presence of background. | important SR rate in the first Astropix layer | Radiation/Fluence have been reevaluated including background. No substantial increase is observed.
FEMCAL | no relevant performance impact (# of hits, total energy, # of clusters, cluster energy, # of hits in cluster, neutral jets : # of jet, jet energy, mass, rapidity, # of clusters) |  | evaluated: no concerns | working on pi0 reconstruction code for day1 calibration with/without BG; cross-check that the Tracking+Ecal jet studies provide consistent results when the appropriate cut on the minimum number of requested hits to reconstruct a track is applied |  | inconsistency calorimeter tracking: probably the at least 4-hit request not used
NHCAL | no feedback
BHCAL | no relevant impact on performance (calibration, space resolution) | Maximum hit rate increases only marginally from 2.2 to 2.5 Hz, well below CALOROC rate limit |  | repeat with larger statistics | simulation files with background with lager statistics
FLHCAL | studies still to be performed
FF |  | not high apart in B0 where they can exceed EICROC capabilities | studies performed, particularly high in B0 |  | proper pixelized AC-LGAD digitization; proper pixelized AC-LGAD digitization; updated B0 geometry in DD4HEP
Luminosity System |  |  |  |  | initial studies indicate the need of shielding around the vacuum pipe: design needed; updated geometry/design of magnets, shielding, collimator are not in the standard configuration geometry; for background, only SR files are available in the lumi region
low Q^2 taggers |  |  |  |  | simulation files with background in the FB; updated baem-line geometry in DD4HEP; digitization