## Slide 1: Double thin gap MPGD tracker CERN test beam prep, 2025

## Slide 2
Funding profile (FY 25)
JLAB : Travel – 18K USD
Shipping – 6K USD
UVA : Travel – 12.3 K USD
CERN test beam period :
November 3, 2025 – November 26, 2025
Travel plan : Be there by November 3 with the equipment
List and Shipment of equipment :
To do : Find the exact list, shipment weight and coordinate shipment from JLAB to CERN
  Sourav Tarafdar will find out the shipment
Cut off date for shipment to CERN : Will find out later and it depends on getting back detector from UVA
List of items to be shipped
  SRS system
  DAQ computer with monitor
  30cm x 30 cm active area double sided thin gap prototype
  GEM reference tracker
  Support structure for the setup
Notes: TB effective day on 5th November when access to set up area will occur. Beam will be for 19 days.
5 people spread out over 3 weeks.

## Slide 3: Work plans (?)
Prototype final assembly (Funding profile from FY 24 funds)
Travel to UVA for mounting mRWELL on GEM+ cathode block – Date and personnel (?)
Bring the prototype to JLAB
Do leakage test and HV test of the entire prototype in UVA
Prepare DAQ (probably CODA ? ) (Funding profile from current FY 25 funds for only labor)
JLAB computer and UVA computer. Responsible person - Xinzhan . Huong will find if UVA computer can be sent to CERN.
Prepare support structure
Raw material exist ? No funds for buying items to prepare support structure . Responsible person to design – Seung Joon and Kondo will come up with plan

## Slide 4: Work plans (?)
Shipment from JLAB to CERN
S.T will start gathering information from JLAB shipment. Need to make sure the items arrive at CERN well before the start of test beam, at least 1 week prior. What should be our cut off date for postponing the test beam ?
CERN shifts
  2 people from JLAB for 3 weeks, third person possible (?) for a week at least. FY25 funds is for 2 people for 2 weeks but can be stretched to 3 weeks.
  2 people from UVA for (?) weeks. FY25 funds is for 2 people for 2 weeks. Can it be stretched to another week for at least 1 person(?)
  Need for someone to take care of gas supply and hooking up gas lines to DUT at CERN - Kondo
  Need to ship the items back from CERN.
Data Quality in Test Beam. - Kondo and shift members
Improve raw APV data visualization on CODA during run time - Xinzhan
Data analysis
  Xinzhan may help to set it up, UVA students and S.T will actively participate.

## Slide 5: Types of measurement @ CERN
Without B field –
  Using ArCO2(80:20) gas
  HV scan (eff. Studies, double hit efficiency,
  position resolution
  Same measurement using isobutane (?) May be not.
With B field
Same set of measurement as above
Hoping to have permanent set up inside Magnet.