## Slide 1
Agenda/powerpoint
(https://indico.bnl.gov/conferenceDisplay.py?confId=3027)
J. Hock’s steel-making progress …  next page
  The brackets/jack-supports were delivered late yesterday afternoon (Apr. 11, 2017)
P. Rosas (Power Supply update) : “We are moving along, we may go a little into next month.”
D. Phillips: “Nothing has been done to finalize the initial layout done over 1 year ago. It needs to be optimized for cable routes and access requirements. I need to get together with Pablo to do this. ”
There was a technical meeting this morning for C. Schultheiss, J. Sandberg, B. Lambiase, C. Theisen, Z. Altinbas, W. Pekrul and myself. They aim at June 15 to have a tested data-acquisition and quench protection system.
Cable/connectors (T. Tallerico)
AOB

## Slide 2
Status (continued)
Steel making progress (J. Hock) :
~A week behind the schedule shown ~Mar. 21, 2017.