## BTOF_action_items
TASKS | Action Items | Responsible Institute | Starrt | End | Status | Notes | Progress
Sensor testing | Procure inkind actual size strip sensor | Japan | 2026-01-01 | 2026-01-31 |  | Based on Satoshi's slide https://indico.bnl.gov/event/30164/
| Final Test actual size strip sensor | Japan | 2026-02-01 | 2026-05-01 |  | Based on Satoshi's slide https://indico.bnl.gov/event/30164/
Thermo mechanical test-2025
| Design stavelet mockup |  |  |  | 100%
| Assemble stavelet mockup with Si heaters and cooling pipe |  |  |  | 100%
| Test mockup for thermal stress |  |  |  | 100%
Document the results
| Finalise the stavelet cooling design |  |  | 2026-02-01
Stavelet assembly set up
| Correct glue identification and test |  | 2026-02-02 | 2026-03-01
| Glue curing instrumentation and test |  | 2026-02-02 | 2026-04-30
| Define Glue robot configuration |  | 2026-03-01 | 2026-06-01
| Glue robot calibration and test |  | 2026-04-01 | 2026-07-01
| Design and test version 1 gluing jigs |  | 2026-01-01 | 2026-07-01
| Define QC procedure for assembly |  | 2026-06-01 | 2026-07-01
| Verify QC procedure using mockup |  | 2026-01-01 | 2026-07-02
Build Database
Half Stave demonstrator mockup |  |  | 2026-07-02 | 2026-07-08
| One stavelet mockup with cooling tubes and Si heaters as ASIC |  | 2026-07-02 | 2026-09-02
| Stavelet QA/QC station assembly |  | 2026-07-08 | 2026-09-02
| Validate QC on 1st stavelet |  | 2026-09-02 | 2026-09-10
| Build rest of the 7 stavelet mockup |  | 2026-09-02 | 2026-09-23
| Validate QC on 7 stavelets |  | 2026-09-23 | 2026-09-30
| Combine stavelets into stave |  | 2026-09-30 | 2026-10-14
| Define and validate QC on half stave |  | 2026-07-02 | 2026-10-14
Build Database
Demonstrator with RDO /service hybrid
| Test sensor with FCFD V1 |  | 2026-10-14 | 2026-12-01 |  | Only 6 channel FCFD v1 will be available in mid 2026
Version 1 Half stave functional demonstrator (with working sensors and FCFD v2) | Validate FCFD v2 |  | 2027-01-01 | 2027-03-01 |  | FCFD v2 will be early 2027 with full 128 channels. However need to see if the final design of module uses 4 ASICs per sensor to optimize sensor performance.
| Test sensor with FCFD v2 |  | 2027-03-01 | 2027-05-01 |  | Need to see how many FCFDs can be provided
| 8 Stavelet assembly with real sensor and ASIC |  | 2027-05-01 | 2027-05-30 |  | Real ASIC contingent upon availability of # of actual ASIC
| QA on each stavelet |  | 2027-06-01 | 2027-07-01
| Assemble half stave |  | 2027-07-02 | 2027-07-30
| QA on half stave |  | 2027-08-01 | 2027-08-31
Finalize assembly items and procedure for production | Finalize gluing zig |  | 2027-08-31 | 2027-09-15
| Finalize glue robot calibration |  | 2027-09-15 | 2027-10-01
| Finalize assmebly procedure by conducting tests in version 1 functional stave |  | 2027-10-02 | 2027-10-17
| Finalize shipping protocols and database |  | 2027-10-18 | 2027-10-30
Non functional full Stave demonstrator mockup | Build 2nd half stave mockup with Si heaters |  | 2027-06-01 | 2027-06-15
| Combine two staves in full stave mockup |  | 2027-06-15 | 2027-07-15
| Test full stave for thermal test |  | 2027-07-15 | 2027-08-15
Functional two half stave demonstrator (with working sensors and FCFD v3) - Full stave Engineering Test article | Validate FCFD v3 |  |  |  |  | Possible availability early 2028
Test sensors with FCFD v3
16 Stavelet assembly with real sensor and ASIC
QA on each stavelets
Assemble both half stave
QA on each half stave
Combine two half staves in full stave
| QA on full stave |  |  | 2028-02-02
Preproduction of 10% stavelet

## FTOF_action_items
TASKS | Action Items | Responsible Institute | Start | End | Status | Notes | Progress
Sensor testing
| Final Test actual size pixel sensor |  | 2026-02-01 | 2026-05-01
Module v1 | Design module |  | 2025-06-01 | 2025-07-01
| Design assebly setup |  | 2025-06-01 | 2025-07-01
| Assemble module uysing Jig based procedure |  | 2025-07-01 | 2025-08-01
| Test mechanical stability of module |  | 2025-08-02 | 2025-08-15
| Assemble module using robotic gantry based procedure |  | 2025-08-15 | 2025-09-15
| Test mechanical stability using robotic gantry based procedure |  | 2025-09-15 | 2025-09-30
| Finalise module assemble method |  | 2025-09-30 | 2025-10-30
Module v2 (thermo-mechanical model) | ASIC and sensor heaters construction |  | 2025-10-30 | 2025-11-30
| Assemble second module based on module V1 with heaters |  | 2025-11-30 | 2026-01-31
| Thermal testing on module v2 |  | 2026-01-31 | 2026-02-28
Module v3 (functional EICROC1+ Dummy sensor) | Design Readout preliminary power distribution |  | 2026-03-01 | 2026-04-01
| Assemble and test power deistribution |  | 2026-04-01 | 2026-05-01
| Assemble module v3 with power distribution |  | 2026-05-01 | 2026-06-01
| Thermal testing on module v3 |  | 2026-06-01 | 2026-07-01
Functional Module (functional EICROC1 + Real sensor) - Article v1 | Test bonding on sensor with EICROC1 |  | 2026-07-01 | 2026-07-15
| QA of EICROC1+ sensor unit |  | 2026-07-15 | 2026-08-15
| Assemble functional module with EICROC1 and full size real sensor : Article v1 |  | 2026-08-15 | 2026-10-30
| Test Article v1 |  |  | 2026-12-01
Functional Module (functional EICROC2 + Real sensor) - Article v2 | Test bonding on sensor with EICROC2 |  |  | 2027-02-01
| QA of EICROC2+ sensor unit |  |  | 2027-03-30
| Assemble functional module with EICROC2 and full size real sensor : Article v2 |  |  | 2027-04-15
| test Article v2 |  |  | 2027-04-30
| Validate production readiness |  |  | 2027-05-31

## Far Forward and backward
Tasks | Action items | Institute | Start | End | Status | Comments | Progress
Sensor testing : exisiting sensors (4x4 and 32x32) | IV testing for EVERY sensor (does sensor work) | UCSC (maybe BNL for next production, as well) | 2025-05-30 | 2025-07-01 | Complete
| Subset of sensor -- test for jitter with fast preamp board | BNL | 2025-07-30 | 2025-12-31 | In-progress
| TCT scans of subset of sensors | UCSC, BNL | 2025-07-30 | 2025-12-31 | In-progress
| Detailed studies of 30um HPK 4x4 sensors with Sr-90 | BNL | 2025-07-30 | 2025-12-31 | In-progress
EICROC0 testing : existing ASICs | Testing of analog and digital output with old firmware | BNL and IJCLab | 2024-01-01 | 2025-05-30 | Complete
| Testing (charge injection) with July 2024 firmware | BNL and IJCLab | 2024-07-01 | 2025-12-31 | In-progress
| Updating of test boards to use new Xilinx FPGA board | BNL and IJCLab | 2025-11-01 | 2025-12-31 | In-progress
| Testing of EICROC with new firmware | BNL and IJCLab | 2025-07-01 | 2026-02-01 | In-progress
(older 4x4) Sensor + EICROC0 testing: existing | TCT scans of sensors wire-bonded to EICROC0 | BNL | 2024-09-01 | 2025-02-01 | Complete
| Sr-90 source measurements with wire-bonded setup | BNL | 2024-09-01 | 2025-02-01 | Complete
| Charge injection with wire-bonded and bump-bonded sensors | BNL and IJCLab | 2002-09-01
| "etched" sensors bump-bonded to EICROC0 | BNL | 2025-06-01 | 2025-07-01 | Complete
| Population of "etched" assemlby for IJCLab testing | BNL | 2025-09-01 | 2025-02-01 | In-progress
| Testing (TCT and Sr-90) of etched assemly | BNL and IJCLab | 2025-07-01 | 2026-02-01 | In-progress
EICROC1 testing | Repeat basic EICROC0 charge injection measurements for validation | BNL and IJCLab (and ORNL?) | 2026-03-01
| Bond (wire or bump) sensors to EICROC1 | BNL |  |  |  | Need to discuss with HPK for small production
| Test integrated sensor (different options) with EICROC1 (Sr-90, TCT, etc.) | BNL and (hopefully) IJCLab