## Slide 1: HRPPD Meeting #5 Update
2026-01-13
Raymond Dawson
Notes: Tip: Keep titles under 60 characters for readability
To change the photo: Right-click on photo and select change photo

## Slide 2: Current Status
Ceramic Tasks: Due by 01/12/2026
PED contract with Incom will be signed soon
Priority tasks:
  Location of new HV tabs and placement of pads/vias on ceramic
  Sidewall chamfer
    Need to fit 8mm chamfer at minimum
  Interposer tolerance stackup (air side)
    Confirmed pad location tolerance with Kyocera
Design File
  Update HRPPD with final design changes
    Need to complete nets connections
    Stitching vias mostly implemented in 1 interposer group, need to copy-paste
    Pad size changes - <1 day
    Estimated to complete: 1 week + TBD changes
Simulations
  TBD – Hi-Z input simulations
Non-Ceramic Tasks: Due after
Interposer downselection - thickness + # grounds vs crosstalk
  Update 1/13 – received 1mm models from Neoconix
Backplane Changes
  Cables
  Safety resistors
  Bypass capacitors + ringing resistors
  Plastic connectors for HV connections
  Pogo pins vs interposer for HV connections
FCFD Test Board
  Buyer out last week, sorting issues with vendor this week for order
  Aiming for arrival mid-February
Notes: Add due date

## Slide 3: Archive

## Slide 4: Record of Design Decisions
Amount of stitching vias will be increased
Vacuum pad size will be 2.75mm square
Interposer footprint will fit either “by2” or “by4” configuration
Preliminary
  Air side pads will be 1.2mm round with ground pour with 8mil clearance
  If needed, HV pads will fit both pogo pins and interposers so either can be used with the ceramic
  1mm vs 3mm interposer will be independent of ceramic design

## Slide 5: Completed Tasks
Simulations
  Complete - stitching vias, air side interposer pad reduction, GND planes
  Complete 12/16 - Vacuum side pad size selection
  Complete 12/23 – air side pad size, interposer ground pour
  Complete 1/6 – Max air pad size + ground pour
  TBD – Hi-Z input simulations
High Voltage (HV) Design
  Complete - preliminary pogo pins selected, HV spacing determined
  Complete 1/6 – determined pad size for 2 pogos or 1 4x4 interposer, if needed
Other
  Complete - Break in ground ring placed
  Test file import with Kyocera
    Update 12/23 Kyocera confirmed successful import of ODB++