## Slide 1
Agenda/powerpoint
(https://indico.bnl.gov/conferenceDisplay.py?confId=3135)
Update on the Cryo test in 912 (without sub-cooler) ?
J. Hock’s steel-making progress …  next page
  If all work out as Jon planned, we may be almost on schedule (as it was planned ~May 23 to June 13 to install Extension and May 29-June 12 to “modify roof plates”).
  Brian Streckenbach is helping with scaffolding/ladder arrangement.
P. Rosas (May 9) : “We had the PS up to 2700 amps into the dummy load open loop, we will be able to run the PS in voltage and then current loop this week and into next week. This is all been done in local control.”
  “open loop” means  bypassing the regulator
Cable/connections (T. Tallerico/R. Meier)
AOB

## Slide 2
For efficiency/safety consideration, Jon et. al. don’t want to install the Magnet until they finish the main roof steel construction (putting them up, measuring the holes and taking them down). Jon expected that the front wall/roof wall steels can be all finished and we may be able to install Magnet around May 31-June 7. We need to take down a piece or two the front wall steels when we install in the Magnet, survey and put them back for installing the Extension.
Status (continued)
Return steel construction progress (J. Hock) :
HFT Iron Shield Status 5/5/17