## Slide 1: Ideas for the way forward

## Slide 2: Objectives
Prepare a credible project for a reduced UK SVT project
  Indications are that STFC might give us a bridging grant to an uncertain shore for the next 3½ – 4 years
    This needs clearly defined deliverables on this time scale, in case the far shore disappears
The US has indicated intent to support supplying "necessary materials and equipment"
  Definition of what this is is still required
  It is clear that this would be sensors and chips, but the US has also already stated that they will not provide support for wafer probing in the UK. There are other grey areas that need to be negotiated
The project we will ask from STFC will be mostly people
Our other objective is that the proposed project covers the interests of the UK institutes and people involved
But, there will be things we will not be able to pursue
And there is obviously a huge uncertainty, whether STFC will support such a programme

## Slide 3: Suggestions from SVT management
I had discussions with Ernst and Laura about how such a project could look like
  Driven by what they think is useful for the project, and what we think can be achieved on that timescale
  This is just a suggestion; it is understood by everybody that the new UK project must work for the UK groups
Milestones to be delivered within 3.5 years (starting from end of CY 2026)
  L3 final design and construction
    Parts needed for L3
      Sensors, AncASIC, FPC, carbon fiber et al for staves
      Tooling for module assembly and stave loading
      Wire bonding spool and maintenance
      PSU, cooling, DAQ for testing staves
    Deliverable: all staves for L3, fully tested and shipped
  Design of the AncASIC (MPW3 and production)
  Design of EIC-LAS (V1 and production)
  Testing of AncASIC, EIC-LAS
  Development of readout boards (FIBs and control boards) and serial powering scheme
    Deliverable: design of all readout boards (for all SVT)

## Slide 4: Slides from Ernst about schedule

## Slide 5: SVT baseline schedule
The current SVT baseline schedule has a completion date of July 2032 for the integration of the IB, OB, and disks into ePIC,
Some pertinent dates in the lead-up to July 2032 are:
  Start of EIC-LAS design (v1) in mid-2026,
  Start of EIC-LAS (production) fabrication in mid-April 2028,
  Start of Ancillary ASIC (production) fabrication in mid-April 2028,
  Start of OB FPC pre-production for system tests in July 2028,
  Start of OB FPCs production in August 2029,
  Start of OB module assembly in November 2029,
  Assembly of L3 and L4 staves between May 2030 and April 2032,
The baseline schedule calls for assembly of L4 staves before L3 staves,
  this is driven by the current “outside-in” integration sequence,
  if this order is reversed, L3 stave assembly completes by mid-2031 all else unchanged,

## Slide 6: SVT L3 stave schedule
A four-year funding path starting in mid-2026 and ending in mid-2030 is at face value a year short of delivering L3 staves (mid-2031) with this one change,
  Reversing the assembly order of L4 and L3 staves alone is necessary but not sufficient,
  L3 stave assembly should start by May 2029 to complete by mid-2031,
OB module assembly (baseline start in November 2029) is the critical path to L3 stave assembly,
FPC (pre-)production is the critical path item to module assembly,
The above implies that:
  OB FPC schedule will need revisiting,
  L3 and L4 FPC effort will need to be broken out and arranged to prioritize L3,

## Slide 7: SVT L3 stave schedule
Recall that the baseline has:
  Start of OB FPC pre-production for system tests in July 2028,
  Start of production OB FPCs in August 2029,
If L3 stave assembly needs to start in May 2029, L3 FPC production would need to start about nine months prior – feasibility will need further study,
  Note that EIC-LAS v1 will most likely derive from ER3, not ER2 as originally planned; this is beneficial and may imply that L3 FPC pre-production can safely be started prior to July 2028,
Key dates of additional L3 prerequisites from the baseline schedule are:
  January 2029 – availability of Ancillary ASIC chips,
  October 2028 – start of thinning and dicing of the EIC-LAS production version,
  September 2028 – L3 site assembly readiness verification,
Delivery of L3 staves by mid-2030 is aggressive – no show-stoppers have been identified so far, provided that the FPC schedule can be met,
Impacts on overall SVT delivery obviously need to be further worked out as well.