## Slide 1: New project

## Slide 2: Programme duration
As noted last time the programme we will aim for is intended to bridge the time until the confirmation of a (hopefully) successful new infrastructure bid
  The current working assumption is that Wave 5 opens in spring 2027 and funding would start ~18 months later, so Autumn 2028
  Realistically, funds would become available at the next start of a FY, so April 2029, i.e. 3 years from now
As discussed last time delivery of the L3 staves would require a 4-year time scale (if critical items (FPC) can be brought forward)
Since last week Daria had discussions with STFC on what we should write into the pro forma
  The guidance received is that we can put whatever we like on the pro forma, as long as it’s duly justified
We therefore propose to develop both a 3y and a 4y project
  Gives us the ability for a quick response if STFC changes their mind again
  If we present both this gives us the opportunity to explain the additional benefits of the 4y project

## Slide 3: Suggested topics – 3y project
Activity (3y) | Deliverable | Effort needed | Equipment/consumables needed | Groups involved
Design of the AncASIC (MPW3 and production) | Design |  |  | 
Design of EIC-LAS (V1 and production) | Design |  |  | 
Testing of AncASIC, EIC-LAS | Deliverable: Test setup (and operation) of a full powering chain, test setup (and operation) of a to be specified number of EIC-LAS |  |  | 
Development of readout boards (FIBs and control boards) and serial powering scheme | Design of all readout boards (for all SVT) |  |  | 
Wafer probing (at CERN) | Contribution to the wafer-probing capabilities |  |  | Brunel
Simulation | Contribution to the SVT simulation effort |  |  | Oxford

## Slide 4: Additional activities – 4y project
These activities will run in parallel to the 3y activities outlined on the previous page during the first part of the project
If the 4y project will not be supported, these activities will not be undertaken
  These activities only make sense if they lead to the production of staves
  If there is no clear commitment that the build of the L3 staves is guaranteed the risk for the experiment to not have a solution for a critical tracking layer is too high
  Efforts for UK institutes are only justified if they lead to physical deliverables
Activity (4y) | Deliverable | Effort needed | Equipment/consumables needed | Groups involved
Design of OB modules |  |  |  | 
Prototype manufacture and testing of OB modules |  |  |  | 
Design of L3 and L4 staves |  |  |  | Oxford
Prototype manufacture and testing of L3 staves |  |  |  | Oxford
Production of L3 modules and staves (including full QC) | 50 L3 staves built, tested and shipped to the US (this includes spares) |  |  | Oxford

## Slide 5: Next steps
Please send me for your institution where you want to contribute, and what your needs for effort and equipment/consumables will be
  Please provide estimates of the costs (incl. overheads)
At this point we are collecting the information for the two scenarios
We will then need to decide what to give to STFC
  We will only get minimal funding, so I think the two scenarios are:
    Only propose the 3y programme
    Propose both options, with a clear statement what we will lose if we only get 3y (visibility, reputation, loss of key groups/people, loss of leading management positions in the project)
      We are likely to only get the 3y programme, but at least we have tried and nobody can say we didn’t tell them what they are losing