## Slide 1: SPS Testbeam preparations for AC-LGADs
TIC Meeting
April 26th, 2026
Alex Jentsch (BNL)

## Slide 2: Basic information
Our SPS testbeam slot is scheduled for July 22nd to July 27th, in parallel with ATLAS HGTD (DC-LGAD detector) in H6.
  Yes, we only got 5 days.
  HGTD has priority, so we don’t have use of the telescope, as far as we know.
We still have outstanding data analysis from several previous testbeams in both Japan and DESY.
  Need to understand these results soon – they were only concerning sensors (no ASIC testing).
ASIC + sensor integration was the primary goal for the SPS testbeam campaign.

## Slide 3: Previous and planned testbeams
Previous campaigns
  FNAL testbeam with small sensors several years ago  established baseline spatial and timing resolution performance within spec for physics.
  JLAB testbeam with large, 30um strip sensors Summer 2025.
    Spatial resolution ~ 32um, timing resolution ~ 63ps, but results with incorrect bias voltage, so performance worse than expectations.
  Older (FY23) small strip sensors tested at DESY in Summer 2025 with FCFDv1.1.
    Timing ~ 40ps, spatial resolution ~ 15um.
  Strip sensors tested at DESY in Dec. 2025  analysis on-going, but preliminary results indicate a spatial resolution ~ 20um, while time resolution analysis is still underway.
  20um and 30um larger pixel sensors tested @ KEK (6.5 GeV electrons) Feb. 19th to 25th, 2026  analysis underway.
  RARiS testbeam with strip sensors (800 MeV electrons) March 3rd to 6th  waiting for updates.
Planned testbeams
  SPS July 2026  focus on pixels and EICROC.
  KEK-PS, 6.5 GeV electrons (sometime in Oct. to Dec. is planned)  focus on FCFDv1.2

## Slide 4: General plan
6 total DUTs
  2 ”large” pixel AC-LGADs readout using preamp boards + CAEN digitizers
  2 “large” strip AC-LGADs, same chain as for pixels
  2 ”small” pixels w/ EICROC0, readout using Xilinx devboards
Main Goals
  Finalize understanding of sensor performance (timing resolution and spatial resolution)  address open questions from previous testbeams.
    Also study spatial resolution performance with two different pad sizes for the pixelated sensors.
  Study performance of full chain readout with EICROC0  e.g. timing resolution.
Need to show that sensors, and most-importantly integrated setups can deliver needed performance for physics.

## Slide 5: Needs (equipment)
Sensors
  2 large pixel AC-LGADs, 2 large strip AC-LGADs, 2 small pixel AC-LGADs. (in-hand)
ASICs
  2 EICROC0 (in-hand).
Readout chain
  Xilinx devkits for EICROC0 (plenty of newer ZCU106 boards, limited number of older boards).
  Analog readout boards for large sensors (25 ordered, fabrication should be complete in a few weeks).
  Digitizers (for large sensors) – we have 2 that we can for sure use from two institutions.
Power supplies
  HV supplies for bias (6 channels); LV supplies for ASICs and preamps (6 channels).
Reference detectors
  Won’t have access to the telescope – being used by HGTD.
  DC-LGADs for timing?
Cooling system + detector mounting
  Grigory from UIC has a setup which we can use, but details still need to be worked out (part of the discussion for upcoming AC-LGAD meeting on Thursday night).

## Slide 6: Needs (firmware and software)
Firmware
  EICROC0 firmware not ready for testbeam data-taking.  work actively on-going to solve issues and ensure readiness.
    Calibration of ASIC with threshold offsets, testing of ASIC with external trigger, etc.
Analysis software
  Codes exist already from previous testbeams using the preamp board + digitizer readout chain.
  Analysis code(s) exist for EICROC digital analysis from groups at BNL and IJCLab.
    Need to work on necessary components missing to ensure robust testing has been carried out early so independent analyses can be done to verify results  in-progress now.

## Slide 7: Testing benchmarks
EICROC0 calibration using new firmware (in-progress)  expected in < 1-2 weeks.
Test of internal trigger with Sr-90 source  early to mid-May.
Test of external trigger (e.g. DC-LGAD with source)  mid-May.
Bonding of large sensors to new analog preamp boards  mid to late-May.
Testing of large sensors with external digitizers on bench (with laser)  late-May to early June.
Integration and testing of full system will be planned over the coming 2 weeks and aimed to begin no later than early-June.
  Need full setup “on” and testing with cosmics to ensure the system can run continuously without any issues.