## Slide 1: Electronics & DAQ WG
Fernando Barbosa (JLab)
16 April 2026

## Slide 2
  Today:
    Project Schedule Steps – Overview of sequence
    Power Trees – Distribution and Regulation
  Next week:
    ALCOR Internal/Peer Review - 22 April 2026
Agenda
Engineering & Design (PED)
Production (Construction)
QA/QC (Testing)
Delivery to Sub-detectors
Current Phase
CD-3
~2 Years

## Slide 3
ASIC & Discrete Readout Internal Reviews
Goals of the reviews:
  Provide a comprehensive assessment of the ASICs and Discrete Readout from design to production
    Specifications & Requirements - frontend, processing, interfaces, power and packaging (including form factors where applicable).
    Digital Interfaces - commands & controls
    Status & Steps to Completion - with schedule and to include testing/validation with detectors
    Production Outlook - to include final production review, production timeline and QA/QC testing
    Documentation - Functionality (e.g. User’s Manual/Spec sheets) and QA/QC Plans, and with planned availability for FEB final designs and Engineering Articles, bump/wire bonding.
Review Schedule:
    EICROC - 1 April 2026 – Good progress. Minutes & Summary @ https://indico.bnl.gov/event/32195/
    ALCOR - 22 April 2026
    SALSA - 6 May 2026
    CALOROC - 13 May 2026
    FCFD - 20 May 2026
    Discrete - 27 May 2026

## Slide 4
Months: -6 -2 0 +8 +9
= Production Readiness Reviews
= ASIC, FEB Production
= FEB Eng. Article
ASIC Development (PED)
ASIC Fab Production
~1 Year each ASIC
ASIC Testing
6 Months
FEB Eng. Article Development (PED
Eng. Article Tests
FEB Production
<1 Year
Production Tests (3 month after start of production)
<1 Year
Integration Tests (In Detectors WBS)
<3 Months
System Tests (In Detectors WBS)
<3 Months
Installation
First Production ASICs
R&D FY23 - FY24
PED FY25 - FY28
ASIC Fab & Eng. Article
CD-3 Construction, Electronics
Fabrication Start
Final ASIC Pinout
FEB Production & Tests
Development Activities (R&D, PED)
ASICs
FEBs
QA/QC
Sub-Detectors
Project Schedule Steps

## Slide 5
ASIC/Discrete Production Schedule
 | Fabrication Start | Funding
Discrete | September 2027 | DOE
CALOROC | November 2027 | In-Kind
EICROC | November 2027 | In-Kind
FCFD | May 2028 | DOE
FCFD Variant | May 2028 | DOE
ALCOR | November 2027 | In-Kind
SALSA | November 2027 | In-Kind