## Slide 1: Inner HCAL WBS 1.4.2
John Lajoie
Iowa State University
(inner)

## Slide 2: Inner HCAL
DELIVERABLE:
32 sectors - 1.16m inner radius, 1.37m outer radius
8 rows of 7mm scintillator tiles (24 tiles per row)
32o tilt angle, flat stainless steel plates ~10.2mm - ~14.7mm
Completed sector is 4.3m long, weighs ~ 1 ton
4 scintillators/tower
48 towers per module
32 modules; 1536 channels
(6144 SiPMs)
Half plates on sides
Flat SS310 steel plates

## Slide 3: HCAL Performance Specifications
HCAL performance driven by jet physics in HI collisions
Uniform fiducial acceptance -1<h<1 and 0<φ<2π
  Extended coverage -1.1<h<-1.1 to account for jet cone
Absorb >95% of energy from a 70 GeV jet
  Requires 5.5 nuclear interaction length depth
Hadronic energy resolution of combined calorimetry:
  with constant term <15%
  Gaussian response (limited tails)
  Performance optimized/demonstrated in three test beams
Inner HCAL is inside superconducting solenoid
  Must be made of non-magnetic material

## Slide 4: Design Drivers
Why an inner and outer HCAL segment?
  Size limitations set by existing interaction hall
  Set by radius of BaBar solenoid, the design of the mechanical support for the detector, and overall cost effectiveness
Why a tilted plate design?
  A tilted plate design can provide a uniform acceptance, adequate energy resolution and simplified construction
How are the tilt angles chosen?
  Chosen to avoid channeling (tails in resolution function)
Why Δη x Δφ ≈ 0.1 x 0.1?
  Driven by occupancy in Heavy Ion collisions
  Good match to scale of hadronic jets

## Slide 5: Test Beam Performance
In all cases, the combined system meets the sPHENIX spec!
EMCAL
IHCAL
OHCAL
Simulated Magnet
Beam
Three test beams (2014/15/16):

## Slide 6: Personnel
BNL
  Edward Kistenev (scientist)
  Don Lynch (engineer)
  Rich Ruggiero (designer)
  Anatoli Gordeev (engineer, OHCAL L3)
ISU
  J. Lajoie (L2 Manager/IHCAL L3)
Colorado (tile testing)
  J. Nagle (faculty)
GSU (tile testing, outer HCAL)
  Megan Connors (faculty)
  Xiaochun He (faculty)
WSU
  Bill Llope (faculty)
  Joern Putschke (faculty)
ACU
  Rusty Towell (faculty)
Rutgers
  Sevil Salur (faculty)
In discussions with Russian institutions (MEPHI/IHEP/Kurchatov)
BNL engineering has decades of experience with PHENIX.
ISU was responsible for the PHENIX LL1 trigger and MPC-EX.
WSU has a wide range of experience in building detectors.
ACU worked on the PHENIX MuTR chambers.

## Slide 7: Schedule Drivers
  Sector Mechanical Prototypes: 3-9/2017
  Prototype v2.1 Test Beam: 2/2018 – 3/2018
  Inner HCAL Production: 11/2019 – 7/2021 (CD3b)
    Mechanical sectors produced every 15 working days
    University assembly (scintillator/electronics/testing) keeps pace
    Shipped in groups of four to BNL; sectors retested
24
Production schedule integrates availability of electronics/SiPMs
(WBS 1.5).
Schedule slip in assembly can be addressed by adding additional University labor.

## Slide 8: Resources/Cost Drivers
SS310 steel is essentially a commodity material but precision machining is expensive
  Cost dominated by production of sector mechanicals
Scintillator tile production
  Surface flatness over long distances a key specification
    Wrapped tile thickness < 7.5mm, Uniplast can meet this spec.
  Uniplast (T2K, PHENIX)
    FNAL/Elgen also investigated, Uniplast most economical for complete tile assemblies
Module Assembly and QA
  Assemble inner HCAL at multiple university sites
    Make use of university labor and facilities
    Deliver assembled, cosmics tested sectors to BNL

## Slide 9: Basis of Estimate
The Inner HCAL will be assembled at two (or more) University sites.
  ISU, WSU and ACU have expressed interest
    Rutgers may provide some machined parts
  Sector assemblies provided by local vendors, populated with scintillator and electronics by University labor
  Shipped to BNL, tested after shipping and stored.
  IHEP Protovino investigating construction alternatives
Costs in BoE are based on:
  Experience with test beam prototypes
  Experience with sector prototypes
  Quotations
  Engineering estimates (Inner HCAL End Ring)

## Slide 10: Sector Prototype
Light cover (reflection)

## Slide 11: Assembled Sector Measurements
In lifting fixture
Assembled sector moved to mill table, supported on ends (4 blocks). Twist and sag in middle measured @ 70oF.
“Back” sags more than front when unsupported (CG shifted towards back). Supported measurements show not all sag is due to weight, some could be taken out by assembling on mill table.
Similar results at 90oF.
Very little twist!
Bot. view
back
front

## Slide 12: Risk Registry/Issues and Concerns
Risk registry currently includes three major items, two of which are rated at moderate risk (all three relevant to inner HCAL).

## Slide 13: Back Up

## Slide 14: sPHENIX HCAL Description
Outer HCAL ≈3.5λI
Magnet ≈1.4X0
Inner HCAL ≈1λI
EMCAL ≈18X0≈1λI
HCAL steel and scintillating tiles with wavelength shifting fiber
  2 longitudinal segments.
  An Inner HCal inside the solenoid.
  An Outer HCal outside the solenoid.
  Δη x Δφ ≈ 0.1 x 0.1
  3,072 readout channels
  σE/E < 100%/√E (single particle)
SiPM Readout

## Slide 15: Why a Sector Prototype?
Need to verify sector cost estimate ($43.6k)
  Are the estimated machining times/effort reasonable?
  Are there any unforeseen difficulties?
  Can the manufacturing process be optimized?
Sector prototype produced by TSI in Ames, IA (contract from Iowa State)
  All machining done by TSI (Jeremy Johnston), with exception of combs, which were sent out for wire EDM machining
  Absorber plates were ordered ground to thickness to reduce bowing/maintain flatness

## Slide 16: Sector Prototype Drawing
Note that baseplate bolts tapped at an angle
Baseplate and “endcaps” are Al; everything else is S310.

## Slide 17: Some Pictures
Comb (wire EDM)
Al baseplate machining
Example of bowing in thin absorber plate (sides), had to be manually straightened.

## Slide 18: More Pictures
Machining baseplate mounting holes in absorber
Test fit of end plates, baseplate and side plates – gap due to bowing in outer plate.

## Slide 19: Finished Product
Light cover (reflection)

## Slide 20: Assembled Sector Measurements
In lifting fixture
Assembled sector moved to mill table, supported on ends (4 blocks). Twist and sag in middle measured @ 70oF.
“Back” sags more than front when unsupported (CG shifted towards back). Supported measurements show not all sag is due to weight, some could be taken out by assembling on mill table.
Similar results at 90oF.
Very little twist!
Bot. view
back
front

## Slide 21: Sector Sag
Bot. view
front
back
 | Unsupported | Supported
Front Mill Jack | 78 mils | 48 mils
Back Mill Jack | 105 mils | 33 mils
@ 70oF :
 | Unsupported | Supported
Front Mill Jack | 72 mils | 45 mils
Back Mill Jack | 98 mils | 34 mils
@ 90oF :

## Slide 22: HCAL Budget Profile

## Slide 23: HCAL Staffing
FTE Profile by Category
FTE Profile by Fiscal Year
WBS Level | Org Sort | Group | FY 17 | FY 18 | FY 19 | FY 20 | FY 21 | FY 22
1.4 | BNL | Purchased Services | 0.00 | 0.00 | 0.18 | 0.46 | 0.12 | 0.00
 |  | Scientific | 0.60 | 0.36 | 0.16 | 0.37 | 0.00 | 0.00
 |  | Technical | 0.74 | 0.31 | 1.29 | 1.87 | 0.51 | 0.00
 |  | Professional | 0.38 | 0.47 | 0.23 | 0.91 | 0.75 | 0.00
 | BNL Sum |  | 1.71 | 1.13 | 1.87 | 3.61 | 1.38 | 0.00
 | Non-BNL | Student | 0.08 | 0.23 | 1.35 | 9.50 | 5.97 | 0.00
 |  | Technical | 0.00 | 0.00 | 0.38 | 1.27 | 1.76 | 0.00
 |  | Professional | 0.00 | 0.00 | 0.00 | 0.12 | 0.10 | 0.00
 |  | Postdoc | 0.00 | 0.00 | 0.82 | 1.46 | 1.61 | 0.00
 | Non-BNL Sum |  | 0.08 | 0.23 | 2.55 | 12.34 | 9.43 | 0.00
Grand Total |  |  | 1.79 | 1.36 | 4.42 | 15.95 | 10.81 | 0.00
Chart: 
| FY 17 | FY 18 | FY 19 | FY 20 | FY 21 | FY 22
BNL - Purchased Services | 0 | 0 | 0.18182 | 0.46136 | 0.12273 | 0
BNL - Scientific | 0.59795 | 0.35886 | 0.15545 | 0.36795 | 0.00045455 | 0
BNL - Technical | 0.73795 | 0.3075 | 1.2939 | 1.8709 | 0.51023 | 0
BNL - Professional | 0.37591 | 0.465 | 0.23386 | 0.91359 | 0.74732 | 0
Non-BNL - Student | 0.081818 | 0.22727 | 1.3545 | 9.4955 | 5.9682 | 0
Non-BNL - Technical | 0 | 0 | 0.38182 | 1.2716 | 1.7557 | 0
Non-BNL - Professional | 0 | 0 | 0 | 0.11714 | 0.095585 | 0
Non-BNL - Postdoc | 0 | 0 | 0.81818 | 1.4568 | 1.6114 | 0

## Slide 24: Quality of Estimate