## Sheet1
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.7.3 | TPC Cooling System | [11 empty] | 66499 | 80941.3
1.2.7.3.4 | Procure TPC Cooling Sys tem equipment(pumps,heat exchanger, PH control, manifolds, tanks…) | [7 empty] | 0.21128 | 44339 | 9367.8 | 53706.8
|  | Chillers watt 10C(3) | Thermo Scientific Merlin | 32000 | Pending | Quote | 0.2 | 6400
|  | Deionizing filters (2) | McMaster | 1644 | Pending | web Quote | 0.2 | 328.8
|  | Particle filters (3) | McMaster | 720 | Pending | web Quote | 0.2 | 144
|  | Valving for Chiller Switchover | McMaster | 825 | Pending | Web Quote | 0.2 | 165
|  | SS Manifolds (4) 12 port | MSC | 1110 | Pending | web quote | 0.2 | 222
|  | Hardware (panel, brackets, mnts) | Mcmaster | 650 | Pending | web Quote | 0.2 | 130
|  | Flowmeter 24(SS) water | Dwyer | 1315 | Pending | web Quote | 0.2 | 263
|  | Compression fittings SS (various) | Swagelok | 2500 | Pending | Quote + experience | 0.4 | 1000
|  | Bypass Valving at detector | McMaster | 1550 | Pending | web Quote | 0.2 | 310
|  | Pressure gauges (8) | Dwyer | 450 | Pending | Web Quote | 0.2 | 90
|  | Manifold valving (24) | Swagelok | 1575 | Pending | web Quote | 0.2 | 315
1.2.7.3.8 | Install TPC Cooling System plumbing | [7 empty] | 0.22507 | 11667 | 2625.9 | 14292.9
|  | 1 1/4" thin walled SS Lines | Mcmaster | 1600 | Pending | old Quote x inflation | 0.25 | 400
|  | 1" SS Thin walled Lines | McMaster | 1450 | Pending | old Quote x inflation | 0.25 | 362.5
|  | 5/16" SS Coil (0.250 ID Min) | McMaster | 1200 | Pending | web quote | 0.2 | 240
|  | SS Pipe fittings | Mcmaster | 700 | Pending | experience | 0.4 | 280
|  | 1 1/4" Braided lines (316 SS) | McMaster | 946 | Pending | web quote | 0.2 | 189.2
|  | Large Compression fittings SS | Swagelok | 3750 | Pending | web quote | 0.2 | 750
|  | Poly lines to detector (Various) | MSC | 924 | Pending | web Quote | 0.2 | 184.8
|  | House Water Manifolding (brass) | McMaster | 1097 | Pending | Web Quote | 0.2 | 219.4
1.2.7.3.9 | Set up TPC Cooling System Interlocks and Safety System | [7 empty] | 0.23336 | 10493 | 2448.6 | 12941.6
|  | Pressure Transmitters (8 min) | Dwyer | 1625 | Pending | quote | 0.2 | 325
|  | Transmitting Flowmeters (SS 1") (8) | Mcmaster | 2050 | Pending | Web Quote | 0.2 | 410
|  | RTDs (8) | Omega | 550 | Pending | Web Quote | 0.2 | 110
|  | RTD transmitter+local read (7) | Omega | 2986 | Pending | Web Quote | 0.2 | 597.2
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | House water Monitor (pressure) | Various | 650 | Pending | Web Quote | 0.2 | 130
|  | Presure Relief Valves 1" (2) SS | Mcmaster | 882 | Pending | web quote | 0.2 | 176.4
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.7.1 | TPC Laser System | [11 empty] | 78927 | 95062.4
1.2.7.1.2 | Procure TPC laser(s) | [7 empty] | 0.2 | 77177 | 15435.4 | 92612.4
|  | Laser | Newport | 77177 | Pending | Manufacturer Quote | 0.2 | 15435.4
1.2.7.1.3 | Procure TPC optics with mirrors | [7 empty] | 0.4 | 1750 | 700 | 2450
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.7.2 | TPC Gas System | [11 empty] | 106755 | 135374
1.2.7.2.2 | Procure TPC Gas System mass flow meters | [7 empty] | 0.2 | 8975 | 1795 | 10770
|  | Flowcontrollers |  | 4500 | Pending | Quote | 0.2 | 900
|  | Power supply |  | 3975 | Pending | Web | 0.2 | 795
|  | Cables |  | 500 | Pending | web | 0.2 | 100
1.2.7.2.3 | Procure TPC Gas System Analyzers (2 for redundancy) | [7 empty] | 0.24947 | 28300 | 7060 | 35360
|  | Cf4 Analyzer |  | 14000 | Pending | past quote | 0.25 | 3500
|  | Iso Analyzer |  | 14000 | Pending | past quote | 0.25 | 3500
|  | Cables |  | 300 | Pending | web | 0.2 | 60
1.2.7.2.4 | Procure TPC Gas System scrubbers | [7 empty] | 0.37939 | 6550 | 2485 | 9035
|  | Vessel |  | 5000 | Pending | experience | 0.4 | 2000
|  | Catalyst |  | 600 | Pending | past quote | 0.25 | 150
|  | Molecular sieves |  | 300 | Pending | past quote | 0.25 | 75
|  | Heater and temp controller | OMEGA | 650 | Pending | estimate | 0.4 | 260
1.2.7.2.5 | Procure TPC Gas System oxygen and water sensors | [7 empty] | 0.25357 | 11200 | 2840 | 14040
|  | H2O analyzers |  | 7000 | Pending | web | 0.2 | 1400
|  | O2 Analyzers |  | 3000 | Pending | experience | 0.4 | 1200
|  | Cables |  | 1200 | Pending | quote | 0.2 | 240
1.2.7.2.7 | Set up TPC Gas System computer control | [7 empty] | 0.2772 | 20375 | 5648 | 26023
|  | Electronics Design | CSINO | 7000 | Pending | Past Cost | 0.25 | 1750
|  | Design Control Software | CSINO | 3300 | Pending | Past Cost | 0.25 | 825
|  | Procure Gas system Electronic Crate | Allied | 1000 | Pending | Past Cost | 0.25 | 250
|  | Procure Electronics Modules | CSino | 3600 | Pending | past cost | 0.25 | 900
|  | Procure Hardware for electronics (Cabels,termanals,Etc) | Various | 2600 | Pending | Estimate | 0.4 | 1040
|  | Procure Gas System Control PC | Dell | 800 | Pending | Web Quote | 0.2 | 160
|  | Procure Power supplies | Omega | 1200 | Pending | estimate | 0.4 | 480
|  | Procure Mounting hardware | McMaster | 200 | Pending | estimate | 0.4 | 80
|  | Procure Al Panels | McMAster | 140 | Pending | estimate | 0.4 | 56
|  | Procure Electronics Rack | Allied | 535 | Pending | web quote | 0.2 | 107
1.2.7.2.8 | Assemble and Plumb TPC Gas System | [7 empty] | 0.28037 | 31355 | 8791 | 40146
|  | Procure Stainless compression fittings | Swagelok | 6500 | Pending | old order | 0.25 | 1625
|  | Procure Stainless Tubing | Swaglok/Mcmaster | 3400 | Pending | old order | 0.25 | 850
|  | Procure Monitoring instrumentation | Dwyer | 6500 | Pending | past order | 0.25 | 1625
|  | Procure Electronic Pressure Controller | Tescom | 2400 | Pending | web quote | 0.2 | 480
|  | Procure Compressors (2) | Aid Dimensions | 4000 | Pending | past quote | 0.25 | 1000
|  | Procure Stainless Solenoids | Parker | 3600 | Pending | estimate | 0.4 | 1440
|  | Procure Stainless Valves | Swagelok | 3500 | Pending | estimate | 0.4 | 1400
|  | Procure AL Panels | McMaster | 520 | Pending | web quote | 0.2 | 104
|  | Procure Mounting hardware | McMaster | 400 | Pending | estimate | 0.4 | 160
|  | Procure Electronics Rack | Allied | 535 | Pending | Web Quote | 0.2 | 107
1.2.7.2.9 | Install and Test TPC Gas System Interlocks | [7 empty] | 0 | 0 | 0 | 0
|  | This is part of Computer control |  | 0 | Pending | Experience | 0.4 | 0
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.1.1 | TPC v1 Field Cage Prototype | [11 empty] | 254933.65 | 299220.442
1.2.1.1.3 | Procure TPC v1 Mandrel Parts | [7 empty] | 0.028415 | 66845.61 | 1899.4 | 68745.01
|  | HVPF Boards | Sierra Express Circuits | 12564.55 | DELIVERED |  | 0 | 0
|  | 8020 parts | McMaster-Carr | 7959.44 | DELIVERED |  | 0 | 0
|  | Clean Hood Motor Repair | Grainger | 554.75 | DELIVERED |  | 0 | 0
|  | Tooling for Mandrel Table | McMaster-Carr | 774.82 | DELIVERED |  | 0 | 0
|  | Optical readout for DVM (IBF) | Mouser | 79.99 | DELIVERED |  | 0 | 0
|  | FR4520 tooling Foam | General Plastics | 4361.98 | DELIVERED |  | 0 | 0
|  | 2" diameter 9' long shaft | Technico | 335 | DELIVERED |  | 0 | 0
|  | RSF-14B-30-F100-24B | Harmonic Drive | 1330 | DELIVERED |  | 0 | 0
|  | SHA32A161SG-B12BLV-10S17b-AN | Harmonic Drive | 4674 | DELIVERED |  | 0 | 0
|  | T-slotted framing 8020 | McMaster-Carr | 4277.84 | DELIVERED |  | 0 | 0
|  | Laminate Trimmer | Grainger | 155 | DELIVERED |  | 0 | 0
|  | Position Encoders | Renishaw | 1202 | DELIVERED |  | 0 | 0
|  | Adhesive, lab supplies | McMaster-Carr | 1440.43 | DELIVERED |  | 0 | 0
|  | Lead Screw | Lin Tech | 3456 | DELIVERED |  | 0 | 0
|  | 2" flanged Collars for motor/encoder | McMaster-Carr | 371.66 | DELIVERED |  | 0 | 0
|  | USB microscope | Microscope Store | 143 | DELIVERED |  | 0 | 0
|  | Motor Controllers | Copley Controls | 1637 | DELIVERED |  | 0 | 0
|  | SM encoder | Automation Direct | 67.25 | DELIVERED |  | 0 | 0
|  | SM motor | MicroMo | 253.49 | DELIVERED |  | 0 | 0
|  | Wire/connectors | DigiKey | 352.41 | DELIVERED |  | 0 | 0
|  | PS for translation motor (24 V 24 A) | Automation Direct | 415 | DELIVERED |  | 0 | 0
|  | PS for shaft motor (48 V 24 A) | Acopian | 1170 | DELIVERED |  | 0 | 0
|  | Motor Controller Access. Kits | Copley Controls | 276 | DELIVERED |  | 0 | 0
|  | Web Tension Applicator Toolset | F.W. Hall Company | 18994 | Pending | Manufacturer Quote | 0.1 | 1899.4
1.2.1.1.6 | Procure TPC v1 Outer Field Cage Parts | [7 empty] | 0.075116 | 70066.88 | 5263.16 | 75330.04
|  | Honeycomb | Plascorp | 1621.08 | DELIVERED |  | 0 | 0
|  | Striped circuit cards | All-flex | 23400 | Pending | Manufacturer Quote | 0.2 | 4680
|  | 3 mil kapton 44" x 108 LF | Dunmore | 21780 | DELIVERED |  | 0 | 0
|  | 3 mil kapton 22" x 108 LF | Dunmore | 20350 | DELIVERED |  | 0 | 0
|  | FR4 outer sheets 4' x 4' | ePlastics | 1145.8 | Pending | Manufacturer Quote | 0.2 | 229.16
|  | HVPW resistors | DigiKey | 1170 | Pending | Manufacturer Quote | 0.2 | 234
|  | High Voltage Cable | Dielectric Sciences | 600 | Pending | Web Search | 0.2 | 120
1.2.1.1.9 | Procure TPC v1 Inner Field Cage Parts | [7 empty] | 0.093052 | 28799.16 | 2679.832 | 31478.992
|  | Striped circuit cards | All-flex | 12000 | Pending | Manufacturer Quote | 0.2 | 2400
|  | 3 mil kapton 44" x 108 LF | Dunmore | 7260 | DELIVERED |  | 0 | 0
|  | 3 mil kapton 44" x 108 LF | Dunmore | 8140 | DELIVERED |  | 0 | 0
|  | FR4 Sheets 4' x 4' | ePlastics | 229.16 | Pending | Manufacturer Quote | 0.2 | 45.832
|  | HVPW Resistors | DigiKey | 1170 | Pending | Manufacturer Quote | 0.2 | 234
1.2.1.1.12 | Procure TPC Field Cage Prototype v1 End Rings | [7 empty] | 0.4 | 20000 | 8000 | 28000
|  | End Rings | Outside Vendor | 20000 | Pending | BNL Shops Estimate | 0.4 | 8000
1.2.1.1.14 | Procure TPC v1 End Cap | [7 empty] | 0.37308 | 46222 | 17244.4 | 63466.4
|  | Aluminum | Yarde Metals | 6222 | Pending | Vendor Quote | 0.2 | 1244.4
|  | Machining | Outside Vendor | 40000 | Pending | Experience | 0.4 | 16000
1.2.1.1.16 | Procure TPC v1 Central Membrane Parts | [7 empty] | 0.4 | 8000 | 3200 | 11200
|  |  |  | 8000 | Pend | Experience | 0.4 | 3200
1.2.1.1.18 | Procure TPC Handling Cart | [7 empty] | 0.4 | 15000 | 6000 | 21000
|  |  |  | 15000 | Pend | Experience | 0.4 | 6000
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.1.2 | TPC v2 Field Cage | [11 empty] | 216818.7 | 278182.44
1.2.1.2.2 | Procure TPC v2 Mandrel Parts | [7 empty] | 0.2 | 10432.66 | 2086.532 | 12519.192
|  | FR4520 tooling Foam | General Plastics | 4361.98 | Pending | Existing PO | 0.2 | 872.396
|  | T-slotted framing 8020 | McMaster-Carr | 4277.84 | Pending | Estimate from v1 | 0.2 | 855.568
|  | Adhesive, lab supplies | McMaster-Carr | 1440.43 | Pending | Estimate from v1 | 0.2 | 288.086
|  | Wire/connectors | DigiKey | 352.41 | Pending | Manufacturer Quote | 0.2 | 70.482
1.2.1.2.5 | Procure TPC v2 Outer Field Cage Parts | [7 empty] | 0.2 | 75826.88 | 15165.376 | 90992.256
|  | Honeycomb | Plascorp | 1621.08 | Pending | Existing PO | 0.2 | 324.216
|  | Striped circuit cards | All-flex | 23400 | Pending | Manufacturer Quote | 0.2 | 4680
|  | 3 mil kapton 44" x 108 LF | Dunmore | 21780 | Pending | Existing PO | 0.2 | 4356
|  | 3 mil kapton 22" x 108 LF | Dunmore | 20350 | Pending | Existing PO | 0.2 | 4070
|  | FR4 outer sheets 4' x 4' | ePlastics | 1145.8 | Pending | Manufacturer Quote | 0.2 | 229.16
|  | HVPW resistors | DigiKey | 6930 | Pending | Manufacturer Quote | 0.2 | 1386
|  | High Voltage Cable | Dielectric Sciences | 600 | Pending | Manufacturer Quote | 0.2 | 120
1.2.1.2.8 | Procure TPC v2 Inner Field Cage Parts | [7 empty] | 0.2 | 34559.16 | 6911.832 | 41470.992
|  | Striped circuit cards | All-flex | 12000 | Pending | Manufacturer Quote | 0.2 | 2400
|  | 3 mil kapton 44" x 108 LF | Dunmore | 7260 | Pending | Manufacturer Quote | 0.2 | 1452
|  | 3 mil kapton 44" x 108 LF | Dunmore | 8140 | Pending | Manufacturer Quote | 0.2 | 1628
|  | FR4 Sheets 4' x 4' | ePlastics | 229.16 | Pending | Manufacturer Quote | 0.2 | 45.832
|  | HVPW Resistors | DigiKey | 6930 | Pending | Manufacturer Quote | 0.2 | 1386
1.2.1.2.11 | Procure TPC Field Cage Prototype v2 End Rings | [7 empty] | 0.4 | 20000 | 8000 | 28000
|  | End Rings | Outside Vendor | 20000 | Pending | BNL Shops Estimate | 0.4 | 8000
1.2.1.2.13 | Procure TPC v2 End Cap | [7 empty] | 0.38235 | 68000 | 26000 | 94000
|  | Aluminum | Yarde Metals | 6000 | Pending | Vendor Quote | 0.2 | 1200
|  | Machining | Outside Vendor | 62000 | Pending | Experience | 0.4 | 24800
1.2.1.2.15 | Procure TPC v2 Central Membrane Parts | [7 empty] | 0.4 | 8000 | 3200 | 11200
|  |  |  | 8000 | Pend | Experience | 0.4 | 3200
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.1.3 | TPC Final Field Cage | [11 empty] | 6000 | 8400
1.2.1.3.2 | Procure TPC v2 Field Cage Modification Parts | [7 empty] | 0.4 | 6000 | 2400 | 8400
|  |  |  | 6000 | Pending | Experience | 0.4 | 2400
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.1.4 | TPC v1 Modules | [11 empty] | 27136 | 35163.2
1.2.1.4.1.2 | Procure TPC v1 Module Gas Enclosure Parts | [7 empty] | 0.275 | 8000 | 2200 | 10200
|  | Gas |  | 5000 | Pending | Recent Purchase | 0.2 | 1000
|  |  |  | 3000 | Pending | Experience | 0.4 | 1200
1.2.1.4.2.2 | Procure TPC v1 Module Strongback | [7 empty] | 0.2 | 1200 | 240 | 1440
|  |  |  | 1200 | Pending | SBU Shop Quote | 0.2 | 240
1.2.1.4.2.4 | Procure TPC v1 Module Frames | [7 empty] | 0.2 | 1000 | 200 | 1200
|  |  |  | 1000 | Pending | Sbu Shop Quote | 0.2 | 200
1.2.1.4.2.6 | Procure TPC v1 Grid Parts | [7 empty] | 0.2 | 500 | 100 | 600
|  |  |  | 500 | Pending | SBU Shop Quote | 0.2 | 100
1.2.1.4.3.2 | Procure TPC cv1a Module Padplane | [7 empty] | 0.2 | 1718 | 343.6 | 2061.6
|  | PadPlane | Somacis | 1718 | Pending | Vendor Quote | 0.2 | 343.6
1.2.1.4.3.4 | Procure TPC v1a Module GEMs | [7 empty] | 0.35385 | 6500 | 2300 | 8800
|  | GEM Mask | CERN | 1500 | Pending | Recent Purchase | 0.2 | 300
|  | GEMs | CERN | 5000 | Pending | Experience | 0.4 | 2000
1.2.1.4.4.2 | Procure TPC v1b Module Padplane | [7 empty] | 0.2 | 1718 | 343.6 | 2061.6
|  | PadPlane | Somacis | 1718 | Pending | Vendor Quote | 0.2 | 343.6
1.2.1.4.4.4 | Procure TPC v1b Module GEMs | [7 empty] | 0.35385 | 6500 | 2300 | 8800
|  | GEM Mask | CERN | 1500 | Pending | Recent Purchase | 0.2 | 300
|  | GEMs | CERN | 5000 | Pending | Experience | 0.4 | 2000
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.1.5 | TPC v2 Modules | [11 empty] | 18918 | 24301.6
1.2.1.5.1.2 | Procure TPC v2 Module Gas Enclosure Parts | [7 empty] | 0.275 | 8000 | 2200 | 10200
|  | Gas |  | 5000 | Pending | Recent Purchase | 0.2 | 1000
|  |  |  | 3000 | Pending | Experience | 0.4 | 1200
1.2.1.5.2.2 | Procure TPC v2 Module Strongback | [7 empty] | 0.2 | 1200 | 240 | 1440
|  |  |  | 1200 | Pending | SBU Shop Quote | 0.2 | 240
1.2.1.5.2.4 | Procure TPC v2 Module Frames | [7 empty] | 0.2 | 1000 | 200 | 1200
|  |  |  | 1000 | Pending | Sbu Shop Quote | 0.2 | 200
1.2.1.5.2.6 | Procure TPC v2 Grid Parts | [7 empty] | 0.2 | 500 | 100 | 600
|  |  |  | 500 | Pending | SBU Shop Quote | 0.2 | 100
1.2.1.5.3.2 | Procure TPC v2a Module Padplane | [7 empty] | 0.2 | 1718 | 343.6 | 2061.6
|  | PadPlane | Somacis | 1718 | Pending | Vendor Quote | 0.2 | 343.6
1.2.1.5.3.4 | Procure TPC v2a Module GEMs | [7 empty] | 0.35385 | 6500 | 2300 | 8800
|  | GEM Mask | CERN | 1500 | Pending | Recent Purchase | 0.2 | 300
|  | GEMs | CERN | 5000 | Pending | Experience | 0.4 | 2000
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.1.6 | TPC Production GEM Acquisition | [11 empty] | 174296 | 209155.2
1.2.1.6.1 | Train Technician to work in CERN Shop on TPC GEMs | [7 empty] | 0.2 | 39080 | 7816 | 46896
|  |  |  | 39080 | Pending | ALICE Contract | 0.2 | 7816
1.2.1.6.2 | Produce TPC GEM foils (includes Technician fees) | [7 empty] | 0.2 | 135216 | 27043.2 | 162259.2
|  |  |  | 135216 | Pending | ALICE Contract | 0.2 | 27043.2
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.1.7 | TPC High Voltage System | [11 empty] | 52100 | 65520
1.2.1.7.2 | Procure TPC GEM HV Power Supplies | [7 empty] | 0.2 | 36500 | 7300 | 43800
|  | 6 cards + Mainframe | CAEN | 36500 | Pending | Vendor Quote | 0.2 | 7300
1.2.1.7.3 | Procure TPC Membrane HV Cable | [7 empty] | 0.2 | 600 | 120 | 720
|  |  |  | 600 | Pending | Web Quote | 0.2 | 120
1.2.1.7.5 | Procure TPC Membrane Power Supply | [7 empty] | 0.4 | 15000 | 6000 | 21000
|  |  |  | 15000 | Pending | Experience | 0.4 | 6000
1.2.2.1 | TPC R1 Module Factory Preparation | [11 empty] | 20019.85 | 25723.82 | 3X
1.2.2.1.1 | Prepare TPC R1 Factory Clean Facility | [7 empty] | 0.23741 | 8019.85 | 1903.97 | 9923.82
|  | Laminar Flow Hood (8 foot) | Kats Enterprises | 6519.85 | Pending | Vendor Quote | 0.2 | 1303.97
|  | Garments, gloves, etc |  | 1500 | Pending | Experience | 0.4 | 600
1.2.2.1.2 | Prepare TPC R1 Factory Tooling | [7 empty] | 0.31667 | 12000 | 3800 | 15800
|  | Gas |  | 5000 | Pending | Current Purchase | 0.2 | 1000
|  | Gluing jigs, small tools |  | 7000 | Pending | Experience | 0.4 | 2800
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.2.2 | TPC R1 Pre-Production Module | [11 empty] | 9418 | 12001.6 | 3X
1.2.2.2.2 | Procure TPC R1 Pre-Production Module Stongbacks | [7 empty] | 0.2 | 1200 | 240 | 1440
|  |  |  | 1200 | Pending | SBU Shop Quote | 0.2 | 240
1.2.2.2.3 | Procure TPC R1 Pre-Production Module Frames | [7 empty] | 0.2 | 1000 | 200 | 1200
|  |  |  | 1000 | Pending | Sbu Shop Quote | 0.2 | 200
1.2.2.2.4 | Procure TPC R1 Pre-Production Module Grids | [7 empty] | 0.2 | 500 | 100 | 600
|  |  |  | 500 | Pending | SBU Shop Quote | 0.2 | 100
1.2.2.2.5 | Procure TPC R1 Pre-Production Module Pad Planes | [7 empty] | 0.2 | 1718 | 343.6 | 2061.6
|  | PadPlane | Somacis | 1718 | Pending | Vendor Quote | 0.2 | 343.6
1.2.2.2.6 | Procure TPC R1 Pre-Production Module GEMs | [7 empty] | 0.34 | 5000 | 1700 | 6700
|  | Production Mask | CERN | 1500 | Pending | Current Purchase | 0.2 | 300
|  | GEMS | CERN | 3500 | Pending | Experience | 0.4 | 1400
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.2.3 | TPC R1 Module Production | [11 empty] | 52733 | 70746.2 | 3X
1.2.2.3.1 | Procure TPC R1 Module frames | [7 empty] | 0.4 | 13333 | 5333.2 | 18666.2
|  |  |  | 13333 | Pending | Experience | 0.4 | 5333.2
1.2.2.3.2 | Procure TPC R1 Module strongbacks | [7 empty] | 0.2 | 15400 | 3080 | 18480
|  | Hardware (O-rings, screws, nylon rod) | McMaster-Carr | 1000 | Pending | Experience | 0.2 | 200
|  | Metal & machining | SBU | 14400 | Pending | SBU Estimate | 0.2 | 2880
1.2.2.3.3 | Procure TPC R1 Module Pad Planes | [7 empty] | 0.4 | 20000 | 8000 | 28000
|  |  |  | 20000 | Pending | Experience | 0.4 | 8000
1.2.2.3.4 | Procure TPC R1 Module Grids | [7 empty] | 0.4 | 4000 | 1600 | 5600
|  |  |  | 4000 | Pending | Experience | 0.4 | 1600
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.5.1 | TPC FEE Prototype v1 | [7 empty] | 0.22215 |  |  |  | 58346 | 71307.8
1.2.5.1.3 | Procure TPC FEE prototype v1 components | [7 empty] | 0.19529 | 7896 | 1542 | 9438
|  | SAMPA chip | CERN | 4320 | Pending | 96 chips (~$45/chip from STAR's info) for 12 boards | 0.15 | 648
|  | FPGA (Artix-7) | Xilinx, Digikey | 1176 | Pending | Web quote (12 boards) | 0.25 | 294
|  | Optical transmitter/receiver | Avago | 600 | Pending | experience (12 boards) | 0.25 | 150
|  | Resistor/capacitor/regulator | Digikey | 1200 | Pending | experience (12 boards) | 0.25 | 300
|  | Card Connectors | Samtec | 600 | Pending | experience (12 boards) | 0.25 | 150
1.2.5.1.4 | Fabricate TPC FEE prototype v1 boards | [7 empty] | 0.2 | 16000 | 3200 | 19200
|  | Initial fee |  | 2000 | Pending | experience | 0.2 | 400
|  | Routing Boards |  | 10000 | Pending | experience | 0.2 | 2000
|  | Board fabrication |  | 4000 | Pending | experience (12 boards) | 0.2 | 800
1.2.5.1.5 | Procure TPC FEE prototype v1 LV power supplies | [7 empty] | 0.15 | 5022 | 753.3 | 5775.3
|  | MegaPac Chassis (5V) | Vicor West Coast | 5022 | Pending | Manifacture quote (Jan, 2016), 1 module | 0.15 | 753.3
1.2.5.1.6 | Develop TPC FEE Test Stand | [7 empty] | 0.26097 | 25928 | 6766.5 | 32694.5
|  | Chain test board fabrication | BNL | 2000 | Pending | experience | 0.2 | 400
|  | Resistor/capacitor/regulator | Digikey | 100 | Pending |  | 0.25 | 25
|  | Optical transmitter/receiver | Avago | 50 | Pending |  | 0.25 | 12.5
|  | SAMPA chip | CERN | 180 | Pending | Two chips (with spare of 2) | 0.15 | 27
|  | FPGA (Artix-7) | Xilinx, Digikey | 98 | Pending | Web quote | 0.25 | 24.5
|  | Card Connectors | Samtec | 50 | Pending |  | 0.25 | 12.5
|  | Pulse distributor board initial fee | BNL | 2000 | Pending |  | 0.2 | 400
|  | Pulse distributor | BNL | 7500 | Pending | experience (25 input selectors) | 0.25 | 1875
|  | Test Pulser (B&K precision 4079B) | B&K precision | 7950 | Pending | Web quote (one dual-pulsers) | 0.2 | 1590
|  | Control PC and parallel I/O card | DELL | 6000 | Pending | experience | 0.4 | 2400
1.2.5.1.7 | Assemble and test TPC FEE prototype v1 | [7 empty] | 0.2 | 3500 | 700 | 4200
|  | Parts mounting initial fee |  | 1000 | Pending | experience | 0.2 | 200
|  | parts mouting on board |  | 2500 | Pending | experience | 0.2 | 500
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.5.2 | TPC FEE Pre-Production | [7 empty] | 0.243 |  |  |  | 22420 | 27868
1.2.5.2.2 | Procure TPC FEE preproducion prototype components | [7 empty] | 0.19545 | 7920 | 1548 | 9468
|  | SAMPA chip | CERN | 4320 | Pending | 96 chips (~$45/chip from STAR's info) for 12 boards | 0.15 | 648
|  | FPGA (Artix-7) | Xilinx, Digikey | 1200 | Pending | Web quote (12 boards) | 0.25 | 300
|  | Optical transmitter/receiver | Avago | 600 | Pending | experience (12 boards) | 0.25 | 150
|  | Resistor/capacitor/regulator | Digikey | 1200 | Pending | experience (12 boards) | 0.25 | 300
|  | Card Connectors | Samtec | 600 | Pending | experience (12 boards) | 0.25 | 150
1.2.5.2.3 | Fabricate TPC FEE preproduction prototype boards | [7 empty] | 0.2 | 6000 | 1200 | 7200
|  | Initial fee |  | 2000 | Pending | experience | 0.2 | 400
|  | Board fabrication |  | 4000 | Pending | experience | 0.2 | 800
1.2.5.2.4 | Modify TPC FEE Test Stand | [7 empty] | 0.4 | 5000 | 2000 | 7000
|  | Modification of Peripheral |  | 5000 | Pending | experience | 0.4 | 2000
1.2.5.2.5 | Assemble and test TPC FEE preproduction prototype | [7 empty] | 0.2 | 3500 | 700 | 4200
|  | Parts mounting initial fee |  | 1000 | Pending | experience | 0.2 | 200
|  | parts mouting on board |  | 2500 | Pending | experience | 0.2 | 500
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.5.3 | TPC FEE Production | [7 empty] | 0.18574 |  |  |  | 807984 | 958056.6
1.2.5.3.1 | Procure TPC FEE components | [7 empty] | 0.18906 | 576000 | 108900 | 684900
|  | SAMPA chip | CERN | 351000 | Pending | 4800 + 3000 chips (~$45/chip) quote | 0.15 | 52650
|  | FPGA (Artix-7) | Xilinx | 75000 | Pending | Weq quote (98 * 600 +25% spare) quote | 0.25 | 18750
|  | Optical transmitter/receiver | Avago | 37500 | Pending | 50 * 600 + 25% spare quote | 0.25 | 9375
|  | Resistor/capacitor/regulator | Digikey | 75000 | Pending | 100 * 600 + 25% spare quote | 0.25 | 18750
|  | Card Connectors | Samtec | 37500 | Pending | 50 * 600 + 25% spare quote | 0.25 | 9375
1.2.5.3.2 | Procure TPC FEE LV power supplies | [7 empty] | 0.15515 | 116484 | 18072.6 | 134556.6
|  | 10AWG 6T00UP Cable | Belden | 6000 | Pending | $1.5/ft, 4000ft. Quote | 0.25 | 1500
|  | MegaPac chassis (5V) | Vicor West Coast | 110484 | Pending | manufacture quote (5022 * 20 + 2 spare) | 0.15 | 16572.6
1.2.5.3.3 | Fabricate and assemble all TPC Fee boards | [7 empty] | 0.2 | 115500 | 23100 | 138600
|  | Initial fee |  | 2000 | Pending | quote | 0.2 | 400
|  | Board fabrication |  | 75000 | Pending | 100 * 600 + 25% spare quote | 0.2 | 15000
|  | parts mounting initial fee |  | 1000 |  | quote | 0.2 | 200
|  | Parts mounting |  | 37500 | Pending | 50 * 600 + 25% spare quote | 0.2 | 7500
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.6.1 | TPC DAM Evaluation --FELIX 1.5 | [11 empty] | 1632 | 1960.4
1.2.6.1.2 | Develop TPC DAM prototype v1 Test Stand | [7 empty] | 0.20123 | 1632 | 328.4 | 1960.4
|  | Nexys Video Artix-7 FPGA: Trainer Board | Digilent, Inc. | 490 | DELIVERED |  | 0 | 0
|  | FELIX v1.5 Prototype PCIe card | ATLAS DAQ Group | 0 | DELIVERED | Borrowed device | 0 | 0
|  | DAQ server | PHENIX DAQ Group | 0 | DELIVERED | Borrowed device | 0 | 0
|  | 2x 48-fiber MTP to 12-fiber breakout cables | Computer Crafts Inc. | 437 | In requsition | Quote | 0.2 | 87.4
|  | 12-fiber MTP/MPO - LC Cassettes | Computer Crafts Inc. | 137 | In requsition | Quote | 0.2 | 27.4
|  | 6x LC duplex fiber | Computer Crafts Inc. | 68 | In requsition | Quote | 0.2 | 13.6
|  | Peripheral accessories and cables | Many | 500 | Pending | Experience | 0.4 | 200
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.6.2 | TPC DAM Evaluation -- FELIX 2.0 | [11 empty] | 39095.3 | 51578
1.2.6.2.1 | Procure FELIX 2.0 board for TPC DAM | [7 empty] | 0.31987 | 37571.34 | 12017.908 | 49589.248
|  | FELIX v2.0 Pre-Production PCIe cards, 2nt | BNL ATLAS DAQ Group | 23431.84 | Pending | Unofficial quote | 0.27697 | 6490.008
|  | 2U rack servers, 12-core Xeon, 16xPCIe, 2nt | Microway | 13000 | Pending | Experience | 0.4 | 5200
|  | 48-fiber MTP to 12-fiber breakout cables, 2nt | Computer Crafts Inc. | 436 | Pending | Quote | 0.2 | 87.2
|  | 12-fiber MTP/MPO - LC Cassettes, 2cnt | Computer Crafts Inc. | 136 | Pending | Quote | 0.2 | 27.2
|  | LC duplex fiber, 6cnt | Computer Crafts Inc. | 67.5 | Pending | Quote | 0.2 | 13.5
|  | Peripheral accessories and cables | Many | 500 | Pending | Experience | 0.4 | 200
1.2.6.2.2 | FPGA Algorithm development | [7 empty] | 0.30499 | 1523.96 | 464.792 | 1988.752
|  | TPC timing distribution board prototype - PCB | Many | 200 | Pending | Experience | 0.4 | 80
|  | TPC timing mezzanine prototype - PCB | Many | 100 | Pending | Experience | 0.4 | 40
|  | SFP+ Optical TX/RX, 4cnt + 100% spare | Avnet | 723.96 | Pending | Catalog: AFBR-709DMZ | 0.2 | 144.792
|  | SMT Chip Resistor Capacitor | Digikey | 500 | Pending | Experience | 0.4 | 200
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Grand Total w/ Contingency
1.2.6.3 | TPC DAM Production | [11 empty] | 511901.088 | 655826.88
1.2.6.3.1 | Procure TPC DAM Felix 2.0 boards | [7 empty] | 0.20502 | 306000.576 | 62737.6896 | 368738.2656
|  | FELIX Production PCIe cards, 24cnt + 20% spare | BNL ATLAS DAQ Group | 229879.296 | Pending | Unofficial quote | 0.20669 | 47513.4336
|  | 48-fiber MTP (M)-MTP (F) cable 5m, 2x48cnt + 20% spare | Computer Crafts Inc. | 32025.6 | Pending | Quote: CCI/T40418PF48-005 | 0.2 | 6405.12
|  | 48-fiber MTP (F)-MTP (F) cable 58m, 48cnt + 20% spare | Computer Crafts Inc. | 35424 | Pending | Quote: CCI/T40408PF48-058 | 0.2 | 7084.8
|  | 1U 19" 12 port MPO feedthru panel with 12X MPO couplers, 2x4+25% spare | Computer Crafts Inc. | 720 | Pending | Quote: CCI/56348-MT | 0.2 | 144
|  | 48F MTP(M) - LC Hydra assembly, 48cnt + 20% spare | Computer Crafts Inc. | 7822.08 | Pending | Quote: CCI/1000450-18I-48F | 0.2 | 1564.416
|  | MTP Coupler, 48cnt + 20% spare | Computer Crafts Inc. | 129.6 | Pending | Quote: CCI/100106 | 0.2 | 25.92
1.2.6.3.3 | Procure of TPC EDBC Computers and Peripherals | [7 empty] | 0.39431 | 205900.512 | 81188.1024 | 287088.6144
|  | 2U rack servers, 24cnt + 20% spare | Microway | 187200 | Pending | Experience, Require R&D for spec | 0.4 | 74880
|  | TPC timing distribution board - PCB, 1cnt + 1 spare | Many | 400 | Pending | Experience | 0.4 | 160
|  | TPC timing mezzanine - PCB, 24cnt + 20% spare | Many | 1440 | Pending | Experience | 0.4 | 576
|  | SFP+ Optical TX/RX, 48cnt + 20% spare | Avnet | 5212.512 | Pending | Catalog: AFBR-709DMZ | 0.2 | 1042.5024
|  | LC duplex fiber, 48cnt + 20% spare | Computer Crafts Inc. | 648 | Pending | Quote: CCI/F26268P302-001 | 0.2 | 129.6
|  | SMT Chip Resistor Capacitor | Digikey | 1000 | Pending | Experience | 0.4 | 400
|  | Peripheral accessories and cables | Many | 10000 | Pending | Experience | 0.4 | 4000

## Sheet2
WBS | Description | Item | Vendor | Total | Status | Basis of Estimate | Contingency | Item Contingency | Wt Contingency | Total | Contingency | Total w/ Contingency | Grand Total | Contingency | Grand Total w/ Contingency
Total | [6 empty] | 0.2462 | [5 empty] | 2550605.598 | 627964.834 | 3178570.432 | Pending Delivery | 20893.4
[16 empty] | Quote 15% | 546624.9
Pending delivery 10% | [12 empty] | 18994 | 1899.4 | 20893.4 | Quote 20% | 1319109.684
|  | Web Tension Applicator Toolset | F.W. Hall Company | 18994 | Pending | Manufacturer Quote | 0.1 | 1899.4 | [7 empty] | Older quote 25% | 404356.848
[16 empty] | Engineering Estimate 25% | 15625
Quote 15% | [12 empty] | 475326 | 71298.9 | 546624.9 | Engineering Estimate 40% | 871960.6
|  | SAMPA chip | CERN | 4320 | Pending | 96 chips (~$45/chip from STAR's info) for 12 boards | 0.15 | 648
|  | MegaPac Chassis (5V) | Vicor West Coast | 5022 | Pending | Manifacture quote (Jan, 2016), 1 module | 0.15 | 753.3
|  | SAMPA chip | CERN | 180 | Pending | Two chips (with spare of 2) | 0.15 | 27
|  | SAMPA chip | CERN | 4320 | Pending | 96 chips (~$45/chip from STAR's info) for 12 boards | 0.15 | 648
|  | SAMPA chip | CERN | 351000 | Pending | 4800 + 3000 chips (~$45/chip) quote | 0.15 | 52650
|  | MegaPac chassis (5V) | Vicor West Coast | 110484 | Pending | manufacture quote (5022 * 20 + 2 spare) | 0.15 | 16572.6
Quote 20% | [12 empty] | 1097976.758 | 221132.926 | 1319109.684
|  | Chillers watt 10C(3) | Thermo Scientific Merlin | 32000 | Pending | Quote | 0.2 | 6400
|  | Deionizing filters (2) | McMaster | 1644 | Pending | web Quote | 0.2 | 328.8
|  | Particle filters (3) | McMaster | 720 | Pending | web Quote | 0.2 | 144
|  | Valving for Chiller Switchover | McMaster | 825 | Pending | Web Quote | 0.2 | 165
|  | SS Manifolds (4) 12 port | MSC | 1110 | Pending | web quote | 0.2 | 222
|  | Hardware (panel, brackets, mnts) | Mcmaster | 650 | Pending | web Quote | 0.2 | 130
|  | Flowmeter 24(SS) water | Dwyer | 1315 | Pending | web Quote | 0.2 | 263
|  | Bypass Valving at detector | McMaster | 1550 | Pending | web Quote | 0.2 | 310
|  | Pressure gauges (8) | Dwyer | 450 | Pending | Web Quote | 0.2 | 90
|  | Manifold valving (24) | Swagelok | 1575 | Pending | web Quote | 0.2 | 315
|  | 5/16" SS Coil (0.250 ID Min) | McMaster | 1200 | Pending | web quote | 0.2 | 240
|  | 1 1/4" Braided lines (316 SS) | McMaster | 946 | Pending | web quote | 0.2 | 189.2
|  | Large Compression fittings SS | Swagelok | 3750 | Pending | web quote | 0.2 | 750
|  | Poly lines to detector (Various) | MSC | 924 | Pending | web Quote | 0.2 | 184.8
|  | House Water Manifolding (brass) | McMaster | 1097 | Pending | Web Quote | 0.2 | 219.4
|  | Pressure Transmitters (8 min) | Dwyer | 1625 | Pending | quote | 0.2 | 325
|  | Transmitting Flowmeters (SS 1") (8) | Mcmaster | 2050 | Pending | Web Quote | 0.2 | 410
|  | RTDs (8) | Omega | 550 | Pending | Web Quote | 0.2 | 110
|  | RTD transmitter+local read (7) | Omega | 2986 | Pending | Web Quote | 0.2 | 597.2
|  | House water Monitor (pressure) | Various | 650 | Pending | Web Quote | 0.2 | 130
|  | Presure Relief Valves 1" (2) SS | Mcmaster | 882 | Pending | web quote | 0.2 | 176.4
|  | Laser | Newport | 77177 | Pending | Manufacturer Quote | 0.2 | 15435.4
|  | Flowcontrollers |  | 4500 | Pending | Quote | 0.2 | 900
|  | Power supply |  | 3975 | Pending | Web | 0.2 | 795
|  | Cables |  | 500 | Pending | web | 0.2 | 100
|  | Cables |  | 300 | Pending | web | 0.2 | 60
|  | H2O analyzers |  | 7000 | Pending | web | 0.2 | 1400
|  | Cables |  | 1200 | Pending | quote | 0.2 | 240
|  | Procure Gas System Control PC | Dell | 800 | Pending | Web Quote | 0.2 | 160
|  | Procure Electronics Rack | Allied | 535 | Pending | web quote | 0.2 | 107
|  | Procure Electronic Pressure Controller | Tescom | 2400 | Pending | web quote | 0.2 | 480
|  | Procure AL Panels | McMaster | 520 | Pending | web quote | 0.2 | 104
|  | Procure Electronics Rack | Allied | 535 | Pending | Web Quote | 0.2 | 107
|  | Striped circuit cards | All-flex | 23400 | Pending | Manufacturer Quote | 0.2 | 4680
|  | FR4 outer sheets 4' x 4' | ePlastics | 1145.8 | Pending | Manufacturer Quote | 0.2 | 229.16
|  | HVPW resistors | DigiKey | 1170 | Pending | Manufacturer Quote | 0.2 | 234
|  | High Voltage Cable | Dielectric Sciences | 600 | Pending | Web Search | 0.2 | 120
|  | Striped circuit cards | All-flex | 12000 | Pending | Manufacturer Quote | 0.2 | 2400
|  | FR4 Sheets 4' x 4' | ePlastics | 229.16 | Pending | Manufacturer Quote | 0.2 | 45.832
|  | HVPW Resistors | DigiKey | 1170 | Pending | Manufacturer Quote | 0.2 | 234
|  | Aluminum | Yarde Metals | 6222 | Pending | Vendor Quote | 0.2 | 1244.4
|  | FR4520 tooling Foam | General Plastics | 4361.98 | Pending | Existing PO | 0.2 | 872.396
|  | T-slotted framing 8020 | McMaster-Carr | 4277.84 | Pending | Estimate from v1 | 0.2 | 855.568
|  | Adhesive, lab supplies | McMaster-Carr | 1440.43 | Pending | Estimate from v1 | 0.2 | 288.086
|  | Wire/connectors | DigiKey | 352.41 | Pending | Manufacturer Quote | 0.2 | 70.482
|  | Honeycomb | Plascorp | 1621.08 | Pending | Existing PO | 0.2 | 324.216
|  | Striped circuit cards | All-flex | 23400 | Pending | Manufacturer Quote | 0.2 | 4680
|  | 3 mil kapton 44" x 108 LF | Dunmore | 21780 | Pending | Existing PO | 0.2 | 4356
|  | 3 mil kapton 22" x 108 LF | Dunmore | 20350 | Pending | Existing PO | 0.2 | 4070
|  | FR4 outer sheets 4' x 4' | ePlastics | 1145.8 | Pending | Manufacturer Quote | 0.2 | 229.16
|  | HVPW resistors | DigiKey | 6930 | Pending | Manufacturer Quote | 0.2 | 1386
|  | High Voltage Cable | Dielectric Sciences | 600 | Pending | Manufacturer Quote | 0.2 | 120
|  | Striped circuit cards | All-flex | 12000 | Pending | Manufacturer Quote | 0.2 | 2400
|  | 3 mil kapton 44" x 108 LF | Dunmore | 7260 | Pending | Manufacturer Quote | 0.2 | 1452
|  | 3 mil kapton 44" x 108 LF | Dunmore | 8140 | Pending | Manufacturer Quote | 0.2 | 1628
|  | FR4 Sheets 4' x 4' | ePlastics | 229.16 | Pending | Manufacturer Quote | 0.2 | 45.832
|  | HVPW Resistors | DigiKey | 6930 | Pending | Manufacturer Quote | 0.2 | 1386
|  | Aluminum | Yarde Metals | 6000 | Pending | Vendor Quote | 0.2 | 1200
|  | Gas |  | 5000 | Pending | Recent Purchase | 0.2 | 1000
|  |  |  | 1200 | Pending | SBU Shop Quote | 0.2 | 240
|  |  |  | 1000 | Pending | Sbu Shop Quote | 0.2 | 200
|  |  |  | 500 | Pending | SBU Shop Quote | 0.2 | 100
|  | PadPlane | Somacis | 1718 | Pending | Vendor Quote | 0.2 | 343.6
|  | GEM Mask | CERN | 1500 | Pending | Recent Purchase | 0.2 | 300
|  | PadPlane | Somacis | 1718 | Pending | Vendor Quote | 0.2 | 343.6
|  | GEM Mask | CERN | 1500 | Pending | Recent Purchase | 0.2 | 300
|  |  |  | 1200 | Pending | SBU Shop Quote | 0.2 | 240
|  |  |  | 1000 | Pending | Sbu Shop Quote | 0.2 | 200
|  |  |  | 500 | Pending | SBU Shop Quote | 0.2 | 100
|  | PadPlane | Somacis | 1718 | Pending | Vendor Quote | 0.2 | 343.6
|  | GEM Mask | CERN | 1500 | Pending | Recent Purchase | 0.2 | 300
|  |  |  | 39080 | Pending | ALICE Contract | 0.2 | 7816
|  |  |  | 135216 | Pending | ALICE Contract | 0.2 | 27043.2
|  | 6 cards + Mainframe | CAEN | 36500 | Pending | Vendor Quote | 0.2 | 7300
|  |  |  | 600 | Pending | Web Quote | 0.2 | 120
|  | Laminar Flow Hood (8 foot) | Kats Enterprises | 19559.55 | Pending | Vendor Quote | 0.2 | 3911.91
|  | Gas |  | 15000 | Pending | Current Purchase | 0.2 | 3000
|  |  |  | 3600 | Pending | SBU Shop Quote | 0.2 | 720
|  |  |  | 3000 | Pending | Sbu Shop Quote | 0.2 | 600
|  |  |  | 1500 | Pending | SBU Shop Quote | 0.2 | 300
|  | PadPlane | Somacis | 5154 | Pending | Vendor Quote | 0.2 | 1030.8
|  | Production Mask | CERN | 4500 | Pending | Current Purchase | 0.2 | 900
|  | Hardware (O-rings, screws, nylon rod) | McMaster-Carr | 3000 | Pending | Experience | 0.2 | 600
|  | Metal & machining | SBU | 43200 | Pending | SBU Estimate | 0.2 | 8640
|  | Test Pulser (B&K precision 4079B) | B&K precision | 7950 | Pending | Web quote (one dual-pulsers) | 0.2 | 1590
|  | Initial fee |  | 2000 | Pending | quote | 0.2 | 400
|  | Board fabrication |  | 75000 | Pending | 100 * 600 + 25% spare quote | 0.2 | 15000
|  | parts mounting initial fee |  | 1000 |  | quote | 0.2 | 200
|  | Parts mounting |  | 37500 | Pending | 50 * 600 + 25% spare quote | 0.2 | 7500
|  | 2x 48-fiber MTP to 12-fiber breakout cables | Computer Crafts Inc. | 437 | In requsition | Quote | 0.2 | 87.4
|  | 12-fiber MTP/MPO - LC Cassettes | Computer Crafts Inc. | 137 | In requsition | Quote | 0.2 | 27.4
|  | 6x LC duplex fiber | Computer Crafts Inc. | 68 | In requsition | Quote | 0.2 | 13.6
|  | 48-fiber MTP to 12-fiber breakout cables, 2nt | Computer Crafts Inc. | 436 | Pending | Quote | 0.2 | 87.2
|  | 12-fiber MTP/MPO - LC Cassettes, 2cnt | Computer Crafts Inc. | 136 | Pending | Quote | 0.2 | 27.2
|  | LC duplex fiber, 6cnt | Computer Crafts Inc. | 67.5 | Pending | Quote | 0.2 | 13.5
|  | SFP+ Optical TX/RX, 4cnt + 100% spare | Avnet | 723.96 | Pending | Catalog: AFBR-709DMZ | 0.2 | 144.792
|  | FELIX Production PCIe cards, 24cnt + 20% spare | BNL ATLAS DAQ Group | 229879.296 | Pending | Unofficial quote | 0.20669 | 47513.4336
|  | 48-fiber MTP (M)-MTP (F) cable 5m, 2x48cnt + 20% spare | Computer Crafts Inc. | 32025.6 | Pending | Quote: CCI/T40418PF48-005 | 0.2 | 6405.12
|  | 48-fiber MTP (F)-MTP (F) cable 58m, 48cnt + 20% spare | Computer Crafts Inc. | 35424 | Pending | Quote: CCI/T40408PF48-058 | 0.2 | 7084.8
|  | 1U 19" 12 port MPO feedthru panel with 12X MPO couplers, 2x4+25% spare | Computer Crafts Inc. | 720 | Pending | Quote: CCI/56348-MT | 0.2 | 144
|  | 48F MTP(M) - LC Hydra assembly, 48cnt + 20% spare | Computer Crafts Inc. | 7822.08 | Pending | Quote: CCI/1000450-18I-48F | 0.2 | 1564.416
|  | MTP Coupler, 48cnt + 20% spare | Computer Crafts Inc. | 129.6 | Pending | Quote: CCI/100106 | 0.2 | 25.92
|  | SFP+ Optical TX/RX, 48cnt + 20% spare | Avnet | 5212.512 | Pending | Catalog: AFBR-709DMZ | 0.2 | 1042.5024
|  | LC duplex fiber, 48cnt + 20% spare | Computer Crafts Inc. | 648 | Pending | Quote: CCI/F26268P302-001 | 0.2 | 129.6
Old Quote 25% | [12 empty] | 322979.84 | 81377.008 | 404356.848
|  | 1 1/4" thin walled SS Lines | Mcmaster | 1600 | Pending | old Quote x inflation | 0.25 | 400
|  | 1" SS Thin walled Lines | McMaster | 1450 | Pending | old Quote x inflation | 0.25 | 362.5
|  | Cf4 Analyzer |  | 14000 | Pending | past quote | 0.25 | 3500
|  | Iso Analyzer |  | 14000 | Pending | past quote | 0.25 | 3500
|  | Catalyst |  | 600 | Pending | past quote | 0.25 | 150
|  | Molecular sieves |  | 300 | Pending | past quote | 0.25 | 75
|  | Electronics Design | CSINO | 7000 | Pending | Past Cost | 0.25 | 1750
|  | Design Control Software | CSINO | 3300 | Pending | Past Cost | 0.25 | 825
|  | Procure Gas system Electronic Crate | Allied | 1000 | Pending | Past Cost | 0.25 | 250
|  | Procure Electronics Modules | CSino | 3600 | Pending | past cost | 0.25 | 900
|  | Procure Stainless compression fittings | Swagelok | 6500 | Pending | old order | 0.25 | 1625
|  | Procure Stainless Tubing | Swaglok/Mcmaster | 3400 | Pending | old order | 0.25 | 850
|  | Procure Monitoring instrumentation | Dwyer | 6500 | Pending | past order | 0.25 | 1625
|  | Procure Compressors (2) | Aid Dimensions | 4000 | Pending | past quote | 0.25 | 1000
|  | FPGA (Artix-7) | Xilinx, Digikey | 98 | Pending | Web quote | 0.25 | 24.5
|  | FPGA (Artix-7) | Xilinx, Digikey | 1200 | Pending | Web quote (12 boards) | 0.25 | 300
|  | FPGA (Artix-7) | Xilinx | 75000 | Pending | Weq quote (98 * 600 +25% spare) quote | 0.25 | 18750
|  | Optical transmitter/receiver | Avago | 37500 | Pending | 50 * 600 + 25% spare quote | 0.25 | 9375
|  | Resistor/capacitor/regulator | Digikey | 75000 | Pending | 100 * 600 + 25% spare quote | 0.25 | 18750
|  | Card Connectors | Samtec | 37500 | Pending | 50 * 600 + 25% spare quote | 0.25 | 9375
|  | 10AWG 6T00UP Cable | Belden | 6000 | Pending | $1.5/ft, 4000ft. Quote | 0.25 | 1500
|  | FELIX v2.0 Pre-Production PCIe cards, 2nt | BNL ATLAS DAQ Group | 23431.84 | Pending | Unofficial quote | 0.27697 | 6490.008
Engineering experience 25% | [12 empty] | 12500 | 3125 | 15625
|  | Optical transmitter/receiver | Avago | 600 | Pending | experience (12 boards) | 0.25 | 150
|  | Resistor/capacitor/regulator | Digikey | 1200 | Pending | experience (12 boards) | 0.25 | 300
|  | Card Connectors | Samtec | 600 | Pending | experience (12 boards) | 0.25 | 150
|  | Resistor/capacitor/regulator | Digikey | 100 | Pending |  | 0.25 | 25
|  | Optical transmitter/receiver | Avago | 50 | Pending |  | 0.25 | 12.5
|  | Card Connectors | Samtec | 50 | Pending |  | 0.25 | 12.5
|  | Pulse distributor | BNL | 7500 | Pending | experience (25 input selectors) | 0.25 | 1875
|  | Optical transmitter/receiver | Avago | 600 | Pending | experience (12 boards) | 0.25 | 150
|  | Resistor/capacitor/regulator | Digikey | 1200 | Pending | experience (12 boards) | 0.25 | 300
|  | Card Connectors | Samtec | 600 | Pending | experience (12 boards) | 0.25 | 150
Engineering Experience 40% | [12 empty] | 622829 | 249131.6 | 871960.6
|  | Compression fittings SS (various) | Swagelok | 2500 | Pending | Quote + experience | 0.4 | 1000
|  | SS Pipe fittings | Mcmaster | 700 | Pending | experience | 0.4 | 280
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Electronic hardware | various | 1750 | Pending | estimate | 0.4 | 700
|  | Vessel |  | 5000 | Pending | experience | 0.4 | 2000
|  | Heater and temp controller | OMEGA | 650 | Pending | estimate | 0.4 | 260
|  | O2 Analyzers |  | 3000 | Pending | experience | 0.4 | 1200
|  | Procure Hardware for electronics (Cabels,termanals,Etc) | Various | 2600 | Pending | Estimate | 0.4 | 1040
|  | Procure Power supplies | Omega | 1200 | Pending | estimate | 0.4 | 480
|  | Procure Mounting hardware | McMaster | 200 | Pending | estimate | 0.4 | 80
|  | Procure Al Panels | McMAster | 140 | Pending | estimate | 0.4 | 56
|  | Procure Stainless Solenoids | Parker | 3600 | Pending | estimate | 0.4 | 1440
|  | Procure Stainless Valves | Swagelok | 3500 | Pending | estimate | 0.4 | 1400
|  | Procure Mounting hardware | McMaster | 400 | Pending | estimate | 0.4 | 160
|  | End Rings | Outside Vendor | 20000 | Pending | BNL Shops Estimate | 0.4 | 8000
|  |  |  | 8000 | Pend | Experience | 0.4 | 3200
|  |  |  | 15000 | Pend | Experience | 0.4 | 6000
|  | Machining | Outside Vendor | 40000 | Pending | Experience | 0.4 | 16000
|  | End Rings | Outside Vendor | 20000 | Pending | BNL Shops Estimate | 0.4 | 8000
|  | Machining | Outside Vendor | 62000 | Pending | Experience | 0.4 | 24800
|  |  |  | 8000 | Pend | Experience | 0.4 | 3200
|  |  |  | 6000 | Pending | Experience | 0.4 | 2400
|  |  |  | 3000 | Pending | Experience | 0.4 | 1200
|  | GEMs | CERN | 5000 | Pending | Experience | 0.4 | 2000
|  | GEMs | CERN | 5000 | Pending | Experience | 0.4 | 2000
|  |  |  | 3000 | Pending | Experience | 0.4 | 1200
|  | GEMs | CERN | 5000 | Pending | Experience | 0.4 | 2000
|  |  |  | 15000 | Pending | Experience | 0.4 | 6000
|  | Garments, gloves, etc |  | 4500 | Pending | Experience | 0.4 | 1800
|  | Gluing jigs, small tools |  | 21000 | Pending | Experience | 0.4 | 8400
|  | GEMS | CERN | 10500 | Pending | Experience | 0.4 | 4200
|  |  |  | 39999 | Pending | Experience | 0.4 | 15999.6
|  |  |  | 60000 | Pending | Experience | 0.4 | 24000
|  |  |  | 12000 | Pending | Experience | 0.4 | 4800
|  | Control PC and parallel I/O card | DELL | 6000 | Pending | experience | 0.4 | 2400
|  | Modification of Peripheral |  | 5000 | Pending | experience | 0.4 | 2000
|  | Peripheral accessories and cables | Many | 500 | Pending | Experience | 0.4 | 200
|  | 2U rack servers, 12-core Xeon, 16xPCIe, 2nt | Microway | 13000 | Pending | Experience | 0.4 | 5200
|  | Peripheral accessories and cables | Many | 500 | Pending | Experience | 0.4 | 200
|  | TPC timing distribution board prototype - PCB | Many | 200 | Pending | Experience | 0.4 | 80
|  | TPC timing mezzanine prototype - PCB | Many | 100 | Pending | Experience | 0.4 | 40
|  | SMT Chip Resistor Capacitor | Digikey | 500 | Pending | Experience | 0.4 | 200
|  | 2U rack servers, 24cnt + 20% spare | Microway | 187200 | Pending | Experience, Require R&D for spec | 0.4 | 74880
|  | TPC timing distribution board - PCB, 1cnt + 1 spare | Many | 400 | Pending | Experience | 0.4 | 160
|  | TPC timing mezzanine - PCB, 24cnt + 20% spare | Many | 1440 | Pending | Experience | 0.4 | 576
|  | SMT Chip Resistor Capacitor | Digikey | 1000 | Pending | Experience | 0.4 | 400
|  | Peripheral accessories and cables | Many | 10000 | Pending | Experience | 0.4 | 4000