## Slide 1: WBS 1.5 Calorimeter Electronics Dry Run
Eric J. Mannel
July 13-14, 2017
BNL

## Slide 2: Electronics Overview-I
WBS 1.5
WBS 1.6
WBS 1.9

## Slide 3: Electronics Overview-II
“Common” design for both EMCal and HCal
  Optical Sensor: Silicon Photomultiplier (SiPM)
  Font End Analog Section:
    Amplification/Shaping
    Gain adjustment
    Different packaging for EMCal and HCal.
  Digital Backend Section:
    Continuous waveform digitization
    Trigger primitives
  Common Low Voltage and Bias Voltage Systems
Advance stage of design:
  3 Stages of prototypes, beam test.
  Use “Off the Shelf” components- No custom ASICS

## Slide 4: WBS 1.5 Technical Overview
Silicon Photomultipliers:
  Immune to magnetic fields
  Susceptible to neutron damage: increased leakage current
  15 x 15 mm2
  Dynamic range: 104
  Gain: 104
Analog Front End
  Common design for EMCal/HCal with different packaging.
  Located “on” detector.
  Shaping time of 30 nSec
  Switchable gain
    normal gain
    x 16 for calibration
  Differential analog drivers
  LED calibration/test system
  Monitoring of voltages, current and temperature
  Gain adjustment via bias voltage
Digitizer Back End
  Identical for EMCal/HCal
  Located “near” detector
  14 Bit ADC (13 bit effective)
  65 MHz maximum sampling frequency
  40 BCO latency for triggering
  Maximum of 32 samples/channel/event
  5 Event buffering
  Generate trigger primitives based on 2x2 towers

## Slide 5: WBS 1.5 Scope
WBS 1.5.1 Optical Sensors:
  EMCal: 98304 SiPMS
  HCal: 13824 SiPMs
WBS 1.5.2 Front End Electronics:
  EMCal: 24576 Channels
  HCal: 3072 Channels
  System consists of:
    Analog preamplifier/Shaper/Driver Circuit
    LED Test Pulse
    Monitoring (e.g: Voltages, Temperatures, Current)
    Bias and Low Voltage systems.
    Internal signal and power cables
    Crates for control modules
WBS 1.5.3: Digitzer System
  Common for EMCal and HCal
  27648 Total Channels
  System consists of:
    432 Digitizer Boards
    144 XMIT Boards
    432 Trigger primitive transmitters
    36 Crates with controllers
    Clock and Trigger distribution
    Power supplies for 36 crates
    624 Patch Fibers
    Crate Power Systems

## Slide 6: WBS 1.5 Boundaries
Inside the Scope
  Optical sensors for EMCal/HCal: 1.5.1
    Test and Sorted
  Front end analog electronics assembled and tested: 1.5.2
    SiPM Daughter boards
    Preamplifier/Shaper boards
    LED based calibration systems
    Slow control and power systems
    Internal signal and power cables
    External Signal and Power cables to patch panels, digitizers and power supplies
  EMCal/HCal digitizer system assembled and tested: 1.5.3
    Digitizer/XMIT/Trigger Trans. Boards
    Crates and Crate controllers
    Optical fiber to patch panels
    Power Systems for digitizer crates
Outside the scope
  Detectors: 1.3 EMCal/1.4 HCal
  Installation of electronics on detector: 1.3 EMCal/1.4 HCal
  Post-installation testing: 1.3 EMCal/1.4 HCal/Commissioning
  Racks, AC power and safety systems:1.9 Infrastructure
  EMCal Cooling: 1.3 EMCal/1.9 Infrastructure
  Optical Fibers between IR and Rack Room: 1.9 Infrastructure
  DAQ System: 1.6 DAQ

## Slide 7: WBS 1.5 Organization
WBS 1.5
Calorimeter Electronics
L2: E.J. Mannel (BNL)
WBS 1.5.1
Optical Sensors
L3: C. Aidala (UofM)
WBS 1.5.2
Front End Electronics
L3: S. Boose (BNL)
WBS 1.5.3
Digitizer System
L3: C-Y Chi (CU/Nevis)
Work Packages:
Optical Sensor Procurement
Work Packages:
Prototype Digitizers
Production Digitizers
Work Packages
EMCal Preproduction
EMCal Production
HCal Preproduction
HCal Production

## Slide 8: WBS 1.5 Organization
Dr Eric Mannel (BNL)
  HiRes Fly’s Eye Project (1995-2011): Oversaw production, testing and operations of the HiRes-II FADC based electronics
  PHENIX VTX/FVTX Electronics Project Engineer (2011-2016)
  sPHENIX Calorimeter Electronics oversight (2015-Present)
Prof. Christine Aidala (Univ. of Michigan)
  PHENIX FVTX Electronics testing and assembly.
  Long standing member of PHENIX and sPHENIX: Executive Council Member, Physics Convener
Steve Boose (BNL)
  PHENIX Electrical Engineer for 20+ years
  Analog front end systems
  Slow control and Monitoring systems
  Power systems.
Dr Cheng-Yi Chi (Columbia Univ./Nevis labs)
  PHENIX Electronics Design & Fabrication: DCMs, HBD, MPC, RPC…
  Neutrino Digitizer Electronics: Mico-Boone, Short-Baseline Near Detector
  ATLAS electronics

## Slide 9: WBS 1.5 Schedule & Cost Drivers
Schedule Drivers:
  SiPM Delivery
Cost Drivers:
  SiPMS: CD-3A item $1.1M
  EMCal Preamps: $0.4M
  EMCal Cables: $0.4M
  Digitizer Boards: $0.9M
Milestones:
  Readiness & Safety reviews
  Procurement start dates
  Staged, scheduled deliveries
  Task completion dates

## Slide 10: WBS 1.5 CD-3A Items
Optical Sensors:
  98K for EMCal
  14K for HCal
Catalog item from single vendor Hamamatsu
  Large Order, ~ $1M
  Long lead time:
    First delivery 3 months from AOR
    10K Devices per months -> ~1Year Delivery time
Requires post delivery assembly, testing and sorting, ~2 months/10K devices
Required for assembly of HCal modules and EMCal sectors
  ~2 month float for first EMCal SiPMs daughter boards to be delivered for installation in modules

## Slide 11: WBS 1.5 Labor Profile
FTE Profile by Category
FTE Profile by Fiscal Year
Row Labels | FY 17 | FY 18 | FY 19 | FY 20 | FY 21 | FY 22
Cat A | 0.05 | 0.03 | 0.16 | 3.09 | 0.22 | 0.00
Scientific | 0.04 | 0.03 | 0.05 | 0.13 | 0.00 | 0.00
Student | 0.01 | 0.00 | 0.12 | 2.96 | 0.22 | 0.00
Cat B | 1.18 | 0.50 | 0.99 | 2.99 | 0.22 | 0.00
Engineering | 0.66 | 0.22 | 0.45 | 0.76 | 0.04 | 0.00
Scientific | 0.18 | 0.01 | 0.18 | 0.91 | 0.13 | 0.00
Technical | 0.34 | 0.27 | 0.37 | 1.33 | 0.06 | 0.00
Grand Total | 1.23 | 0.53 | 1.16 | 6.08 | 0.44 | 0.00
Chart: 
| Scientific | Student | Engineering | Scientific | Technical | Cat A | Cat B
FY 17 | 0.039591 | 0.011364 | 0.66115 | 0.18227 | 0.33725
FY 18 | 0.033818 | 0 | 0.21572 | 0.013636 | 0.2673
FY 19 | 0.04596 | 0.11747 | 0.4469 | 0.17927 | 0.36672
FY 20 | 0.13245 | 2.9562 | 0.75924 | 0.90755 | 1.326
FY 21 | 0 | 0.22091 | 0.036818 | 0.12886 | 0.055227
FY 22 | 0 | 0 | 0 | 0 | 0

## Slide 12: WBS 1.5 Dictionary

## Slide 13: Basis for BOE and RLS
All components are standard off the shelf items.
  2 long lead time item, SiPMs & SiPM Bias Supplies,
  No custom ASICs
  “Standard” PCB fabrication and assembly
Design work completed during R&D Phase
  Use BOMs for component cost, scaled to larger orders
  Use prototype fabrications costs, scaled to larger orders.
  Working with some local vendors to “value engineer some assemblies.
Standard lead times for placing orders
  Time to prepare order documentation- 1 month typical
  2-6 months for PO to be issued based on expected order cost
  Delivery times based on vendor estimates, engineering experience
Three CAM Accounts/BoE Files as of July 2017
  WBS 1.5.1: Optical Sensors
  WBS 1.5.2: Front End Electronics
  WBS 1.5.3: Digitizers

## Slide 14: WBS 1.5 BoE Example: BoE Page 1
Have detailed BOE for each work package, 7 Total:
Identify what type of estimates were used in each work package
Guidelines used for estimates, both cost and time

## Slide 15: WBS 1.5 BoE Example: BoE Page 2
Identify what is included in the BOE,
What the total cost and cost + contingency
Explain how the contingency was determined and the levels used.

## Slide 16: WBS 1.5 Task Summary Example
Used to:
Summarize cost at the task level
Estimate labor requirements

## Slide 17: WBS 1.5 BoE Example: System Cost
Costs are estimated at the task level
Based on:
  Number of modules required
  BOMs for prototype boards
Includes 10% loss due to yield estimates

## Slide 18: WBS 1.5 Risk Registry

## Slide 19: WBS 1.5 Prototypes
Most devices in advanced stage of development- Three prototype stages to date with beam tests
Cost estimates based on prototype designs
Analog modules used as part of T-1044
Low technical risk
Digitizer Module
2x8 EMCal Preamp Module
Preamp Noise Measurement

## Slide 20: Issues and Concerns
SiPM Procurement:
  Single vendor
  Long lead time
  Will need to monitor purchase process closely
SiPM Testing/Assembly
  Critical for EMCal/HCal performance
  Tied to SiPM delivery schedule
  Monitor schedule closely, multiple test facilities
  Value Engineer assembly process with potential assembly house(s)
  Multiple testing sites
Front End Electronics Assembly & Testing
  Needed for EMCal Sector/HCal assembly
  Closely monitor schedule
  Early design of test procedures, value engineering

## Slide 21: Back Up

## Slide 22: WBS 1.5: Detailed Cost Estimate
Used to estimate board costs
Based on prototype BOMs
Catalog pricing/Vendor budgetary quotes