## Slide 1: sPHENIX Director’s Review 1.6. DAQ/Trigger
L2 Manager: Martin L Purschke, BNL

## Slide 2: WBS 1.6 – DAQ-Trigger
Ed Desmond, BNL (DAQ)
Jamie Nagle and Dennis Perepelitsa, U Colorado (Trigger)
Martin Purschke, BNL (DAQ, Trigger, Timing)
Electronics Engineers (Firmware Development)

## Slide 3: What 1.6 contains
The actual Data Acquisition 1.6.1
The Trigger System 1.6.2
The Global Level 1 1.6.3
The Timing System 1.6.4
You will find all information in the assorted work package documents

## Slide 4: Package Walkthrough
FEM
DCM2
SEB
10+ Gigabit
Network
Switch
Buffer Box
ATP
Many
(but not in scope here)
many
dozens
one
o(100)
o(10)
Front-end module
Data Collection Module
Sub-Event Buffer
Network Switch
Assembly and Trigger Module
Buffer box
FEM

## Slide 5: 1.6.1 Data acquisition
DCM
DCM
DCM
DCM2
SEB
SEB
To
HPSS
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Rack Room
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
Interaction Region
Rack Room
Computing
Facility
Rack Room
Event Builder
SEB
EBDC
DAM
EBDC
DAM
EBDC
DAM
10+ Gigabit
Crossbar
Switch
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
Buffer Box
Buffer Box
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE

## Slide 6: 1.6.1 Data acquisition
DCM
DCM
DCM
DCM2
SEB
SEB
To
HPSS
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Rack Room
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
Interaction Region
Rack Room
Computing
Facility
Rack Room
Event Builder
SEB
EBDC
DAM
EBDC
DAM
EBDC
DAM
10+ Gigabit
Crossbar
Switch
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
Buffer Box
Buffer Box
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
Not in 1.6 Scope

## Slide 7: What does what?
Core DAQ System
Entire data flow and event building
Data logging and data transfer to tape storage system
Configuration (Slow Control)
Global Level 1 (GL1)
Decides for each RHIC beam crossing if the data should be taken
Receives and digests the Local Level 1 information
Keeps track of the DAQ busy
Local Level 1
Collect data from a given detector system to determine if a given collision is “valuable” – input to GL1
Timing System
Distributes the RHIC clock to the front-end modules
Sends the accepted L1 accepts to the FEMs
Manages multi-event buffering (how deep we have stacked events)

## Slide 8: Data rates
The TPC dominates the data volume
Calorimeter values based on occupancy estimates
peak data rates (Gbit/s)
The ~100 Gbit/s peak rate would require 10 Buffer Boxes with 10Gbit/s interfaces
BufferBoxes’ role is to concentrate the data and level the output data flow from peak to to average values - provides some headroom
Chart: 
| TPC | Emcal | Inner Hcal | Outer Hcal
 | 80 | 13 | 4 | 4

## Slide 9: Description of major engineering tasks
Core DAQ System
Working implementation exists, many software enhancements and updates
Define and implement APIs and hand-off point with TPC-EBDC
Global Level 1 (GL1)
Porting existing firmware to a modern-day board
Enhancing and developing firmware
Local Level 1
Select FPGA board, implement physics algorithms in FPGA
Timing System
Select FPGA boards and right transceivers
Porting existing firmware
Enhancing and developing firmware

## Slide 10: 4 Stages for Local Level 1 - 1.6.2
Due to the anticipated complexity and dual nature (physics capabilities and technical implementation) of the LL1, we added one more prototype stage to this one.
Every other item has a standard design-prototype-production 3-stage cycle
1.6.2.1 Design
1.6.2.2 Prototype v1
1.6.2.3 Preproduction Prototype
1.6.2.4 Production

## Slide 11: Risk Registry
DAQ Prototype |  | DAQ prototype throughput and performance is below specifications |  |  |  | Low
Network switch |  | Network switch more expensive than projected |  |  |  | Low
Global Lvl1 |  | adaptation of PHENIX GL1 runs into obstacles |  |  |  | Low
Timing System |  | Conversion/adaptation from GLINK problematic, or envisioned replacement board cannot be used |  |  |  | Low
Local LVL1 |  | Performance of LLVL1 algorithms inadequate. Trigger latency too high. |  |  |  | Moderate
Storage |  | Data volume, especially from the TPC, too high |  |  |  | Moderate
Local Lvl1 “Simulations reveal the failure of an envisioned algorithm”
Storage “The TPC or other subsystem exceeds the allotted bandwidth … additional compression strategies would need to be developed”

## Slide 12: WBS Dictionary Example
Part of sPHENIX WBS Dictionary- Link
Defined down to the work package level
“This work package covers the development cycles of the Global Level 1 (GL1) system, from design to final commissioning. The GL1 manages the triggering and busy states of the detector, and receives, in addition to the minimum bias information, the outputs of the local level 1 triggers”

## Slide 13: Schedule
Schedule Drivers:
COTS procurements as late as possible to take advantage of price decreases or next-gen hardware
DAQ infrastructure as early as needed to support detectors’ installation and commissioning cycle

## Slide 14: Labor Profiles
FTE Profile by Category
FTE Profile by Fiscal Year
Chart: 
| FY 17 | FY 18 | FY 19 | FY 20 | FY 21 | FY 22
BNL - Purchased Services | 0 | 0 | 0 | 0.018182 | 0 | 0
BNL - Scientific | 0.32831 | 0.49581 | 0.22723 | 1.1727 | 0.7 | 0
BNL - Technical | 0.045455 | 0.040909 | 0.028409 | 0.47159 | 0 | 0
BNL - Professional | 0.36045 | 0.39523 | 0.21932 | 1.0691 | 0.54545 | 0
Non-BNL - Scientific | 0.478 | 0.26777 | 0.086267 | 0.35909 | 0.0031818 | 0
Non-BNL - Student | 0 | 0.67045 | 0.063636 | 0.92727 | 1.1182 | 0
Non-BNL - Professional | 0.14955 | 0.23227 | 0.1 | 0.58864 | 0 | 0
WBS Level | Org Sort | Group | FY 17 | FY 18 | FY 19 | FY 20 | FY 21 | FY 22
1.6 | BNL | Purchased Services | 0.00 | 0.00 | 0.00 | 0.02 | 0.00 | 0.00
 |  | Scientific | 0.33 | 0.50 | 0.23 | 1.17 | 0.70 | 0.00
 |  | Technical | 0.05 | 0.04 | 0.03 | 0.47 | 0.00 | 0.00
 |  | Professional | 0.36 | 0.40 | 0.22 | 1.07 | 0.55 | 0.00
 | BNL Sum |  | 0.73 | 0.93 | 0.47 | 2.73 | 1.25 | 0.00
 | Non-BNL | Scientific | 0.48 | 0.27 | 0.09 | 0.36 | 0.00 | 0.00
 |  | Student | 0.00 | 0.67 | 0.06 | 0.93 | 1.12 | 0.00
 |  | Professional | 0.15 | 0.23 | 0.10 | 0.59 | 0.00 | 0.00
 | Non-BNL Sum |  | 0.63 | 1.17 | 0.25 | 1.88 | 1.12 | 0.00
Grand Total |  |  | 1.36 | 2.10 | 0.72 | 4.61 | 2.37 | 0.00

## Slide 15: Issues and Concerns
Concerns:
The Local Level 1 system needs work on more than one front (physics simulation, then implementation on the FPGA). Reflected in 2 prototype stages.
The TPC data volume might be higher than current estimates, leaving us with little headroom. This may require additional compression/reduction strategies (principally deeper buffering).
The good:
Already today, we take data with the near-final EmCal electronics. We will use this in the next test beam. There is no switch in readout hardware and APIs later.
Lots of experience in lossless online data compression - other experiments have copied our methods (TPC data will benefit most.)

## Slide 16: Backup

## Slide 17: Individual high cost items
10+ Gigabit
Network
Switch
Candidate if he had to purchase today

## Slide 18: Individual high-cost items (2)
Buffer Box
$517,000 / 16 * 6 = $195,000
Candidate if he had to purchase today

## Slide 19: Individual high-cost items (2)
Buffer Box
$517,000 / 16 * 6 = $195,000
Machine in use in the RACF
(being set up)
Candidate if he had to purchase today

## Slide 20: Individual $$$ items (2)
10+ Gigabit
Network
Switch
Buffer Box
ATP
$517,000 / 16 * 6 = $195,000