## Slide 1: S-PHENIX Director’s Cost and Schedule Review Closeout
August 4, 2017

## Slide 2
Thanks….........
Our focus is to advise you about what to do to be ready for a successful CD-1 review in spring 2018. Tough love if/when needed.
In closeout and report we separate evaluation of MIE and “infrastructure and facilities upgrades”
Committee subgroups from breakouts will present closeout material
But first some high level comments & recommendations

## Slide 3
Overall assessment
S-PHENIX should be positioned for a successful CD-1 review in the spring of 2018 if continued progress in made in development of the technical, management and cost/schedule aspects of the project.
Following the advice and recommendations of this committee will significantly enhance the likelihood of a successful CD-1

## Slide 4: Overall Comments/Recommendations
Project team is experienced, well structured and, with adequate resources, should be capable of successfully carrying out S-PHENIX
The technical expertise and experience is high.
Scientific collaboration is strong and engaged. The science case is strong.
The Laboratory wants S-PHENIX to succeed. Support from CAD, Physics, SMD will be essential.
These are necessary (but not sufficient) ingredients for success.

## Slide 5: Overall Comments/Recommendations
The MIE scope is in flux due to excess cost. The current cost estimate exceeds the MIE cap. Descope options are being evaluated and value engineering is planned
  Recommendation- By the end of CY2017 the project should resolve descope options to bring the MIE cost within cap.
The schedule is aggressive, technically limited and based on a highly unlikely MIE funding profile.
  Recommendation- By the end of CY 2017 the project should develop a realistic profile expectation with DOE, plans for things like phased funding and then adjust the schedule accordingly to be realistic.

## Slide 6
Time between now and CD-1 allows for in-depth reviews of key design/technical/management issues/concerns/risks.
  Recommendation- BNL management should plan for and execute in-depth reviews, with action items cleared, well before Director’s pre-CD-1 review. Reviews:
  Cost & schedule including contingency, realistic resource profile ($ and people) for both MIE,” upgrade support” and “infrastructure and facility upgrades”
  Needs outside of project for software, storage and processing of the data
  Technical review of calorimeters and electronics.
  Technical review of TPC and electronics
  Then hold Director’s pre- CD-1 Review at least 2 months before CD-1 review

## Slide 7
The “upgrade support” and “infrastructure and facility upgrades” are under BNL control. Needed staff has been defined but not yet locked in with mutual agreements.
  Recommendation- By November 2017, Project should execute mutual agreements with the relevant BNL departments defining support for S-PHENIX including staff.

## Slide 8
At this point the project presented no plans for assuring EH&S at remote sites (other Labs and universities) or documentation related to activities to occur within the BNL Physics Department. These may represent serious oversights.
Recommendation- The project leadership must remedy this as soon as possible.
Notes: Concern about being BNL centric, myopic

## Slide 9
The project does not have a single individual responsible for all systems engineering functions. The current distribution of systems engineering tasks among the project leadership leads to significant risk of something important falling through the crack.
Recommendation–In the next month the Project should assign one person as project system engineer with appropriate authority and responsibility.

## Slide 10
The current schedule doesn’t have time to map the magnet volume. The project states that they will investigate whether this mapping is required and, if so, the schedule would be extended to accommodate it. It is also not clear that the project has a clear idea about how to do the mapping if needed.
Recommendation– Well before the CD1 review the project must decide whether mapping of the field volume is needed, and if so the schedule must be modified to accommodate this and solid plans made to do the mapping. Alternatively, if the issue can’t be settled before CD-1, schedule time for mapping should be added to the project and if later it is determined not to be needed, then there would be additional schedule contingency.

## Slide 11
The s-PHENIX project seems not yet to have fully explored their schedule and cost risks. A number of risks surfaced during this review that should have been identified at this point.
Recommendation– By the end of September the project should reassess and update their risk register with special attention to schedule and cost risk. It might be useful to have a few knowledgeable BNL people from outside s-PHENIX look over the resulting set of risks.

## Slide 12: Closeout talks from breakout areas including responses to relevant charge items
Calorimeter etc.– Howard Gordon
Tracking etc.– Helen Caines
Management– Bill Edwards
Infrastructure and facility upgrade– Yousef Makdisi

## Slide 13
Answer to Charge Questions: Calorimeters and Electronics
1 Is the conceptual design technically sound and likely to meet the objectives of its scientific case?
–We find that the conceptual design has been backed up by significant R&D efforts in recent years, and the design should meet the scientific objectives of sPHENIX.
3 Are the resources, including (wo)men-power adequate and likely to be provided?
–The groups for building calorimeters and electronics are experienced and strong, and detailed estimates of the needed resources are documented. The costs for the calorimeters have risen significantly, leading to the total project cost exceeding the envelop. Significant efforts need to be made for reducing the cost, including investigation of descoping. The resources for labor cost, both on MIE through university contracts, or off-project with BNL funding have been estimated but should be formalized through agreements with the relevant departments.
3 Are the EH&S aspects being properly addressed?
–ES&H needs to address safety issues outside BNL, and document procedures concerning safety in all relevant departments at BNL.

## Slide 14: Calorimeter
Finding: SiPM’s are susceptible to radiation damage from low energy neutrons. sPHENIX has calculated that the amount of exposure should lead to an acceptable excess leakage current after five years of heavy ion running at RHIC.
Comment: Since the SiPM’s are so critical to the physics performance it is important to carryout further study of the radiation damage.
Recommendation: Continue studying neutron radiation damage to SiPM’s.

## Slide 15: Calorimeter
Findings: The Collaboration has worked very successfully with a firm in Russia on HCal. The firm has given a proposal to supply scintillators with grooves machined and wavelength fibers inserted.
Comment: We worry that in the current climate conditions may occur where business relations with Russia may become impossible.
Recommendation: Identify and quantify the cost and schedule for an alternate source for the HCal scintillator.

## Slide 16: Calorimeter
Findings: The University of Illinois at Urbana Champaign has shown great leadership in the development of EMCal scintillating fiber blocks filled with tungsten powder/epoxy.
Comment: This is a sole source for the EMCal and the fabrication of these blocks is on the critical path.
Recommendation: Quantify the cost and schedule impact and mitigation of the risk should Illinois not be able to deliver.
Recommendation-Advance the R&D to mitigate the risk of production delays

## Slide 17: Calorimeter
Finding: The schedule for the MIE was moved out by one year due to the funding uncertainties in FY18.
Comment: Perhaps some of this time could be used productively by moving other tasks earlier.
Recommendation: Move tasks funded by non-MIE sources such as tooling and installation fixtures earlier in the schedule.

## Slide 18: Calorimeter
Finding: Plans for water cooling the EMCal are being finalized. The calorimeter electronics are also close to final design.
Comment: It is always best to test complete systems.
Recommendation: Test the full electronics system including the water cooling in the February 2018 beam test.

## Slide 19: Tracking/DAQ/Trigger -response to charge-
Is the conceptual design technically sound and likely to meet the objectives of its scientific case?
  We find that the conceptual designs of the TPC, trigger, DAQ and tracking approach to be technically sound and likely to meet the requirements for the success of the sPHENIX physics program
Are the resources, including (wo)men-power adequate and likely to be provided?
  An adequate workforce is identified with the groups involved having a solid reputation in supplying the promised personnel on schedule. It is not entirely clear how the resources are funded
Are the EH&S aspects being properly addressed?
  ES&H needs to address safety issue outside BNL

## Slide 20: General
Comments:
  Mechanical requirements or corrections should be developed based on the tracking precision required for good Upsilon resolution. This includes field cage precision, space charge corrections and the B field map. It is likely that a sagitta resolution of 70 µm will be required.
  More on interfacing of the inner detectors would be desirable. For example how will beampipe bake out be done in the presence of inner detectors.
  An integrated detector cooling plan is desired

## Slide 21: TPC
Comments:
  The GEM schedule drives module production schedule and hence the TPC’s overall schedule. Since CERN is the sole source of GEM production, a formal agreement with CERN should be obtained as soon as possible
  The bench tests required to confirm the stability issues of IBF should be addressed as soon as possible

## Slide 22: TPC Electronics
Comments:
  SAMPA chip is a significant fraction of the cost estimate of the TPC electronics. Better sources for the cost estimates should be obtained.
  A summary of the radiation tolerance requirements of TPC FEE should be documented and used to justify the design choice.

## Slide 23: TPC Support
The cooling plate of the FEE scope is not covered by either TPC FEE WBS or TPC support WBS
Recommendation
  A BOE should be developed and included in an appropriate WBS

## Slide 24: DAQ/Trigger
Comment:
    The sPHENIX raw data will be sent to RACF at an estimated rate of 20-30 PBytes/year. It is estimated that it will take ~350 weeks to reconstruct with computing power available for RHIC at BNL today. While this is not technical issue we suggest that sPHENIX continues discussions with RACF and BNL management to ensure adequate computing requirements for reconstruction and simulations/embedding are available for quick publication of first data.

## Slide 25: Response to Charge – Infrastructure & Facility Upgrades
Answer 1- Basically yes , but see recommendations
Answer 2 -The BOE were thorough and the MS project was reasonable for this state of the project.
Answer 3- Yes
Answer 4- Many other BNL groups are used for project. Need to get commitments from respective organizations.
Answer 5- The assumptions and dependencies appear in the risk registry. The major risk of
the magnet is being addressed in the high current test. ESH risk at outside institutions
need to be addressed. The risk of insufficient available labor should be addressed with
mutual agreements between the project and the outside organizations.
1. Is the scope adequate to support the scientific goals of MIE?
2. Are the cost and schedule estimates properly justified and documented?
3. Are the technical risks of this scope reasonable and acceptable?
4. Are the resources needed, including (wo)men-power adequate and likely to be provided?
5. Are the assumptions and dependencies outside the direct control of sPHENIX project management clearly documented? Have the risks associated with these assumptions and dependencies been identified and possible mitigations documented?

## Slide 26: Response to Charge – Infrastructure & Facility Upgrades
Answer 6- See management section of the review
Answer 7- Several documents have been drafted, but additional effort will need to be added to this are to address concerns of the committee. See recommendations
6. Is management structure and coordination between MIE, the upgrade facility and the inner detectors appropriate and documented
7. Are the ES&H aspects properly addressed?

## Slide 27: Infrastructure and Facility Upgrade
ES&H
Most sPHENIX ES&H documents relating to DOE and BNL SBMS requirements are in draft form.
  Recommendation -These should be submitted to the respective authorities for comments and final approval.
The ES&H presentation focused on primarily on the review and operational requirements between sPHENIX and C-AD. However, a significant effort of MIE detector assembly will be carried out at the Physics department.
Recommendation-The ES&H related issues and required training should be defined in particular for the Physics department.

## Slide 28
Similarly, significant amount of work will be carried out at collaborating institutions and vendors. Project managers make periodic visits to these institutions and vendors.
  Recommendation- ES&H requirements should be stated in the respective mutual agreements. It would help to have one draft agreement completed before the CD-1 review.
A more engaging presentation for the CD-1 review would be desirable. It would help to have the presentation reviewed by a lab ES&H professional before the CD-1 review.

## Slide 29
Magnet
The effort is a collaboration between C-AD, SMD, and Physics for magnetic field calculations, cryogenics, engineering, valve box modification and extension, power supply, controls, quench protection, and magnetic field measurement. The solenoid was successfully cooled and tested at low current. It is being prepared for a full current test utilizing a temporary return yolk later this year.
Recommendation- Study if the magnet is susceptible to a quench due the RHIC beam pre-fire.
Recommendation- The cryo-system design should be subjected to an external review.
Recommendation- The power supply quench protection contactors should have snubber circuits across the contacts to minimize noise generated into adjacent electronics.

## Slide 30
Facilities
The existing PHENIX water cooling systems served both the warm magnets and detectors, The latter will be required for sPHENIX.
Recommendation-To that end, detector cooling needs should be defined to assess if the current system needs upgrading.
The existing IR HVAC system is deemed adequate.
Recommendation-The Rack room requirements should be defined and the related HVAC system upgraded if necessary, as it experienced some problems in the past.
Labor: All tasks are well defined and BOE’s established.

## Slide 31
Integration
Systems designs are at a conceptual stage. The de-scoping is likely to impact this effort.
The labor requirements are well defined.
Management has employed drawing control and engineering change control systems.
Recommendation- Set up a grounding task force with a grounding czar for the full detector system.
Related to both Integration and facilities…..
For the uninitiated, the BOE’s were difficult to navigate.
Recommendation- Provide some guidelines or instructions for drill down purposes.

## Slide 32: Management Subcommittee - Response to charge items--MIE
Are the cost and schedule estimates credible and reasonable for this stage of the project?
A: the cost estimates are fairly complete and reasonable for a CD-1 maturity. The schedule is credible and reasonable for CD-1. However, some durations seem optimistic (for example procurement steps) and it was difficult to associate resources with the funding source (MIE or other).

## Slide 33: Management Subcommittee - Response to charge items--MIE
Is the project appropriately managed? Is there a capable team in place to effectively manage risks, interfaces and ensure quality?
A: Yes, mostly… This is a strong team with a long history of working together. However, we worry about the specific lack of experience with current formal DOE OPA and NP expectations. The team can learn, but may not be fully prepared for all the rigor involved in preparing and executing a successful OPA CD review, completing monthly EVMS reporting, and so on.

## Slide 34: Management Subcommittee - Response to charge items-- MIE
Has the project met all CD-1 prerequisites and is ready for CD-1?
A: There is a lot left to do. For example, an sPHENIX specific PHAD hazards assessment needs to be completed, a re-work on the risk management plan, a great deal of scrubbing of schedule and cost, smoothing of the funding profile, decisions on CD-1 scope, is needed.

## Slide 35: Management Subcommittee - Response to charge items-- MIE
Is the project ready for long lead procurements and meets the appropriate DOE requirements?
A: No, not yet. Design reviews need to take place and recommendations addressed. Also, scope decisions need to be made to determine the final list of 3a items and quantities.

## Slide 36: Management Subcommittee
Comment: All the L3 managers, approximately 20 are currently listed as Control Account Managers (CAMs). This is too many. We would suggest that the project develop an understanding of the full set of CAM responsibilities with regard to monthly reporting and variance analysis and communicate this to the proposed CAMs. Consider the number and skill set…and interest level…of the people you want to train to hold this responsibility.
Recommendation: The L2 managers (not the L3’s) should be made CAMs and receive all the associated CAM training for EVMS reporting.

## Slide 37: Management Subcommittee
Comment: The contingency of 30% is lower than what is typical for projects preparing for CD-1. The project should look carefully at their BOE documentation to shore up the cost estimate and resulting contingency estimate. Current contingency analysis does not include all the impact of the risks in the registry.
Recommendation: Include the impact of appropriate risks in the contingency. Consider a MC analysis of the cost/schedule impacts associated with the risk registry. This is then added to the cost contingency to form the total contingency.

## Slide 38: Management Subcommittee
Comment: The logic and data in the BOEs should be independently reviewed prior to the CD-1 reviews. Holding these independent reviews can help during the agency reviews because you have an independent assessment and report to point the committee to.
Recommendation: Organize and hold independent Basis of Estimate (BOE) reviews prior to the CD-1/3a review.

## Slide 39: Management Subcommittee
Comment: The current plan for holding Final Design Reviews (FDRs) and Operational Readiness Reviews (ORRs) is not sufficient. Earlier design feedback are valuable and help focus effort. Production Readiness Reviews (PRRs) focused on the final drawing set, technical specification, likely vendors are also productive.
Recommendation: Add a Preliminary Design Review (PDR) and a Production Readiness Review (PRR) for all major elements.

## Slide 40: Management Subcommittee
Comment: There is a potential conflict of interest when the ES&H manager position is occupied by the same person who is designing the infrastructure and the associated the safety system.
Comment: The Safety Officer/Engineer talk and the PHAD too often referenced prior work of PHENIX or C-AD leaving the wrong impression with the committee.
Recommendation: At the CD-1 review A more rigorous, all encompassing talk will be needed to make sure EHS reviewers are comfortable that safety is a primary focus of s-PHENIX

## Slide 41: Management Subcommittee
Comment: All the “system” lead engineers (5+) report directly to the Project Director. This would seem to create too flat of an organization with too many people reporting to the top.
Recommendation: All the various system level engineering entities should report through the Project Engineer. The lone exception would be the Safety Engineer function that should continue to report to the Project Director.

## Slide 42: Management Subcommittee
Comment: It is very challenging for the reviewers to understand the difference between contributed and costed labor.
Recommendation: At the CD-1 review present the contributed and costed labor in a consistent and clear way.
Comment: OPC and TEC costs need to be separated clearly and consistently. It will be useful to present the cost profile at a lower level in the L2 talks. In addition a slide for the major cost drivers in each sub-system would be useful.

## Slide 43
Questions or comments?