- What is the timeframe for completing the transfer of the schedule from MS Project to P6?  When will use of MS Project be fully retired.  When can the cost/obligations profile be captured in P6/COBRA for example.  When will the coding for different labor types will be completed?

WBS 1.1-1.11 is in P6. The plan is to retire MS Project after this review and have a series of meeting with PM, L2s and CAMs to ensure P6 schedule buy-in. The coding will be finished in September. By November we should be able to generate cost/obligation profiles.

- What is the plan for maintaining the schedule – e.g. is Irina going to maintain and update the schedule or the CAMs are going to be trained to work in the schedule? How many FTEs project controls?

The plan is to communicate with CAMs and L2s via Excel, and have Project Controls (Irina Sourikova) serve as a schedule gate keeper. We have 90% of Irina as project controls.

We also have an outside P6 consultant assisting us at 25% of his time until CD-1. At what level this needs to be continued after CD-1 will depend on our experience with the workload for Project Controls, the level that the L2 Managers and CAMs can contribute to the work via Excel, and the amount of Project Controls work that can be delegated to other members of the Project team.

- There is ~1.2M MIE cost in FY17, obviously the project will not receive MIE funds this FY. Is this cost going to be removed assuming some of the scope was completed using R&D funds?

The $1.2M in FY17 is OPC funds.  Of the $1.2M, $260k is project management salary for overseeing the Conceptual Design and the rest is R&D. We have a similar level of OPC funds planned for FY18, although DOE recently asked us to revise the number upwards and plan for a more aggressive R&D program in FY18 that will allow for a faster start in FY19 once we get CD-1 authorization.

- What is the plan to synchronize the BOEs and the schedule?

The plan is to have the P6 RLS as the repository of current sPHENIX financial and schedule information. That updated information in P6 would be transferred to the L2’s and CAMs on a regular basis for updating the BOEs.

- In Jim Mills talk this morning we asked if we could see the Comment Resolution list/system.   Both to see that it is done systematically and to see how prior recommendations have been dispositioned.

We have decided that we better status the comment resolution database to make sure that it is accurate and up to date before sharing it with the committee, or anyone outside of the Project team and L2 Managers.

- Distinguishing cost, funding and obligations can be difficult – I assume what we have been shown (in most cases) is actually funding, not necessarily at year cost.   It would be good to have that clarified.

Yes, the slides are reflecting required Budget Authority (BA).  Commitment and Costing profiles will be completed when the likely funding profile target is agreed upon with the NP Program Office.

- Already clear the desired scope won’t fit in the MIE box – what is the process (and timeline) for scope reductions? TBD with consultation with the Collaboration (Spokespeople and EC). I would like to have the next round of scrubbing done by Oct 1.

- Related to descoping – what are the time bound decision points for restoring or adding scope? We don’t have the information to answer this today. It depends on many factors.

- This may get answered tomorrow (it was suggested a bit today) – who in PPM (Procurement and Property Management) is the contact for sPHENIX work?   Also related does the schedule include the ‘standard’ procurement strings for RFP and RFQs?

We have been assigned a Buyer in BNL PPM to handle the large sPHENIX contracts and orders, Emily Mastronardi. We have included sufficient time in the RLS for RFQ procurements based on the size of the procurement.  We have also included sufficient procurement time for the one RFP that we have, the extension of the RHIC cryogenics into the 1008 IR by a commercial vendor. There are 20 weeks scheduled in the RLS to go from the start of procurement preparation to award.

- Matrixed resources – how are you going to keep on top of getting your assigned or contributed resources available when you need them.

We control the personnel resources inside the Physics department. They work in the sPHENIX group. We will put in place Memoranda of Agreement with CAD, SMD and Instrumentation defining the resources that sPHENIX will need, defining the dates according to the RSL, durations, tasks,  and skill sets. We plan to manage this similar to how we managed the Operations of the PHENIX experiment. There weekly CAD work planning meetings that sPHENIX reps will attend and will be weekly sPHENIX work planning meetings that CAD reps will attend. The jobs and resource needs for the week will be decided there. Any schedule slippage due to lack of resources will get resolved between the Project Management team and CAD/SMD/IO Management.

- What happens if NP cannot deliver the funding on the timescale you are planning?  Or, what happens if CD-3b is delayed by 1 year? Does the Project TPC increase?  And, if so, approximately by how much?   Have you worked on any of these scenarios?

We have designed the project to carry little labor on purpose so that we are not vulnerable to the standing army problem. Any general schedule slippage of 1 year would increase the TPC due to a 2% escalation in M&S. Up until now we haven’t worked on any but the simplest multiple scenarios using the RLS because of the challenge of doing scenarios using MS-Project. We have looked at the effects of a 1 year slip which is what we presented to the committee.  Once in a fully-vetted P6 we should be able to look in detail at the impact of various funding scenarios.

- What is your understanding of the responsibilities, skill set and training required of CAMs? We will train all of the CAMs in EVMS.

The PEP section 7.12 describes the CAM responsibility.

7.12 Control Account Managers

The sPHENIX Control Account Managers are responsible for completing the activities within their Control Accounts within the time and budget constraints stated in the Resource-Loaded Schedule (RLS). Specific responsibilities include:

- Carry out the design, construction, and assembly of the subsystem in accordance with the scope, schedule, and budget, assuming funding and resources as described in the PEP.

- Provide monthly EVMS data to the L2 Managers in order that the L2 Managers can prepare their L2 reports for the Project Control Manager.

- No sPHENIX specific hazards have been identified, analyzed or mitigated in the draft HAR (PHAR).  In what document are these items captured? JH.

The PHAR is a draft that relies on referencing detailed CAD Safety documents. It needs to be written as a document that can be understood stand-alone. We also recognize that it needs to be expanded to address sPHENIX Safety issues beyond the CAD complex, not only the BNL Physics Department but sPHENIX Collaborator production facilities as well.

Needs to be captured in the PHAR

- Assuming that subcontracts will be the method for distributing Project funding to collaborating institutions (University groups, Labs), have any of these subcontracts been completed?  How many of these subcontracts will the project have?

We currently have R&D contracts with SBU, UIUC and Columbia Univ, but nothing yet that is part of the Total Project Cost. However within the next 3 months I expect OPC contracts with all 3 institutions. Eventually the project expects to have contacts with: Stony Brook Univ, Iowa State Univ, Univ of  Illinois-UC, Univ Michigan, Columbia Univ, Vanderbilt Univ, Weizmann Inst, Wayne State Univ, PNPI, and perhaps Florida State,  Lehigh, Univ Colorado, Abilene Christian Univ, Debrecen Univ. During the 13 years that I was PHENIX Operations Director, I managed contracts with most of these universities as well as many others.  The BNL Physics Department has business support personnel experienced in managing numerous university contracts. They have been doing this for PHENIX, ATLAS, STAR and other projects for many years.