## Slide 1: Electronics & DAQ WG
Fernando Barbosa (JLab)
3 September 2026

## Slide 2
  Today: ASIC & Electronics monthly updates
  DOE OPA IPR – 15-18 September 2026
  AOB
Agenda
Schedule Issue:
  Electronics P6 was updated with info from recent ASIC reviews and linked to other WBSs:
    SALSA is on the critical path (zero float):
      SALSA --- FEB --- MPGDs (assembly, tests & installation)
        Impacts project schedule --- delay
          Damien to review scheduling with colleagues at Saclay.
  Mitigation: next slide

## Slide 3: SALSA – Schedule Mitigation
ASIC SALSA
  SALSA3 is the final version submission as Engineering Run; ePIC only needs less than 10 wafers in total.
  If SALSA3 meets the performance requirements, the final production phase (just wafers) should occur in Q3 2028.
SALSA FEB
  The SALSA FEB schedule will also benefit from early Engineering Article qualification with pre-production ASIC SALSA chips, which will be available prior to the start of the ASIC production (Production Readiness Review).
  The SALSA FEB will also be tested with the first production ASICs at ~6 months after start of ASIC production, serving as the Production Readiness Review for SALSA FEB production.
  These concurrent developments may shorten the FEB schedule by ~3 months.
Version |  | Status | Notes
SALSA1 | 4 ch | Complete | Tested with MPGDs, TID tests at CERN next
SALSA2 | 32 ch | Submission Q4 2026 | Most IP blocks included
SALSA3 | 64 ch | Submission Q1-Q2 2028 | Full functionality
SALSA | 64 ch | Submission Q3 2029 | Production of SALSA3
Final Eng. Run
Final prod. phase
ASIC SALSA
SALSA FEB
MPGDs