## Phi-Coverage
BToF options to increase the acceptance in Phi
General Note: | Only two layer designs are considered as all other ones do not fit in the envelope assigned to the bToF or require unrealistic design requirements for the service hybrid
Problem: | Phi acceptance as fct of momentum is as low as 60% at low pt.
Note on Service Hybrid: | For all cases discussed the service hybrid height needs to be reduced to 25 mm. This requires to use the design for the dc-dc converted based on the bpol48 from the hungarian group. The location of the service hybrid can be optimized on the stave versus off the stave, which makes the serviceability easier.
Simulations: | Should be done before any other actions. We need simulations to see the impact of the stave width of 60mm vs. 55 mm vs. 50 mm. The impact of increasing the sensor to close the Phi acceptance gap needs to be also simulated
Additional Concerns | what is the justification to first produce stavelets and then staves; take decissions on all other possible options in the stave design.
Solution | Reduce Stave width from 60 mm to 55 mm or 50 mm | Increase sensor width from 33 mm to ~39 mm
Impact on Sensor | None | Need to verify with Hamamatsu this is possible and what the consequences for resolution and timing are. Risk: Yield of the sensors, cost and impact on all downstream components.
Impact on FPC | width needs to be reduced. Risk: FPC yield, increased cross talk and performance issues. Solution: 1. Contact vendor to see what is possible. 2. Separate FPC signal and power. Maybe use cables along the stave for power --> prefered solution | Need to adapt the FPC to the increased power needs and more signal lines. Risk: FPC yield, increased cross talk and performance issues. Solution: 1. Contact vendor to see what is possible. 2. Separate FPC signal and power. Maybe use cables along the stave for power --> prefered solution
Impact on Service Hybrid | Needs to be reconfigured in a less wide but longer board. We need to find a connector which has the correct height and width. | We need to find a connector which has the correct height and width.
FCFD | None | the number of channels per FCFD needs to be increased to match the number of strips
Other | Need to study with simulations if 55 mm or 50 mm width gives the needed aceptance | This decission needs to be taken asap, that the FCFD design is not too far advancing and no change can be made anymore or are very costly. Answers from Hamatsu need to be obtained now.
PRO | Only the FPC is touched and the Service Hybrid formfactor is touched
CON |  | Every component needs to be touched

## ETA Coverage
BToF options to increase the acceptance in ETA
General Note: | Only two layer designs are considered as all other ones do not fit in the envelope assigned to the bToF or require unrealistic design requirements for the service hybrid
Problem: | Gaps in Eta acceptance as fct of momentum.
Note on Service Hybrid: | For all cases discussed the service hybrid height needs to be reduced to 25 mm. This requires to use the design for the dc-dc converted based on the bpol48 from the hungarian group. The location of the service hybrid can be optimized on the stave versus off the stave, which makes the serviceability easier.
Simulations: | Should be done before any other actions. We need simulations to see the impact of the reduced eta coverage, if possible separate from the phi coverage issue.
Solution | Change Stave design to increase ETA coverage
Impact on Sensor | None
Impact on FPC | potentially need two differnet mechanical layouts for the FPC
Impact on Service Hybrid | Same as before
FCFD | None
Other | Need to change the pitch between sensors for top and bottom stave to shift them relative to each other along z