## Slide 1: Preparations for the European Spallation Source beam commissioning
Lali Tchelidze
Operations Section Leader
Accelerator Division
October 3, 2018
Workshop on Accelerator Operations

## Slide 2: Part 1
EUROPEAN SPALLATION SOURCE

## Slide 3: European Spallation Source – what & where – future layout
ESS
MAX-IV
Science Village
Lund
Copenhagen

## Slide 4: Global ESS schedule
2014
Construction Starts on Green Field Site
2009
Decision to Site ESS in Lund
2025
ESS Construction Phase Complete
2003
European Design of ESS Completed
2012
ESS Design Update Phase Complete
2019
Start of Initial Operations Phase
2023
Start Of User Program
(SOUP)

## Slide 5
Lund Tramway Depot
Permanent
Office Campus
2021
New 2018 ESS offices for all staff
PermanentEntrance

## Slide 7: Target Monolith & Utility
Last set of diagonal walls before high bay in progress.
Utility area, base slab works.

## Slide 8: Target, Monolith Circular walls around puck

## Slide 9: Active Cell

## Slide 10: A2T Accelerator to Target, bottom slab works

## Slide 11: E-buildings

## Slide 12: Accelerator – Scope
Design Drivers:
High Average Beam Power
5 MW
High Peak Beam Power
125 MW
High Availability
95%
Key parameters:
    -2.86 ms pulses
    -2 GeV
    -62.5 mA peak
    -14 Hz
    -Protons (H+)
    -Low losses
    -Minimize energy use
    -Flexible design for mitigation and future upgrades
18 IK partners I 8 countries and 5 collaboration partners

## Slide 13: Accelerator Collaboration
13

## Slide 14: Part 2
HOW WE ORGANIZE WORK

## Slide 15: Process to get to beam commissioning
License
Safety Readiness Review
Beam Permit
Beam commissioning
Operation
Hardware commissioning
NOTE: GREEN FIELD FACILITY/EVERYTHING NEW/TAKES TIME
NOTE: We will be commissioning in stages

## Slide 16: Commissioning stages
Ion source and LEBT (75 keV), beam to FC
RFQ and MEBT (3.6 MeV), beam to FC
DTL1 (22 MeV), beam to FC
DTL2 to DTL4 (40 MeV, 57 MeV, 74 MeV), beam to FC
DTL5 and SCL, beam to Beam Dump
Full accelerator, beam to Target

## Slide 17: Ion source & LEBT installation

## Slide 18: Licensing process and timeline (agreed on June 2018)
2019
2021
ESS
SSM
Intentional neutron production trial operation review
2022
2020
2017
RBoT
RFQBeam
BoD
Conditional permit
SRR5
SRR4
Submission 2021-04-15
SC LINAC trial operation review
Conditional permit
Submission 2020-04-30
SRR2
Submission 2018-12-15
Conditional permit
Warm LINAC trial operation review
BoT
Ref Doc ready 2018-06-30
PSAR updated
Self Assessment
Independent Safety Review
Ref Doc ready 2019-11-15
PSAR updated
Self Assessment
Independent Safety Review
Ref Doc ready 2020-10-30
PSAR updated
Self Assessment
Independent Safety Review
IoS
permit
Response to
questions
PSAR – Preliminary Safety Analysis Report
SRR - Safety Readiness Review
SSM – Swedish Radiation Safety Authority
RFQ – Radio Frequency Quadropole
BoD – Beam on Dump
BoT - Beam on Target
RBoT - Ready for Beam on Target
IoS
Extension
For Klystron test
IoS Extension
For cavity test
TS2
Extension
IoS Beam
SRR1
SRR
Submission
Submission
Subm.
Currently ESS holds a license for construction, installation and operation of ion source and LEBT (as of June 2018); also for storing and using radioactive source

## Slide 19: Safety Readiness Review
SRR process at ESS is equivalent of the Accelerator Readiness Review process for the national labs in the US.
The purpose of the SRR process it to review the readiness to safely commission and operate a system.
The SRR is a process by which hardware, personnel and procedures associated with commissioning and operation of the system is verified.
SRR is organized by ESH&Q using external and internal (independent) reviewers.
SRR1 (for ion source and LEBT) was performed on July 2018

## Slide 20: Beam Permit
Pre-start items were finished, relevant equipment was handed over to the operations section and the beam permit was signed by the laboratory management on September 19th
Pre-requisite for beam permit:
  Equipment handover
  Operational Limits and Conditions (safety envelope)

## Slide 21: Beam commissioning
We do the beam commissioning under the “operations organization”
The beam commissioning activities are performed from the control room, under the shift leader
A commissioning / study leader is present and the system experts are called as necessary
Operations section
Shift leaders/operators
System group
Study leader
System group
System group
System group
Currently staff from the technical divisions are trained and perform the role of the shift leader on rotation
Training program is generated and run by the operations section
WE WILL BE HIRING SHIFT LEADERS and OPERATORS SOON

## Slide 22: Joint installation/commissioning on construction site
We are in construction, installation and commissioning simultaneously
We follow the rules for construction site
A tight link is established between the stakeholders from the installation and operations
8:30 am daily meetings in control room where the plan of the day (commissioning) is announced and installation coordinators are present to comment/inform about possible conflicting activities

## Slide 23: First results of beam commissioning
See Marc Munoz’s poster later

## Slide 24
Thank you!
Campus