## Slide 1: Low-Energy RHIC electron Cooling (LEReC) Near term Goals and To Do Tasks July 2, 2018

## Slide 2: Remaining major tasks
Finish PS tests with Cornell’s chassis.
Implement changes to BNL chassis and confirm that PS in stable.
Pulsed mode: finish commissioning of remaining instrumentation, including energy spectrometer and energy calibration.
Complete MPS certification to allow both long-trains and CW operation to high-power beam dump.
Establish CW transport to high-power beam dump.
Establish required RF stability both in amplitude and phase.
Achieve required laser stability and profile uniformity
Establish beam-based alignment
Establish orbit and energy stability control

## Slide 3: Remaining major goals (KPPs) for July
Establish required electron beam parameters (emittance and energy spread) in both cooling sections for design electron beam charge.
Transport 1mA CW current to high-power beam dump.
Study cathode QE lifetime with 30mA current (at reduced energy to injection dump (can we go to 15kW?) or at full energy to high power beam dump). Need several long term (>1 hour) runs at 30mA.

## Slide 4: Remaining major goals (beyond KPPs)
Establish stable high-current 30mA at 1.6MeV in high-power beam dump (going through all hold points, faults studies, beam halo/losses studies, etc.)
Commission full accelerator at 2.0 MeV
Commission full accelerator at 2.6 MeV (requires SRF booster conditioning to 2.2 MV)

## Slide 5: To Do items by subsystems

## Slide 6: DC Gun and HVPS
DC Gun:
Requires better vacuum. Will add more pumps to the Gun. Not taking Gun apart?
Gun anode assembly modifications
3. Repair resister chain on the Gun side?
HVPS:
1. Stability issues. Results of transformer. Results of Cornell’s control chassis?
We need to implement changes to BNL’s control chassis to make it identical to Cornell’s and confirm that PS with BNL’s chassis is stable before Cornell chassis goes back to Cornell.
2. Voltage ripple measurement. Are we are adding capacitance? On the Gun side?
3. Voltage regulation bandwidth: it does not appear that it can be increased to few kHz.
4. Taking control chassis out of RHIC tunnel.
Time estimate for all the modifications?

## Slide 7: Laser
1. When should we expect reliable temporal shaping measurement?
2. When can we expect stable laser intensity: both short-term and long-term?
3. When can we expect thermal issues in crystals resolved?
4. Should we expect 10W on Gun table before iris cut as our maximum or 10W on cathode is a possibility?
5. What can be done to provide more uniform laser beam profile to the Gun table?

## Slide 8: RF
1. 2.1 GHz PA: When should we expect permanent fix to allow up to 250kV operation?
2. Beamloading feedback development
3. Achieving design specs on amplitude and phase.
4. Stability of energy to 1e-4 level. Feedback from hybrid BPM.
5. RF clock timing locked to RHIC. When can we expect it?

## Slide 9: Instrumentation
Loosing BPMs electronics during CW operation:
1. Did we tried everything to prevent it?
2. Effect of RF noise on electronics
3. NMR problems and when we expect them fixed?
4. FCT calibration issues.
5. What do we do about using BLMs as part of MPS in RHIC environment?
6. What is main MPS instrumentation for high-current to final beam dump?
Other issues?

## Slide 10: Cathodes
Second cathode production system, timeline?
Production of cathode with off center active area.
Looks like we have established reliable cathode production with very good QE.
Cathode delivery and baking procedure is also established.
Will off cathode area help with constant requirement to re-condition the Gun after CW running?

## Slide 11: Gun issues
Light (only few trips) Gun re-conditioning can be done with running resistor. However, real conditioning with many trips can be done only with processing resistor.
Is implementation of a switch between resistors a possibility?
Will off cathode area help with constant requirement to re-condition the Gun after CW running?
Typically, requirement for re-conditioning was a result of Gun trip. Most recently Gun radiation came back without any obvious reason and reconditioning with running resistor was not effective.

## Slide 12: Other required repairs before next year Run
Cryogenics: He sub-cooler fix
Gun anode assembly modifications
Inspection of cathode surface area?
Adding more pumps to improve Gun vacuum
Gun resistor chain repairs.
Adding capacitors for voltage ripple reduction.
Implementation of resistor switch?
Gun-to-booster corrector modifications
When these repairs could be fully completed (assuming start date September 16) so that we can plan to re-start LEReC testing to be ready for next year?
When all Gun modifications will be completed and Gun will be ready for Conditioning?
When should we plan to have SRF Booster cold and restart beam tests?