## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  |  | L3 Project Name (Control Account) |  | L3 WBS Number
Time Projection Chamber |  | 1.02 |  |  | TPC FEE |  | 1.02.05
| Work Package Name |  | WBS Number |  |  | Basis of Estimate Link
| TPC FEE Prototype v1 |  | 1.02.05.01 |  |  | FEE Prototype v1
| TPC FEE Pre-Production |  | 1.02.05.02 |  |  | FEE Pre-Production
| SAMPA chip 80 nsec |  |  | 1.02.05.03 |  | Sampa 80 nsec
| TPC FEE Production |  | 1.02.05.04 |  |  | FEE Production

## FEE Prototype v1
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-03-25
[7 empty] | Prepared By: | Takao Sakaguchi
[7 empty] | DocNo. (refer Rev. Log) | 43 v19
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
TPC FEE Prototype v1 |  |  |  | 1.02.05.01
WBS Dictionary Definition:
TECHNICAL SCOPE: CONTAINS ALL TASKS WHICH ARE REQUIRED TO DESIGN, PROCURE, FABRICATE AND ASSEMBLE COMPONENTS FOR FEE PROTOTYPE V1. WORK STATEMENT: PROVIDE MATERIAL/EQUIPMENT TO PRODUCE AND TEST THE FEE PROTOTPYE V1 FOR THE TPC.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
We assume here that the SAMPA chip develolped for the ALICE experiment will be used as our main amplifier and digitizer device. We assume that all development costs of that chip will be born by ALICE. Therefore we only develop a custom board onto which we place the SAMPA chips. The SAMPA chip will be operated (except during calibration) with the internal DSP active and handling the zero suppression task. This means that the data will be confined to hits above pedestal only. As a result the FPGA localed on the FEE board will have very light duty, simply shipping the data off to the DAM module without any significant processing or formatting.
Details of the Base Estimate (explanation of the Work)
We base this cost on a combination of the ALICE test stand being developed at ORNL and on past experience with development of similar systems at BNL instrumentation. The cost basis has been done in close collaboration with Joe Mead of the BNL Instrumentation group and frequent colsultation from Tonko Ljubicic from STAR. STAR is implementing a 2-chip SAMP board with a single FPGA and their experience makes our design tasks immensely simplified. In particular, we will NOT be investigatin in-chip operational issues since these are already resolved by ALICE and STAR.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
Entries into the detailed Cost Summary (FY17 Direct) have been color coded based upon the appropriate level of Estimate Uncertainty that is applied to the item with green being the lowest Estimate Uncertainty and red being the highest. We have assumed 12 prototype boards since this will allow for 1 R2 module to be fully populated, one board on the bench, and 3 spares.
|  |  | Grand Total |  | #REF! | #REF! | Labor Hours
|  |  | 3150 |  | #REF! | #REF! | 480
Estimate Uncertainty
The Estimate Uncertainty has been evaluated independently for each line items in accord with the standard sPHENIX Estimate Uncertainty guidelines. Contingencies spread over several items are weighted by item cost to determine a summary Estimate Uncertainty for each WBS entry. Because of existing relations between STAR and ALICE regarding the SAMPA chip, we feel comfortable applying 15% Estimate Uncertainty to the purchase of the SAMPA chips themselves. We apply 20% Estimate Uncertainty to standard baord parts, and 40% Estimate Uncertainty to the not-yet-designed PC interface (made from commercial parts).

## FEE Pre-Production
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-03-25
[7 empty] | Prepared By: | Takao Sakaguchi
[7 empty] | DocNo. (refer Rev. Log) | 43 v19
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
TPC FEE Pre-Prototype |  |  |  | 1.02.05.02
WBS Dictionary Definition:
TECHNICAL SCOPE: CONTAINS ALL TASKS WHICH ARE REQUIRED TO DESIGN, PROCURE, FABRICATE AND ASSEMBLE COMPONENTS FOR THE PRE-PRODUCTION FEE. WORK STATEMENT: PROVIDE MATERIAL/EQUIPMENT TO PRODUCE AND TEST THE PRE-PRODUCTION FEE FOR THE TPC.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
We assume here that the SAMPA chip develolped for the ALICE experiment will be used as our main amplifier and digitizer device. We assume that all development costs of that chip will be born by ALICE. Therefore we only develop a custom board onto which we place the SAMPA chips. Because of the progress of bothe ALICE and STAR in developing multi-SAMPA FEE cards, we believe that many of the pitfalls already identified will allow us to move directly from the v1 prototype to the pre-production prototype.
Details of the Base Estimate (explanation of the Work)
We base this cost on a combination of the ALICE test stand being developed at ORNL and on past experience with development of similar systems at BNL instrumentation. We continue to assume 15% Estimate Uncertainty for SAMPA chips (which will be bought in bulk), but bump the other component costs to 25% Estimate Uncertainty since this design is further away as compared to present progress than the v1 design. We additionally account for the liklihood of needing to upgrade the test stand and assign 40% Estimate Uncertainty there since the details of what will be required are quite vague.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
Entries into the detailed Cost Summary (FY17 Direct) have been color coded based upon the appropriate level of Estimate Uncertainty that is applied to the item with green being the lowest Estimate Uncertainty and red being the highest. This is cheaper than the v1 stage since there will be a re-use of the test stand.
|  |  | Grand Total |  | #REF! | #REF! | Labor Hours
|  |  | 20977.05 |  | #REF! | #REF! | 2624
Estimate Uncertainty
The Estimate Uncertainty has been evaluated independently for each line items in accord with the standard sPHENIX Estimate Uncertainty guidelines. Contingencies spread over several items are weighted by item cost to determine a summary Estimate Uncertainty for each WBS entry. The most significant changes to the Estimate Uncertainty as compared to teh v1 round of prototyping are that we bump the parts cost to 25% (the v1 parts list of known at the time of this writing and the pre-production is subject to change) and we assign 40% Estimate Uncertainty to our estimate of "upgrades" required for the test stand.

## Sampa80
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-03-25
[7 empty] | Prepared By: | Takao Sakaguchi
[7 empty] | DocNo. (refer Rev. Log) | 43 v19
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
TPC FEE Production |  |  |  | 1.02.05.03
WBS Dictionary Definition:
TECHNICAL SCOPE: CONTAINS ALL TASKS WHICH ARE REQUIRED TO MODIFY THE SAMPA CHIP TO INCLUDE A FASTER SHAPING TIME OPTION WORK STATEMENT: PROVIDE LABOR/MATERIAL/EQUIPMENT TO PRODUCE AND TEST MODIFIED SAMPA CHIP.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
We assume here that the SAMPA chip develolped for the ALICE experiment will be used as our main amplifier and digitizer device. The original plan for the SAMPA included three possible shaping times 80, 160, and 320 nsec. We had planned to use the fastest (80 nsec) shaping time. Recent changes to the SAMPA design eliminated the faster shaping time option (80 nsec) making the chip either 160 nsec or 320 nsec. This item would involve a design change to the chip so that the two options would instead be 80 nsec and 160 nsec.
Details of the Base Estimate (explanation of the Work)
The price included here is an estimate from ongoing discussions with the chip's original designers.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
Entries into the detailed Cost Summary (FY17 Direct) have been color coded based upon the appropriate level of Estimate Uncertainty that is applied to the item with green being the lowest Estimate Uncertainty and red being the highest.
|  |  | Grand Total |  | #REF! | #REF! | Labor Hours
|  |  | 711151 |  | #REF! | #REF! | 745
Estimate Uncertainty
The Sao Paulo group has generated four versions of the SAMPA chip to date and we therefore feel that their cost estimate is based upon knowledge and experience.

## FEE Production
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-03-25
[7 empty] | Prepared By: | Takao Sakaguchi
[7 empty] | DocNo. (refer Rev. Log) | 43 v19
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
TPC FEE Production |  |  |  | 1.02.05.04
WBS Dictionary Definition:
TECHNICAL SCOPE: CONTAINS ALL TASKS WHICH ARE REQUIRED TO PROCURE, FABRICATE AND ASSEMBLE COMPONENTS FOR FEE PRODUCITON AND PERFORM QA TESTING. WORK STATEMENT: PROVIDE MATERIAL/EQUIPMENT TO PRODUCE AND TEST THE FEE PRODUCTION FOR THE TPC.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
We assume here that the SAMPA chips we will use are successfully developed by minor revision of the working version for the ALICE experiment (SAMPA ver 5). We have detailed estimate in SAMPA80 BOE. The costs of the FEE are dominated by the cost of the optical tranceivers and minor parts that have 20% uncertainties.
Details of the Base Estimate (explanation of the Work)
Production orders are estimated using 30% for additional FEE parts, 15% for DC power (same brand and model as used many times in PHENIX) and 20% fabrication Estimate Uncertainty from experience with the appropriate board house.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
Entries into the detailed Cost Summary (FY17 Direct) have been color coded based upon the appropriate level of Estimate Uncertainty that is applied to the item with green being the lowest Estimate Uncertainty and red being the highest.
|  |  | Grand Total |  | #REF! | #REF! | Labor Hours
|  |  | 697550.996 |  | #REF! | #REF! | 1175
Estimate Uncertainty
Production orders are estimated using 30% for additional FEE parts, 15% for DC power (same brand and model as used many times in PHENIX) and 20% fabrication Estimate Uncertainty from experience with the appropriate board house.

## Prototype v1-Details
Material
WBS | Activity # | Description | Item | Vendor | Line Total | Status | Basis of Estimate | Total | Grand Total
1.02.05.01 |  | TPC FEE Prototype v1 | [6 empty] | 3150
1.02.05.01 | 134500 | Procure TPC FEE prototype v1 components | [5 empty] | 0
|  |  | SAMPA chip | CERN | 0 | received | 100 chips received as free samples for the final
|  |  | Other parts (incl opt mod., connectors) | Digikey etc | 2967.84 | received | Detailed quote = (quote - $44 (SAMPA)*8)*12
1.02.05.01 | 134700 | Fabricate TPC FEE prototype v1 boards | [5 empty] | 0
|  |  | Board fab (incl initial and shipping) |  | 2777.5 | received | Detailed quote (10 initial + 5 later spare boards)
1.02.05.01 | 134900 | Procure TPC FEE prototype v1 LV power supplies | [5 empty] | 0
|  |  | MegaPac Chassis (5V) | Vicor West Coast | 4099 | received | Purchased (Nov, 2016), 1 module
1.02.05.01 | 135100 | Develop TPC FEE Test Stand | [5 empty] | 0
|  |  | SAMPA test board | BNL | 330.82 | received | Completed
|  |  | Board fab (incl initial and shipping) | palpilot | 1199.15 | received | Completed
|  |  | FPGA (Artix-7) eval board | Xilinx, Digikey | 490 | received | Purchased
|  |  | SAMPA chip | CERN | 0 | received | Two chips (with spare of 2) as free samples
|  |  | Pulse distributor board fabrication | BNL | 3000 | received | experience
|  |  | Pulse distributor | BNL | 10000 | received | experience (25 boards)
|  |  | Test Pulser (B&K precision 4079B) | B&K precision | 7950 | received | Web quote (one dual-pulsers)
|  |  | Control PC and parallel I/O card | DELL | 6000 | received | experience
1.02.05.01 | 135300 | Assemble and test TPC FEE prototype v1 | [5 empty] | 0
|  |  | Parts mounting initial fee |  | 1000 | received | experience
|  |  | parts mouting on board |  | 2500 | received | experience
1.02.05.01 | 135500 | Assemble and test TPC FEE prototype v1a |  |  | 3150 |  | experience | 3150
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL | Hours Completed
1.02.05.01 | 135200 | Assemble and test TPC FEE prototype v1 | Similar to PHENIX HBD | PROF |  | 0 | 64
|  |  |  | TECH |  |  | 64
|  |  |  | TECH |  |  | 64
|  |  |  | SCI |  |  | 32
|  |  |  | STUD |  |  | 96
1.02.05.01 | 135400 | Assemble and test TPC FEE prototype v1a | Similar to PHENIX HBD | PROF | 96 | 480
|  |  |  | TECH | 96
|  |  |  | TECH | 96
|  |  |  | SCI | 48
|  |  |  | STUD | 144
1.02.05.01 | 134300 | Design TPC FEE protoype v1 | Similar to STAR ITS Upgrade | PROF |  | 0 | 228
|  |  |  | TECH |  |  | 228
1.02.05.01 | 135000 | Develop TPC FEE Test Stand | Similar to STAR ITS Upgrade | PROF |  | 0 | 80
|  |  |  | TECH |  |  | 96
|  |  |  | TECH |  |  | 80
|  |  |  | SCI |  |  | 32
|  |  |  | STUD |  |  | 32
1.02.05.01 | 134600 | Fabricate TPC FEE prototype v1 boards | Similar to PHENIX HBD | PROF |  | 0 | 20
1.02.05.01 | 134400 | Procure TPC FEE prototype v1 components | Similar to PHENIX HBD | PROF |  | 0 | 16
1.02.05.01 | 134800 | Procure TPC FEE prototype v1 LV power supplies | Similar to PHENIX HBD | SCI |  | 0 | 5
|  |  |  | PROF |  |  | 5
|  |  |  | TECH |  |  | 5
1.02.05.01 | 134200 | Write TPC FEE prototype v1 design specification | Similar to ALICE ITS Upgrade | PROF |  | 0 | 6
|  |  |  | SCI |  |  | 5
|  |  |  | TECH |  |  | 6
|  | Grand Total |  |  | 480 | 480 | 1164

## Pre-Production-Details
Material
WBS | Activity # | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.05.02 |  | TPC FEE Pre-Production | [6 empty] | 20977.05
1.02.05.02 | 137000 | Procure TPC FEE preproducion prototype components | [5 empty] | 5871.05
|  |  | SAMPA chip | CERN | 0 | received | 150 chips (ver4) received as free sample
|  |  | Other parts (incl opt mod., connectors) | Digikey etc | 2075.4 | Pending | Quote
|  |  | Optical module | Avago | 561.8 | Pending | $28.09/module 20 modules
|  |  | Xilinx Artix-7 XC7A200T-1FBG484C | Avnet | 3233.85 | Pending | $215.59 per chip
1.02.05.02 | 137200 | Fabricate TPC FEE preproduction prototype boards | [5 empty] | 1476
|  |  | Board fab (incl initial and shipping) |  | 1476 | Pending | Quote
1.02.05.02 | 137400 | Modify TPC FEE Test Stand | [5 empty] | 8000
|  |  | Modification of Peripheral |  | 8000 | Pending | experience
1.02.05.02 | 137600 | Assemble and test TPC FEE preproduction prototype | [5 empty] | 5630
|  |  | Parts mounting initial fee | AA technology | 950 | Pending | Quotes
|  |  | parts mouting on board | AA technology | 4680 | Pending | Quotes
Labor
WBS | Activity # | Description | Justification | Category | Hours | TOTAL
1.02.05.02 | 137500 | v2 Assemble and test TPC FEE preproduction prototype | Similar to PHENIX HBD | PROF | 248 | 712
|  |  |  | TECH | 64
|  |  |  | TECH | 64
|  |  |  | SCI | 240
|  |  |  | STUD | 96
1.02.05.02 | 136800 | v2 Design TPC FEE preproduction protoype | Similar to STAR ITS Upgrade | PROF | 664 | 1456
|  |  |  | TECH | 792
1.02.05.02 | 137100 | v2 Fabricate TPC FEE preproduction prototype boards | Similar to STAR ITS Upgrade | PROF | 20 | 20
1.02.05.02 | 137300 | v2 Modify TPC FEE Test Stand | Similar to STAR ITS Upgrade | PROF | 240 | 420
|  |  |  | TECH | 72
|  |  |  | TECH | 60
|  |  |  | SCI | 24
|  |  |  | STUD | 24
1.02.05.02 | 136900 | v2 Procure TPC FEE preproducion prototype components | Similar to PHENIX HBD | PROF | 16 | 16
|  | Grand Total |  |  | 2624 | 2624

## Sampa80-Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.05.03 |  | TPC FEE Production | [6 empty] | 711151
1.02.05.03 | 139000 | Procure SAMPA 80 nsec development | [5 empty] | 365500
|  |  | New SAMPA chip design effort | Sao Paulo | 365500 | Ordered | Discussions with Sao Paulo Group
1.02.05.03 | 138500 | Multi-project wafer run for component testing | [5 empty] | 42651
|  |  | Wafer production and packaging | IMEC | 42651 | Received | IMEC quote
1.02.05.03 | 139700 | Procure Full SAMPA chip design/submission/reception | [5 empty] | 67000
|  |  | full SAMPA design to reception effort | Sao Paulo | 67000 | Pending | Discussions with Sao Paulo Group
1.02.05.03 | 140400 | Procure engineering run of Full SAMPA chip | [5 empty] | 233000
|  |  | MLM mask and 12 wafers | IMEC | 125000 | Pending | Initial quote from IMEC
|  |  | additional 36 wafers | IMEC | 75000 | Pending | Initial quote from IMEC
|  |  | MOQ (50k pieces) of BGA substrate | IMEC | 28000 | Pending | Initial quote from IMEC
|  |  | BGA assemble | IMEC | 5000 | Pending | Initial quote from IMEC
1.02.05.03 | 140500 | Populate pre-production FEE with full SAMPA chip | [5 empty] | 3000
|  |  | parts mounting | AA Technology | 3000 | Pending | Estimate for 2 boards based on Quote
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.05.03 | 140600 | Test v2 prototype board with 80 nsec full SAMPA chip | Similar to STAR ITS Upgrade | PROF | 200 | 400
|  |  |  | SCI | 200
1.02.05.03 | 140700 | Review results of SAMPA 80ns full chip performance w/ v2 prototype TPC FEE board | Similar to STAR ITS Upgrade | PROF | 80 | 265
|  |  |  | SCI | 185
1.02.05.03 | 139100 | Procure layout/simulation/submission/Reception of Full SAMPA chip - Provide requirements to Procurement | Similar to STAR ITS Upgrade | SCI | 40 | 40
1.02.05.03 | 139800 | Procure Engineering Run of Full SAMPA Chip - Provide Requirements to Procurement | Similar to STAR ITS Upgrade | SCI | 40 | 40
|  | Grand Total |  |  | 745 | 745

## Production-Details
Material
WBS | Activity # | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.05.04 |  | TPC FEE Production | [6 empty] | 697550.996
1.02.05.04 | 141500 | Procure TPC FEE components - Optical | [5 empty] | 29663.04
|  |  | Optical tranceiver | Avago | 29663.04 | Pending | $28.09/module with 10% spare
1.02.05.04 | 141800 | Procure TPC FEE components - all but Optical and SAMPA | [5 empty] | 266693.856
|  |  | Other parts (incl opt mod., connectors) | Digikey etc | 118712.88 | Pending | Estimate from v1a quote with 10% spare
|  |  | Xilinx Artix-7 XC7A200T-1FBG484C | Avnet | 147980.976 | Pending | $215.59 per chip
1.02.05.04 | 142500 | Procure TPC FEE LV power supply system | [5 empty] | 190056
|  |  | 6AWG welding cable |  | 1008 | Pending | $0.63/ft, 1600ft.
|  |  | 16AWG Cables for each FEE |  | 36480 | Pending | 6 cond.+shield $0.76/ft, 48000ft.
|  |  | MegaPac chassis (5V) | Vicor West Coast | 87048 | Pending | manufacture quote (6696 * 12 + 1 spare)
|  |  | Power distribution boards | in house | 65520 | Pending | FVTX experience by Steve ($35/FEE * 624 * 3 lines)
1.02.05.04 | 143200 | Fabricate and assemble all TPC Fee boards | [5 empty] | 150982.9 |  | P6 still has $163,283
|  |  | Board fabrication |  | 18566.9 | Pending | 20 initial + 610 later + 70 later (incl 10% spare) |  |  | Need to fix
|  |  | parts mounting initial fee | AA technology | 2000 | pending | Quote |  |  | Board count was 800 not 700 in P6 number
|  |  | Parts mounting | AA technology | 130416 | Pending | Quote
1.02.05.04 | 136500 | Payment for TPC cooling sytem production | [5 empty] | 60155.2
|  |  | Copper Plate |  | 19968 | Pending | M&S Quote and estimate of blazing/machining
|  |  | Heat pipe |  | 3120 | Pending | M&S Quote and estimate of blazing/machining
|  |  | Screw/Nuts |  | 400 | Pending | Material, engineering estimate
|  |  | Thermal Gap Pad |  | 16848 | Pending | M&S Quote
|  |  | Alminum Block 1 |  | 10720.2 | Pending | Quote
|  |  | Alminum Block 2 |  | 9099 | Pending | Quote
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.05.04 | 135900 | Prepare contract to produce TPC FEE Cooling sytem | Similar to FVTX cooling | SCI | 10 | 20
|  |  |  | PROF | 10
1.02.05.04 | 135800 | Prepare TPC FEE Cooling system specs | Similar to FVTX cooling | SCI | 0 | 400
|  |  |  | PROF | 400
1.02.05.04 | 142600 | Fabricate and assemble all TPC Fee boards - Provide Requirements to Procurement | Similar to STAR ITS Upgrade | PROF | 44 | 44
1.02.05.04 | 143300 | Perform QA Testing on TPC FEE | Similar to PHENIX HBD | TECH | 168 | 883
|  |  |  | PROF | 56
|  |  |  | STUD | 280
|  |  |  | SCI | 379
1.02.05.04 | 140900 | Procure TPC FEE components - Provide Requirements to Procurement | Similar to STAR ITS Upgrade | PROF | 80 | 216
|  |  |  | TECH | 80
|  |  |  | SCI | 56
1.02.05.04 | 141900 | Procure TPC FEE LV power supplies - Provide Requirements to Procurement | Similar to many PHENIX systems | PROF | 32 | 32
|  | Grand Total |  |  | 1175 | 1175

## Quotations
SAMPA chip Production