## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Time Projection Chamber |  | 1.02 |  | TPC DAM |  | 1.02.06
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| TPC DAM Evaluation -- FELIX 1.5 |  | 1.02.06.1 |  | TPC DAM Evaluation --FELIX 1.5
| TPC DAM Evaluation -- FELIX 2.0 |  | 1.02.06.2 |  | TPC DAM Evaluation -- FELIX 2.0
| TPC DAM Production |  | 1.02.06.3 |  | TPC DAM Production

## Felix 1.5-Summary
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[7 empty] | Prepared By: | Jin Huang
[7 empty] | DocNo. (refer Rev. Log) | 138 v3
Work Package Name: |  |  |  |  | WBS Number: |  |  | Control Account Number
TPC DAM Evaluation --FELIX 1.5 |  |  |  |  | 1.02.06.01
WBS Dictionary Definition:
TECHNICAL SCOPE: CONTAINS ALL TASKS WHICH ARE REQUIRED TO EVALUATE THE DAM WITH THE PROTOTYPE V1 (FELIX 1.5 SYSTEM). WORK STATEMENT: DESIGN, DEVELOP, AND MEASURE DAM PROTOTYPE V1 PROPERTIES .
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
We have assumed that the sPHENIX experiment will make use of the FELIX board developed for ATLAS as our DAM module. As a result we rely on ATLAS to bear all cost of the develment of these boards. Our task is then reduced to evluating the board performance as compared to our known throughput specifications. Furthermore, we have made an agreement that the FELIX 1.5 version board used for initial tests will be borrowed instead of bought. Therefore our initial testing of the borrowed Felix 1.5 board requires little more than connectors.
Details of the Base Estimate (explanation of the Work)
The test stand for this project will require handling of purely digital information. As such, we can generate simulated data using a commercial ATRIX 7 FPGA.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
Entries into the detailed Cost Summary (FY17 Direct) have been color coded based upon the apropriate levek iof Estimate Uncertainty that is applied to the item with green being the lowest Estimate Uncertainty and red being the highest. The total cost at this stage is $1.6k which rises to $2.0k when including Estimate Uncertainty. NOTE that borrowing of existing parts is only possible at this stage since ATLAS is finished with development of the FELIX 1.5 We will be required to pay full costs when moving onto FELIX 2.0
|  |  |  | Task |  | Cost | Labor Hours
|  |  | Develop TPC DAM prototype v1 Test Stand |  |  | 1631 | 977
Estimate Uncertainty
The Estimate Uncertainty has been evaluated independently for each line items in accord with the standard sPHENIX Estimate Uncertainty guidelines. Contingencies spread over several items are weighted by item cost to determine a summary Estimate Uncertainty for each WBS entry.

## Felix 2.0-Summary
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[7 empty] | Prepared By: | Jin Huang
[7 empty] | DocNo. (refer Rev. Log) | 138 v3
Work Package Name: |  |  |  |  | WBS Number: |  |  | Control Account Number
TPC DAM Evaluation --FELIX 2.0 |  |  |  |  | 1.02.06.02
WBS Dictionary Definition:
TECHNICAL SCOPE: CONTAINS ALL TASKS WHICH ARE REQUIRED TO EVALUATE THE DAM WITH THE PROTOTYPE V2 (FELIX 2.0 SYSTEM). WORK STATEMENT: PROCURE, DEVELOP, AND MEASURE DAM PROTOTYPE V2 PROPERTIES.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
We have assumed that the sPHENIX experiment will make use of the FELIX board developed for ATLAS as our DAM module. As a result we rely on ATLAS to bear all cost of the develment of these boards. Our task is then reduced to evluating the board performance as compared to our known throughput specifications. Furthermore, we have made an agreement that the FELIX 2.0 version board used for tests will be purchased rather than borrowed.
Details of the Base Estimate (explanation of the Work)
The test stand for this project will require handling of purely digital information. As such, we can generate simulated data using a commercial ATRIX 7 FPGA as well as data generated y early FEE prototypes. Out test stand will have unique requirements to generate simluated TPC data streams. We will use eth ATRIX to perform this function.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
Entries into the detailed Cost Summary (FY17 Direct) have been color coded based upon the apropriate levek iof Estimate Uncertainty that is applied to the item with green being the lowest Estimate Uncertainty and red being the highest. Our cost for the pre-production and Estimate Uncertainty is summarized below:
|  |  |  | Task |  | Cost | Labor Hours
|  |  | Procure TPC DAM Felix 2.0 boards (DAQ THROUGHPPUT TEST) |  |  | 73523.5
|  |  |  | Procure Full Set of Data Fiber for Design Validation |  | 2875.76
|  |  |  | FPGA Algorithm development |  | 2563.35
|  |  |  | Total |  | 78962.61 | 3089
Estimate Uncertainty
The Estimate Uncertainty has been evaluated independently for each line items in accord with the standard sPHENIX Estimate Uncertainty guidelines. Contingencies spread over several items are weighted by item cost to determine a summary Estimate Uncertainty for each WBS entry. We take 25% Estimate Uncertainty on the ATLAS board following the advice of ATLAS. Cabling and power is taken at 20% based upon vendor quotes. The rest of the peripherals which are not fully specified are set at 40% Estimate Uncertainty.

## Production-Summary
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-13
[7 empty] | Prepared By: | Jin Huang
[7 empty] | DocNo. (refer Rev. Log) | 138 v3
Work Package Name: |  |  |  |  | WBS Number: |  |  | Control Account Number
TPC DAM Production |  |  |  |  | 1.02.06.03
WBS Dictionary Definition:
TECHNICAL SCOPE: CONTAINS ALL TASKS WHICH ARE REQUIRED TO PRODUCE THE DAM FOR THE TPC. WORK STATEMENT: PROCURE ALL PARTS AND PERFOM QA TESTING FOR THE FINAL TPC DAM.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
We assume that FELIX production 2.0 version will suit our needs. Furthermore, we assume that we will require one FELIX card per TPC sector, housed in its own high speed PC. Costs for the 12 core rack servers are included in the scope of this WBS rather than as a part of infrastructure. Additionally, we carry partial costs of the timing distributuion system as approproate for our system's fractional load.
Details of the Base Estimate (explanation of the Work)
The estimate includes production, quality assurance, and installation of the DAM system. Fiber costs are born in this WBS rather than in the TPC FEE to which the DAM module is connected.
Cost Summary (FY17 Direct)
(follow link for detailed summary)
Entries into the detailed Cost Summary (FY17 Direct) have been color coded based upon the apropriate levek iof Estimate Uncertainty that is applied to the item with green being the lowest Estimate Uncertainty and red being the highest. The cost before Estimate Uncertainty and with Estimate Uncertainty are summarized below.
|  |  | Task |  |  | Cost | Labor Hours
|  |  | Procure TPC DAM Felix 2.0 boards |  |  | 130362
|  |  | Optical data fiber and distribution |  |  | 80745
|  |  | Procure TPC EDBC Computers and Peripherals |  |  | 210882.9
|  |  | Total |  |  | 421989.9 | 5106
Estimate Uncertainty
The Estimate Uncertainty has been evaluated independently for each line items in accord with the standard sPHENIX Estimate Uncertainty guidelines. Contingencies spread over several items are weighted by item cost to determine a summary Estimate Uncertainty for each WBS entry. We have used guidance from ATLAS to set the FELIX board Estimate Uncertainty at 25% and all other components of the final DAM module production are set to 40% Estimate Uncertainty.

## Felix 1.5--Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.02.06.01 |  | TPC DAM Evaluation --FELIX 1.5 | [6 empty] | 1631
1.02.06.01 | 143700 | Develop TPC DAM prototype v1 Test Stand | [5 empty] | 1631
|  |  | Nexys Video Artix-7 FPGA: Trainer Board | Digilent, Inc. | 490 | DELIVERED
|  |  | FELIX v1.5 Prototype PCIe card | ATLAS DAQ Group | 0 | DELIVERED | Borrowed device
|  |  | DAQ server | PHENIX DAQ Group | 0 | DELIVERED | Borrowed device
|  |  | 2x 48-fiber MTP to 12-fiber breakout cables | Computer Crafts Inc. | 436 | DELIVERED | Quote
|  |  | 12-fiber MTP/MPO - LC Cassettes | Computer Crafts Inc. | 137 | DELIVERED | Quote
|  |  | 6x LC duplex fiber | Computer Crafts Inc. | 68 | DELIVERED | Quote
|  |  | Peripheral accessories and cables | Many | 500 | DELIVERED | Actual cost
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.06.01 | 143600 | Develop TPC DAM prototype v1 Test Stand | Similar to STAR ITS Upgarde | PROF | 160 | 320
|  |  |  | TECH | 160
1.02.06.01 | 143800 | Measure TPC DAM prototype v1 Throughput | Similar to PHENIX DAQ tests | PROF | 240 | 480
|  |  |  | TECH | 240
1.02.06.01 | 143500 | Write Design Spec for TPC DAM prototype v1 | Similar to STAR ITS Upgrade | PROF | 62 | 177
|  |  |  | SCI | 53
|  |  |  | TECH | 62
|  | Grand Total |  |  | 977 | 977 | This entire WBS has been collected into FY17/FY18 Actuals in the RLS
because the work has been completed

## Felix 2.0--Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total |  | Unit Price | P6 Feb 2019
1.02.06.02 |  | TPC DAM Evaluation -- FELIX 2.0 | [6 empty] | 78962.61 |  |  | 76524
1.02.06.02 |  | Procure FELIX 2.0 board for TPC DAM | [5 empty] | 13953.06 |  | Removed from sum; completed in FY2018 |  | Probably before P6 baseline
|  |  | FELIX v2.0 Pre-Production PCIe cards | BNL ATLAS DAQ Group | 7855.06 | DELIVERED
|  |  | 4U rack servers | Microway | 6098 | DELIVERED
1.02.06.02 | 145700 | Procure TPC DAM Felix 2.0 boards (DAQ THROUGHPPUT TEST) | 10 |  |  |  |  | 73523.5 |  |  | 7352.35 | 75000
|  |  | Field programing gate arrays, Xilinx (XLX), XCKU115-2FLVF1924E | AVNET | 33370 | Pending | Quote: AVNET 701913858 |  |  |  | 3337
|  |  | PCB | TTM Technologies | 6855.1 | Pending | Quote: TTM 602848-0 |  |  |  | 685.51
|  |  | MiniPOD Transmitter, AFBR-814FH1Z | AVNET | 7899.6 | Pending | AVNET Web Quote Feb 2018 |  |  |  | 789.96
|  |  | MiniPOD Receiver, AFBR-824FH1Z | AVNET | 5183.6 | Pending | AVNET Web Quote Feb 2018 |  |  |  | 518.36
|  |  | Small Components for FELIX | Digikey/Mouser | 8519.8 | Pending | Recent production cost of same board by the BNL ATLAS Group |  |  |  | 851.98
|  |  | Assembly | AA-Tech | 8225 | Pending | Recent production cost of same board by the BNL ATLAS Group |  |  |  | 822.5
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | Computer Crafts Inc. | 1782 | Pending | Quote: CCI/1000681-L |  |  |  | 178.2
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | Computer Crafts Inc. | 1688.4 | Pending | Quote: CCI/1000681-S |  |  |  | 168.84
1.02.06.02 | TBD | Procure Full Set of Data Fiber for Design Validation | 2 |  |  |  |  | 2875.76 |  | Activity to be added to P6 | 1437.88 | Combined to above
|  |  | 48-fiber MTP (F)-MTP (F) on OM3 cable, Polarity straight, 3m | Computer Crafts Inc. | 406.4 | Pending | Quote: CCI/T40408PF48-003 |  |  |  | 203.2
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 58m | Computer Crafts Inc. | 1086.4 | Pending | Quote: CCI/T40418PF48-058 |  |  |  | 543.2
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 15m | Computer Crafts Inc. | 550.4 | Pending | Quote: CCI/T40418PF48-015 |  |  |  | 275.2
|  |  | 1U 19" 12 port MPO feedthru panel with 12X MPO couplers. | Computer Crafts Inc. | 85.2 | Pending | Quote: CCI/56348-MT |  |  |  | 42.6
|  |  | 48F MTP(M) - LC Hydra assembly 900um OM3 18" length | Computer Crafts Inc. | 296.6 | Pending | Quote: CCI/1000450-18I-48F |  |  |  | 148.3
|  |  | COUPLER LC/LC Duplex, Aqua, Zirconia Sleeve | Computer Crafts Inc. | 63.36 | Pending | Quote: CCI/F26268P302-001 |  |  |  | 31.68
|  |  | MTP Coupler | Computer Crafts Inc. | 9.8 | Pending | Quote: CCI/100106 |  |  |  | 4.9
|  |  | LC to LC duplex Uni-Boot, 2mm OM3 Aqua, 1 meter length | Computer Crafts Inc. | 377.6 | Pending | Quote: CCI/F26268P302-001 |  |  |  | 188.8
1.02.06.02 | 146300 | FPGA Algorithm development | [5 empty] | 2563.35 |  |  |  | 1524
|  |  | TPC timing distribution board prototype - PCB | Many | 200 | Pending | Experience
|  |  | TPC timing mezzanine prototype - PCB | Many | 100 | Pending | Experience
|  |  | SFP+ Optical TX/RX, 10cnt + 50% spare | Avnet | 763.35 | Pending | Catalog: AFBR-709DMZ |  |  |  |  | <- Reduced with new transceiver quote
|  |  | SMT Chip Resistor Capacitor | Digikey | 500 | Pending | Experience
|  |  | Peripheral accessories and cables | Many | 1000 | Pending | Experience |  |  |  |  | <- moved to here from 1st task
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.06.02 | 146200 | Develop TPC DAM FPGA Algorithm | Similar to STAR ITS Upgrade | PROF | 320 | 1831 | Check labor mix vs P6
|  |  |  | TECH | 384 |  | Check labor mix vs P6
|  |  |  | TECH | 384 |  | Check labor mix vs P6
|  |  |  | SCI | 743 |  | Check labor mix vs P6
1.02.06.02 | 146400 | Measure Throughput of FELIX 2.0 for TPC DAM | Similar to STAR ITS Upgrade | PROF | 48 | 148
|  |  |  | SCI | 100 |  |  |  | 36683.1
1.02.06.02 | 144800-- | Procure FELIX 2.0 board for TPC DAM - Provide Requirements to Procurement | Similar to STAR ITS Upgrade | PROF | 16 | 16 | Task left out when split procurement strings
1.02.06.02 | 146700 | Develop TPC DAM FPGA Algorithm - Round 2 | Similar to STAR ITS Upgrade | PROF | 630 | 1094
|  |  |  | SCI | 254
|  |  |  | STUD | 210
|  | Grand Total |  |  | 3089 | 3089
Fiber BOM
|  |  | Item | Part Number | Quantity | Unit price | Total Price
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | CCI/1000681-L | 30 | 178.2 | 5346
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | CCI/1000681-S | 30 | 168.84 | 5065.2
|  |  | 48-fiber MTP (F)-MTP (F) on OM3 cable, Polarity straight, 3m | CCI/T40408PF48-003 | 2 | 203.2 | 406.4
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 58m | CCI/T40418PF48-058 | 2 | 543.2 | 1086.4
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 15m | CCI/T40418PF48-015 | 2 | 275.2 | 550.4
|  |  | 1U 19" 12 port MPO feedthru panel with 12X MPO couplers. | CCI/56348-MT | 1 | 85.2 | 85.2
|  |  | 48F MTP(M) - LC Hydra assembly 900um OM3 18" length | CCI/1000450-18I-48F | 2 | 148.3 | 296.6
|  |  | COUPLER LC/LC Duplex, Aqua, Zirconia Sleeve | CCI/F26268P302-001 | 32 | 1.98 | 63.36
|  |  | MTP Coupler | CCI/100106 | 4 | 2.45 | 9.8
|  |  | LC to LC duplex Uni-Boot, 2mm OM3 Aqua, 1 meter length | CCI/F26268P302-001 | 32 | 11.8 | 377.6

## Production--Details
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total |  | P6-Feb Comparison
1.02.06.03 |  | Production | [6 empty] | 421989.9 | Unit price | 436902
1.02.06.03 | 147300 | Procure TPC DAM Felix 2.0 boards | 20 |  |  |  |  | 130362 |  | 7352.35 | 231001 | 211107
|  |  | Field programing gate arrays, Xilinx (XLX), XCKU115-2FLVF1924E | AVNET | 50055 | Pending | Quote: AVNET 701913858 |  |  | 3337 | Reduced with Xilinx donation
|  |  | PCB | TTM Technologies | 13710.2 | Pending | Quote: TTM 602848-0 |  |  | 685.51
|  |  | MiniPOD Transmitter, AFBR-814FH1Z | AVNET | 15799.2 | Pending | AVNET Web Quote Feb 2018 |  |  | 789.96
|  |  | MiniPOD Receiver, AFBR-824FH1Z | AVNET | 10367.2 | Pending | AVNET Web Quote Feb 2018 |  |  | 518.36
|  |  | Small Components for FELIX | Digikey/Mouser | 17039.6 | Pending | Recent production cost of same board by the BNL ATLAS Group |  |  | 851.98
|  |  | Assembly | AA-Tech | 16450 | Pending | Recent production cost of same board by the BNL ATLAS Group |  |  | 822.5
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | Computer Crafts Inc. | 3564 | Pending | Quote: CCI/1000681-L |  |  | 178.2
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | Computer Crafts Inc. | 3376.8 | Pending | Quote: CCI/1000681-S |  |  | 168.84
1.02.06.03 | 147370 | Optical data fiber and distribution | 30 |  |  |  |  | 80745 |  | 2691.5 | Included in last task
|  |  | 48-fiber MTP (F)-MTP (F) on OM3 cable, Polarity straight, 3m | Computer Crafts Inc. | 11520 | Pending | Quote: CCI/T40408PF48-003? |  |  | 384
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 58m | Computer Crafts Inc. | 30492 | Pending | Quote: CCI/T40418PF48-058? |  |  | 1016.4
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 15m | Computer Crafts Inc. | 15552 | Pending | Quote: CCI/T40418PF48-015? |  |  | 518.4
|  |  | 1U 19" 12 port MPO feedthru panel with 12X MPO couplers. | Computer Crafts Inc. | 852 | Pending | Quote: CCI/56348-MT |  |  | 28.4
|  |  | 48F MTP(M) - LC Hydra assembly 900um OM3 18" length | Computer Crafts Inc. | 8718 | Pending | Quote: CCI/1000450-18I-48F |  |  | 290.6
|  |  | COUPLER LC/LC Duplex, Aqua, Zirconia Sleeve | Computer Crafts Inc. | 2664 | Pending | Quote: CCI/F26268P302-001 |  |  | 88.8
|  |  | MTP Coupler | Computer Crafts Inc. | 147 | Pending | Quote: CCI/100106 |  |  | 4.9
|  |  | LC to LC duplex Uni-Boot, 2mm OM3 Aqua, 1 meter length | Computer Crafts Inc. | 10800 | Pending | Quote: CCI/F26268P302-001 |  |  | 360 | New Item
1.02.06.03 | 148400 | Procure TPC EDBC Computers and Peripherals | [5 empty] | 210882.9 |  |  | 205901
|  |  | 4U rack servers, 24cnt + 20% spare | Microway | 195000 | Pending | Quote: Aberdeen server
|  |  | TPC timing distribution board - PCB, 1cnt + 1 spare | Many | 400 | Pending | Experience
|  |  | TPC timing mezzanine - PCB, 24cnt + 20% spare | Many | 1440 | Pending | Experience
|  |  | SFP+ Optical TX/RX, 48cnt + 25% spare | Avnet | 2705.4 | Pending | Catalog: AFBR-709DMZ
|  |  | LC duplex fiber, 24cnt + 25% spare | Computer Crafts Inc. | 337.5 | Pending | Quote: CCI/F26268P302-001
|  |  | SMT Chip Resistor Capacitor | Digikey | 1000 | Pending | Experience
|  |  | Peripheral accessories and cables | Many | 10000 | Pending | Experience
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.02.06.03 | 147400 | Perform QA Testing on TPC DAM FELIX 2.0 boards | Similar to STAR ITS Upgrade | TECH | 264 | 755
|  |  |  | PROF | 44
|  |  |  | STUD | 220
|  |  |  | SCI | 227
1.02.06.03 | 146600 | Procure TPC DAM Felix 2.0 boards - Provide Requirements to Procurement | Similar to STAR ITS Upgrade | PROF | 300 | 570
|  |  |  | TECH | 240
|  |  |  | SCI | 30
1.02.06.03 | 147310 | Procure TPC DAM Felix 2.0 Optical Components - Provide Requirements to Procurement | Similar to STAR ITS Upgrade | PROF | 300 | 570
|  |  |  | TECH | 240
|  |  |  | SCI | 30
1.02.06.03 | 147500 | TPC DAM Felix 2.0 Bandwidth test in 1008 | Similar to PHENIX muon tracker system | PROF | 320 | 387 |  |  |  |  | <- Need to move in P6
|  |  |  | SCI | 67
1.02.06.03 | 147700 | Develop TPC DAM FPGA Algorithm - Round 3 (Planning package) | Similar to PHENIX Event Builder | PROF | 120 | 504
|  |  |  | STUD | 220
|  |  |  | SCI | 164
1.02.06.03 | 147800 | Procure of TPC EDBC Computers and Peripherals - Provide Requirements to Procurement | Similar to PHENIX Event Builder | PROF | 192 | 480
|  |  |  | TECH | 144
|  |  |  | SCI | 144
1.02.06.03 | 148500 | Test Full TPC DAM System | Similar to multiple DAQ stress tests in PHENIX | PROF | 960 | 1840
|  |  |  | SCI | 880
|  | Grand Total |  |  | 5106 | 5106
Fiber BOM
|  |  | Item | Part Number | Quantity | Used | Spare | Unit price | Total Price
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | CCI/1000681-L | 30 | 24 | 6 | 178.2 | 5346
|  |  | MTP-48(M) to 4 x PRIZM-12 Fiber Assembly | CCI/1000681-S | 30 | 24 | 6 | 168.84 | 5065.2
|  |  | 48-fiber MTP (F)-MTP (F) on OM3 cable, Polarity straight, 3m | CCI/T40408PF48-003? | 60 | 48 | 12 | 192 | 11520
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 58m | CCI/T40418PF48-058? | 60 | 48 | 12 | 508.2 | 30492
|  |  | 48-fiber MTP (F)-MTP (M) on OM3 cable, Polarity straight, 15m | CCI/T40418PF48-015? | 60 | 48 | 12 | 259.2 | 15552
|  |  | 1U 19" 12 port MPO feedthru panel with 12X MPO couplers. | CCI/56348-MT | 10 | 8 | 2 | 85.2 | 852
|  |  | 48F MTP(M) - LC Hydra assembly 900um OM3 18" length | CCI/1000450-18I-48F | 60 | 48 | 12 | 145.3 | 8718
|  |  | COUPLER LC/LC Duplex, Aqua, Zirconia Sleeve | CCI/F26268P302-001 | 1440 | 1152 | 288 | 1.85 | 2664
|  |  | MTP Coupler | CCI/100106 | 60 | 48 | 12 | 2.45 | 147
|  |  | LC to LC duplex Uni-Boot, 2mm OM3 Aqua, 1 meter length | CCI/F26268P302-001 | 960 | 768 | 192 | 11.25 | 10800