## Navigation
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  |  | L3 Project Name (Control Account) |  | L3 WBS Number
sPHENIX Infrastructure (click to see WBS structure for this Subsystem) |  | 2.03 |  |  | Detector Mechanical Systems |  | 2.03
Instructions: How to use this document
| Work Package Name |  | WBS Number |  |  | Basis of Estimate Link
| Cradle Carriage Work Package |  | 2.03.01 |  |  | Go To BoE
| Internal Detector Structural Support Work Package |  | 2.03.02 |  |  | Go To BoE
| Barrel Steel/OHCal Sectors |  | 2.03.03 |  |  | Go To BoE
| End Caps/ Pole Tips Work Package |  | 2.03.04 |  |  | Go To BoE
| Cradle Carriage Bridge, Mid Platforms and Access Work Package |  | 2.03.05 |  |  | Go To BoE
Description of this Control Account:
Document Control
Version | Date | Author(s)
1 | 2017-05-19 | D. Lynch
2 | 2017-07-27 | D. Lynch
3 | 2017-08-03 | D. Lynch
4 | 2018-02-09 | D. Lynch, P. Giannotti |  | Updated to include corrections and renumbering in P6
5 | 2018-02-17 | D. Lynch, P. Giannotti |  | Updated to change from fte-days to hours and correct errors
6 | 2019-03-19 | C. Pontieri, J. Hock, J. Mills |  | Updated sections 2.03.01.01, 0.02, 0.03, .04, .05

## Infrastructure Acct Structure
| Subsystems | 2.03 & 2.04: Infrastructure
| Control Accounts | 2.03: Detector Mechanical Systems | 2.04.01: Detector Support Systems | 2.04.02: Facility Support Systems
|  |  | (See WBS 2.04.01 BoE for Work Packages in above Control Account) | (See WBS 2.04.02 BoE for Work Packages in above Control Account)
| Work Packages | 2.03.01: Cradle Carriage Work Package
2.03.02 : Internal Detector Structural Support Work Package
2.03.03 : Outer HCal Steel Sectors Ready for Electronics
2.03.04: End Caps/ Pole Tips Work Package
2.03.05: Cradle Carriage Bridge, Mid Platforms and Access Work Package
Return to Navigation Page

## BoE for Detector Mech Sys
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2018-02-17
[7 empty] | Prepared By: | Don Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  |  | WBS number: |  |  | Control Account
Detector Mechanical Systems |  |  |  |  | 2.03 |  |  | TBD
Return to Navigation Page
WBS Dictionary Definition:
Technical Scope: WBS 2.03.01 is the Control Account for all scientific, engineering and technical staff efforts to plan and supervise all aspects of the design, fabrication and assembly of the sPHENIX infrastructure components associated with sPHENIX facility Cradle Carriage, structural support, Magnet Barrel Steel/OHCal Sectors, Magnet Pole Tips and Platforms: 1. Cradle Carriage 2. Internal detector structural supports. (includes the structural support mounting and positional alignment features for the Inner HCal/EMCal, superconducting solenoid, TPC, INTT, MVTX and Min Bias detector subsystems) 3. Magnet Barrel Steel/Outer HCal Steel Sectors 4. Flux return end caps/pole tips and related mounting components 5. Upper (bridge), intermediate and lower carriage work platforms and access (stairs) on the cradle carriage Work Statement: The assembly of the cradle carriage and actual installation of these components and equipment will take place at the sPHENIX experiment complex at building 1008 (in the asembly hall) and is covered in the sPHENIX 2.05.01 control account. There are 4 work packages included in this control account where the actual work is defined for these items. Each work package has its own separate Basis of Estimate (BoE) document elsewhere in this workbook. These documents can be accessed from the Navigation page in this workbook. (see link below).
Estimate Type (check all that apply):
Work Complete
| x | Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this control account)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials as described above, to support the sPHENIX detector subsystems. 3. The detector subsystems and magnet which are supported by the structural equipment detailed in the work packages for this Control Acount are themselves detailed in their own subsystem, control account and work packages. *See WBS items 1.01 through 1.07, 2.0 2, 3.01 and 3.02. Installation on of these subsystems and integration with the carriage cradle and other structural components described herein are detailed in WBS 2.05.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of structural equipment and components as indicated in the "Dictionary Definition" section above. 2. Procured material costs detailed to the appropriate level for the current state of design for these items. 2. All labor for installation of these structural components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
| 2.03.01 |  | Cradle Carriage Work Package |  |  | 1286860.1485
| 2.03.02 |  | Internal Detector Structural Support Work Package |  |  | 273890
| 2.03.03 |  | Outer HCal Steel Sectors Ready for Electronics |  |  | 4698773.85
| 2.03.04 |  | End Caps/ Pole Tips Work Package |  |  | 616612.25
| 2.03.05 |  | Cradle Carriage Bridge, Mid Platforms and Access Work Package |  |  | 320659.4683
|  | Total Procurements Cost [2019 dollars, no overhead or estimate uncertainty added] for the WBS #2.03: Detector Mechanical Systems Control Account |  |  |  | 7196795.7167

## BoE for Cradle Carriage
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2018-02-17
Prepared By:
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS Number: |  | Control Account Number
Cradle Carriage Work Package |  |  |  | 2.03.01 |  | TBD
Return to Navigation Page
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to analyze the requirements for an integrated support ("Cradle Carriage") system which will support all of the sPHENIX experimental detector subsystems and the effort required to fully design the system. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are also in the scope of this work package. Design and analyses, procurement etc., for the equipment and components which comprise the susbsyetms supported by this Cradle carriage are not in the scope of this work package but rather in the scope of the work packages and control accounts associated with those subsystems. (See WBS 1.02 through 1.07, 2.02, 3.01 and 3.02 for more detailed information about those control accounts and work packages.) Work Statement: This work package includes the following tasks/activities: 1. Evaluate the requirements for the structural integrity, accuaracy, stability and repeatability for the carriage with respect to the direct support of the Outer HCal and the indirect support of the other detector and support subsystems. 2. Prepare appropriate drawings and related documenation 3.Review the design; make appropriate modifications per review recommendations 4. Procure equipment needed to implement this design. 5. Deliver the equipment to building 1008 the sPHENIX complex ready to be installed. (Note: actual assembly and installation of these components and equipment is covered under sPHENIX WBS 2.05.01)
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
| x | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this control account)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials as described above, to support the sPHENIX detector subsystems. 3. The detector subsystems and magnet which are supported by the structural equipment detailed in the work packages for this Control Acount are themselves detailed in their own subsystem, control account and work packages. *See WBS items 1.01 through 1.07, 2.02, 3.01 and 3.02. Installation on of these subsystems and integration with the carriage cradle and other structural components described herein are detailed in WBS 2.05.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of structural equipment and components as indicated in the "Dictionary Definition" section above. 2. Procured material costs detailed to the appropriate level for the current state of design for these items. 2. All labor for assembly and installation of these structural components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for assembly and installation of the cradle are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for Cradle assembly and installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $1,286,860

## BoE for Int Struct Support
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2018-04-06
[5 empty] | Prepared By: | Don Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  | Control Account
Internal Detector Structural Support Work Package |  |  |  | 2.03.02 |  | TBD
Return to Navigation Page
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to analyze the requirements for an integrated support system which will support all of the sPHENIX experimental detector subsystems not directly supported by the cradle carriage and the effort required to fully design the system. The analyses required to determine the components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are also in the scope of this work package. Design and analyses, procurement etc., for the equipment and components which comprise the susbsystems supported by these support structures are not in the scope of this work package nor is the cradle carriage, support for end caps/pole tips, nor structures supporting and/or comprising the work platforms and access but rather in the scope of the work packages and control accounts associated with those subsystems. (See WBS 1.02 through 1.07, 2.02 and 3.01 through 3.02 and work packages 2.03.01.01, 2.03.01.03, 2.03.01.04 and 2.03.01.05 in this control account for more detailed information about those control accounts and work packages.) Work Statement: This work package includes the following tasks/activities: 1. Evaluate the requirements for the structural integrity, accuaracy, stability and repeatability for the carriage with respect to the support of the sPHENIX superconducting solenoid magnet, and inner detector subsystems (Inner HCal , EMCal, TPC, INTT, MVTX and Min Bias) and inner detector subsystem utilities support. 2. Prepare appropriate drawings and related documenation 3. Review the design; make appropriate modifications per review recommendations 4. Procure equipment needed to implement this design. 5. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.01)
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the cost estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials as described above, to support the sPHENIX detector subsystems. 3. Installation of the subsystem support structure described herein and integration with the Outer HCal, Cradle Carriage and other structural components described herein are detailed in WBS 2.05.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of structural equipment and components as indicated in the "Dictionary Definition" section above. 2. Procured material costs detailed to the appropriate level for the current state of design for these items. 2. All labor for assembly and installation of these structural components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $273,890

## BoE for OHCal Steel
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2018-04-06
[5 empty] | Prepared By: | Don Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  | Control Account
Outer HCal Steel Sectors Ready for Electronics |  |  |  | 2.03.03 |  | TBD
Return to Navigation Page
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to design, review, procure, inspect and stow the 32 modular steel sectors for the sPHENIX Outer HCal. This includes only the steel for the sectors which form the structural enclosure for the sPHENIX superconducting solenoid magnet and the detectors which reside inside the magnet and inside the steel sectors. These sectors when assembled into their final configuration also comprise the energy absorbing dense material of the Outer HCal and serve as the major portion of the sPHENIX superconducting magnet flux return. Also included in this work package is the review and procurement of a lifting fixture and sector assembly and storage supports. Work Statement: This work package includes the following tasks/activities: 1. Provide procurement specs for full sector prototype & full sector production options 2. Solicit bids, select vendor and award contract for full sector prototype & full sector production options 3. Recieve prototype evaluate and redesign to final configuration 4. Design and procurement reviews for final detector option 5. Address Issues from design and procurement reviews 6. Exercise option and procure 32 Outer HCal steel sectors ready to be outfitted with electronics 7. Design, review and procure lifting fixtures, acceptance test equipment 8. First article and remaining production acceptance testing
Estimate Type (check all that apply):
Work Complete
| x | Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the cost estimate for this Work Package)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials as described above, to support the sPHENIX detector subsystems. 3. Installation of the subsystem support structure described herein and integration with the Outer HCal, Cradle Carriage and other structural components described herein are detailed in WBS 2.05.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of structural equipment and components as indicated in the "Dictionary Definition" section above. 2. Procured material costs detailed to the appropriate level for the current state of design for these items. 2. All labor for assembly and installation of these structural components and equipment is covered by WBS 1.04 (Hadronic Calorimeters) or WBS 2.05 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by Those WBS subsystems.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for Outer HCal sector steel tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $4,698,774

## BoE for End Caps_Pole Tips
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2018-02-17
[5 empty] | Prepared By: | Don Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  | Control Account
End Caps/ Pole Tips Work Package |  |  |  | 2.03.04 |  | TBD
Return to Navigation Page
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to analyze the requirements for the sPHENIX superconducting solenoid magnet end caps/pole tips. The analyses required to determine the structural support components and equipment needed, the design, procurement and acceptance of such equipment and reviews of these analyses are also included in this work package. Magnetic analyses, the superconducting solenoid magnet itself, and all other magnet support equipment and services are not part of this work package. (See WBS 2.02 for more detailed information about those work packages.) Work Statement: This work package includes the following tasks/activities: 1. Evaluate the requirements for the sPHENIX superconducting solenoid magnet end caps/pole tips and related mounting hardware. 2. Prepare appropriate drawings and related documenation 3. Review the design; make appropriate modifications per review recommendations 4. Procure equipment needed to implement this design. 5. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05)
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this control account)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible. 2. Labor estimates are for analyses, design and procurement of infrastructure materials as described above, to support the sPHENIX detector subsystems. 3. Installation of the subsystem support structure described herein and integration with the Outer HCal, Cradle Carriage and other structural components described herein are detailed in WBS 2.05.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of end cap/pole tips material fabrication and components as indicated in the "Dictionary Definition" section above. 2. Procured material costs detailed to the appropriate level for the current state of design for these items. 2. All labor for assembly and installation of these components is covered by WBS 2.05.2 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.2.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $616,612

## BoE for Bridge, Platforms, etc
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  | Date of Est: | 2018-02-17
[5 empty] | Prepared By: | Don Lynch
DocNo. (refer Rev. Log)
WBS Title: |  |  |  | WBS number: |  | Control Account
Cradle Carriage Bridge, Mid Platforms and Access Work Package |  |  |  | 2.03.05 |  | TBD
Return to Navigation Page
WBS Dictionary Definition:
Technical Scope: This work package includes all scientific, engineering and technical staff efforts to analyze the requirements for the work platforms and access to these work platforms on the sPHENIX cradle carriage. Design and analyses, procurement etc., for the equipment and components which comprise the work platforms and access are also in the scope of this work package. Design and analyses, procurement etc., for the equipment and components which comprise the cradle carriage itself and the various subsystems components and equipment that are to be mounted on the work platforms are not in the scope of this work package, but rather in the scope of the work packages and control accounts associated with those subsystems. (See the BoE documents in WBS 1.02 through 1.07 and 2.02, 3.01 and 3.02 and 2.03.01.01 through 2.03.01.04 in 2.03 for more detailed information about those control accounts and work packages.) Work Statement: This work package includes the following tasks/activities: 1. Evaluate the requirements for the safe, efficient and effective allocation of space for magnet cryo, electrical and control equipment, electronic power, monitoring and service racks and patch panels, access and egress and all other related concerns. 2. Prepare appropriate drawings and related documenation 3. Review the design; make appropriate modifications per review recommendations 4. Procure equipment needed to implement this design. 5. Deliver the equipment to building 1008 the sPHENIX complex ready to be install. (Note: actual installation is covered under sPHENIX WBS 2.05.01)
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
(click here to see the details of the labor and material estimate for this work package)
Assumptions Used in Developing Estimate
1. Reuse of existing materials and equipment from PHENIX removal and repurposing (R&R) efforts wherever possible, most notably for reuse of the bridge platform and other platforms, ladders and stairs used in/on the PHENIX detector carriages. 2. Labor estimates are for analyses, design and procurement of infrastructure materials as described above, to support the sPHENIX detector subsystems. 3. Installation of the subsystem support structure described herein and integration with the Outer HCal, Cradle Carriage and other structural components described herein are detailed in WBS 2.05.
Details of the Base Estimate (explanation of the Work)
This estimate covers the labor and material cost estimates for the following: 1. Labor involved in planning, design and procurement of structural equipment and components as indicated in the "Dictionary Definition" section above. 2. Procured material costs detailed to the appropriate level for the current state of design for these items. 2. All labor for assembly and installation of these structural components and equipment is covered by WBS 2.05.01 (Integration and Installation). Supplies, fixtures, tooling and related materials used only for installation of these items are also covered by WBS 2.05.01.
Cost Summary
Cost summary for this work package is limited to hardware and installation specific tooling and fixtures for infrastructure installation tasks as indicated in the "Dictionary Definition" section above.
Total unburdened material cost for this work package = $320,659

## Procurement $ by Work Package
WBS # | WBS Title | Work Package Procurements (Total) (includes purchased parts, Central Shops fabricated parts, contract labor. Does not include BNL labor other than Central Shops fabrication.) $ | NOTES/LINKS
2.03.01 | Cradle Carriage Work Package | 1286860.1485
2.03.02 | Internal Detector Structural Support Work Package | 273890
2.03.03 | Outer HCal Steel Sectors Ready for Electronics | 4698773.85
2.03.04 | End Caps/ Pole Tips Work Package | 616612.25
2.03.05 | Cradle Carriage Bridge, Mid Platforms and Access Work Package | 320659.4683
| Total Procurements Cost [2017 dollars, no overhead or estimate uncertainty added] for the WBS #Detector Mechanical Systems: Account/Work Package/Tasks/Activities Control Account | 7196795.7167
Return to Navigation Page

## Infrastructure Control Account
Return to Navigation Page
WBS # (CLICK ON WORK PACKAGE WBS# TO SEE WORK PACKAGE DETAILS) | 2.03
Detector Mechanical Systems
Account/Work Package/Tasks/Activities
2.03 | Detector Mechanical Systems
2.03.01 | Cradle Carriage Work Package | Refer to Work Package
2.03.02 | Internal Detector Structural Support Work Package | Refer to Work Package
2.03.03 | Outer HCal Steel Sectors Ready for Electronics | Refer to Work Package
2.03.04 | End Caps/ Pole Tips Work Package | Refer to Work Package
2.03.05 | Cradle Carriage Bridge, Mid Platforms and Access Work Package | Refer to Work Package

## Int Struct Support Work Package
Return to Navigation Page
WBS # | 2.03.02 | Task/Activity Description | Duration (d) | Administrator ADMIN1 PO |  | Scientist |  | Scientist (hrs) |  |  |  | Engineer |  | Engineer/Professional (hrs) |  |  |  |  | Designer |  | Designer/Drafter (hrs) | [6 empty] | Technician |  | Technicians (hrs) | [9 empty] | Trade |  | Bargaining Unit Trades (hrs) | [5 empty] | Student (unpaid) |  | Materials and Supplies $ |  | RISK CODE/% |  |  | NOTES |  | Labor Description/Risk Code | Material Description/Risk Code |  | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Internal Detector Structural Support Work Package | [6 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  |  |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  |  |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  |  |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  |  |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [13 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students |  |  | Total Material Cost with estimate uncertainty
| TASK/ACTIVITY |  |  | hrs |  | hrs |  | Scientist | Scientist | Scientist |  | hrs | [6 empty] | hrs | [8 empty] | hrs | [11 empty] | hrs | [7 empty] | hrs |  |  |  | Labor | Material | [6 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
S316400/S316410 | Analyze and Evaluate Structural Support for Internal Detectors | Technical Scope: All tasks related to the physical, structural and performance analyses of the Structural Support for sPHENIX Internal Detectors. This includes the structural support and alignment requirements for all detector subsystems except the Outer HCal (see 2.03.01.01 for Structural support and alignment of the Outer HCal). Work Statement: Gather load info from all subsystems, create an FEA model from the layout, iterate on design features to minimize stresses and optimize load capacity and space utilization. Take into account static, dynamic and magnetic loads. Make sure adequate safety margins are maintained for worst case and design loading cases. | 44 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 120 | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 120 | 32 | 24 | 0 | 0 | 0 | 0 | 12516 | 2595.2 | 1946.4 | 0 | 0 |  |  | 0
S316500/S316510 | Create Internal Detector Structural Support Assembly Drawings | Technical Scope: All tasks related to the creation of assembly drawings for the structural support and alignment of all sPHENIX detectors radially inside the Outer HCal. Work Statement: Starting from the layout and envelope drawings and guided by the results of the engineering analyses for structural and space utilization optimization, create assembly drawings with appropriate references to all subassemblies and detail components. | 40 | 0 |  | 0 |  | 0 | 0 | 0 |  | 64 |  | 64 | 0 | 0 | 0 |  | 60 |  | 60 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 6675.2 | 4866 | 0 | 0 | 0 |  |  | 0
S316600/S316610 | Create Internal Detector Structural Support Detail Drawings | Technical Scope: All tasks related to the creation of all subassembly and detail drawings as required to fully define the design of all features and all components of the structural support and alignment for the structural support and alignment of all sPHENIX detectors radially inside the Outer HCal. Work Statement: Starting from the layout and envelope drawings and guided by the results of the engineering analyses for structural and space utilization optimization, create sub assembly and detail component drawings of the structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 48 |  | 48 | 0 | 0 | 0 |  | 50 |  | 50 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 48 | 50 | 0 | 0 | 0 | 0 | 0 | 5006.4 | 4055 | 0 | 0 | 0 |  |  | 0
S316700/S316710 | Review Internal Detector Structural Support Safety | Technical scope: preparation for and execution of safety review of the structural support and alignment of all sPHENIX detectors radially inside the Outer HCal for compliance with all relevant safety requirements. Work Statement: gather documentation describing the design, assembly and installation of the structural support and alignment of all sPHENIX detectors radially inside the Outer HCal. Prepare a presentation describing this design and how it implements all relevant safety requirements. Present to a panel determined by sPHENIX engineering and management. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 834.4 | 324.4 | 324.4 | 0 | 0 |  |  | 0
S316800/S316810 | Review Internal Detector Structural Support Design | Technical scope: preparation for and execution of review for engineering design of sPHENIX Cradle Carriage for compliance with all relevant design requirements. Work Statement: gather documentation describing the design, assembly and installation of the sPHENIX Cradle Carriage. Prepare a presentation describing this design and how it implements all relevant design requirements. Present to a panel determined by sPHENIX engineering and management. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 16 | 8 | 4 | 0 | 0 | 0 | 0 | 1668.8 | 648.8 | 324.4 | 0 | 0 |  |  | 0
S316900/S316910 | Address Action Items from Internal Detector Structural Support Design & Safety Reviews | Technical scope: evaluation and implementation of recommendations from structural support and alignment of all sPHENIX detectors radially inside the Outer HCal engineering and safety reviews. Work Statement: receive action items from reviewers, evaluate action items, implement changes, modifications to plans and equipment to appropriately satisfy each action item. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 |  | 20 |  | 20 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 40 | 20 | 0 | 0 | 0 | 0 | 0 | 4172 | 1622 | 0 | 0 | 0 |  |  | 0
S317000 | Design/Safety Reviews Complete, Internal Detector Structural Support Released for Production | Milestone | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
S317100/S317110 | Prepare Procurement Package(s) for Internal Detector Structural Support | Technical Scope: Develop the procurement packages for components of structural support and alignment of all sPHENIX detectors radially inside the Outer HCal Work Statement: gather all relevant information from existing documentation of structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal.. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 120 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 120 | 24 | 24 | 0 | 0 | 0 | 0 | 12516 | 1946.4 | 1946.4 | 0 | 0 |  |  | 0
S317200/S317210 | Evaluate & Process Bid for Internal Detector Structural Support | Technical Scope: Evaluation of structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal bid documents. Work Statement: Prepare bid documents for structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal; initiate procurement of components. | 20 | 0 |  | 0 |  | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 32 | 16 | 16 | 0 | 0 | 0 | 0 | 3337.6 | 1297.6 | 1297.6 | 0 | 0 |  |  | 0
S317300/S317310 | Procure & Deliver Internal Detector Structural Support (leadtime and fabrication included) | Technical Scope: Procurement and delivery of structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal. Work Statement: Monitor and manage procurement process for structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal. | 120 | 0 |  | 0 |  | 0 | 0 | 0 |  | 192 |  | 192 | 0 | 0 | 0 |  | 96 |  | 96 | 0 | 0 | 0 | 0 | 0 |  | 96 |  | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29 |  | 0 | 0 | 29 | 0 | 0 |  | 0 |  | 273890 |  | 25% | 40% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | Design is conceptual/M5 |  | 0 | 0 | 192 | 96 | 96 | 29 | 0 | 0 | 0 | 20025.6 | 7785.6 | 7785.6 | 3291.21 | 0 |  |  | 383446
S318000/S318010 | Perform Internal Detector Structural Support Acceptance | Technical Scope: Performance of Acceptance Tests for structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal. Work Statement: receive, inspect and accept the structural support and alignment components of all sPHENIX detectors radially inside the Outer HCal. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 |  | 20 |  | 20 | 0 | 0 | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 25% | 0% |  |  |  | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 |  | 0 | 0 | 16 | 20 | 8 | 0 | 0 | 0 | 0 | 1668.8 | 1622 | 648.8 | 0 | 0 |  |  | 0
S318100 | Internal Detector Structural Support Components Ready for Installation |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S317400 | Procure Internal Detector Structural Support-Provide requirements to Procurement |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S317500 | Procure Internal Detector Structural Support- Prepare and Send Solicitation |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S317600 | Procure Internal Detector Structural Support- Vendor Response and Selection |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S317700 | Procure Internal Detector Structural Support- Contract Award |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S317800 | Procure Internal Detector Structural Support- Leadtime |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S317910 | Procure Internal Detector Structural Support-Delivery Acceptance |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0% | 0% |  |  |  | n/a | n/a |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S318100 | Internal Detector Structural Support Components Ready for Installation | Milestone | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Materials and Supplies Details | [57 empty] | Resource summary for this work package resource requirements in Hours by Resource Category |  | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
[60 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Labor w/estimate uncertainty | Total material w/estimate uncertainty | Total Material | Effective Labor estimate uncertainty for this Work Package | Effective Material estimate uncertainty for this Work Package
WBS | Description | Item | Vendor |  |  | QTY | QTY | Unit Cost | Total | Status |  | Basis of Estimate |  | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total |  | estimate uncertainty |  | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [34 empty] | 0 | 0 | 656 | 330 | 176 | 29 | 0 | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 0 | 0 | 383446 | 273890 | #DIV/0! | 40%
[67 empty] | 0 | 0 | 68420.8 | 26763 | 14273.6 | 3291.21 | 0
S317900 | Procure & Deliver Internal Detector Structural Support (leadtime and fabrication included) | [7 empty] | 273890
|  | Inner HCal Mechanical Support | [6 empty] | 45850 |  |  | EA
|  | EMCal Mechanical Support | [6 empty] | 18040 |  |  | EA
|  | Magnet Mechanical Support | [6 empty] | 50000 |  |  | EA
|  | TPC/Tracker Mechanical Support | [6 empty] | 50000 |  |  | EA
|  | INTT Mechanical Support | [6 empty] | 50000 |  |  | ROM
|  | MVTX Mechanical Support | [6 empty] | 50000 |  |  | ROM
|  | Min Bias Mechanical Support | [6 empty] | 10000 |  |  | EA
Labor Estimate Details
WBS | Description | Step | Duration | Resource |  |  | QTY | Qty (Repeats) | Total | Status |  | Basis of Estimate |  | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total |  | estimate uncertainty |  | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes
2137.606
Component | Quantity | Cost Factor | Weight | Total |  |  |  | Source | Spec Sheet
Inner HCal Support | 2 | 5 | 4585.097 | 45850.97 |  |  |  | ROM | N/A
EMCal Support | 64 | 281.88 | N/A | 18040.32 |  |  |  | Quote | WS-10-120
Magnet Support |  |  |  | 50000 |  |  |  | ROM | N/A
TPC/Tracker Support |  |  |  | 50000 |  |  |  | ROM | N/A
INTT Mechanical Support |  |  |  | 50000
MVTX Mechanical Support |  |  |  | 50000
Min Bias Mechanical Support |  |  |  | 10000

## Cradle Carriage Work Package
Return to Navigation Page
Activity ID | 2.03.01 | Task/Activity Description | Duration (d) | Administrator ADMIN1 PO |  | Scientist |  | Scientist (hrs) |  |  |  | Engineer |  | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | NOTES | Hours for each Resource Category by WBS#
| Cradle Carriage Work Package | [6 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  |  |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 |  |  |  | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
| TASK/ACTIVITY |  |  | hrs |  | hrs |  | Scientist | Scientist | Scientist |  | hrs | [5 empty] | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs
S309800/S309810 | Carriage Cradle - Perform Analyses, Design & System Integration (Final) | Technical Scope: All tasks related to the design of of the sPHENIX cradle carriage layout. Work Statement: gather all relevant information and analyze requirements, calculate performance , create layout drawing. | 41 | 0 |  | 0 |  | 0 | 0 | 0 |  | 250 |  | 250 | 0 | 0 | 0 | 328 | 164 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 250 | 328 | 0 | 0 | 0
S310000/S310010 | Carriage Cradle - Create Assembly & Detail Drawings | Technical Scope: All tasks related creating carriage assembly and detail drawings. Work Statement: Under engineering guidance create a package of drawings to fully define the carriage cradle. | 186 | 0 |  | 0 |  | 0 | 0 | 0 |  | 440 |  | 440 | 0 | 0 | 0 | 960 | 480 | 0 | 0 | 480 | 0 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 440 | 960 | 64 | 0 | 0
S310100/S310110 | Carriage Cradle - Final Review (Design & Safety) | Technical Scope: All tasks related to the design and safety review of the carriage cradle. Work Statement: Review all aspects of the proposed design for the carriage cradle | 10 | 0 |  | 8 |  | 0 | 8 | 0 |  | 120 |  | 120 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8 | 120 | 80 | 8 | 0 | 0
S310200/S310210 | Carriage Cradle - Address Action Items from Design & Safety Reviews | Technical Scope: All tasks related to addressing issues raised during the design and safty review. Work Statement: Revisit design calculations, revise designs and drawings as necessary to satisfy issues raised during design and safety review. | 15 | 0 |  | 8 |  | 0 | 8 | 0 |  | 120 |  | 120 | 0 | 0 | 0 | 120 | 60 | 0 | 0 | 60 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 8 | 120 | 120 | 8 | 0 | 0
S310400/S310410 | Carriage Cradle - Prepare Procurement Package(s) | Technical Scope: All tasks related to the preparation of procurement documents for the cradle carriage. Work Statement: Create statement of work, design specifications and RFQ drawing package to support procurement effort. | 20 | 0 |  | 0 |  | 0 | 0 | 0 |  | 44 |  | 44 | 0 | 0 | 0 | 48 | 24 | 0 | 0 | 24 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 44 | 48 | 24 | 0 | 0
S310900/S310910 | Carriage Cradle - Vendor Selection | Technical scope: All tasks related to selection of a endor to fabricate the cradle carriage. Work Statement: Review Vendor propsals, rate and select an appropriate vendor. | 40 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 72 | 36 | 0 | 0 | 36 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 40 | 72 | 72 | 0 | 0
S311100/S311110 | Carriage Cradle - BNL Oversight | Technical scope: All tasks related to documentation review and control for cradle carriage engineering and procurement documents. Work Statement: Release drawings for review, check, engineering, safety, QA and management review of documents | 180 | 0 |  | 0 |  | 0 | 0 | 0 |  | 80 |  | 80 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 80 | 20 | 40 | 0 | 0
S311350/S311300/S311310 | Carriage Cradle - Delivery Acceptance | Technical scope: All tasks associated with receipt of CC components Work Statement: Receive parts, inspect and acceptance tests. Disposition as apropriate. | 20 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 16 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1077530 |  | 0 | 0 | 40 | 32 | 80 | 0 | 0
S309900/S309910 | Carriage Cradle - Preliminary Design Review (Assembly, System Integration, Final Layout) | Technical scope: All tasks associated with organizing and executing a prliminary design review of theCC. Work Statement: Review and provide action items to be addressed in the design of the CC. | 15 | 0 |  | 0 |  | 0 | 0 | 0 |  | 180 |  | 180 | 0 | 0 | 0 | 120 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 180 | 120 | 0 | 0 | 0
S310500/S310510 | Carriage Cradle - Procurement Readiness Review | Technical Scope: All tasks related to the procurement readiness review of the carriage cradle. Work Statement: Review all aspects of the procurement documents for the carriage cradle | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 24 | 12 | 0 | 0 | 12 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 24 | 24 | 24 | 0 | 0
S310600 | Carriage Cradle - Provide Requirement to Procurement | Technical Scope: Provide documents to BNL procurement office. Work Statement: Gather copies of procurement documents provide to BNL procurement. | 5 | [8 empty] | 8 |  | 8
S311500/S311510 | Carriage Cradle - Assembly Fixtures & Survey Tooling Engineering | Technical Scope: All engineering tasks associated with the design of tooling and fixtures for the assembly and survey of the CC. Work Statement: Analyses and modeling for ass'y and survey tooling and fixture design. | 20 | 0 |  | 0 |  | 0 | 0 | 0 |  | 240 |  | 240 | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 240 | 160 | 0 | 0 | 0
S311600/S311610 | Carriage Cradle - Assembly Fixtures & Survey Tooling Design | Technical Scope: All tasks associated with the physical design/drawing effort for tooling and fixtures. Work Statement: Monitor and manage procurement process for the sPHENIX Cradle Carriage components. | 20 | 0 |  | 0 |  | 0 | 0 | 0 |  | 240 |  | 240 | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 240 | 160 | 0 | 0 | 0
2.03.01.01.13 - Needs to be added to P6 | Carriage Cradle - Fabricate Fixtures & Tooling | Technical Scope: Manufacturing effort. Work Statement: Fabricate Tooling and fixtures for assembly and survey of the CC as appropriate. | 40 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S311800/S311810 | CC Drive & Alignment System - Engineering | Technical Scope: Engineering effort for CC drive and alignment system. Work Statement: Analyze and model CC drive and alignment system as appropriate. | 60 | 0 |  | 0 |  | 0 | 0 | 0 |  | 94 |  | 94 | 0 | 0 | 0 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 94 | 30 | 0 | 0 | 0
S312000/S312010 | CC Drive & Alignment System - Assembly & Detail Drawings | Technical Scope: All tasks related creating CC Drive & Alignment System assembly and detail drawings. Work Statement: Under engineering guidance create a package of drawings to fully define the CC Drive & Alignment System. | 60 | 0 |  | 0 |  | 0 | 0 | 0 |  | 200 |  | 200 | 0 | 0 | 0 | 480 | 240 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 200 | 480 | 0 | 0 | 0
S314700/S314710 | Track Modifications - Structural Analysis of Existing Track System & Preliminary Design | Technical Scope: All tasks related to the design of of the sPHENIX Track Modificationse layout. Work Statement: gather all relevant information and analyze requirements, calculate performance , create layout drawing. | 60 | 0 |  | 0 |  | 0 | 0 | 0 |  | 360 |  | 360 | 0 | 0 | 0 | 240 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 360 | 240 | 0 | 0 | 0
S314900/S314910 | Track Modifications - Assembly & Detailed Drawings | Technical Scope: All tasks related creating Track Modifications assembly and detail drawings. Work Statement: Under engineering guidance create a package of drawings to fully define the carriage cradle. | 50 | 0 |  | 0 |  | 0 | 0 | 0 |  | 140 |  | 140 | 0 | 0 | 0 | 400 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 140 | 400 | 0 | 0 | 0
S315000/S315010 | Track Modifications - Final Design Reviews (Design & Safety) | Technical Scope: All tasks related to the design and safety review of the Track modifications. Work Statement: Review all aspects of the proposed design for the carriage cradle | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 120 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 120 | 80 | 0 | 0 | 0
S315200/S315210 | Track Modifications - Prepare Procurement Package | Technical Scope: All tasks related to the preparation of procurement documents for the cradle track modifications. Work Statement: Create statement of work, design specifications and RFQ drawing package to support procurement effort. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 48 |  | 48 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 48 | 80 | 0 | 0 | 0
S315300/S315310 | Track Modifications - Procurement Readiness Review | Technical Scope: All tasks related to the procurement readiness review of the CC Track Modification. Work Statement: Review all aspects of the procurement documents for the Track Modification. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 24 | 40 | 0 | 0 | 0
S315100/S315110 | Track Modifications - Address Action Items from Design & Safety Reviews | Technical Scope: All tasks related to addressing issues raised during the design and safty review. Work Statement: Revisit design calculations, revise designs and drawings as necessary to satisfy issues raised during design and safety review. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 80 |  | 80 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 80 | 80 | 0 | 0 | 0
S311900 | CC Drive & Alignment System - Design Carriage Controls & Limits | Technical Scope: All tasks needed to assess CC Drive & Alignment System needs for the sPHENIX experiment. Work Statement: Gather dimensional, performance and structural information for CC seismic restraint requirements. Perform dimensional, operational and structural analyses as appropriate to model. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0
S313300 | CC Seismic Restraints - Engineer & Analysis | Technical Scope: All tasks related to the design of of the sPHENIX cradle seismic restraints. Work Statement: gather all relevant information and analyze requirements, calculate performance , create layout drawing. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 360 |  | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 360 | 0 | 0 | 0 | 0
S313400/S313410 | CC Seismic Restraints - Assembly & Detail Drawings | Technical Scope: All tasks related to the creation of assembly & Detail drawings for the CC Seismic Restraints. Work Statement: Starting from the layout and envelope drawings and guided by the results of the engineering analyses for structural and space utilization optimization, create assembly & detail drawings with appropriate references to all subassemblies and detail components. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 120 | 0 | 0 | 0 | 240 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 120 | 240 | 0 | 0 | 0
S313500/S313510 | CC Seismic Restraints - Final Design Reviews (Design & Safety) | Technical Scope: All tasks related to the design and safety review of the carriage seismic restraints. Work Statement: Review all aspects of the proposed design for the carriage seismic restraints | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 40 | 40 | 0 | 0 | 0
S313600/S313610 | CC Seismic Restraints - Address Action Items from Design & Safety Reviews | Technical Scope: All tasks related to addressing issues raised during the design and safty review. Work Statement: Revisit design calculations, revise designs and drawings as necessary to satisfy issues raised during design and safety review. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 60 |  | 60 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 60 | 40 | 0 | 0 | 0
S313700/S313710 | CC Seismic Restraints - Prepare Procurement Package | Technical Scope: All tasks related to the preparation of procurement documents for the cradle seismic restraints. Work Statement: Create statement of work, design specifications and RFQ drawing package to support procurement effort. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 28 |  | 28 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 28 | 40 | 0 | 0 | 0
S313800/S313810 | CC Seismic Restraints - Procurement Readiness Review | Technical Scope: All tasks related to the procurement readiness review of the CC seismic restraints. Work Statement: Review all aspects of the procurement documents for the CC seismic restraints. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 28 |  | 28 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 28 | 40 | 0 | 0 | 0
S310600 | Carriage Cradle - Provide Requirement to Procurement | Technical Scope: Provide documents to BNL procurement office. Work Statement: Gather copies of procurement documents provide to BNL procurement. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0
S310800/S310810 | Carriage Cradle - Vendor Responses | Technical Scope: Engineering monitoring and communications with vendor during procurement. Work Statement: Communicate with and monitor vendor performance as necessary. Address all issues as they arise and institute contingencies as appropriate to minimize impact on budget and schedule. | 60 | 0 |  | 0 |  | 0 | 0 | 0 |  | 72 |  | 72 | 0 | 0 | 0 | 72 | 36 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 72 | 72 | 0 | 0 | 0
S314800/S314810 | Track Modifications - Preliminary Design Review (Design & Safety) | Technical Scope: All tasks related to the preliminary design and safety review of the cradle track modifications. Work Statement: Review all preliminary design and safety aspects of the cradle track modifications and provide feedback action items for correcting/improving the design. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 80 |  | 80 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 80 | 80 | 0 | 0 | 0
S316200/S316210 | Track Modifications - Installation | Technical Scope: All tasks related to the installation of track modifications. Work Statement: Design and fabricate track modification tools as necessary. Perform installation verify installation. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 16 | 8 | 0 | 0 | 8 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 |  | 0 | 0 | 32 | 16 | 120 | 120 | 0
S312100/S312110 | CC Drive & Alignment System - Final Design Reviews (Design & Safety) | Technical Scope: All tasks related to the design and safety review of the carriage drive and alignment system. Work Statement: Review all aspects of the proposed design for the carriage drive and alignment system. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 120 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 120 | 80 | 0 | 0 | 0
S312300/S312310 | CC Drive & Alignment System - Prepare Procurement Package | Technical Scope: All tasks related to the preparation of procurement documents for the cradle drive and alignment system. Work Statement: Create statement of work, design specifications and RFQ drawing package to support procurement effort. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 28 |  | 28 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 28 | 40 | 0 | 0 | 0
S312400/S312410 | CC Drive & Alignment System - Procurement Readiness Review | Technical Scope: All tasks related to the procurement readiness review of the CC Drive & Alignment System. Work Statement: Review all aspects of the procurement documents for the CC Drive & Alignment System | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 28 |  | 28 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 28 | 40 | 0 | 0 | 0
S312200/S312210 | CC Drive & Alignment System - Address Action Items from Design & Safety Reviews | Technical Scope: All tasks related to addressing issues raised during the design and safty review. Work Statement: Revisit design calculations, revise designs and drawings as necessary to satisfy issues raised during design and safety review. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 120 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 120 | 80 | 0 | 0 | 0
S312800/S312810 | CC Drive & Alignment System - Vendor Selection | Technical Scope: All tasks necessary to solicit proposals for the fabrication of CC Drive & Alignment System. Work Statement: Research appropriate vendors, submit list and procurement documents to BNL procurement, receive and evaluate proposals, select winning vendor. | 25 | 0 |  | 0 |  | 0 | 0 | 0 |  | 26 |  | 26 | 0 | 0 | 0 | 36 | 18 | 0 | 0 | 18 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 26 | 36 | 36 | 0 | 0
S313000/S313010 | CC Drive & Alignment System - BNL Oversite | Technical Scope: Oversight of BNL engineering management for design and procurement documents. Work Statement: Prepare documents for configuration management review and approval. Circulate and address any concerns raised by approvers. | 84 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 40 | 20 | 40 | 0 | 0
S313250/S313200/S313210 | CC Drive & Alignment System - Delivery Acceptance | Technical Scope: Receive and accept delivery of CC Drive & Alignment System as received from Vendor. Work Statement: Arrange for receipt, inspection, acceptance testing etc. as appropriate and deliver CC Drive & Alignment System to pre-determined storage area until needed for installation. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 36 |  | 36 | 0 | 0 | 0 | 32 | 16 | 0 | 0 | 16 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56580 |  | 0 | 0 | 36 | 32 | 80 | 0 | 0
S312500 | CC Drive & Alignment System - Provide Requirement to Procurement | Technical Scope: Provide documents to BNL procurement office. Work Statement: Gather copies of procurement documents provide to BNL procurement. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0
S312700/S312710 | CC Drive & Alignment System - Vendor Responses | Technical Scope: Engineering monitoring and communications with vendor during procurement. Work Statement: Communicate with and monitor vendor performance as necessary. Address all issues as they arise and institute contingencies as appropriate to minimize impact on budget and schedule. | 25 | 0 |  | 0 |  | 0 | 0 | 0 |  | 26 |  | 26 | 0 | 0 | 0 | 36 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 26 | 36 | 0 | 0 | 0
S314200/S314210 | CC Seismic Restraints - Vendor Selection | Technical Scope: All tasks necessary to solicit proposals for the fabrication of CC Drive & Alignment System. Work Statement: Research appropriate vendors, submit list and procurement documents to BNL procurement, receive and evaluate proposals, select winning vendor. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 26 |  | 26 | 0 | 0 | 0 | 36 | 18 | 0 | 0 | 18 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 26 | 36 | 36 | 0 | 0
S314400/S314410 | CC Seismic Restraints - BNL Oversight | Technical Scope: Oversight of BNL engineering management for design and procurement documents. Work Statement: Prepare documents for configuration management review and approval. Circulate and address any concerns raised by approvers. | 60 | 0 |  | 0 |  | 0 | 0 | 0 |  | 48 |  | 48 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 48 | 20 | 40 | 0 | 0
S314650/S314600/S314610 | CC Seismic Restraints - Delivery Acceptance | Technical Scope: Receive and accept delivery of CC Seismic Restraints as received from Vendor. Work Statement: Arrange for receipt, inspection, acceptance testing etc. as appropriate and deliver CC Seismic Restraints to pre-determined storage area until needed for installation. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 6 |  | 6 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 4 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 |  | 0 | 0 | 6 | 8 | 20 | 0 | 0
S313900 | CC Seismic Restraints - Provide Requirement to Procurement | Technical Scope: Provide documents to BNL procurement office. Work Statement: Gather copies of procurement documents provide to BNL procurement. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0
S314100/S314110 | CC Seismic Restraints - Vendor Responses | Technical Scope: Engineering monitoring and communications with vendor during procurement. Work Statement: Communicate with and monitor vendor performance as necessary. Address all issues as they arise and institute contingencies as appropriate to minimize impact on budget and schedule. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 26 |  | 26 | 0 | 0 | 0 | 36 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 26 | 36 | 0 | 0 | 0
S315700/S315710 | Track Modifications - Vendor Selection | Technical Scope: All tasks necessary to solicit proposals for the fabrication of Track Modifications. Work Statement: Research appropriate vendors, submit list and procurement documents to BNL procurement, receive and evaluate proposals, select winning vendor. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 26 |  | 26 | 0 | 0 | 0 | 36 | 18 | 0 | 0 | 18 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 26 | 36 | 36 | 0 | 0
S315900/S315910 | Track Modifications - BNL Oversight | Technical Scope: Oversight of BNL engineering management for design and procurement documents. Work Statement: Prepare documents for configuration management review and approval. Circulate and address any concerns raised by approvers. | 60 | 0 |  | 0 |  | 0 | 0 | 0 |  | 38 |  | 38 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 38 | 20 | 40 | 0 | 0
S316000/S316100/S316110 | Track Modifications - Delivery Acceptance | Technical Scope: Receive and accept delivery of Track Modifications as received from Vendor. Work Statement: Arrange for receipt, inspection, acceptance testing etc. as appropriate and deliver Track Modifications to pre-determined storage area until needed for installation. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 14 |  | 14 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 10 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26750 |  | 0 | 0 | 14 | 20 | 80 | 0 | 0
S315400 | Track Modifications - Provide Requirement to Procurement | Technical Scope: Provide documents to BNL procurement office. Work Statement: Gather copies of procurement documents provide to BNL procurement. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0
S315600/S315610 | Track Modifications - Vendor Responses | Technical Scope: Engineering monitoring and communications with vendor during procurement. Work Statement: Communicate with and monitor vendor performance as necessary. Address all issues as they arise and institute contingencies as appropriate to minimize impact on budget and schedule. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 26 |  | 26 | 0 | 0 | 0 | 36 | 18 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 26 | 36 | 0 | 0 | 0
[44 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
2.03.01.01
| Item |  |  | Material | Length (in) | #/in | Weight (#) | Qty | Mat'l Cost | Machining | Welding | cost
[13 empty] | Steel Price= | 1.75 | $/#
| Cradle Carriage (Total) | [9 empty] | Total | 1286860.1485
S311350 | Cradle Assembly | [9 empty] | Totals: | 1077530.0985
|  | Cradle Base weldment | [5 empty] | 2 |  | 200 | 1600 | 691676.0755
169838.0378
|  |  | W14X193 | A992 Steel | 146.5 | 16.0833 | 2356.2083 | 6 | 4123.3646 | 2 |  | 25700.1875
|  |  | Plate 16.5"X1.5" | A36 Steel | 300 | 7.0537 | 2116.125 | 2 | 3703.2188 | 40 |  | 13806.4375
|  |  | Bar 12"X1" | A36 Steel | 300 | 3.42 | 1026 | 2 | 1795.5 | 5 |  | 4391
|  |  | Plate 6"X56" | A36 Steel | 76 | 95.76 | 7277.76 | 2 | 12736.08 | 40 |  | 31872.16
|  |  | W14X193 | A992 Steel | 55.1 | 16.0833 | 886.1917 | 4 | 1550.8354 | 20 |  | 12603.3417
|  |  | W14X193 | A992 Steel | 66.3 | 16.0833 | 1066.325 | 2 | 1866.0687 | 20 |  | 6932.1375
|  |  | W14X193 | A992 Steel | 66.3 | 16.0833 | 1066.325 | 2 | 1866.0687 | 20 |  | 6932.1375
|  |  | W14X193 | A992 Steel | 51.7 | 16.0833 | 831.5083 | 6 | 1455.1396 | 20 |  | 18330.8375
|  |  | Plate1"X12.6" | A36 Steel | 51.68 | 3.591 | 185.5829 | 4 | 324.77 | 3 |  | 2259.0802
|  |  | Plate1"X12.6" | A36 Steel | 29.87 | 3.591 | 107.2632 | 4 | 187.7105 | 3 |  | 1710.8422
|  |  | Plate 1"X15.48" wide | A36 Steel | 32.86 | 4.4118 | 144.9717 | 4 | 253.7006 | 6 |  | 2934.8022
|  |  | 1.5" plate 149.5" wide | A36 Steel | 300 | 63.9112 | 19173.375 | 1 | 33553.4062 | 100 |  | 41553.4062
|  |  | Plate 1"X15" wide | A36 Steel | 32.86 | 4.275 | 140.4765 | 2 | 245.8339 | 2 |  | 811.6677
|  | Cradle | Plate 4"X60"X240" | A36 Steel |  |  |  | 4 |  |  |  | 100000 | Quote from strecks inc
|  | Cradle Brace | [5 empty] | 8 |  |  | 4 | 20624.8323
|  |  | W18X60 | A992 Steel | 115 | 5 | 575 | 1 | 1006.25 | 10 |  | 1806.25
|  |  | Plate 75"X7.6" | A36 Steel | 18.24 | 1.6245 | 29.6309 | 1 | 51.854 | 4 |  | 371.854
|  | Top Beam | [5 empty] | 6 |  | 40 | 8 | 48136.6475
|  |  | W14X257 | A992 Steel | 72.5 | 21.4167 | 1552.7083 | 1 | 2717.2396 | 2 |  | 2877.2396
|  |  | Plate 1.5"X7.5 | A36 Steel | 12.4 | 2.1375 | 26.505 | 4 | 46.3837 | 3 |  | 1145.535
|  | Top Doubler | Plate 1"X58" | A36 Steel | 66.5 | 24.795 | 1648.8675 | 6 | 1648.8675 | 20 |  | 19493.205
|  | End Bracket | [5 empty] | 8 |  |  | 8 | 28420.1819
|  |  | Plate 1"X11.25 | A36 Steel | 38.25 | 3.2062 | 122.6391 | 1 | 214.6184 | 10 |  | 1014.6184
|  |  | Plate 1"X7 | A36 Steel | 30.5 | 1.995 | 60.8475 | 1 | 106.4831 | 10 |  | 906.4831
|  |  | Plate 1"X7" | A36 Steel | 9 | 1.995 | 17.955 | 1 | 31.4212 | 10 |  | 831.4212
|  | Column Brace | Plate .75"X42 " | A36 Steel | 118.5 | 8.9775 | 1063.8338 | 4 | 1861.7091 | 16 |  | 12566.8363
joining plate
|  | Fasteners | [5 empty] | 1 | 4500 |  |  | 4500
| x-y Table | [6 empty] | 4 |  |  |  | 112853.1
|  | Body | Weldment | A36 |  |  | 690 | 1 | 1207.5 | 40 | 20 | 6007.5
|  | Jack Block | Plate 5"X26" | A36 Steel | 26 | 37.05 | 963.3 | 1 | 1685.775 | 20 |  | 3285.775
|  | bearing |  | oilite |  |  |  | 1 | 1000 | 4 |  | 1320
|  | Jack 50 ton | Enepac RC-502 |  |  |  |  | 4 | 1400 |  |  | 5600
|  | Jack 400 ton | Enepac HD-4004 |  |  |  |  | 1 | 8000 |  |  | 8000
|  | Hydraulic System | [5 empty] | 1 |  |  |  | 4000
|  |  | valve |  |  |  |  | 4 | 300 |  |  | 1200
|  |  | fittings |  |  |  |  | 1 | 1000 |  |  | 1000
|  |  | tubing |  |  |  |  | 1 | 1000 |  |  | 1000
|  |  | pump |  |  |  |  | 1 | 500 |  |  | 500
|  |  | accumulator |  |  |  |  | 1 | 300 |  |  | 300
|  |  | tank |  |  |  |  | 1 | 100 |  |  | 100
| Roller Assembly Long | [6 empty] | 4 |  |  |  | 19829.61
|  | mounting Plate | Plate 1"X18" | A36 Steel | 68 | 5.13 | 348.84 | 1 | 610.47 | 6 |  | 1090.47
|  | Boss | Bar 1"X1.5" | A36 Steel | 36 | 0.4275 | 15.39 | 1 | 26.9325 | 3 |  | 266.9325
|  | Roller | Hilman 300-XT |  |  |  |  | 1 | 3300 |  |  | 3300 | 4 in house
|  | Fasteners | [5 empty] | 1 | 300 |  |  | 300
| Roller Assembly Long | [6 empty] | 4 |  |  |  | 17429.61
|  | mounting Plate | Plate 1"X18" | A36 Steel | 68 | 5.13 | 348.84 | 1 | 610.47 | 6 |  | 1090.47
|  | Boss | Bar 1"X1.5" | A36 Steel | 36 | 0.4275 | 15.39 | 1 | 26.9325 | 3 |  | 266.9325
|  | Roller | Hilman 200-XT |  |  |  |  | 1 | 2700 |  |  | 2700 | 4 in house
|  | Fasteners | [5 empty] | 1 | 300 |  |  | 300
| Miscellaneous Parts/Hardware | [7 empty] | 2000 |  |  | 2000
S314650 | Seismic Restraints |  | Mics Plate Steel | A36 Steel |  |  | 3371.4 | 4 | 5899.95 | 200 | 120 | 125999.8
S316000 | Track Modifications |  | Mics Plate Steel | A36 Steel |  |  | 245.72 | 25 | 430.01 | 4 | 4 | 26750.25
S313250 | CC Drive and Alignment System | [10 empty] | 56580
|  | Detector Drive Controller | [9 empty] | 50000
|  | Position Controler | [5 empty] | 1 |  |  |  | 6580
|  |  | linear pot. |  |  |  |  | 12 | 300 |  |  | 3600
|  |  | Power supply |  |  |  |  | 1 | 100 |  |  | 100
|  |  | WIFI DAQ Caed |  |  |  |  | 1 | 400 |  |  | 400
|  |  | Limit Switch |  |  |  |  | 4 | 20 |  |  | 80
|  |  | Miscellaneous Parts | [8 empty] | 2400
[11 empty] | Total | 1286860.1485

## OHCal Steel Work Package
Return to Navigation Page
WBS # | 2.03.03 | Task/Activity Description | Duration (d) | Administrator ADMIN1 PO |  | Scientist |  | Scientist (hrs) |  |  | Engineer | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Labor Description/Risk Code | Material Description/Risk Code | Hours for each Resource Category by WBS# | [6 empty] | Project Labor Cost by Resource Category
| Outer HCal Steel Sectors Ready for Electronics | [6 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [7 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost
| TASK/ACTIVITY |  |  | hrs |  | hrs |  | Scientist | Scientist | Scientist | hrs |  |  |  |  | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs | 63.15 | 121.5 | 104.3 | 81.1 | 81.1 | 113.49 | 0
2.03.01.03.01 | Outer HCal sector steel initial procurement requirements (prototype) | Milestone | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | This procurement performed and paid for in HCal subsystem WBS 1.04. | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S318200 | Outer HCAL Sector Mechanical Structure Production and Assembly-Provide Requirements
S318300 | Final Mechanical Design of Outer HCAL Sector
S318400 | Internal Review of Outer HCAL Sector Mechanical Design
S318500 | Address Issues from Internal Review of Outer Hcal Sector Mechanical Design
S318600 | Outer HCAL Sector Mechanical Design Complete
S318700 | Internal Review of Outer HCAL Lifting Fixture and Supports
S318800 | Address Issues from Internal Review of Outer Hcal Lifting Fixture and Supports
S318900 | Outer HCAL Lifting Fixture and Supports Design Complete
S319000 | Procure Outer HCAL Lifting Fixture and Supports - Provide BNL Central Shops
S319100 | Procure Outer HCAL Lifting Fixture and Supports - Delivery Acceptance | Technical Scope: All tasks related to the Procurement of OHCal lifting fixtures and supports in support of HCal steel acceptance. Work Statement: Prepare documents, solicit proposals execue procurement of fixtures and tools. | 40 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 25% | 40% | This was completed September 2018 and is therefore not included in the M&S totals for FY2019 and later | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S319200 | Procure Outer HCAL Mechanical Structure Components - Prepare & Send Solicitation
S319300 | Procure Outer HCAL Mechanical Structure Components - Vendor Responses
S319400 | Procure Outer HCAL Mechanical Structure Components - Vendor Selection
S319500 | Procure Outer HCAL Mechanical Structure Components - Contract Award (Raw Mat'l & Sector Assemblies)
S319600 | Procure Outer HCAL Mechanical Structure Components - Contract Award (First Article)
S319700 | Procure Outer HCal Mechanical Structure Components - Lead Time (First Article)
S319800 | Design and procure Outer HCAL acceptance testing tooling Labor
S319900 | Design and procure Outer HCAL acceptance testing tooling - M&S
S320000 | Outer HCAL Sector Mechanical Structure First Article Acceptance Testing | Technical Scope: All tasks related to the evaluation of the Outer HCal full sector steel prototpye and redesign Outer HCal sector steel based on such evaluation. Work Statement: Receive prototype, inspect and survey prototype, redesign based on evaluation. | 10 | 0 |  | 16 |  | 0 | 16 | 0 | 16 | 0 | 0 | 16 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% | This was completed in FY2018 and therefore not included in Labor Totals for FY2019 and later | sPHENIX Engineers, Technicians, Designers and Scientists; effort is well defined/ L4 | No Materials required for this task/M1 | 0 | 16 | 16 | 80 | 80 | 0 | 0 | 0 | 1944 | 1668.8 | 6488 | 6488 | 0 | 0 |  | This was completed in FY2018 and therefore not included in Labor Totals for FY2019 and later
S320100 | Procure Outer HCal Mechanical Structure Components - Del. Accept. (First Article)
S320200 | Procure Outer HCAL Mechanical Structure Components - Vendor purchases raw material
S320300 | Procure Outer HCAL Mechanical Structure Components - Payment for purchases raw material
S320400 | Procure Outer HCAL Mechanical Structure Components - Lead Time
S320500-S323600 | Procure Outer HCAL Mechanical Structure Components - Del. Accept. (Sector Structural Assembly 1-32)
S323700 | Outer HCAL Sector Mechanical Structure Acceptance Testing FY18
S323800 | Outer HCAL Sector Mechanical Structure Acceptance Testing FY19 | Technical Scope: All tasks related to the evaluation and acceptance of the Outer HCal of all OHCal steel sectors including normal and chimney sectors. Work Statement: Receive sectors, inspect and survey to verify dimensional and structural requirements. | 178 | 0 |  | 62 |  | 0 | 62 | 0 | 62 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620 | 0 | 0 | 620 | 0 | 0 | 0 | 4698773.85 | 25% | 0% |  | n/a | n/a | 0 | 62 | 62 | 0 | 310 | 620 | 0 | 0 | 7533 | 6466.6 | 0 | 25141 | 70363.8 | 0
S323900 | Completion of Outer HCAL Sector Mechanical Structure Procurement
Materials and Supplies Details | [44 empty] | Resource summary for this work package resource requirements in Hours by Resource Category | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
[46 empty] | hrs | hrs | hrs | hrs | hrs | hrs | hrs | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students | Total Labor Cost for Work Package | Total Material
WBS | Description | Item | Vendor |  |  | QTY | QTY | Unit Cost | Total | Status | Basis of Estimate | estimate uncertainty | Item estimate uncertainty | Wt estimate uncertainty | Total | estimate uncertainty | Total w/ estimate uncertainty | Grand Total | Grand Total w/ estimate uncertainty | Link(s) | Notes | [24 empty] | 0 | 78 | 78 | 80 | 390 | 620 | 0 | Total Labor Costs for this work package by Resource Catgory | [6 empty] | 0 | 4738773.85
[53 empty] | 0 | 9477 | 8135.4 | 6488 | 31629 | 70363.8 | 0
Purchase Order | Description
BNL-0000324562 | Outer HCAL Steel Assembly
PO # 0000324562
Strecks Inc. | [8 empty] | BOE Total | 4698773.85
Line | Item/Description | Quantity | UOM | PO Price | Extended Amount | Due Date
1 | sPHENIX Outer Hcal Full Sector Assembly First Article | 1 | EA | 189874 | 189874 | 2018-04-20 |  |  |  |  | Completed FY2018
2 | Steel Order and Payment | 1 | EA | 750000 | 750000 | 2018-05-31 |  |  |  |  | Completed FY2018
3 | Production Assembly | 12 | EA | 151573.35 | 1818880.2 | 2019-07-31
4 | Production Assembly Phase Fund 2 | 20 | EA | 151573.35 | 3031467 | 2019-07-31
|  |  |  | Total PO Amount | 5790221.2
|  |  | Paid in FY 18 | First Article | -189874 | [5 empty] | Completed FY2018
|  |  | Paid in FY 18 | Steel Order | -750000 | [5 empty] | Completed FY2018
|  |  | Paid in FY 18 | 1 Production Assembly | -151573.35 | [5 empty] | Completed FY2018
|  |  |  | Total | 4698773.85

## End Caps_Pole Tips Work Package
Return to Navigation Page
Activity ID | 2.03.04 | Task/Activity Description | Duration (d) | Administrator ADMIN1 PO |  | Scientist |  | Scientist (hrs) |  |  |  | Engineer |  | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | NOTES |  | Hours for each Resource Category by WBS#
| End Caps/ Pole Tips Work Package | [6 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  |  |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 |  |  |  |  | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
| TASK/ACTIVITY |  |  | hrs |  | hrs |  | Scientist | Scientist | Scientist |  | hrs | [5 empty] | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  |  |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs
S324200/S324210 | End Caps/ Pole Tips - Assembly & Detail Drawing | Technical Scope: All tasks related to the creation of assembly & detail drawings for End Caps/Pole Tips and structural support components for the End Cap/Pole Tips. Work Statement: Starting from the layout and envelope drawings and guided by the results of the engineering analyses for structural and space utilization optimization, create assembly and detail drawings with appropriate references to all subassemblies and detail components. | 65 | 0 |  | 24 |  | 0 | 24 | 0 |  | 394 |  | 370 | 0 | 24 |  | 480 | 240 | 0 | 0 | 240 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 24 | 394 | 480 | 24 | 0 | 0
S324300/S324310 | End Caps/ Pole Tips - Final Design Reviews (Design & Safety) | Technical Scope: All tasks related to the final design and safety review of the pole tips. Work Statement: Review all design and safety aspects of the pole tips and provide feedback action items for correcting/improving the design. | 5 | 0 |  | 4 |  | 0 | 4 | 0 |  | 60 |  | 60 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 4 | 60 | 40 | 0 | 0 | 0
S324400/S324410 | End Caps/ Pole Tips - Address Action Items from Design & Safety Reviews | Technical Scope: All tasks to respond to review committee findings. Work Statement: Receive committee report and evaluate, address committee concerns and respond to action items, redesign and re convene committee to review updated design as necessary and appropriate. Repeat until all concerns are fully addressed. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 60 |  | 60 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 60 | 80 | 8 | 0 | 0
S324500 | Design/Safety Reviews Complete, End Caps/ Pole Tips Released for Production | Milestone | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S324600/S324610 | End Caps/ Pole Tips - Prepare Procurement Package(s) | Technical Scope: All tasks necessary to prepare a procurement package for the End Caps/ Pole Tips. Work Statement: Gather technical documents, create SOW and/or specifcation documents as appropriate. | 21 | 0 |  | 0 |  | 0 | 0 | 0 |  | 56 |  | 56 | 0 | 0 | 0 | 240 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 56 | 240 | 0 | 0 | 0
S325100/S325110 | End Caps/ Pole Tips - Vendor Selection | Technical Scope: All tasks necessary to solicit proposals for the fabrication of End Caps/ Pole Tips. Work Statement: Research appropriate vendors, submit list and procurement documents to BNL procurement, receive and evaluate proposals, select winning vendor. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 32 | 20 | 0 | 0 | 0
S324000/S324010 | End Caps/ Pole Tips - Engineering & Analysis (includes drive system) | Technical Scope: All tasks needed to assess End Caps/Pole Tips needs for the sPHENIX experiment. Work Statement: Gather dimensional and structural information for End Caps/Pole Tips requirements. Perform dimensional and structural analyses as appropriate to model. | 35 | 0 |  | 0 |  | 0 | 0 | 0 |  | 380 |  | 380 | 0 | 0 | 0 | 140 | 70 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 380 | 140 | 0 | 0 | 0
S324100/S324110 | End Caps/ Pole Tips - Design Controls for Drive System | Technical Scope: All tasks needed to assess End Caps/Pole Tips drive controls needs for the sPHENIX experiment. Work Statement: Gather dimensional and structural information for End Caps/Pole Tips drive controls requirements. Perform dimensional and structural analyses as appropriate to model. | 15 | 0 |  | 0 |  | 0 | 0 | 0 |  | 120 |  | 0 | 0 | 0 | 120 | 120 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 120 | 120 | 0 | 0 | 0
S324700/S324710 | End Caps/ Pole Tips - Procurement Readiness Review | Technical Scope: All tasks to prepare and present the End Caps/Pole Tips procurement documents to a readinesss committee. Work Statement: Prepare documents, organize review & appropriate committee, present procurement documents to reviewers. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 40 | 40 | 24 | 0 | 0
S324800 | End Caps/ Pole Tips - Provide Requirement to Procurement | Technical Scope: Provide documents to BNL procurement office. Work Statement: Gather copies of procurement documents provide to BNL procurement. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 16 | 0 | 0 | 0 | 0
S325000/S325010 | End Caps/ Pole Tips - Vendor Responses | Technical Scope: Engineering monitoring and communications with vendor during procurement. Work Statement: Communicate with and monitor vendor performance as necessary. Address all issues as they arise and institute contingencies as appropriate to minimize impact on budget and schedule. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 20 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 32 | 20 | 0 | 0 | 0
S325400/S325500/S325510 | End Caps/ Pole Tips - Delivery Acceptance Support Labor | Technical Scope: Receive and accept delivery of End Caps/ Pole Tips as received from Vendor. Work Statement: Arrange for receipt, inspection, acceptance testing etc. as appropriate and deliver End Caps/ Pole Tips to pre-determined storage area until needed for installation. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 88 |  | 88 | 0 | 0 | 0 | 88 | 44 | 0 | 0 | 44 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616612 |  |  | 0 | 0 | 88 | 88 | 40 | 0 | 0
S325600 | End Caps/ Pole Tips Ready for Installation | Milestone | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0
Return to Navigation Page
2.03.01.04
Item |  |  | Material | Length (in) | #/in | Weight (#) | Qty | Mat'l Cost | Machining | Welding | cost
[12 empty] | Steel Price= | 1.75 | $/#
Pole Tips | S325400 | [9 empty] | 616612.25
| Pole Tip Assembly | [5 empty] | 4 |  |  | 200 | 504661.25
|  | Plate 8"X110" | 1010 Steel | 212 | 250.8 | 53169.6 | 1 | 93046.8 | 200 |  | 109046.8
|  | Plate .74"X8" | A36 Steel | 84 | 1.71 | 143.64 | 1 | 251.37 | 2 |  | 411.37
|  | Plate 2"X8" | A36 Steel | 33 | 4.56 | 150.48 | 1 | 263.34 | 4 |  | 583.34
|  | Plate .74"X8" | A36 Steel | 90 | 1.71 | 153.9 | 1 | 269.325 | 6 |  | 749.325
|  | Plate 2"X90" | A36 Steel | 84 | 51.3 | 4309.2 | 1 | 7541.1 | 4 |  | 7861.1
|  | Plate .74"X8" | A36 Steel | 63 | 1.71 | 107.73 | 1 | 188.5275 | 2 |  | 348.5275
|  | Plate 2"X8" | A36 Steel | 15 | 4.56 | 68.4 | 1 | 119.7 | 4 |  | 439.7
|  | Plate .75"X8" | A36 Steel | 90 | 1.71 | 153.9 | 1 | 269.325 | 6 |  | 749.325
|  | Plate 2"X90" | A36 Steel | 63 | 51.3 | 3231.9 | 1 | 5655.825 | 4 |  | 5975.825
| trolleys hilman rd-30 | [5 empty] | 8 | 1000 |  |  | 8000
| Track | Bar 6"2" | A36 Steel | 150 | 3.42 | 513 | 4 | 897.75 | 10 |  | 6791
| Actuator | [5 empty] | 4 |  |  |  | 13160
|  | Gear Rack |  |  |  |  | 1 | 500 |  |  | 500
|  | Pion |  |  |  |  | 1 | 290 |  |  | 290
|  | Motor/gear Box |  |  |  |  | 1 | 2500 |  |  | 2500
| Stops and Supports | [5 empty] | 6 | 2750 |  |  | 16500
| Fasteners and other hardware | [5 empty] | 1 | 32500 |  |  | 32500
| Miscellaneous Materials | [5 empty] | 1 | 35000 |  |  | 35000

## Bridge Platforms Work Package
Return to Navigation Page
Activity ID | 2.03.05 | Task/Activity Description | Duration (d) | Administrator ADMIN1 PO |  | Scientist |  | Scientist (hrs) |  |  |  | Engineer |  | Engineer/Professional (hrs) |  |  |  | Designer | Designer/Drafter (hrs) | [5 empty] | Technician | Technicians (hrs) | [8 empty] | Trade | Bargaining Unit Trades (hrs) |  |  |  |  | Student (unpaid) | Materials and Supplies $ | RISK CODE/% |  | NOTES | Hours for each Resource Category by WBS#
| Cradle Carriage Bridge, Mid Platforms and Access Work Package | [6 empty] | BNL SCI3_AD | Project SCI3 PO | University SCI3_Inst_X |  |  |  | CAD Engineer PROF4 AD | Mag. Div, Engineer PROF4 AM | sPHENIX Engineer Mechanical PROF4 PO M | sPHENIX Engineer Electrical PROF4 PO E |  | Designer/ Drafter Mech. TECH3 PO D | Designer/ Drafter Elect. TECH3 PO D | Designer/ Tech JOBSHOP | Designer/ Drafter CAD TECH3 PO D | Designer/ Drafter Mag. Div. TECH3 PO D | University Designer/ Drafter TECH3 PO D |  | sPHENIX Technician Mech. TECH3 PO M | sPHENIX Technician Elect. TECH3 PO E | Job Shopper Mech. JOBSHOP PO M | CAD Technician TECH3 AD | CAD Technician Cryo TECH3 AD | CAD Technician Vacuum TECH3 AD | Mag. Div. Technician TECH3 AM | University. Technician TECH3_Inst_X | Student Intern (Paid) Student_Paid_BNL |  | Carpenter (Trades) CRAFT3 | Electrician (Trades) CRAFT3 | Rigger (Trades) CRAFT3 | Welder (Trades) CRAFT3 | Plumber (Trades) CRAFT3 | [5 empty] | Administrators | Scientists | Engineers | Designers | Technicians | Trades | Students
| TASK/ACTIVITY |  |  | hrs |  | hrs |  | Scientist | Scientist | Scientist |  | hrs | [5 empty] | hrs | [6 empty] | hrs | [9 empty] | hrs | [5 empty] | hrs |  | Labor | Material |  | hrs | hrs | hrs | hrs | hrs | hrs | hrs
S325800/S325810 | CC Bridge, Mid Platforms & Access - Assembly & Detail Drawings | Technical Scope: All tasks related to the creation of assembly & Detail drawings for the Cradle Carriage Bridge, Mid Platforms and Access components. Work Statement: Starting from the layout and envelope drawings and guided by the results of the engineering analyses for structural and space utilization optimization, create assembly & detail drawings with appropriate references to all subassemblies and detail components. | 80 | 0 |  | 0 |  | 0 | 0 | 0 |  | 480 |  | 480 | 0 | 0 | 0 | 640 | 320 | 0 | 0 | 320 | 0 | 0 | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 480 | 640 | 32 | 0 | 0
S325900/S325910 | CC Bridge, Mid Platforms & Access - Final Design Reviews (Design & Safety) | Technical Scope: All tasks to prepare and present the CC Bridge, Mid Platforms & Access to design and safety review committees. Work Statement: Prepare documents, organize review & appropriate committee, present design to reviewers. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 60 |  | 60 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 60 | 80 | 8 | 0 | 0
S326000/S326010 | CC Bridge, Mid Platforms & Access - Address Action Items from Design & Safety Reviews | Technical Scope: All tasks to respond to review committee findings. Work Statement: Receive committee report and evaluate, address committee concerns and respond to action items, redesign and re convene committee to review updated design as necessary and appropriate. Repeat until all concerns are fully addressed. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 60 |  | 60 | 0 | 0 | 0 | 80 | 40 | 0 | 0 | 40 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 60 | 80 | 8 | 0 | 0
S326100 | Design/Safety Reviews Complete, Cradle Carriage Bridge, Mid Platforms and Access Design Released for Production | Milestone | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
S326200/S326210 | CC Bridge, Mid Platforms & Access - Prepare Procurement Package(s) | Technical Scope: All tasks necessary to prepare a procurement package for the CC Bridge, Mid Platforms & Access. Work Statement: Gather technical documents, create SOW and/or specifcation documents as appropriate. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 56 |  | 56 | 0 | 0 | 0 | 160 | 80 | 0 | 0 | 80 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 56 | 160 | 24 | 0 | 0
S326700/S326710 | CC Bridge, Mid Platforms & Access - Vendor Selection | Technical Scope: All tasks necessary to solicit proposals for the fabrication of CC Bridge, Mid Platforms & Access. Work Statement: Research appropriate vendors, submit list and procurement documents to BNL procurement, receive and evaluate proposals, select winning vendor. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 120 | 60 | 0 | 0 | 60 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 32 | 120 | 24 | 0 | 0
S326900/S326910 | CC Bridge, Mid Platforms & Access - BNL Oversite | Technical Scope: Oversight of BNL engineering management for design and procurement documents. Work Statement: Prepare documents for configuration management review and approval. Circulate and address any concerns raised by approvers. | 90 | 0 |  | 0 |  | 0 | 0 | 0 |  | 90 |  | 90 | 0 | 0 | 0 | 72 | 36 | 0 | 0 | 36 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 90 | 72 | 72 | 0 | 0
S325700/S325710 | CC Bridge, Mid Platforms & Access - Engineering Analysis | Technical Scope: All tasks needed to assess the platform and access needs for the sPHENIX experiment. Work Statement: Gather dimensional and structural information for CC Bridge, Mid Platforms & Access requirements. Perform dimensional and structural analyses as appropriate to model. | 40 | 0 |  | 0 |  | 0 | 0 | 0 |  | 480 |  | 480 | 0 | 0 | 0 | 320 | 160 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 480 | 320 | 0 | 0 | 0
S326300/S326310 | CC Bridge, Mid Platforms & Access - Procurement Readiness Review | Technical Scope: All tasks to prepare and present the CC Bridge, Mid Platforms & Access procurement documents to a readinesss committee. Work Statement: Prepare documents, organize review & appropriate committee, present procurement documents to reviewers. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 40 |  | 40 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 20 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 40 | 40 | 24 | 0 | 0
S326400 | CC Bridge, Mid Platforms & Access - Provide Requirement to Procurement | Technical Scope: Provide documents to BNL procurement office. Work Statement: Gather copies of procurement documents provide to BNL procurement. | 5 | 0 |  | 0 |  | 0 | 0 | 0 |  | 16 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 16 | 0 | 0 | 0 | 0
S326600/S326610 | CC Bridge, Mid Platforms & Access - Vendor Responses | Technical Scope: Engineering monitoring and communications with vendor during procurement. Work Statement: Communicate with and monitor vendor performance as necessary. Address all issues as they arise and institute contingencies as appropriate to minimize impact on budget and schedule. | 30 | 0 |  | 0 |  | 0 | 0 | 0 |  | 24 |  | 24 | 0 | 0 | 0 | 120 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0% |  | 0 | 0 | 24 | 120 | 0 | 0 | 0
S327100/S327200/S327210 | CC Bridge, Mid Platforms & Access - Delivery Acceptance Support Labor | Technical Scope: Receive and accept delivery of CC Bridge, Mid Platforms & Access as received from Vendor. Work Statement: Arrange for receipt, inspection, acceptance testing etc. as appropriate and deliver CC Bridge, Mid Platforms & Access to pre-determined storage area until needed for installation. | 10 | 0 |  | 0 |  | 0 | 0 | 0 |  | 32 |  | 32 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 4 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 320659 | 25% | 30% |  | 0 | 0 | 32 | 8 | 8 | 8 | 0
S327300 | Cradle Carriage Bridge, Mid Platforms and Access Ready for Installation | Milestone | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Return to Navigation Page
Item |  |  | Material | Length (in) | #/in | Weight (#) | Qty | Mat'l Cost | Machining | Welding | cost
[12 empty] | Steel Price= | 1.75 | $/#
2.03.01.05
Platform | S327100 | [9 empty] | 320659.4683
| Column | [5 empty] | 8 |  |  | 12 | 100844.942
|  | W14X211 | A992 | 252 | 17.5833 | 4431 | 1 | 7754.25 | 30 |  | 10154.25
|  | Plate 1.5"X15.5" | A36 Steel | 24 | 6.7545 | 162.108 | 1 | 283.689 | 4 |  | 603.689
|  | Plate 1.5"X18.25" | A36 Steel | 24 | 7.8019 | 187.245 | 1 | 327.6788 | 4 |  | 647.6788
| Column Brace | [5 empty] | 8 |  |  | 12 | 67627.49
|  | W14X145 | A992 | 252 | 12.0833 | 3045 | 1 | 5328.75 | 12 |  | 6288.75
|  | Plate 1"X15.5" | A36 Steel | 21 | 4.4175 | 92.7675 | 2 | 162.3431 | 4 |  | 964.6862
| Girder | W14X176 | A992 | 300 | 14.6667 | 4400 | 4 | 7700 | 25 |  | 38800
| Valve Box Extention | [5 empty] | 2 |  |  | 12 | 8942.5058
|  | W14X145 | A992 | 63.68 | 12.0833 | 769.4667 | 1 | 1346.5667 | 12 |  | 2306.5667
|  | Plate 1"X15.5" | A36 Steel | 21 | 4.4175 | 92.7675 | 2 | 162.3431 | 4 |  | 964.6862
| Valve Box Girder | [5 empty] | 2 |  |  | 12 | 8014.2504
|  | W14X53 | A992 | 114.17 | 4.4167 | 504.2508 | 1 | 882.439 | 12 |  | 1842.439
|  | Plate 1"X15.5" | A36 Steel | 21 | 4.4175 | 92.7675 | 2 | 162.3431 | 4 |  | 964.6862
| Extention Support | Plate .75"X52" | A36 Steel | 72 | 11.115 | 800.28 | 2 | 1400.49 | 10 |  | 4400.98
| Floor Joist | W5X16 | A992 | 300 | 1.3333 | 400 | 12 | 700 | 8 |  | 16080
| Decking | Grate 1" X .125" | Aluminum | 300 |  |  | 50 | 180 | 3 |  | 21000
| Stairs | stairs w/4 landings |  |  |  |  | 1 | 16000 |  |  | 16000
| Railing | [9 empty] | 6292
|  | base flange |  |  |  |  | 30 | 30 |  |  | 900
|  | tee |  |  |  |  | 24 | 20 |  |  | 480
|  | elbow |  |  |  |  | 8 | 31 |  |  | 248
|  | 3way elbow |  |  |  |  | 8 | 22 |  |  | 176
|  | railing |  |  |  |  | 66 | 68 |  |  | 4488
| Fasteners | [5 empty] | 1 | 18000 |  |  | 18000
Top Cat Walk
| Beam Assembly | [5 empty] | 8 |  |  | 1 | 2744.65
|  | S6X12.5 | A36 Steel | 36 | 1.0417 | 37.5 | 1 | 65.625 |  |  | 65.625
|  | Plate .5"X5" | A36 Steel | 7 | 0.7125 | 4.9875 | 2 | 8.7281 | 1 |  | 177.4563
| Decking | Grate 1" X .125" | Aluminum | 144 |  |  | 2 | 600 | 3 |  | 1680
Mid-Level cat walk
| Beam Assembly | [5 empty] | 8 |  |  | 1 | 2744.65
|  | S6X12.5 | A36 Steel | 36 | 1.0417 | 37.5 | 1 | 65.625 |  |  | 65.625
|  | Plate .5"X5" | A36 Steel | 7 | 0.7125 | 4.9875 | 2 | 8.7281 | 1 |  | 177.4563
| Decking | Grate 1" X .125" | Aluminum | 144 |  |  | 2 | 600 | 3 |  | 1680
| Railing | [9 empty] | 1308
|  | base flange |  |  |  |  | 16 | 30 |  |  | 480
|  | tee |  |  |  |  | 16 | 20 |  |  | 320
|  | elbow |  |  |  |  | 4 | 31 |  |  | 124
|  | 3way elbow |  |  |  |  | 2 | 22 |  |  | 44
|  | railing |  |  |  |  | 5 | 68 |  |  | 340
| Stairs | stairs w/1 landings |  |  |  |  | 1 | 4500 |  |  | 4500