## Outer HCAL Sector Mech. Str.
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-02-19
[7 empty] | Prepared By: | John G. Lajoie
[7 empty] | DocNo. (refer Rev. Log) | 143 v5
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Outer HCAL Mechanical Structure |  |  |  | 1.04.02
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO DESIGN AND MANUFACTURE COMPONENTS FOR THE OUTER HCAL MECHANICAL STRUCTURE, DESIGN AND CONSTRUCT THE MECHANICAL ELEMENTS OF THE OUTER HADRONIC CALORIMETER. WORK STATEMENT: PROVIDE OUTER HADRONIC CALORIMETER MECHANICAL STRUCTURE.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
Click for detailed summary
Guidelines Used in Developing Estimate
The primary elements in this work package, the outer HCAL lifting fixtures and splice plates, supplement the outer HCAL steel purchase in WBS 2.09. Together they enable the construction and assembly of the entire outer HCAL. All labor in this work package (BNL technician, engineering and design) are costed at current BNL rates with a 20% uncertainty. We justify the uncertainty based on the advanced state of the design and the engineers estimate of the work remaining. The splice plates are costed based on an engineering estimate at with a 40% uncertainty. The lifting fixtures are similarly based on an engineering estimate with a 40% uncertainty.
Details of the Base Estimate (explanation of the Work)
This work item covers the remaining mechanical structure for the outer HCAL, outside of WBS 2.09. The outer HCAL is comprised of 32 sectors, which when assembled form the outer barrel of sPHENIX and part of the flux return for the magentic field. Each sector is comprised of longitundinal iron plates with ten slots for scintillating tiles in azimuth. The tiles are organized into 24 towers longitudinally and two towers in azimuth, for 48 tower per sector. In addition to the design and manufacture of the outer HCAL structures, this work item also included the engineering design and manufacture of the "splice plates" that will combine the outer HCAL strutures when assembled. The lifting fixtures are the outer HCAL structures are also included here as they will be necessary to move the sectors into and out of the assembly area.
Cost Summary
(follow link for detailed summary)
[5 empty] | Materials Total | Labor Hours
[5 empty] | 326560 | 424
Uncertainty
Uncertainty is estimates at 40% for engineering estimates or for parts where a full design does not exist. Small orders for catalog items are assigned a 10-20% uncertainty. Engineering design time is assigned a 25% uncertainty based on past experience and the fact that each element includes rounds of review and time for additional redesign. Tech labor is assigned a 25% uncertainty based on experience with two previous test beam prototypes.

## Sector Mechanical - Details
Materials |  | c
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.04.02 |  | Outer HCAL Mechanical Structure | [6 empty] | 326560
| S204300 | Procure Preproduction Outer HCAL Splice Plates - Delivery Acceptance | [5 empty] | 20000
|  |  | Manufacture Preproduction Test Splice Plates |  | 20000 | Pending | Quotation
| S205100 | Procure Outer HCAL Splice Plates - Delivery Acceptance | [5 empty] | 266560
|  |  | Manufacture Splice Plates |  | 70000 | Pending | Conceptual Design
| S206200 | Procure Outer HCAL Lifting Fixtures and Supports - Delivery Acceptance | [5 empty] | 40000
|  |  | Manufacture Lifting Fixtures/Supports |  | 40000 | Pending | Engineering Estimate
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.04.02 | S203900 | Design Revision of Outer HCAL Splice Plates (Dog Bones) | Engineering Estimate | SCI | 32 | 144 | Complete
|  |  |  | PROF | 32
|  |  |  | TECH | 80
1.04.02 | S204000 | Internal Review of Inner HCAL Support Structure | Engineering Estimate | SCI | 16 | 32 | Complete
|  |  |  | PROF | 16
1.04.02 | S204100 | Address Issues from Internal Review of Outer HCAL Splice Plates | Engineering Estimate | SCI | 8 | 36 | Complete
|  |  |  | PROF | 8
|  |  |  | TECH | 20
1.04.02 | S204500 | Procure Outer HCAL Splice Plates - Provide Requirements to Procurement | Engineering Estimate | PROF | 36 | 72
|  |  |  | TECH | 36
1.04.02 | S204400 | Procure Preproduction Outer HCAL Splice Plates - Use in Test Assembly | Engineering Estimate | PROF | 0 | 40
|  |  |  | TECH | 40
1.04.02 | S205200 | Design Revision of Outer HCAL Lifting Fixture and Supports | Engineering Estimate | SCI | 16 | 72
|  |  |  | PROF | 16
|  |  |  | TECH | 40
1.04.02 | S205300 | Internal Review of Outer HCAL Lifting Fixture and Supports | Engineering Estimate | SCI | 8 | 24
|  |  |  | PROF | 8
|  |  |  | TECH | 8
1.04.02 | S205400 | Address Issues from Internal Review of Outer HCAL Lifting Fixture and Supports | Engineering Estimate | SCI | 8 | 36
|  |  |  | PROF | 8
|  |  |  | TECH | 20
1.04.02 | S205600 | Procure Outer HCAL Lifting Fixtures and Supports - Requirements to Procurement | Engineering Estimate | SCI | 36 | 180
|  |  |  | PROF | 72
|  |  |  | TECH | 72
|  | Grand Total |  |  | 424 | 424