## Procure HCAL Scint. Tiles
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-02-19
[7 empty] | Prepared By: | John G. Lajoie
[7 empty] | DocNo. (refer Rev. Log) | 155 v2
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Procure HCAL Scintillating Tiles |  |  |  | 1.04.03
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO DESIGN THE OUTER AND MANUFACTURE THE OUTER HADRONIC CALORIMETER SCINTILLATING TILE ASSEMBLIES. WORK STATEMENT: PROVIDE SCINTILLATING TILES FOR THE INNER AND OUTER HADRONIC CALORIMETER
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
Click for detailed summary
Guidelines Used in Developing Estimate
The cost estimate in this work item is based on a quotation for fully assembled outer HCAL scintillating tiles from Uniplast corporation in Vladimir, Russia. Uniplast has provided tiles assemblies for three test beam prototypes and has been intimately involved in the design of the inner and outer HCAL scintillating tiles.
Details of the Base Estimate (explanation of the Work)
The design labor in this estimate includes the design of all 24 different styles of scintillating tiles for the outer HCAL, including the mounting and fixtures to hold the tiles in place in the a assembled sector gaps. The tiles themselves will come from Uniplast fully assembled, including the wavelength shifter fiber installed in routed traces in the tile, and an integrated light block and SiPM holder with calibration fiber holder. The full assembly is fully wrapped and light-tight and each tile will be verified for mechanical specifications by Uniplast prior to shipment. Uniplast will also manufacture the calibration "pigtails" that will connect LED's to multiple to a set of 0.5mm fibers, that will then be routed to the individual tiles. These pigtials are currently undesigned and costed with a 40% uncertainty, captured under the LED scintillating fibers. As part of the project, BNL will provide the optical epoxy, wavelength shifting fiber, Tyvek wrap and LED calibration fibers. BNL will be responsible for the cost of shipping the tiles from Vladimir, Russia to BNL.
Cost Summary
(follow link for detailed summary)
[5 empty] | Materials Total | Labor Hours
[5 empty] | 1253131 | 1579
Uncertainty
Uncertainty is estimates at 40% for engineering estimates or for parts where a full design does not exist. Small orders for catalog items are assigned a 10-20% uncertainty. Engineering design time is assigned a 25% uncertainty based on past experience and the fact that each element includes rounds of review and time for additional redesign. Tech labor is assigned a 25% uncertainty based on experience with two previous test beam prototypes.

## Scint. Tiles - Detail
Materials
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.04.03 |  | Outer HCAL Scintillating Tiles | [6 empty] | 1253131
| S207600 | Procure Outer HCAL LED/Calibration Fibers - Delivery Acceptance | [5 empty] | 13050
|  |  | LED calibration system fibers | Ind. Fiber Optics/Uniplast | 13050 | Pending | Quotation
| S208300 | Procure Outer HCAL Scintillating Tiles - Delivery Acceptance | [5 empty] | 1240081
|  |  | Scintillating Tiles ($180/tile, 6365 tiles incl. 2% spares) | Uniplast | 1145700 | Pending | Budgetary Quotation
|  |  | Tile Retainer Clips (6365 @ $1/clip) | Uniplast | 6365 | Pending | Estimate
|  |  | Tyvec Wrap (8 sqf per large tile) and Kapton Tape | Uline | 9800 | Pending | Quotation
|  |  | Epoxy (EJ-500) (48x 600gm kits) | Eljen | 6816 | Pending | Quotation
|  |  | WLS Fibers (30km) | Kurary | 61400 | Pending | Quotation
|  |  | Materials Shipping to Uniplast |  | 10000 | Pending | Estimate
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.04.03 | S207500 | Procure Outer HCAL LED/Calibration Fibers - Labor | Estimate | SCI | 36 | 36
1.04.03 | S207700 | Procure Outer HCAL Scintillating Tile Production - Provide Requirements to Procurement | Estimate | SCI | 20 | 80 | Complete
|  |  |  | PROF | 40
|  |  |  | TECH | 20
1.04.03 | S207800 | Procure Outer HCAL Scintillating Tiles - Prepare and Send Solicitation | Estimate | SCI | 10 | 50 | Complete
|  |  |  | PROF | 30
|  |  |  | TECH | 10
1.04.03 | S208000 | Procure Outer HCAL Scintillating Tiles - Vendor Selection | Estimate | SCI | 10 | 30 | Complete
|  |  |  | PROF | 10
|  |  |  | TECH | 10
1.04.03 | S208400 / S204810 | Outer HCAL Scintillating Tile Acceptance Testing (two students testing, 25 tested tiles/day) On student on budget at $10/hr | Estimate (past experience) | SCI | 83 | 1543
|  |  |  | PROF | 120
|  |  |  | TECH | 40
|  |  |  | STUD | 1300
|  | Grand Total |  |  | 1579 | 1579