## Sector Assembly & Testing
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-02-19
[7 empty] | Prepared By: | John G. Lajoie
[7 empty] | DocNo. (refer Rev. Log) | 156 v2
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Outer HCAL Sector Assembly and Testing |  |  |  | 1.04.04
WBS Dictionary Definition:
TECHNICAL SCOPE: THIS ITEM CONTAINS ALL TASKS WHICH ARE REQUIRED TO ASSEMBLE THE PREPRODUCTION OUTER HADRONIC CALORIMETER SECTORS, AND ALL TASKS WHICH ARE REQUIRED TO ASSEMBLE THE PRODUCTION OUTER HADRONIC CALORIMETER SECTORS. WORK STATEMENT: PROVIDE PREPRODUCTION OUTER CALORIMETER SECTORS. PROVIDE PRODUCTION OUTER CALORIMETER SECTORS, READY FOR INSTALLATION INTO SPHENIX
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
Expert Opinion
Supporting Documents (including but not limited to):
Click for detailed summary
Guidelines Used in Developing Estimate
The bulk of the assumptions in this estimate are based on previous experience with the assembly of two test beam prototypes. The preproduction assembly area at BNL will consist of one assembly station with overhead crane coverage to allow for bringing in new sectors and sending out finished sectors for assembly. The production assembly area at BNL will consist of four separate assembly stations with overhead crane coverage to allow for bringing in new sectors and sending out finished sectors for assembly. It is an expanded version of the preproduction assembly area. All four stations will operate in parallel. Assembly consists of four steps (populate with tiles, electronics, test, cosmics calibration) and each stage is allocated five work days for completion. All stages and sectors will run in series.
Details of the Base Estimate (explanation of the Work)
The assembly process requires four steps: -> Scintillating tile installation -> Electronics Installation -> LED testing -> Cosmics calibration Based on past experince, we assume that each step will require one week with adequate schedule uncertainty. Scintillating tile installation will involve installing SiPM daugtherbords on the tile and installing them in the sector. Electronics installtion consists of installting the tower preamps and sector boards, cabling, and LED fibers installtion. LED testing will test each tile, and tiles/SiPMs that do not meet spec or appear to be dead will be repaired/replaced. Finally, cosmics data will be collected to set the initial tower calibration for the sector. This estimate assumes one full-time BNL technician for preproduction and two for production, and rigging labor for moving the modules. The bulk of the assembly will be done by collaboration students and postdocs.
Cost Summary
(follow link for detailed summary)
[5 empty] | Materials Total | Labor Hours
[5 empty] | 442269 | 19709
Uncertainty
Uncertainty is estimates at 40% for engineering estimates or for parts where a full design does not exist. Small orders for catalog items are assigned a 10-20% uncertainty. Engineering design time is assigned a 25% uncertainty based on past experience and the fact that each element includes rounds of review and time for additional redesign. Tech labor is assigned a 25% uncertainty based on experience with two previous test beam prototypes.

## Sector Assembly - Details
Materials
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Total | Grand Total
1.04.04 |  | Outer HCAL Scintillating Tiles (Preproduction) | [6 empty] | 442269
| S202200 | Procure Outer HCAL Scintillating Tiles (Preproduction) - Delivery Acceptance | Batch 1 |  |  |  |  | 111394
| S202300 | Procure Outer HCAL Scintillating Tiles (Preproduction) - Delivery Acceptance | Batch 2 |  |  |  |  | 111394
| S202400 | Procure Outer HCAL Scintillating Tiles (Preproduction) - Delivery Acceptance | Batch 3 |  |  |  |  | 95481
|  |  | Scintillating Tiles ($180/tile, 1469 tiles incl. 2% spares) | Uniplast | 264430 | Pending | Quotation
|  |  | Tile Retainer Clips (1469 @ $1/clip) | Uniplast | 1469 | Pending | Estimate
|  |  | Tile Retainer Clip Injection Molds | Uniplast | 10000 | Pending | Estimate
|  |  | Tyvec Wrap (8 sqf per large tile) | Home Depot | 15530 | Pending | Catalog
|  |  | Epoxy | EPOTEC | 4685 | Pending | Estimate
|  |  | WLS Fibers (7.5km) | Kurary | 19350 | Pending | Quotation
|  |  | Materials Shipping to Uniplast |  | 2805 | Pending | Estimate
| S202900 | Procure Table for Outer HCAL sector assembly and testing area (Preproduction) Material | [5 empty] | 15000
|  |  | Assembly and Testing Equipment |  | 15000 | Pending | Conceptual Design
| S203000 | Procure Miscellaneous Tools for HCAL sector assembly and testing area (Preproduction) Material | [5 empty] | 10000
|  |  | Assembly and Testing Equipment |  | 10000 | Pending | Conceptual Design
| S203400 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) Material | [5 empty] | 4800
|  |  | Light Tighting Materials |  | 4800 | Pending | Conceptual Design
| S203800 | Build Tile Test Box/Fixture Materials | [5 empty] | 3000 | Complete
|  |  | Tile Test Box Fixture Materials |  | 3000 | Pending | Conceptual Design
| S209600 | Procure Outer HCAL Assembly & Testing Equipment- Delivery Acceptance | [5 empty] | 75000
|  |  | Assembly and Testing Equipment |  | 75000 | Pending | Conceptual Design
| S210100 | Procure Outer HCAL LED Testing and Light Tighting Materials | [5 empty] | 19200
|  |  | Light Tighting Materials |  | 19200 | Pending | Conceptual Design
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.04.04 | S201300 | Procure Outer HCAL Scint. Tiles for Preproduction - Provide Requirements to Procurement | Estimate | CRAFT | 40 | 80 | Complete
|  |  |  | TECH | 40
1.04.04 | S201400 | Procure Outer HCAL Scint. Tiles for Preproduction - Prepare & Send Solicitation (STUD labor is one postdoc and one student) | Estimate | CRAFT | 8 | 48 | Complete
|  |  |  | TECH | 40
1.04.04 | S202500 / S202510 | Outer HCAL Scintillating Tile Acceptance Testing (Preproduction) (STUD is grad student and undergrad) | Estimate | PROF | 31 | 575
|  |  |  | SCI | 118
|  |  |  | TECH | 10
|  |  |  | STUD | 416
1.04.04 | S202700 | Procure Table for Outer HCAL sector assembly and testing area (STUD is grad student and postdoc) | Estimate | CRAFT | 5 | 20
|  |  |  | TECH | 5
|  |  |  | STUD | 10
1.04.04 | S202800 | Procure Tools for Outer HCAL sector assembly and testing area (STUD is grad student and postdoc) | Estimate | CRAFT | 5 | 20
|  |  |  | TECH | 5
|  |  |  | STUD | 10
1.04.04 | S203100 / S203110 | Populate Outer HCAL sectors with scintillating tiles (Preproduction) | Estimate | TECH | 372 | 1027
|  |  |  | SCI | 97
|  | (STUD labor is one postdoc and one student) |  | STUD | 558
1.04.04 | S203200 / S203210 | Populate Outer HCAL sectors with electronics (Preproduction) | Estimate | TECH | 372 | 1027
|  |  |  | SCI | 97
|  |  |  | STUD | 558
1.04.04 | S203300 / S203310 | Outer HCAL Sector LED testing and Light Tighting (Preproduction) Labor | Estimate | TECH | 248 | 903
|  |  |  | SCI | 97
|  |  |  | STUD | 558
1.04.04 | S203500 / S203510 | Outer HCAL Cosmics testing and initial calibration (Preproduction) | Estimate | STUD | 558 | 655
|  |  |  | SCI | 97
1.04.04 | S203600 | Outer HCAL Sector Transportation to Storage Area (Preproduction) | Estimate | TECH | 12 | 60
|  |  |  | CRAFT | 48
1.04.04 | S203700 | Build Tile Test Box/Fixture Labor | Estimate | TECH | 80 | 80 | Complete
1.04.04 | S209000 | Procure Outer HCAL Assembly & Testing Equipment - Provide Requirements to Procurement (STUD labor is one postdoc and one student) | Estimate | CRAFT | 80 | 160
|  |  |  | TECH | 80
1.04.04 | S209700 | Prepare Outer HCAL Assembly Area for Production (STUD labor is one postdoc and one student) | Estimate | CRAFT | 160 | 800
|  |  |  | TECH | 320
|  |  |  | STUD | 320
1.04.04 | S209800 / S209810 | Populate Outer HCAL sectors with scintillating tiles | Estimate | TECH | 1318 | 3867
|  |  |  | SCI | 209
|  |  |  | STUD | 2340
1.04.04 | S209900 / S209910 | Populate Outer HCAL sectors with electronics | Estimate | TECH | 1318 | 3867
|  |  |  | SCI | 209
|  |  |  | STUD | 2340
1.04.04 | S210000 / S210010 | Outer HCAL Sector LED Testing and Light Tighting | Estimate | TECH | 1318 | 3867
|  |  |  | SCI | 209
|  |  |  | STUD | 2340
1.04.04 | S210200 / S210210 | Outer HCAL Cosmics Testing and Initial Calibration | Estimate | STUD | 2340 | 2549
|  |  |  | SCI | 209
1.04.04 | S210300 | Outer HCAL Sector Transportation to Storage (CRAFT assumes 2 riggers x 4 hrs per module) | Estimate | TECH | 104 | 312
|  |  |  | CRAFT | 208
|  | Grand Total |  |  | 19709 | 19709
Tile acceptance testing assumes two undergrad/grad students, one paid by University contract, the other contributed.
Preproduction Assembly labor assumes one station, one undergrad student and one postdoc.
Assembly labor assumes four stations, two undergrad students per station. All four stations are supervised by one postdoc, labor divided equally between stations.
This yields 1040 + 1040 + 260 = 2340 STUD hours per station
Technician Labor assumes two technicians assigned to the factory, dividing time between the first three stations, minus 4 hrs per module for transportation