## OVERVIEW
|  |  | Labor (h) | Fixed Costs (Material)
|  |  | total | total | total w/est. Uncert. |  | Totals
1.03.02.01 | Set Up Module Production, Sector Assembly Test Area |  | 44 | 40600 | 0 |  |  | labor (h) | Materials ($)
[7 empty] | 1.03.02 | 51731 | 857713.7688
|  |  | total | total | total w/est. Uncert. | Set Up | 1.03.02.01 | 44 | 40600
1.03.02.02 | EMCal Module Production |  | 16859 | 365876 | 0 | Modules | 1.03.02.02 | 16859 | 365876
1.03.02.02.01 | V2.1 prototype |  | 0 | 0 | 0 | Sectors | 1.03.02.03 | 34828 | 451237.7688
1.03.02.02.02 | PreProduction Prototype (Sectors 0 -12) |  | 4769 | 96002 | 0
1.03.02.02.03 | Final Production (Sectors 13-64) |  | 12090 | 269874 | 0
|  |  | total | total | total w/est. Uncert.
1.03.02.03 | Sector Assembly |  | 34828 | 451237.7688 | 0
1.03.02.03.01 | V2.1 prototype |  | 0 | 0 | 0
1.03.02.03.02 | PreProduction Prototype (Sectors 0 -12) |  | 11265 | 128987.2594 | 0
1.03.02.03.03 | Final Production (Sectors 13-64) |  | 23563 | 322250.5094 | 0
Previous version: May 2018 OPA

## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
EMCAL |  | 1.03 |  | EMCAL Module Production and Sector Assembly |  | 1.03.02
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| Set Up Module Production, Sector Assmbly and Test Area |  | 1.03.02.01 |  | Set Up Area
| EMCAL Module Production |  | 1.03.02.02 |  | EMCAL Module Production
| EMCAL Sector Assembly |  | 1.03.02.03 |  | EMCAL Sector Assembly

## Set Up Area SUMMARY
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-23
[8 empty] | Prepared By: | Sean Stoll
[8 empty] | DocNo. (refer Rev. Log) | 141 v2
Work Package Name: |  |  |  |  | WBS Number: |  |  |  | Control Account Number
Set Up Module Production, Sector Assembly, and Test Area |  |  |  |  | 1.03.02.01
WBS Dictionary Definition:
Set up and organize space and furnishing for module and sector production work. This includes areas for receiving/unpacking, preparation and storage of blocks, assembly of modules, assembly of sectors, testing of assembled sectors, and storage of 64 completed sectors prior to installation. Equipment necessary to move and store ~900lb sectors.
Estimate Type (check all that apply):
Work Complete
| x | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| x | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| x | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
Two to three different workspaces will be needed for the different types of work required: - adequate access and proximity to machine shop for initial unpacking/handling, cleaner area for module assembly. Assume that space will be available with basic lighting and climate control, floor loading requirements - ground floor, with access for receiving/shipping/storing heavy items. Some existing work tables, storage shelves, cabinets may be available for use. Storage space will be needed to store 64 EMCal enclosurers and incoming blocks, evolving to storage of 64 completed sectors.
Details of the Base Estimate (explanation of the Work)
Set Up Area - Labor -Details
Cost Summary
Set Up Area - Materials - Details
[6 empty] | Labor |  | materials
|  | 1.03.02.01 | Set Up module Production, Sector Assembly and Test Area |  |  | total (h) |  | total
[6 empty] | 44 |  | 40600
[7 empty] | total | 40600
[6 empty] | total hours: | 44
Estimate Uncertainty
Most items are from catalog. Assembly required.

## Module Production SUMMARY
|  |  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-23
[8 empty] | Prepared By: | Sean Stoll
[8 empty] | DocNo. (refer Rev. Log) | 141 v2
Work Package Name: |  |  |  |  | WBS Number: |  |  |  | Control Account Number
EMCAL Module Production |  |  |  |  | 1.03.02.02
WBS Dictionary Definition:
Assembly of EMCal absorber blocks, received from UIUC, into modules of 4 blocks. This includes preparation of the blocks: attaching reflectors, light guides, and readout electronics to each block. Modules will be prepared in production runs for Sector 0, Sectors 1-12, and then Sectors 13-64.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
*The cost estimates are based on our experience processing blocks for the V2 and V2.1 prototypes and assembling the prototype detectors. We assume that the blocks for future prototypes and the final detector will be similar, and that the light guides, reflectors, and mounting hardware will not change significantly. We assume that the 2x2 tower absorber blocks will be produced at Univ of Illinois and delivered to BNL, correctly dimensioned and ready for assembly into sectors. The lightguides will be manufactured by an outside vendor and delivered to BNL - Some additional work (machining, tapping, polishing) will be required to prepare the lightguides. The electronic readout boards with sipms will be procured and assembled under a separate WBS item( WBS 1.5.1) and provided for the block assembly
Details of the Base Estimate (explanation of the Work)
As noted above, experience has been gained for the Modules in assembling prototypes of the same size and complexity for testing with Cosmics and at FNAL. The hours needed to do the work were noted and form the basis for estimating hours for the pre-production prototyping and the production work.
EMC Module Production - Labor -Details
Cost Summary
Module Production - MATERIALS
[7 empty] | Labor | Materials
[7 empty] | total (h) | total
|  | 1.03.02.02 | EMCal Module Production |  |  |  | 16859 | 365876
|  | 1.03.02.02.01 | EMCAL Prototype V2.1 Module Production |  |  |  | 0 | 0
|  | 1.03.02.02.02 | EMCAL PreProduction Prototype Module Production (sector 0 + sectors 1-12) |  |  |  | 4769 | 96002
|  | 1.03.02.02.03 | EMCAL Final Module Production (Sectors 13-64) |  |  |  | 12090 | 269874
[6 empty] | total hours: | 16859
Estimate Uncertainty
M& S Contingency Rules Applied

## Sector Assembly SUMMARY
EMCal
[5 empty] | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-23
[9 empty] | Prepared By: | Sean Stoll
[9 empty] | DocNo. (refer Rev. Log) | 141 v2
| Work Package Name: |  |  |  |  | WBS Number: |  |  |  | Control Account Number
| EMCAL Sector Assembly |  |  |  |  | 1.03.02.03
WBS Dictionary Definition:
Assembly of EMCAL modules into sectors: installation of modules into sector boxes, including attaching modules to backplane, installation of readout electronics, cabling, and cooling. This BOE covers the cost of construction of the EMCal Sectors in production runs for Sector 0, Sectors 1-12, and Sectors 13-64. The sector enclosures are of stainless steel sheet metal construction connected to a strongback and are supported by bearing blocks mounted to rails on the Inner HCal. There are 2 EMCal sectors (North and South) for each HCal sector.
Estimate Type (check all that apply):
Work Complete
|  | x | Existing Purchase Order
|  | x | Catalog Listing or Industrial Construction Database
|  | x | Documented Vendor Quotation based on Drawings/Sketches/Specifications
|  | x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
|  | x | Engineering Estimate based on Similar Items or Procedures
|  | x | Engineering Estimate based on Analysis
|  | X | Expert Opinion
Supporting Documents (including but not limited to):
(see Electronic BoE file [docdb) for supporting documentation
Assumptions Used in Developing Estimate
• 1.0 mm total deflection per sector (not including Inner Hcal and bearing block contributions) is acceptable to meet program objectives. More rigid structure may be required. *The cost estimates are based on our experience processing blocks for the V2 prototype and assembling the prototype detectors. We assume that the blocks for future prototypes and the final detector will be similar, and that the light guides, reflectors, and mounting hardware will not change significantly. We assume that the 2x2 tower absorber blocks will be produced at Univ of Illinois and delivered to BNL, correctly dimensioned and ready for assembly into sectors. The lightguides will be manufactured by an outside vendor and delivered to BNL - Some additional work (machining, tapping, polishing) will be required to prepare the lightguides. The electronic readout boards with sipms will be procured and assembled under a separate WBS item( WBS 1.5.1) and provided for the block assembly
Details of the Base Estimate (explanation of the Work)
Sector Assembly - Labor - Details
Cost Summary
(Sector Assembly - Materials - details)
[7 empty] | Labor | materials
[7 empty] | total (h) | total
|  |  | 1.03.02.03 | Sector Assembly |  |  | 34828 | 451237.7688
|  |  | 1.03.02.03.01 | V2.1 prototype |  |  | 0 | 0
|  |  | 1.03.02.03.02 | PreProduction Prototype |  |  | 11265 | 128987.2594
|  |  | 1.03.02.03.03 | Final Production |  |  | 23563 | 322250.5094
[6 empty] | total hours: | 34828
Estimate Uncertainty

## Set Up Area - Labor
WBS/Activity ID | ACTIVITY ID | Description |  | Duration (d) | Budgeted Labor (h) | Resource Name | Basis of Estimate | Grand Total |  | NOTES
1.03.02.01 |  | Set Up module Production, Sector Assembly and Test Area |  |  | 44 |  |  | 44
| S180200 | Set Up EMCal Final Module Prod and Sector Assembly Area | subtotal |  | 44
|  | Set up module productiction, sector assembly and test area |  | 80 | 18 | TECH3 PO M | past experience |  | "past experience" takes account of
|  | plan layout |  | 10 | 1 | SCI3 PO |  |  | setting up existing lab areas at BNL
|  | assemble/arrange shelving and cabinets |  | 10 | 5 | SCI3 PO |  |  | to produce prototypes of similar size and mass
|  | organize storage |  | 5 | 2 | SCI3 PO
|  | design custom fixtures for moving/handling sectors |  | 8 | 6 | SCI3 PO
|  | design/produce gluing fixtures to attach light guides |  | 8 | 6 | SCI3 PO
|  | design/produce gluing fixtures to assemble sectors |  | 10 | 6 | TECH3 PO M
| S180500 | Set Up EMCal Test Area | subtotal |  | 36 |  |  |  | Complete FY2018
|  | Set up test area |  | 40 | 16 | SCI3 PO | past experience
|  | set up DAQ/computers |  | 40 | 16 | TECH3 PO M
|  | set up cosmic test stand |  | 40 | 4 | SCI3 PO
| S180700 | Safety Review of Assembly and Test Areas | subtotal |  | 4 |  |  |  | Complete FY2018
|  | Safety Reviews |  | 5 | 4 | SCI3 PO | past experience
[6 empty] | Resource Name | Initials | Group
[6 empty] | ADMIN1 PO | A | Administrative
[6 empty] | PROF3 PO E | P | Engineering
[6 empty] | PROF3 PO M | P | Engineering
[6 empty] | PROF4 PO E | P | Engineering
[6 empty] | PROF4 PO M | P | Engineering
[6 empty] | SCI3 PO | S | Scientific
[6 empty] | TECH3 PO E | T | Technical
[6 empty] | TECH3 PO M | T | Technical
[6 empty] | TECH3 PO D | T | Technical
[6 empty] | JOBSHOP PO M | T | Technical

## Set Up Area -MATERIALS
WBS | ACTIVITY ID | Description | space req (ft^2) | Item | Vendor | Total | Status | Basis of Estimate | Grand Total
1.03.02.01 |  | Set Up module Production, Sector Assembly and Test Area | [6 empty] | 40600
| S180300 / S180400 | Set up EMCAL Final module production and sector assembly areas |  |  |  | 40600
|  | handling/lifting/moving sectors |  | Lift truck | McMaster | 5000 |  | catalog/web search
|  | carts for moving blocks / parts |  |  | McMaster | 500 |  | catalog/web search
|  | assembly/work tables |  | rolling work tables | McMaster | 2000 |  | catalog/web search
|  | assembly/work tables |  | stationary tables | McMaster | 1000 |  | catalog/web search
|  | supplementary lighting |  | bench lights | McMaster | 300 |  | catalog/web search
|  | power strips/misc electrical |  | power strips, extension cords | McMaster | 300 |  | catalog/web search
|  | storage for mechanical parts | 20 | cabinets | McMaster | 1000 |  | catalog/web search
|  | storage for light guides and electronics | 20 | cabinets | McMaster | 200 |  | catalog/web search
|  | storage for blocks | 1000 | unistrut storage shelves | McMaster | 1000 |  | catalog/web search
|  | storage for assembled blocks/modules | 500 | unistrut storage shelves | McMaster | 1000 |  | catalog/web search
|  | storage for electronic components | 1000 | cabinets | McMaster | 200 |  | catalog/web search
|  | storage shelves for 12 assembled sectors |  | storage shelves | McMaster | 2000 |  | catalog/web search
|  | storage shelves for 52 assembled sectors | 1500 | storage shelves | McMaster | 5500 |  | catalog/web search
|  | misc tools | 20 |  |  | 1000 |  | estimate
|  | desktop computers for logging data |  |  | Dell | 3000 |  | catalog/web search
|  | custom fixtures for moving/handling sectors |  | rails, stands, etc | custom | 3000 |  | quote, Eng estimate
|  | rail pallettes for handling/storage of sectors (1-12) | 16 | 1.5m rail segment + plywood base | Igus | 3200 |  | IGUS QUOTE |  | needed Apr 2019
|  | rail pallettes for handling/storage of sectors (13-64) | 52 | 1.5m rail segment + plywood base | Igus | 10400 |  | IGUS QUOTE |  | needed Apr 2020
| S180600 | Set Up EMCal Test Area |  |  |  | 3000 |  |  |  | Complete FY2018
|  | computer for measurements / logging data |  |  |  | 3000 |  | catalog/web search

## Mod Prod-Labor
WBS | ACTIVITY ID | Description | Item | Duration (days) | Task labor hours | Resource Name | Status | Grand Total | TECH | PROF | SCI
1.03.02.02 |  | EMCal Module Production |  | 898 | 16859 |  |  | 16859
1.03.02.02.01 |  | EMCAL Prototype V2.1 Module Production |  | 101 | 247 |  | complete
| S180800 | Design 2D projective blocks for v2.1 prototype |  | 10 | 40 |  | complete
| S180900 | Design screens for v2.1 prototype blocks |  | 5 | 20 |  | complete
| S181000 | Design light guides for v2.1 prototype blocks |  | 30 | 120 |  | complete
| S181100 | Procure light guides for v2.1 prototype modules |  | 50 | 4 |  | complete
| S181200 | Procure mechanical parts for V2.1 prototype modules |  | 30 | 3 |  | complete
| S181500 | Prepare light guides for V2.1 prototype |  | 5 | 40 |  | complete
| S181300 | Receive, unpack, log and inspect blocks for v2.1 prototpe |  | 1 | 8 |  | complete
inspect end surfaces / photograph
measure/log dimensions, weight
| S181600 | Install light guides on v2.1 prototype blocks |  | 4 | 4 |  | complete
sort, machine, polish
design/produce gluing fixtures for attaching LGs to blocks
epoxy LG to block (+ 24h epoxy curing time)
| S181400 | Install reflectors and glue v2.1 prototype blocks |  | 1 | 4 |  | complete
epoxy end reflector (+ 24h epoxy curing time)
| S181700 | Install SiPMs & daughterboards on v2.1 prototype blocks |  | 1 | 4 |  | complete
optically couple sipms/daughterboard to LG (+ 24h epoxy curing time)
1.03.02.02.02 |  | EMCAL PreProduction Prototype Module Production (sector 0 + sectors 1-12) |  |  | 4769
|  | Preproduction prototype (Sector 0) |  | subtotal: | 299
|  | produce gluing fixtures |  |  | 16 |  | complete
|  | assemble / epoxy 4 blocks into a module (+24h epoxy curing time) |  |  | 8 |  | complete
Past experience refers to experience with the
| S182300 | Design 2D projective blocks for preproduction prototype |  | 5 | 20 |  | complete |  | EMCal prototypes, which had similar shape, size
| S182400 | Design screens for preproduction prototype blocks |  | 5 | 20 |  | complete |  | and construction. We noted the hours
| S182500 | Design light guides for preproduction prototype |  | 5 | 20 |  | complete |  | needed for those tasks and use that as basis
| S182600 | Procure light guides for preproduction prototype modules for Sector 0 |  | 20 | 7 | SCI3 PO | complete
| S183100 | Procure mechanical parts for preproduction prototype modules for Sector 0 |  | 20 | 4 | PROF3 PO M | Past experience
| S183300 | Receive, unpack, log & inspect preproduction prototype blocks for sector 0 |  | 35 | 39 | PROF4 PO E, TECH3 PO M | Past experience |  | 7 | 32 | 0
inspect end surfaces / photograph
measure/log dimensions, weight
| S183700 | Install light guides on preproduction prototype blocks |  | 35 | 64 | PROF4 PO E, TECH3 PO M | Past experience |  | 32 | 32 | 0
sort, machine, polish
design/produce fixtures for epoxying LGs to blocks
epoxy LG to block (+ 24h epoxy curing time)
| S183500 | Install reflectors and mounting supports on preproduction prototype blocks |  | 35 | 64 | PROF4 PO E, TECH3 PO M | Past experience |  | 32 | 32 | 0
epoxy end reflector (+ 24h epoxy curing time)
| S183900 | Install SiPMs & daughterboards on preproduction prototype blocks |  | 5 | 64 | PROF4 PO E, TECH3 PO M | Past experience |  | 32 | 32
optically couple sipms/daughterboard to LG (+ 24h epoxy curing time)
| S184000 | Glue preproduction prototype blocks together into modules sector 0 |  | 5 | 64 |  |  |  | 32 | 32
|  | Preproduction prototype (Sectors 1-12) |  | subtotal | 4470
| S184200-800 | Procure light guides for Prepro Sector 1-12 modules |  |  | 0 | PROF3 PO M | Past experience
| S184900-185500 | Procure mechanical parts for Prepro Sector 1-12 modules |  | 40 | 40 | PROF3 PO M | Past experience
| S185700 | Receive, unpack, log & inspect Prepro Sectors 1-12 blocks |  | 120 | 846 | PROF4 PO E, TECH3 PO M | Past experience |  | 628 | 218
| S185900 | Install reflectors on blocks for Prepro Sector 1-12 modules |  | 120 | 896 | PROF4 PO E, TECH3 PO M | Past experience |  | 678 | 218
| S186000 | Install light guides on preproduction prototype blocks |  | 120 | 896 | PROF4 PO E, TECH3 PO M | Past experience |  | 678 | 218
| S186100 | Install SiPM daughterboards on blocks for Prepro Sector 1-12 modules |  | 120 | 896 | PROF4 PO E, TECH3 PO M | Past experience |  | 678 | 218
| S186200 | Glue blocks together into modules for Prepro Sector 1-12 modules |  | 120 | 896 | PROF4 PO E, TECH3 PO M | Past experience |  | 678 | 218
1.03.02.02.03 |  | EMCAL Final Module Production (Sectors 13-64) |  |  | 12090
| S186300 | Revise module production procedure based on preproduction prototype |  | 10 | 144 | PROF4 PO M | Past experience
| S186400 | Readiness Review for Final Module Production |  | 5 | 360 | PROF4 PO E, SCI3_PO_PM, SCI 4 | Past experience |  | 0 | 80 | 280
| S186500-187100 | Procure mechanical parts for final modules |  | 5 | 56 | TECH3 PO D | Past experience
sort and store parts
| S187200-400 | Procure light guides for final modules (completed during prePreod 1-12 phase)
sort and store LGs
|  | Procure epoxies for block module assembly | [6 empty] | SUBSUMED INTO THE SECTORS 1-12 WORK
Prepare LightGuides for final blocks
| S187500 | Receive, unpack, log & inspect final blocks |  | 290 | 2306 | PROF4 PO E, TECH3 PO M | Past experience |  | 1844 | 462
organize database for block data
inspect end surfaces / photograph
measure/log dimensions, weight
store blocks
| S187600 | Install light guides on final blocks |  | 290 | 2306 | PROF4 PO E, TECH3 PO M | Past experience |  | 1844 | 462
design/produce fixtures for epoxying LGs to blocks
machine, polish LGs
epoxy LG to block (+ 24h epoxy curing time)
| S187800 | Install reflectors and mounting supports on final blocks |  | 290 | 2306 | PROF4 PO E, TECH3 PO M | Past experience |  | 1844 | 462
epoxy end reflector (+ 24h epoxy curing time)
| S188800 | Install SiPMs & daughterboards on final blocks |  | 290 | 2306 | PROF4 PO E, TECH3 PO M | Past experience |  | 1844 | 462
optically couple sipms/daughterboard to LG (+ 24h epoxy curing time)
| S188200 | Glue final blocks together into modules |  | 290 | 2306 | PROF4 PO E, TECH3 PO M | Past experience |  | 1844 | 462
[7 empty] | Resource Name | Group
[7 empty] | ADMIN1 PO | Administrative
[7 empty] | PROF3 PO E | Engineering
[7 empty] | PROF3 PO M | Engineering
[7 empty] | PROF4 PO E | Engineering
[7 empty] | PROF4 PO M | Engineering
[7 empty] | SCI3 PO | Scientific
[7 empty] | TECH3 PO E | Technical
[7 empty] | TECH3 PO M | Technical
[7 empty] | TECH3 PO D | Technical
[7 empty] | JOBSHOP PO M | Technical

## Mod Prod - MATERIALS
WBS-ok | ACTIVITY ID | Description | Item | Vendor | Total | Status | Basis of Estimate | Grand Total
1.03.02.02 |  | EMCal Module Production |  |  | 365876 |  |  | 365876
1.03.02.02.01 |  | EMCAL Prototype V2.1 Module Production |  |  | 0
| S181800 | Procure light guides for V2.1 prototype modules | subtotal |  | 24510 | complete
|  |  | mold tooling | NN Inc | 17950 | complete | quote
|  |  | per part $ 8.20 x 800 |  | 6560 | complete | quote
| S181900 | Procure Mechanical parts for v2.1 prototype blocks | subtotal |  | 222 | complete
|  |  | 3M DP460 epoxy | McMaster | 25 | complete | catalog/web
|  |  | misc mech hdwr: nuts, screws, etcs | McMaster | 20 | complete | catalog/web
|  |  | 2-56 set screws and nuts (pcb to LG) | McMaster | 15 | complete | catalog/web
| S182100 | Procure EMCAL Prototype V2.1 Blocks & Modules - Delivery Acceptance
| S181600 | Install light guides on v2.1 prototype blocks | Saint Gobain BC600 optical epoxy | Saint Gobain | 96 | complete | catalog
|  | Produce LG gluing fixtures | light guide gluing fixtures | BNL |  | complete | 3D printed
| S182000 | Install reflectors and glue v2.1 prototype blocks | polished Al (1/16") 0.0625" thick | McMaster | 66 | complete | catalog
| S182200 | Install SiPMs & daughterboards on v2.1 prototype blocks | Momentive RTV615 couplant (stock) | Momentive | 0 | complete | catalog
1.03.02.02.02 |  | EMCAL PreProduction Module Production |  |  | 96002
|  | EMCAL PreProduction Module Production for Sector 0 |  |  | 2804
| S182700 | Procure light guides for preproduction prototype sector 0 | subtotal |  | 0 | complete
|  | 800/800 from V2.1 quote/order | already purchased during V2.1 | NN Inc | 0 | complete
| S182800-900 | Procure mechanical parts for modules for preproduction prototype sector 0 | subtotal |  | 2164
|  |  | misc hdwr | McMaster | 500 |  | catalog/web
|  |  | 2-56 set screws and nuts (pcb to LG) | McMaster | 48 |  | catalog/web
|  |  | polished Al reflective end plates (8 shapes) | BNL shops | 1200 |  | quote
|  |  | Momentive RTV615 for optical coupling sipms to LGs | Momentive | 320 |  | catalog/web
|  |  | StGob BC600 for coupling LGs & refl to blocks | StGobain | 96 |  | catalog/web
| S183200 | Receive, unpack, log & inspect preproduction prototype blocks sector 0 M&S |  |  | 25
| S183400 | Install reflectors on preproduction prototype blocks sector 0 | gluing fixtures |  | 350 |  | eng estimate
| S183600 | Install light guides on preproduction prototype blocks sector 0 | light guide gluing fixtures | BNL | 265 |  | estimate
|  | EMCAL PreProduction Module Production for Sectors 1-12 |  |  | 93198
| S184800 | Procure light guides for Prepro Sector 1-12 modules | 6200 pieces including machining, mold mod, and fixtures | NN Inc | 79700 |  | quote #BR02622 Jan 2019
| S185500 | Procure mechanical parts for Prepro Sector 1-12 modules | subtotal |  | 13148
|  |  | misc hdwr | McMaster | 1000 |  | engin est.
|  |  | 2-56 set screws and nuts (pcb to LG) | McMaster | 576 |  | catalog
|  | Al reflective plates | polished Al reflective end plates (8 shapes) | Eclipse Metal | 10740 |  | Eclipse Quote
|  |  | Momentive RTV615 for optical coupling sipms to LGs | Momentive | 640 |  | catalog
|  |  | StGob BC600 for coupling LGs & refl to blocks | StGobain | 192 |  | catalog
| S185600 | Receive, unpack, log & inspect blocks for Prepro Sectors 1-12 |  |  | 0 |  |  |  | not clear any materials are needed
| S185800 | Install reflectors on blocks for Prepro Sector 1-12 modules | gluing fixtures |  | 350 |  | engin est.
1.03.02.02.03 |  | EMCAL Final Module Fabrication |  |  | 269874 |  |  |  | (0.75 x 0.77 75% remaining, descoped x 0.77))
Revise module production procedure based on preproduction prototype
Readiness Review for Final module production
| S186500-187100 | Procure mechanical parts for final modules | subtotal |  | 52680
|  |  | misc hdwr | McMaster | 5000 |  | catalog/web
|  |  | 2-56 set screws and nuts (pcb to LG) | McMaster | 7200 |  | catalog/web
|  | Procure epoxies for block-module assembly | Momentive RTV615 for optical coupling sipms to LGs | Momentive | 3200 |  | catalog/web
|  |  | StGob BC600 for coupling LGs & refl to blocks | StGobain | 1920 |  | catalog/web |  | 32 x $158/500ml kit 9/2017
|  | Al reflective plates | Polished Al reflectors (8 shapes,52 sect.) | Eclipse | 35360 |  | Eclipse Quote
| S187200-400 | Procure light guides for final blocks | subtotal |  | 215244
|  | sectors 13-64 | including machining | NN Inc | 215244 |  | NN Quote
|  |  | per part @$10.7622 x 20000 (updated Jan/19) | NN Inc
| S187700 | Install light guides on final blocks | subtotal |  | 1650
|  | produce fixtures for epoxying LGs to blocks | light guide gluing fixtures | BNL | 1650 |  | engin est
| S187900 | Install Reflectors on final blocks | [6 empty] | No added materials needed
| S188100 | Install SiPMs daughterboards on final blocks M&S |  |  | 300

## Sector Assembly - Labor
WBS | ACTIVITY ID | Description | Item | Duration (d) | Task Labor Hours | Resource Name | Status | Grand Total | TECH | PROF | SCI | STU
1.03.02.03 |  | EMCal Sector Assembly |  |  | 34828 |  |  | 34828
1.03.02.03.01 |  | EMCAL Prototype V2.1 Module Production |  |  | 0
| S188300 | Design Cooling System for v2.1 |  | 30 | 72 |  | complete
| S188400 | Procure parts for cooling system for V2.1 prototype |  | 110 | 8 |  | complete
| S188500 | Prepare mounting supports for V2.1 prototype | assemble frame/enclosure | 3 | 24 |  | complete
| S188600 | Install blocks in v2.1 prototype |  | 2 | 8 | TECH3 PO M | complete
| S188700 | Install readout electronics on v2.1 prototype |  | 1 | 4 |  | complete
| S188900 | Install cooling system on v2.1 prototype |  | 5 | 6 |  | complete
| S189000 | Test v2.1 prototype with LEDs & cosmic rays |  | 34 | 240 | PROF4 PO E | complete
| S189100 | Pack & ship v2.1 prototype to Fermilab |  | 4 | 6 | PROF4 PO E, TECH3 PO M | complete |  | 4 | 2
| S189300 | Test v2.1 prototype in test beam |  | 26 | 1212 | PROF4 PO E, TECH3 PO M, STU, SCI 4 | complete |  | 12 | 240 | 480 | 480
| S189500 | Analyze test beam results from v2.1 prototype |  | 10 | 800 | STU, SCI 4 | complete |  |  |  | 160 | 640
1.03.02.03.02 |  | EMCAL Preproduction Prototype Sector Assembly and testing (Sector 0 & sectors 1-12) |  | 285 | 11265
|  | Preproduction prototype (Sectors 0) |  |  | 2036
| S189700 | Design mechanical enclosure for preproduction prototype Sector 0 |  | 60 | 48 | TECH3 PO D | complete
| S189800 | Design mechanical support structure for preproduction prototype Sector 0 |  | 60 | 48 | TECH3 PO D | complete
| S189900 | Design cooling system for preproduction prototype Sector 0 |  | 60 | 128 | PROF4 PO M, TECH3 PO D | complete |  | 32 | 96
| S190400-500 | Procure mechanical parts for preproduction prototype Sector 0 |  | 30 | 18 | TECH3 PO D | Past experience
| S190600-700 | Procure parts for cooling system for preproduction prototype Sector 0 |  | 40 | 18 | PROF4 PO M | Past experience
| S191000 | Build mechanical enclosure for preproduction prototype Sector 0 |  | 20 | 48 | TECH3 PO M | Engineering judgement
| S191100 | Build mechanical support for preproduction prototype Sector 0 |  | 20 | 48 | TECH3 PO M | Engineering judgement
| S191200 | Build cooling system for preproduction prototype Sector 0 |  | 30 | 48 | TECH3 PO M | Engineering judgement
| S191300 | Install modules in preproduction prototype Sector 0 |  | 5 | 128 | PROF4 PO E, TECH3 PO M | Engineering judgement |  | 96 | 32
| S191400 | Install readout electronics on preproduction prototype Sector 0 |  | 20 | 128 | PROF4 PO E, TECH3 PO E, TECH3 PO M | Engineering judgement |  | 96 | 32
| S191500 | Install cables and cooling system on preproduction prototype Sector 0 |  | 20 | 96 | PROF4 PO E, PROF4 PO M, TECH3 PO M | Engineering judgement |  | 32 | 64
| S191600 | Revise module and sector design based on performance of Sector 0 |  | 20 | 440 | PROF4 PO E, SCI3_PO_PM, SCI 4 | Engineering judgement |  |  | 160 | 280
| S191700 | Test preproduction prototype Sector 0 with LEDs & cosmic rays |  | 20 | 208 | PROF4 PO E, STU, SCI 4 | Past experience |  |  | 32 | 16 | 160
| S191800 | Analyze test results from preproduction prototype Sector 0 |  | 20 | 416 | SCI3 PO, STU, SCI 4 | Past experience |  |  |  | 96 | 320
| S191900 | Performance review of preproduction prototype Sector 0 |  | 5 | 440 | PROF4 PO E, SCI3_PO_PM, SCI 4 | Past experience |  |  | 160 | 280
|  | Preproduction prototype (Sectors 1-12) | Assumes avg production rate 1 sector/10days for initial production |  | 9229
| S192100 | Readiness Review for Prepro Sectors 1-12 |  | 1 | 8 | SCI3 PO | Past experience
| S192200-800 | Procure mechanical parts for Prepro Sectors 1-12 |  | 30 | 24 | TECH3 PO D | Past experience
| S192900-193500 | Procure parts for cooling system for Prepro Sectors 1-12 |  | 30 | 24 | PROF4 PO M | Past experience
| S193600 | Build mechanical enclosure for Prepro Sectors 1-12 |  | 30 | 336 | TECH3 PO M | Engineering judgement
| S193700 | Build mechanical support for Prepro Sectors 1-12 |  | 30 | 336 | TECH3 PO M | Engineering judgement
| S193800 | Build cooling system for Prepro Sectors 1-12 |  | 30 | 216 | TECH3 PO M | Engineering judgement
| S193900 | Install modules in Prepro Sectors 1-12 |  | 120 | 1332 | PROF4 PO E, TECH3 PO M | Engineering judgement |  | 1114 | 218
| S194000 | Install readout electronics on Prepro Sectors 1-12 |  | 120 | 1332 | PROF4 PO E, TECH3 PO E, TECH3 PO M | Engineering judgement |  | 1114 | 218
| S194100 | Install cables and cooling system on Prepro Sectors 1-12 |  | 120 | 1812 | PROF4 PO E, PROF4 PO M, TECH3 PO M | Engineering judgement |  | 986 | 826
| S194200 | Test preproduction sectors 1-12 with LEDs & cosmic rays |  | 120 | 2086 | PROF4 PO E, STU, SCI 4 | Past experience |  |  | 218 | 170 | 1698
| S194300 | Analyze test results from Prepro Sectors 1-12 |  | 120 | 1723 | SCI3 PO, STU, SCI 4 | Past experience |  | 231 | 154 | 250 | 1088
1.03.02.03.03 |  | EMCAL Final Sector Assembly (Sectors 13-64) |  |  | 23563
|  | Final Production (Sectors 13-64) | Assumes increased avg production rate 1 sector/6 days for "Full" production
|  | Design mechanical structure for final EMCAL | Already done for sectors 1-12
|  | Design mechanical fixtures for final sectors | Already done for sectors 1-12
|  | Design cooling system for final sectors | Already done for sectors 1-12
| S194500 | Revise sector assemby procedure based on preproduction prototype |  | 20 | 144 | PROF4 PO M | Engineering judgement
| S194600 | Readiness Review for final sector 13-64 production |  | 5 | 360 | PROF4 PO E, SCI3_PO_PM, SCI 4 | Past experience |  |  | 80 | 280
| S194800-195400 | Procure mechanical parts for final sectors |  | 5 | 56 | TECH3 PO D | Past experience
| S195500-196100 | Procure parts for cooling system for final sector production |  | 5 | 56 | PROF4 PO M | Past experience
| S196200 | Build mechanical enclosures for final sectors |  | 60 | 720 | TECH3 PO M | Engineering judgement
| S196300 | Build mechanical fixtures for final sectors |  | 60 | 720 | TECH3 PO M | Engineering judgement
| S196400 | Build cooling system for final sectors |  | 60 | 180 | PROF4 PO M | Engineering judgement
| S196500 | Install modules in final sectors |  | 290 | 3228 | PROF4 PO E, TECH3 PO M | Engineering judgement |  | 2766 | 462
| S196700 | Install readout electronics on final sectors |  | 290 | 3228 | TECH3 PO M, PROF4 PO E | Engineering judgement |  | 2766 | 462
| S196800 | Install cables & cooling system on final sectors |  | 290 | 4956 | PROF4 PO E, PROF4 PO M, TECH3 PO M | Engineering judgement |  | 2766 | 2190
| S196900 | Test final sectors with LEDs & cosmic rays |  | 290 | 5994 | PROF4 PO E, TECH3 PO E, STU | Past experience |  | 924 | 462 |  | 4608
| S197000 | Repair or rework any sectors as required |  | 290 | 3921 | PROF4 PO M, TECH3 PO M, STU, SCI 4, PROF4 PO E, TECH3 PO E | Past experience |  | 693 | 462 | 462 | 2304
| S197200 | Installation Readiness Review |  | 10 |  |  | Past experience |  | NEED TO ASSIGN HOURS HERE AND IN P6 - 40 each SCI AND PROF
Resource Name | Initials | Group
ADMIN1 PO | A | Administrative
PROF3 PO E | P | Engineering
PROF3 PO M | P | Engineering
PROF4 PO E | P | Engineering
PROF4 PO M | P | Engineering
SCI3 PO | S | Scientific
TECH3 PO E | T | Technical
TECH3 PO M | T | Technical
TECH3 PO D | T | Technical
JOBSHOP PO M | T | Technical

## Sector Assembly -MATERIAL
WBS | ACTIVITY ID | Description | Item | Vendor | Total | Status | Basis of Estimate | Grand Total
1.03.02.03 |  | EMCal Sector Assembly |  |  | 451237.7688 |  |  | 451237.7688
1.03.02.03.01 |  | EMCAL Prototype V2.1 Production |  |  | 0
| S188800 | Procure parts for cooling system for V2.1 prototype M&S | misc parts |  | 2500 | complete | catalog
| S188600 | Install blocks in v2.1 prototype | misc hdwr: screws, etc | McMaster | 5 | complete | catalog
|  | Install readout electronics on v2.1 prototype | misc screws/hdwr | McMaster | 5 | complete | catalog
|  | Install cooling system on v2.1 prototype | misc screws/hdwr | McMaster | 5 | complete | catalog
|  | Test v2.1 prototype with LEDs & cosmic rays | existing test stand |  |  | complete
| S189200 | Pack & ship v2.1 prototype to Fermilab M&S |  |  | 3000 | complete | estimate
| S189400 | Test v2.1 prototype in test beam at Fermilab M&S |  |  | 200 | complete | estimate
| S189600 | Completion of v2.1 prototype |  |  |  | complete
1.03.02.03.02 |  | EMCAL Preproduction - Sector Assembly and testing (Sectors 0, 1-12) |  |  | 128987.2594 |  |  |  |  | 242759.1094
|  | Preproduction prototype (Sector 0) |  |  | 35111.0219 |  |  |  |  | 24608.4219
| S190200-300 | Procure mechanical parts for preproduction prototype Sector 0 M&S FY19 | subtotal (one sector parts + jigs/fixtures) |  | 32205.1 |  |  |  |  | 19171
|  |  | sector box (x2) | Eclipse | 3981.1 | pending | quote
|  |  | rails and rail blocks for 1 sector | IGUS | 987.42 | complete | quote
|  |  | sawtooth supports 8 pieces (x2) | SBU shop | 23889 | ordered | quote
|  |  | misc hardware | McMaster | 335 |  | catalog
|  |  | subtotal 1 sector + spare |  | 28205.1 |  |  |  |  | 15171
|  |  | jigs and fixtures |  | 4000 |  | estimate |  |  | 4000
| S190800-900 | Procure parts for cooling system for preproduction prototype (Sector 0) | subtotal |  | 2405.9219 |  |  |  |  | 4937.4219
|  | Interior Sector 0 (updated 2/5/2019) | Alum PreAmp Cooling plate | Eclipse | 882 |  | Eclipse quote
|  | PreAmp Loop | Fittings | Mcmaster | 287.1094 |  | web quote
|  |  | thermal gap pads | Digikey | 419.5312 |  | web quote
|  |  | Thermal epoxy | Omega | 90.2344 |  | web quote
|  |  | hardware | Mcmaster | 46.875 |  | estimate
|  |  | Thermal paste | Omega | 51.5625 |  | quote
|  |  | Copper tubing (3/8") | Mcmastr | 137 |  | web quote
SIPM Cooling Loop
|  |  | Copper tubing (1/4") | McMcaster | 70.3125 |  | web Quote
|  |  | Copper tabs | mcmaster | 58.5938 |  | web quote
|  |  | thermal strap | Digikey | 105.4688 |  | estimate
|  |  | thermal Gap Pad adhesive | digikey | 32.8125 |  | quote
|  |  | Solder | Mcmaster | 15.2344 |  | quote
Interface Board
|  |  | Copper tubing (3/8") | mcmaster | 137 |  | web quote
|  |  | thermal Gap Pad | Digikey | 49.2188 |  | web quote
|  |  | Copper Pads | Mcmaster | 22.9688 |  | web quote
| S191110 | Build mechanical stand/support for preproduction prototype (Sector 0) | subtotal |  | 500 |  | estimate | (left out of P6) |  | 500
|  | Preproduction prototype (Sectors 1-12) |  |  | 93876.2375 |  |  |  |  | 218150.6875
| S192200-810 | Procure mechanical parts for preproduction prototype sectors 1-12 | subtotal (12 sectors worth + jigs/fixtures) |  | 73596.3 |  |  |  |  | 175889
|  |  | sector box (x12) | Eclipse | 15294.3 |  | quote
|  |  | rails and rail blocks for 1 sector ($375.75 /sector) | IGUS | 4510 |  | quote
|  |  | sawtooth supports (8 pcs/sector) | SBU Shop | 43552 |  | quote
|  |  | misc hardware | McMaster | 3840 |  | catalog
|  |  | 3M DP460 epoxy | McMaster | 2400 |  | catalog
|  |  | subtotal 13 sectors |  | 69596.3 |  |  |  |  | 171889
|  |  | jigs and fixtures |  | 4000 |  | estimate |  |  | 4000
| S193500 | Procure parts for cooling system for preproduction prototype (Sectors 1-12) | subtotal |  | 19779.9375 |  |  |  |  | 41761.6875
|  | Interior Sector 1-12 plus 4 process spare | Alum PreAmp Cooling plate & support mount | Eclipse | 4642.5 |  | quote
|  | PreAmp Loop | Fittings | McMaster | 2985.9375 |  | web quote
|  |  | thermal gap pads | Digikey | 4363.125 |  | web quote
|  |  | Thermal epoxy | Omega | 938.4375 |  | web quote
|  |  | hardware | McMaster | 487.5 |  | estimate
|  |  | Thermal paste | Omega | 536.25 |  | quote
|  |  | Copper tubing (3/8") | McMaster | 1407 |  | web quote
SIPM Cooling Loop
|  |  | Copper tubing (1/4") | McMaster | 731.25 |  | web quote
|  |  | Copper tabs | McMaster | 609.375 |  | web quote
|  |  | thermal strap | Digikey | 1096.875 |  | estimate
|  |  | thermal Gap Pad adhesive | Digikey | 341.25 |  | quote
|  |  | Solder | McMaster | 158.4375 |  | quote
Interface Board
|  |  | Copper tubing (1/4") | McMaster | 731.25 |  | web quote
|  |  | thermal Gap Pad | Digikey | 511.875 |  | web quote
|  |  | Copper Pads | McMaster | 238.875 |  | web quote
| S193710 | Build mechanical stand/support for preproduction prototype (Sectors 1-12) | subtotal |  | 500 |  | estimate | (Left out of P6)
1.03.02.03.03 |  | EMCAL Final Sector Assembly (remaining 53 sectors, Descoped by x 0.77) |  |  | 322250.5094 |  |  |  | This is $63,000 low
| S194800-195400 | Procure mechanical parts for final sectors - deliv accpt. | subtotal |  | 251357.4 |  |  |  | See note below on cooling
|  | Sheet Metal Boxes (from Dan C. 7/2017) | sector box (6 sides) | Eclipse | 44068.4 |  | quote |  | S196100
|  | Absorber Block Supports (custom) | rails and rail blocks | IGUS | 14302 |  | quote
|  |  | sawtooth supports (2x4/sect) | SBU shop | 164832 |  | quote
|  |  | 3M DP460 epoxy | McMaster | 12000 |  | catalog/web
|  |  | misc hardware | McMaster | 11520 |  | catalog
|  |  | subtotal |  | 246722.4
|  |  | jigs and fixtures | BNL | 4635 |  | estimate
| S195500- 196100 | Procure parts for cooling system for final sectors |  |  | 70893.1094 |  |  |  | P6 has an error
|  | Interior 52 sectors plus 1 process spare | Alum PreAmp Cooling plates | Eclipse | 14364 |  | quote |  | It lists $7,893, not $70,893
|  | PreAmp Loop | Fittings | McMaster | 11158.9844 |  | web quote |  | Exactly $63,000 too low
|  |  | thermal gap pads | Digikey | 16305.7813 |  | web quote |  | Left out a "0" in enterring value
|  |  | Thermal epoxy | Omega | 3507.1094 |  | web quote
|  |  | hardware | McMaster | 1821.875 |  | estimate
|  |  | Thermal paste | Omega | 2004.0625 |  | quote
|  |  | Copper tubing (3/8") | McMaster | 5216 |  | web quote
SIPM Cooling Loop
|  |  | Copper tubing (1/4") | McMcaster | 2732.8125 |  | web Quote
|  |  | Copper tabs | McMaster | 2277.3438 |  | web quote
|  |  | thermal strap | Digikey | 4099.2188 |  | estimate
|  |  | thermal Gap Pad adhesive | Digikey | 1275.3125 |  | quote
|  |  | Solder | McMaster | 592.1094 |  | quote
Interface Board
|  |  | Copper tubing (1/4") | McMaster | 2732.8125 |  | web quote
|  |  | thermal Gap Pad | Digikey | 1912.9688 |  | web quote
|  |  | Copper Pads | McMaster | 892.7188 |  | web quote

## Quotations
IGUS QUOTE