## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
Calorimeter Electronics |  | 1.05 |  | Calorimeter Frontend Electronics |  | 1.05.02
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| EMCal Electronics: Preproduction Prototype |  | 1.05.02.01 |  | WBS1.05.02.01 Basis of Estimate
| EMCal Electronics: Production |  | 1.05.02.02 |  | WBS1.05.02.02 Basis of Estimate
| HCal Electronics: Preproduction Prototype |  | 1.05.02.03 |  | WBS1.05.02.03 Basis of Estimate
| HCal Electronics: Production |  | 1.05.02.04 |  | WBS1.05.02.04 Basis of Estimate
| WBS 1.5.2 System Costing |  | 1.05.02 |  | WBS1.05.02 System Costs
| Control Account |  | Description
| Calorimeter Frontend Electornics |  | This account is responsible for the design, layout, procurement of all components, assembly and Q/A testing of the front end electronics for the EMCal and HCal preproduction and production electronics.
Note on K15: Eric Mannel:
Note on D21: Eric Mannel:

## WBS1.05.02.01 BoE
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-04
[7 empty] | Prepared By: | E. J. Mannel
[7 empty] | DocNo. (refer Rev. Log) | 66 v20
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
EMCal Electronics: Preproduction Prototype |  |  |  | 1.05.02.01
WBS Dictionary Definition:
The work package covers the design, layout, fabrication and Q/A testing of the EMCal preproduction prototype electroncs. The front end electronics includes the all front end analog circuits, excluding the SiPM components (WBS 1.5.1), the digital control and monitoring electronics, signal and power cables "on detector", and power systems. It will deliver a total of 4992 channels of EMCal front end electornics for installation on the preproduction EMCal modules 0-6. Installation and post-installation testing are part of WBS 1.3.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Task Summary
Costing
Guidelines Used in Developing Estimate
The following guideline were used in the cost estimate: 1) For designed boards, the bill of materials was used to look up catalog prices for all components. 2) Printed circuit board and assembly costs were estimated on early R&D production or production of similar design and functionality. 3) Commercial vendors are assumed for all board fabrication and assembly. 4) Costs include a 10% loss due to yield. The following guidelines were used for the time estimates: 1) Component/PCB orders are less then $10K per order, <1 month for PO to be issued. 2) Componets catalog items with short lead times, 1 month delivery AOR. 3) PCBs are standard type PCBs with not special fabrication requirements and have standard delivery times, 2-3 weeks. 5) Board assembly is done by assembly houses and requires no non-standard assembly procedures. Post-assembly testing is done "in-house" by BNL/Collaboration engineers, technicians and students. Installation on detector and post-installation testing are part of EMCal Preproduction Prototype module assembly, WBS 1.3
Details of the Base Estimate (explanation of the Work)
This work package covers the preproduction design, layout, fabrication and Q/A testing of the EMCal frontend electronics. The design and layout stages covers all modifications to earlier prototype designs. Procurement covers obtaining all quotes, placing and tracking orders, and receipt of orders. Q/A testing covers the cost of all test equipment and the testing of the fabricated modules prior to installation.
Cost Summary
|  | Task | Cost Basis |  | Cost | Cost + %Design Uncertainty
|  | Board Assembly and Testing: Sector 0 | Catalogue/Quote/Eng Estimate |  | 41464.7189 | 47289.3205
|  | Total Cost: Sector 0 |  |  | 41464.7189 | 47289.3205
|  | Board Assembly and Testing: Sector 1-12 | Catalogue/Quote/Eng Estimate |  | 457863.0015 | 570224.3157
|  | Total Cost: Sector 1-12 |  |  | 457863.0015 | 570224.3157
|  | Total Cost |  |  | 499327.7205 | 617513.6362
Design Uncertainty
For Parts: M3 (20%) Based on BOMs for most recent prototypes
For Assembly: M4 (30%) Engineering estimate based on last round of prototype assembly.
For Cables: M4 (40%) Engineering estimate based on early prototype
BNL Labor for design, layout, assembly oversight, and testing oversight: L3 (25%)

## WBS1.05.02.02 BoE
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-04
[7 empty] | Prepared By: | E. J. Mannel
[7 empty] | DocNo. (refer Rev. Log) | 66 v20
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
0EMCal Electronics: Production |  |  |  | 1.05.02.02
WBS Dictionary Definition:
The work package covers the design, layout, fabrication and Q/A testing of the EMCal production electroncs. The front end electronics includes the all front end analog circuits, excluding the SiPM components (WBS 1.5.1), the digital control and monitoring electronics, signal and power cables "on detector", and power systems for EMCal Sectors 13-64. There are a total of 14976 channels in these modules. This portion of the WBS includes Q/A testing of delivered electronics. Installation and post installation testing are covered under WBS 1.3
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Task Summary
Costing
Guidelines Used in Developing Estimate
The following guideline were used in the cost estimate: 1) For designed boards, the bill of materials was used to look up catalog prices for all components. 2) Printed circuit board and assembly costs were estimated on early R&D production or production of similar design and functionality. 3) Commercial vendors are assumed for all board fabrication and assembly. 4) Costs include a 10% loss due to yield. The following guidelines were used for the time estimates: 1) Component/PCB orders are less then $100K per order, 3 month for PO to be issued. 2) Componets catalog items with short lead times, 1 month delivery AOR. 3) PCBs are standard type PCBs with not special fabrication requirements and have standard delivery times, 4-6 weeks. 5) Board assembly is done by assembly houses and requires no non-standard assembly procedures. Post-assembly testing is done "in-house" with Collaboration contributed labor and oversite by BNL/Collaboration engineers and technicians. Installation on detector and post-installation testing are part of EMCal Production module assembly, WBS 1.3
Details of the Base Estimate (explanation of the Work)
This work package covers the preproduction design, layout, fabrication and Q/A testing of the EMCal frontend electronics. The design and layout stages covers all modifications to earlier prototype designs. Procurement covers obtaining all quotes, placing and tracking orders, and receipt of orders. Q/A testing covers the cost of all test equipment and the testing of the fabricated modules prior to installation. This workpackage also includes the controller boards required for HCal which are identical in design and functionality. Installation of electronics and post-installation are part of EMCal module assembly.
Cost Summary
|  | Task | Cost Basis |  | Cost | Cost + %Design Uncertianty
|  | Board Assembly and Testing | Catalogue/Quote/Eng Estimate |  | 1333694.5918 | 1333694.5918
|  | Total Work Package Cost |  |  | 1333694.5918 | 1333694.5918
Design Uncertianty
For Parts: M3 (20%) Based on BOMs for most recent prototypes
For Assembly: M4 (30%) Engineering estimate based on last round of prototype assembly.
For Cables: M4 (40%) Engineering estimate based on early prototype
BNL Labor for design, layout, assembly oversight, and testing oversight: L3 (25%)
Univeristy Students for testing: L3 (25%)

## WBS1.05.02.03 BoE
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2017-03-20
[7 empty] | Prepared By: | E. J. Mannel
[7 empty] | DocNo. (refer Rev. Log) | 66 v20
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
HCal Electronics: Preproduction Prototype |  |  |  | 1.05.02.03
WBS Dictionary Definition:
The work package covers the design, layout, fabrication and Q/A testing of the HCal preproduction prototype electroncs. The front end electronics includes the all front end analog circuits, excluding the SiPM components (WBS 1.5.1), the digital control and monitoring electronics, signal and power cables "on detector", and power systems. It will deliver a total of 288 channels of HCal front end electornics for installation on the HCal modules 1-6. Installation and post-installation testing are part of WBS 1.4.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Task Summary
Costing
Guidelines Used in Developing Estimate
The following guideline were used in the cost estimate: 1) For designed boards, the bill of materials was used to look up catalog prices for all components. 2) Printed circuit board and assembly costs were estimated on early R&D production or production of similar design and functionality. 3) Commercial vendors are assumed for all board fabrication and assembly. 4) Costs include a 10% loss due to yield. The following guidelines were used for the time estimates: 1) Component/PCB orders are less then $10K per order, <1 month for PO to be issued. 2) Componets catalog items with short lead times, 1 month delivery AOR. 3) PCBs are standard type PCBs with not special fabrication requirements and have standard delivery times, 2-3 weeks. 5) Board assembly is done by assembly houses and requires no non-standard assembly procedures. Post-assembly testing is done "in-house" by BNL/Collaboration engineers, technicians and students. Installation on detector and post-installation testing are part of HCal Preproduction Prototype module assembly, WBS 1.4
Details of the Base Estimate (explanation of the Work)
This work package covers the preproduction design, layout, fabrication and Q/A testing of the HCal frontend electronics. The design and layout stages covers all modifications to earlier prototype designs. Procurement covers obtaining all quotes, placing and tracking orders, and receipt of orders. Q/A testing covers the cost of all test equipment and the testing of the fabricated modules prior to installation.
Cost Summary
|  | Task | Cost Basis |  | Cost | Cost + %Design Uncertianty
|  | Board Assembly and Testing | Catalogue/Quote/Eng Estimate |  | 1333694.5918 | 1333694.5918
|  | Total Cost |  |  | 1333694.5918 | 1333694.5918
Design Uncertianty
For Parts: M3 (20%) Based on BOMs for most recent prototypes
For Assembly: M4 (20-30%) Engineering estimate based on last round of prototype assembly and level of design modification.
For Cables: M4 (40%) Engineering estimate based on early prototype
BNL Labor for design, layout, assembly oversight, and testing oversight: L3 (25%)

## WBS1.05.02.04 BoE
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-01-04
[7 empty] | Prepared By: | E. J. Mannel
[7 empty] | DocNo. (refer Rev. Log) | 66 v20
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
HCal Electronics: Production |  |  |  | 1.05.02.04
WBS Dictionary Definition:
The work package covers the design, layout, fabrication and Q/A testing of the HCal production electroncs. The front end electronics includes the all front end analog circuits, excluding the SiPM components (WBS 1.5.1), the digital control and monitoring electronics, signal and power cables "on detector", and power systems. It will deliver a total of 1248 channels of HCal front end electornics for installation on the production HCal modules 7-32. Installation and post-installation testing are part of WBS 1.4.
Estimate Type (check all that apply):
Work Complete
Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| X | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
| X | Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Guidelines Used in Developing Estimate
The following guideline were used in the cost estimate: 1) For designed boards, the bill of materials was used to look up catalog prices for all components. 2) Printed circuit board and assembly costs were estimated on early R&D production or production of similar design and functionality. 3) Commercial vendors are assumed for all board fabrication and assembly. 4) Costs include a 10% loss due to yield. The following guidelines were used for the time estimates: 1) Component/PCB orders are less then $100K per order, 3 month for PO to be issued. 2) Componets catalog items with short lead times, 1 month delivery AOR. 3) PCBs are standard type PCBs with not special fabrication requirements and have standard delivery times, 4-6 weeks. 5) Board assembly is done by assembly houses and requires no non-standard assembly procedures. Post-assembly testing is done "in-house" with Collaboration contributed labor and oversite by BNL/Collaboration engineers and technicians. Installation on detector and post-installation testing are part of HCal Production module assembly, WBS 1.4
Details of the Base Estimate (explanation of the Work)
This work package covers the preproduction design, layout, fabrication and Q/A testing of the HCal frontend electronics. The design and layout stages covers all modifications to earlier prototype designs. Procurement covers obtaining all quotes, placing and tracking orders, and receipt of orders. Q/A testing covers the cost of all test equipment and the testing of the fabricated modules prior to installation.
Cost Summary
|  | Task | Cost Basis |  | Cost | Cost + %Design Uncertianty
|  | Board Assembly and Testing | Catalogue/Quote/Eng Estimate |  | 362643.7623 | 526402.7779
|  | Total Cost |  |  | 362643.7623 | 526402.7779
Design Uncertianty
For Parts: M3 (20%) Based on BOMs for most recent prototypes
For Assembly: M4 (20-30%) Engineering estimate based on last round of prototype assembly and level of design modification.
For Cables: M4 (40%) Engineering estimate based on early prototype
BNL Labor for design, layout, assembly oversight, and testing oversight: L3 (25%)
Univeristy Students for testing: L3 (25%)

## WBS1.05.02SystemCosts
WBS 1.05.02 System Costs
Date: 5-Mar-2017
Last Revision Date: 15-Mar-2019
| Module | Quantity Required | Quantity Produced | Cost | NRE | Total Cost | Total Cost + 10% | %Design Uncertianty | Total Cost + %Design Uncertianty
Sector 0 Production:
| SiPM Daughter Boards- Turnkey Parts | 96 | 96 | 7.2301 |  | 694.0896 | 694.0896 | 0 | 694.0896
| SiPM Daughter Boards- Turnkey Assembly | 96 | 96 | 23 |  | 2208 | 2208 | 0 | 2208
| SiPM Daughter Boards- Total |  |  |  |  | 2902.0896 | 2902.0896 |  | 2902.0896
| EMCal Preamp Boards- Turnkey Assembly | 24 | 32 | 570.3 |  | 18249.6 | 18249.6 | 0 | 18249.6
| EMCal Preamp Boards- Total |  |  |  |  | 18249.6 | 18249.6 |  | 18249.6
| EMCal Interface Boards- Parts | 6 | 8 | 556.0824 |  | 4448.6594 | 4893.5254 | 0 | 4893.5254
| EMCal Interface Boards- Assembly | 6 | 8 | 97.5 |  | 780 | 858 | 0 | 858
| EMCal Interface Boards- Total |  |  |  |  | 5228.6594 | 5751.5254 |  | 5751.5254
| EMCal Controller Boards- Parts | 1 | 0 | 982.5176 |  | 0 | 0 | 0.2 | 0
| EMCal Controller Boards- Assembly | 1 | 0 | 150 |  | 0 | 0 | 0.2 | 0
| EMCal Controller Boards- Total |  |  |  |  | 0 | 0 |  | 0
| Power Systems | 1 | 0 | 4400 |  | 0 | 0 | 0.4 | 0
| EMCal Cables- Internal | 1 | 1 | 9177.0878 |  | 9177.0878 | 10094.7965 | 0.4 | 14132.7152
| EMCal Cables- External | 1 | 1 | 4060.6431 |  | 4060.6431 | 4466.7074 | 0.4 | 6253.3904
| Misc Total |  |  |  |  | 13237.7309 | 14561.504 |  | 20386.1056
| Total Sector 0 Costs |  |  |  |  | 39618.0799 | 41464.7189 |  | 47289.3205
Sector 1-12 Production:
| EMCal SiPM Daughter Boards- Turnkey Part | 1152 | 1250 | 6.35 |  | 7937.5 | 7937.5 | 0.1 | 8731.25
| EMCal SiPM Daughter Boards- Turnkey Assembly | 1152 | 1250 | 13 | 1300 | 17550 | 17550 | 0.1 | 19305
| EMCal SiPM Daughter Boards- Total |  |  |  |  | 25487.5 | 25487.5 |  | 28036.25
| EMCal Preamp Boards- Turnkey Assembly | 288 | 350 | 451 |  | 157850 | 157850 | 0.1 | 173635
| EMCal Preamp Boards- Total |  |  |  |  | 157850 | 157850 |  | 173635
| EMCal Interface Boards- Parts | 72 | 80 | 556.0424 | 360 | 44843.3911 | 49327.7302 | 0.2 | 59193.2763
| EMCal Interface Boards- Assembly | 72 | 80 | 97.5 | 875 | 8675 | 9542.5 | 0.2 | 11451
| EMCal Interface Boards- Total |  |  |  |  | 53518.3911 | 58870.2302 |  | 70644.2763
| EMCal/HCal Test Pulse Boards- Parts | 2 | 4 | 460.7754 | 820 | 2663.1016 | 2929.4118 | 0.2 | 3515.2942
| EMCal/HCal Test Pulse Boards- Assembly | 2 | 4 | 150 | 575 | 1175 | 1292.5 | 0.4 | 1809.5
| EMCal/HCal Test Pulse Boards- Total | 2 |  |  |  | 3838.1016 | 4221.9118 |  | 5324.7942
| EMCal/HCal Controller Boards- Parts | 14 | 15 | 982.5176 | 820 | 15557.7639 | 17113.5402 | 0.2 | 20536.2483
| EMCal/HCal Controller Boards- Assembly | 14 | 15 | 150 | 575 | 2825 | 3107.5 | 0.4 | 4350.5
| EMCal/HCal Controller Boards- Total |  |  |  |  | 18382.7639 | 20221.0402 |  | 24886.7483
| EMCal Controller Crate | 1 | 0 | 1211.71 |  | 0 | 0 | 0.2 | 0
| EMCal LV Power Supplies | 1 | 1 | 14000 |  | 14000 | 15400 | 0.4 | 21560
| EMCal Bias Power Supplies | 1 | 1 | 34606 |  | 34606 | 38066.6 | 0.4 | 53293.24
| EMCal Cables- Internal | 1 | 1 | 76495.6637 |  | 76495.6637 | 84145.23 | 0.4 | 117803.3221
| EMCal Cables- External | 1 | 1 | 48727.7174 |  | 48727.7174 | 53600.4892 | 0.4 | 75040.6849
| Misc Total |  |  |  |  | 173829.3811 | 191212.3192 |  | 267697.2469
| Total Sector 1-12 Costs |  |  |  |  | 432906.1377 | 457863.0015 |  | 570224.3157
Module 1-6 Production
| HCal SiPM Boards- Parts | 1440 | 2000 | 2.4 | 650 | 5450 | 5995 | 0.2 | 7194
| HCal SiPM Boards- Assembly | 1440 | 2000 | 10 | 650 | 20650 | 22715 | 0.4 | 31801
| HCal SiPM Boards- Total |  |  |  |  | 26100 | 28710 |  | 38995
| HCal Preamps- Turnkey Assembly | 288 | 320 | 42.76 | 1019 | 14702.2 | 14702.2 | 0 | 14702.2
| HCal Preamps- Total |  |  |  |  | 14702.2 | 14702.2 |  | 14702.2
| HCal Interface Boards- Parts | 12 | 15 | 380.8659 |  | 5712.9886 | 6284.2875 | 0 | 6284.2875
| HCal Interface Boards- Assembly | 12 | 15 | 97.5 | 735 | 2197.5 | 2417.25 | 0 | 2417.25
| HCal Interface Boards- Total |  |  |  |  | 7910.4886 | 8701.5375 |  | 8701.5375
| HCal Backplane Boards- Parts | 12 | 15 | 208.1319 | 0 | 3121.9791 | 3434.177 | 0 | 3434.177
| HCal Backplane Boards- Assembly | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0
| HCal Backplane Boards- Total |  |  |  |  | 3121.9791 | 3434.177 |  | 3434.177
| HCal LED Driver Boards- Parts | 12 | 15 | 475.4625 | 500 | 7631.9375 | 8395.1313 | 0.2 | 10074.1575
| HCal LED Driver Boards- Assembly | 12 | 15 | 250 | 500 | 4250 | 4675 | 0.4 | 6545
| HCal LED Boards- Total |  |  |  |  | 11881.9375 | 13070.1313 |  | 16619.1575
| HCal Controller Crate | 0 | 0 | 1211.71 |  | 0 | 0 | 0.2 | 0
| HCal Power Supplies | 0 | 0 | 0 |  | 0 | 0 | 0.4 | 0
| HCal Cables- Internal | 1 | 1 | 19066.6598 |  | 19066.6598 | 20973.3258 | 0.4 | 29362.6562
| HCal Cables-External | 1 | 1 | 3467.04 |  | 3467.04 | 3813.744 | 0.4 | 5339.2416
| Misc Total |  |  |  |  | 22533.6998 | 24787.0698 |  | 34701.8978
| Module 1-6 Total Costs |  |  |  |  | 86250.3051 | 93405.1156 |  | 117153.9698
EMCal Sector 13-64 Production
| SiPM Daughter Boards- Turnkey Assembly | 3744 | 4000 | 65190 |  | 65190 | 65190 | 0.2 | 78228
| SiPM Daughter Boards- Total |  |  |  |  | 65190 | 65190 |  | 78228
| EMCal Preamp Boards- Turnkey Assembly | 936 | 1050 | 451 |  | 473550 | 473550 | 0.2 | 568260
| EMCal Preamp Boards- Total |  |  |  |  | 473550 | 473550 |  | 568260
| EMCal Interface Boards- Parts | 260 | 270 | 534.4543 |  | 144302.6716 | 158732.9387 | 0.25 | 198416.1734
| EMCal Interface Boards- Assembly | 260 | 270 | 97.5 |  | 26325 | 28957.5 | 0.4 | 40540.5
| EMCal Interface Boards- Total |  |  |  |  | 170627.6716 | 187690.4387 |  | 238956.6734
| EMCal/HCal Controller Boards- Parts | 58 | 65 | 960.4442 | 0 | 62428.8717 | 68671.7589 | 0.25 | 85839.6986
| EMCal/HCal Controller Boards- Assembly | 58 | 65 | 150 | 0 | 9750 | 10725 | 0.4 | 15015
| EMCal/HCal Controller Boards- Total |  |  |  |  | 72178.8717 | 79396.7589 |  | 100854.6986
| EMCal/HCal Test Pulse Boards- Parts | 7 | 11 | 432.6209 | 0 | 4758.8293 | 5234.7123 | 0.2 | 6281.6547
| EMCal/HCal Test Pulse Boards- Assembly | 7 | 11 | 150 | 0 | 1650 | 1815 | 0.4 | 2541
| EMCal/HCal Test Pulse Boards- Total |  |  |  |  | 6408.8293 | 7049.7123 |  | 8822.6547
| EMCal Controller Crate | 3 | 4 | 1211.71 |  | 4846.84 | 5331.524 | 0.25 | 6664.405
| EMCal LV Power System | 1 | 1 | 32000 |  | 32000 | 35200 | 0.4 | 49280
| EMCal Bias Power System | 1 | 1 | 121935 |  | 121935 | 134128.5 | 0.4 | 187779.9
| EMCal Cables- Internal | 1 | 1 | 225723.9369 |  | 225723.9369 | 248296.3306 | 0.4 | 347614.8628
| EMCal Cables- External | 1 | 1 | 161233.4422 |  | 161233.4422 | 177356.7865 | 0.4 | 248299.501
| Misc Total |  |  |  |  | 545739.2191 | 600313.141 |  | 839638.6688
| Total Sector 13-64 Costs |  |  |  |  | 1333694.5918 | 1413190.0509 |  | 1834760.6956
HCal Modules 7-32
| HCal SiPM Boards- Parts | 6240 | 7000 | 2.4 |  | 16800 | 18480 | 0.25 | 23100
| HCal SiPM Boards- Assembly | 6240 | 7000 | 10 |  | 70000 | 77000 | 0.4 | 107800
| HCal SiPM Boards- Total |  |  |  |  | 86800 | 95480 |  | 130900
| HCal Preamps- Turnkey Assembly | 1248 | 1350 | 30.64 |  | 41364 | 41364 | 0.15 | 47568.6
| HCal Preamps- Total |  |  |  |  | 41364 | 41364 |  | 47568.6
| HCal Interface Boards- Parts | 52 | 60 | 346.2914 |  | 20777.4852 | 22855.2337 | 0.15 | 26283.5188
| HCal Interface Boards- Assembly | 52 | 60 | 97.5 |  | 5850 | 6435 | 0.25 | 8043.75
| HCal Interface Boards- Total |  |  |  |  | 26627.4852 | 29290.2337 |  | 34327.2688
| HCal Backplane Boards- Parts | 52 | 60 | 183.5707 |  | 11014.242 | 12115.6662 | 0.25 | 15144.5828
| HCal Backplane Boards- Assembly | 52 | 60 | 50 | 735 | 3000 | 3300 | 0.4 | 4620
| HCal Backplane Boards- Total |  |  |  |  | 14014.242 | 15415.6662 |  | 19764.5828
| HCal LED Driver Boards- Parts | 52 | 60 | 417.6864 |  | 25061.1834 | 27567.3017 | 0.25 | 34459.1272
| HCal LED Driver Boards- Assembly | 52 | 60 | 250 | 0 | 15000 | 16500 | 0.4 | 23100
| HCal LED Boards- Total |  |  |  |  | 40061.1834 | 44067.3017 |  | 57559.1272
| HCal Controller Crate | 1 | 2 | 1211.71 |  | 2423.42 | 2665.762 | 0.2 | 3198.9144
| HCal Power Supplies | 1 | 1 | 62396 |  | 62396 | 68635.6 | 0.4 | 96089.84
| HCal Cables- Internal | 1 | 1 | 73933.5917 |  | 73933.5917 | 81326.9508 | 0.4 | 113857.7312
| HCal Cables-External | 1 | 1 | 15023.84 |  | 15023.84 | 16526.224 | 0.4 | 23136.7136
| Misc Total |  |  |  |  | 153776.8517 | 169154.5368 |  | 236283.1992
| Module 7-32 Total Costs |  |  |  |  | 362643.7623 | 394771.7385 |  | 526402.7779
EMCal High Eta Electronics
| SiPM Daughter Boards- Turnkey Assembly | 1248 | 1300 | 19.35 | 0 | 24148.8 | 25155 | 0.2 | 30186
| SiPM Daughter Boards- Total |  |  |  |  | 24148.8 | 25155 |  | 30186
| EMCal Preamp Boards- Turnkey Assembly | 312 | 350 | 451 | 0 | 140712 | 157850 | 0.2 | 189420
| EMCal Preamp Boards- Total |  |  |  |  | 140712 | 157850 |  | 189420
| EMCal Interface Boards- Parts | 52 | 55 | 556.0424 | 0 | 28914.2042 | 33640.5645 | 0.25 | 42050.7057
| EMCal Interface Boards- Assembly | 52 | 55 | 97.5 | 0 | 5070 | 5362.5 | 0.4 | 7507.5
| EMCal Interface Boards- Total |  |  |  |  | 33984.2042 | 39003.0645 |  | 49558.2057
| EMCal/HCal Controller Boards- Parts | 0 | 0 | 960.4442 | 0 | 0 | 0 | 0.25 | 0
| EMCal/HCal Controller Boards- Assembly | 0 | 0 | 150 | 0 | 0 | 0 | 0.4 | 0
| EMCal/HCal Controller Boards- Total |  |  |  |  | 0 | 0 |  | 0
| EMCal/HCal Test Pulse Boards- Parts | 0 | 0 | 460.7754 | 0 | 0 | 0 | 0.2 | 0
| EMCal/HCal Test Pulse Boards- Assembly | 0 | 0 | 150 | 0 | 0 | 0 | 0.4 | 0
| EMCal/HCal Test Pulse Boards- Total |  |  |  |  | 0 | 0 |  | 0
| EMCal Controller Crate | 0 |  | 0 |  | 0 | 0 | 0.25 | 0
| EMCal LV Power System | 0 |  | 0 |  | 0 | 0 | 0.4 | 0
| EMCal Bias Modules | 7 | 7 | 3115 |  | 21805 | 21805 | 0.4 | 30527
| EMCal Cables- Internal | 1 |  | 63698.6969 |  | 63698.6969 | 70068.5666 | 0.4 | 98095.9932
| EMCal Cables- External | 1 |  | 49920 |  | 49920 | 54912 | 0.4 | 76876.8
| Misc Total |  |  |  |  | 135423.6969 | 146785.5666 |  | 205499.7932
| Total Sector 13-64 Costs |  |  |  |  | 334268.7011 | 368793.6311 |  | 474663.9989

## EMCal_SiPM_DaughterBoards
205-1000-2x30: EMCal SiPM Daughter Board
Creation: 28-Dec-2018
Last Revision Date: 11-Feb-2018
Item Number | Quantity | Reference | MFG Part # | Vendor Part # | Value | Tolerance | PCB Footprint | Unit Cost | Total | Vendor
1 | 4 | C1,C2,C3,C4 | C2012X7S2A105K125AE |  | 1uF |  | CC0805 | 0.1308 | 0.5232
2 | 1 | J1 | 52207-1460 |  |  |  | 68611414122 | 1.1562 | 1.1562
3 | 1 | LED1 | SM0603UV-400 |  |  |  | LED/0603 | 0.38502 | 0.38502
4 | 1 | RT1 | NCP18XH103F03RB |  |  |  | CC0603 | 0.05787 | 0.05787
5 | 4 | R1,R2,R3,R4, R5 | RC0402FR-07100RL |  | 100R | 1% | CR0402 | 0.00194 | 0.00776
7 | 16 | SI1,SI2,SI3,SI4,SI5,SI6,SI7,SI8,SI9,SI10,SI11,SI12,SI13,SI14,SI15,SI16 | S12572-015P |  |  |  | S10931
| 1 | Bare board | [5 empty] | 2 | 2
| 1 | Assembly | [5 empty] | 8 | 8
[7 empty] | Part Cost |  | 4.1301
[7 empty] | Assembly |  | 8
[7 empty] | Unit Total |  | 12.1301
[7 empty] | NRE- Board Fab |  | 500
Turn-Key Fabrication:
| 96 | EMCal Sector 0 Part Kit: BNL Provided | [5 empty] | 4.1301 | 396.4896
| 96 | EMCal SiPM Daughter Boards PCBS- Sector 0: Vendor CEM | [5 empty] | 3.1 | 297.6
| 96 | EMCal Sector 0 SiPM Daughter Board Assembly: Vendor CEM | [5 empty] | 23 | 2208
|  | EMCal Sector 0 SiPM Daughter Board Fabrication Total | [6 empty] | 2902.0896
| 1250 | EMCal SiPM Daughter Boards PCBS- Sector 1-12: Vendor CEM | [5 empty] | 3.1 | 3875
| 1250 | EMCal Sector 1-12 SiPM Daughter Boards Parts Ki:t Vendor CEM | [5 empty] | 3.25 | 4062.5
| 1250 | EMCal Sector 1-12 SiPM Daughter Board Assembly: Vendor CEM | [5 empty] | 13 | 16250
| 2 | Solder Paster Stencile NRE | [5 empty] | 650 | 1300
|  | EMCal Sector 1-12 SiPM Daughter Board Fabrication Total | [6 empty] | 25487.5
| 4100 | EMCal SiPM Daughter Boards PCBS- Sector 13-64: Vendor CEM | [5 empty] | 2.15 | 8815
| 4100 | EMCal Sector 13-64 SiPM Daughter Boards Parts Ki:t Vendor CEM | [5 empty] | 2.75 | 11275
| 4100 | EMCal Sector 13-64 SiPM Daughter Board Assembly: Vendor CEM | [5 empty] | 11 | 45100
|  | EMCal Sector 13-64 SiPM Daughter Board Fabrication Total | [6 empty] | 65190
| 1300 | EMCal SiPM Daughter Boards PCBS- Sector 1-12: Vendor CEM | [5 empty] | 3.1 | 4030
| 1300 | EMCal Sector 1-12 SiPM Daughter Boards Parts Ki:t Vendor CEM | [5 empty] | 3.25 | 4225
| 1300 | EMCal Sector 1-12 SiPM Daughter Board Assembly: Vendor CEM | [5 empty] | 13 | 16900
|  | EMCal Sector 1-12 SiPM Daughter Board Fabrication Total | [6 empty] | 25155

## EMCal_Preamp_Boards
205-1000-2x20: EMCal Preamp
Creation: 28-Dec-2018
Last Revision Date: 30-Dec-2018
Item | Quantity | Reference | MFG Part # | Vendor Part # | Value | Tolerance | PCB Footprint | Sector 0 Unit Cost | Sector 0 Total | Sector 1-12 Unit Cost | Sector 1-12 Total | Sector 13-64 Unit Cost | Sector 13-64 Total | Vendor | Comments
1 | 288 | C1,C5,C7,C11,C13,C15,C16,C21,C23,C24,C25,C30,C33,C34,C36,C37,C38,C40,C41,C45,C47,C51,C53,C55,C56,C61,C63,C64,C65,C70,C73,C74,C76,C77,C78,C80,C81,C85,C87,C91,C93,C95,C96,C101,C103,C104,C105,C110,C113,C114,C116,C117,C118,C120,C121,C125,C127,C131,C133,C135,C136,C141,C143,C144,C145,C150,C153,C154,C156,C157,C158,C160,C161,C165,C167,C171,C173,C175,C176,C181,C183,C184,C185,C190,C193,C194,C196,C197,C198,C200,C201,C205,C207,C211,C213,C215,C216,C221,C223,C224,C225,C230,C233,C234,C236,C237,C238,C240,C241,C245,C247,C251,C253,C255,C256,C261,C263,C264,C265,C270,C273,C274,C276,C277,C278,C280,C281,C285,C287,C291,C293,C295,C296,C301,C303,C304,C305,C310,C313,C314,C316,C317,C318,C320,C321,C325,C327,C331,C333,C335,C336,C341,C343,C344,C345,C350,C353,C354,C356,C357,C358,C360,C361,C365,C367,C371,C373,C375,C376,C381,C383,C384,C385,C390,C393,C394,C396,C397,C398,C400,C401,C405,C407,C411,C413,C415,C416,C421,C423,C424,C425,C430,C433,C434,C436,C437,C438,C440,C441,C445,C447,C451,C453,C455,C456,C461,C463,C464,C465,C470,C473,C474,C476,C477,C478,C480,C481,C485,C487,C491,C493,C495,C496,C501,C503,C504,C505,C510,C513,C514,C516,C517,C518,C520,C521,C525,C527,C531,C533,C535,C536,C541,C543,C544,C545,C550,C553,C554,C556,C557,C558,C560,C561,C565,C567,C571,C573,C575,C576,C581,C583,C584,C585,C590,C593,C594,C596,C597,C598,C600,C601,C605,C607,C611,C613,C615,C616,C621,C623,C624,C625,C630,C633,C634,C636,C637,C638,C640 | CL05B104KO5NNWC | 1276-1509-2-ND | 100nF |  | C0402 | 0.003 | 0.864 | 0.00499 | 1.4371 | 0.00499 | 1.4371 | Digikey
2 | 80 | C2,C10,C17,C27,C29,C42,C50,C57,C67,C69,C82,C90,C97,C107,C109,C122,C130,C137,C147,C149,C162,C170,C177,C187,C189,C202,C210,C217,C227,C229,C242,C250,C257,C267,C269,C282,C290,C297,C307,C309,C322,C330,C337,C347,C349,C362,C370,C377,C387,C389,C402,C410,C417,C427,C429,C442,C450,C457,C467,C469,C482,C490,C497,C507,C509,C522,C530,C537,C547,C549,C562,C570,C577,C587,C589,C602,C610,C617,C627,C629 | CL05B103KO5NNNC | 1276-1051-2-ND | 10nF |  | C0402 | 0.003 | 0.24 | 0.00391 | 0.3128 | 0.00391 | 0.3128 | Digikey
3 | 16 | C3,C43,C83,C123,C163,C203,C243,C283,C323,C363,C403,C443,C483,C523,C563,C603 | CL05C100JB5NNNC | 1276-1139-1-ND | 10pF |  | C0402 | 0.003 | 0.048 | 0.00713 | 0.11408 | 0.00713 | 0.11408 | Digikey
4 | 16 | C4,C44,C84,C124,C164,C204,C244,C284,C324,C364,C404,C444,C484,C524,C564,C604 | C0402C101G5GACTU | 399-11111-1-ND | 100pF |  | C0402 | 0.003 | 0.048 | 0.25954 | 4.1526 | 0.25954 | 0.21296 | Digikey | Digikey- Limited Quantity
5 | 48 | C6,C19,C32,C46,C59,C72,C86,C99,C112,C126,C139,C152,C166,C179,C192,C206,C219,C232,C246,C259,C272,C286,C299,C312,C326,C339,C352,C366,C379,C392,C406,C419,C432,C446,C459,C472,C486,C499,C512,C526,C539,C552,C566,C579,C592,C606,C619,C632 | GCM155R71C473KA37D | 490-6042-1-ND | 47nF |  | C0402 | 0.003 | 0.144 | 0.01331 | 0.63888 | 0.01331 | 0.63888 | Digikey
6 | 32 | C8,C9,C48,C49,C88,C89,C128,C129,C168,C169,C208,C209,C248,C249,C288,C289,C328,C329,C368,C369,C408,C409,C448,C449,C488,C489,C528,C529,C568,C569,C608,C609 | GRT188R61E106ME13D | 490-12323-2-ND | 10uF |  | C0603 | 0.072 | 2.304 | 0.13599 | 4.3517 | 0.13599 | 4.3517 | Digikey
7 | 128 | C12,C14,C18,C22,C26,C31,C35,C39,C52,C54,C58,C62,C66,C71,C75,C79,C92,C94,C98,C102,C106,C111,C115,C119,C132,C134,C138,C142,C146,C151,C155,C159,C172,C174,C178,C182,C186,C191,C195,C199,C212,C214,C218,C222,C226,C231,C235,C239,C252,C254,C258,C262,C266,C271,C275,C279,C292,C294,C298,C302,C306,C311,C315,C319,C332,C334,C338,C342,C346,C351,C355,C359,C372,C374,C378,C382,C386,C391,C395,C399,C412,C414,C418,C422,C426,C431,C435,C439,C452,C454,C458,C462,C466,C471,C475,C479,C492,C494,C498,C502,C506,C511,C515,C519,C532,C534,C538,C542,C546,C551,C555,C559,C572,C574,C578,C582,C586,C591,C595,C599,C612,C614,C618,C622,C626,C631,C635,C639 | GRM155C81C105KE11D | 490-12700-2-ND | 1uF |  | C0402 | 0.00189 | 0.24192 | 0.04063 | 5.2006 | 0.04063 | 5.2006 | Digikey
8 | 16 | C20,C60,C100,C140,C180,C220,C260,C300,C340,C380,C420,C460,C500,C540,C580,C620 | CC0402JRNPO8BN181 | 311-3336-1-ND | 180pF |  | C0402 | 0.003 | 0.048 | 0.01 | 0.16 | 0.01 | 0.16 | Digikey
9 | 16 | C28,C68,C108,C148,C188,C228,C268,C308,C348,C388,C428,C468,C508,C548,C588,C628 | GCM1555C1H1R0BA16D | WM10949TR-ND | 1pF |  | C0402 | 0.004 | 0.064 | 0.94125 | 15.06 | 0.8785 | 14.056 | Digikey
10 | 4 | FF1,FF2,FF3,FF4 | 52207-1460 | 490-12208-1-ND | 14 pos |  | WM522071460A | 1.156 | 4.624 | 0.24675 | 0.987 | 0.24675 | 0.987 | Digikey
11 | 16 | L1,L2,L3,L4,L5,L6,L7,L8,L9,L10,L11,L12,L13,L14,L15,L16 | LQW15CAR18J00D | 490-12208-1-ND | 180nH |  | C0402 | 0.57 | 9.12 | 0.24675 | 3.948 | 0.24675 | 3.948 | Digikey
12 | 2 | PRE1,PRE2 | TSSH-115-01-L-D |  |  |  | TSSH-115 | 0.2 | 0.4 |  | 0 |  | 0
13 | 8 | P1,P2,P3,P4,P5,P6,P7,P8 | 951105-7622-AR | 3M156414-05-ND |  |  | HDR5/2MM | 0.19 | 1.52 | 0.3456 | 2.7648 | 0.3456 | 2.7648 | Digikey
14 | 16 | Q1,Q3,Q5,Q7,Q9,Q11,Q13,Q15,Q17,Q19,Q21,Q23,Q25,Q27,Q29,Q31 | BFR93AW | BFR93AWH6327XTSA1TR-ND |  |  | SOT323 | 0.086 | 1.376 | 0.11942 | 1.9107 | 0.10644 | 1.703 | Digikey
15 | 16 | Q2,Q4,Q6,Q8,Q10,Q12,Q14,Q16,Q18,Q20,Q22,Q24,Q26,Q28,Q30,Q32 | NTS4409N | NTS4409NT1GOSTR-ND |  |  | SOT323 | 0.0797 | 1.2752 | 0.11 | 1.76 | 0.11 | 1.76 | Digikey
16 | 4 | RT1,RT2,RT3,RT4 | NCU18XH103F60RB | 490-16279-1-ND |  |  | CC0603 | 0.07922 | 0.31688 | 0.05787 | 0.23148 | 0.05787 | 0.23148 | Digikey | Limited Quantity
17 | 66 | R1,R2,R10,R18,R24,R37,R45,R51,R64,R72,R78,R91,R99,R105,R118,R126,R132,R145,R153,R159,R172,R180,R186,R199,R207,R213,R226,R234,R240,R253,R261,R267,R280,R288,R294,R307,R315,R321,R334,R342,R348,R361,R369,R375,R388,R396,R402,R415,R423,R429,R435,R436,R437,R438,R439,R440,R441,R442,R443,R444,R445,R446,R447,R448,R449,R450 | RMCF0402FT10K0 | RMCF0402FT10K0TR-ND | 10K |  | C0402 | 0.00095 | 0.0627 | 0.00163 | 0.10758 | 0.00132 | 0.08712 | Digikey
18 | 48 | R3,R17,R25,R30,R44,R52,R57,R71,R79,R84,R98,R106,R111,R125,R133,R138,R152,R160,R165,R179,R187,R192,R206,R214,R219,R233,R241,R246,R260,R268,R273,R287,R295,R300,R314,R322,R327,R341,R349,R354,R368,R376,R381,R395,R403,R408,R422,R430 | ERJ-2RKF1021X | P1.02KLTR-ND | 1.02K |  | C0402 | 0.00095 | 0.0456 | 0.00521 | 0.25008 | 0.00431 | 0.20688 | Digikey
19 | 32 | R4,R16,R31,R43,R58,R70,R85,R97,R112,R124,R139,R151,R166,R178,R193,R205,R220,R232,R247,R259,R274,R286,R301,R313,R328,R340,R355,R367,R382,R394,R409,R421 | ERJ-2RKF2610X | P261LTR-ND | 261R |  | C0402 | 0.00095 | 0.0304 | 0.00521 | 0.16672 | 0.00465 | 0.1488 | Digikey
20 | 16 | R5,R32,R59,R86,R113,R140,R167,R194,R221,R248,R275,R302,R329,R356,R383,R410 | ERJ-2RKF2200X | P220LCT-ND | 220R |  | C0402 | 0.00095 | 0.0152 | 0.00805 | 0.1288 | 0.00805 | 0.1288 | Digikey
21 | 48 | R6,R7,R19,R33,R34,R46,R60,R61,R73,R87,R88,R100,R114,R115,R127,R141,R142,R154,R168,R169,R181,R195,R196,R208,R222,R223,R235,R249,R250,R262,R276,R277,R289,R303,R304,R316,R330,R331,R343,R357,R358,R370,R384,R385,R397,R411,R412,R424 | ERJ-2RKF49R9X | P49.9LTR-ND | 49R9 |  | C0402 | 0.00095 | 0.0456 | 0.00644 | 0.30912 | 0.00532 | 0.25536 | Digikey
22 | 48 | R8,R14,R23,R35,R41,R50,R62,R68,R77,R89,R95,R104,R116,R122,R131,R143,R149,R158,R170,R176,R185,R197,R203,R212,R224,R230,R239,R251,R257,R266,R278,R284,R293,R305,R311,R320,R332,R338,R347,R359,R365,R374,R386,R392,R401,R413,R419,R428 | ERJ-2RKF10R0X | P10.0LTR-ND | 10R |  | C0402 | 0.00095 | 0.0456 | 0.00521 | 0.25008 | 0.00431 | 0.20688 | Digikey
23 | 16 | R9,R36,R63,R90,R117,R144,R171,R198,R225,R252,R279,R306,R333,R360,R387,R414 | ERJ-2RKF1000X | P100LCT-ND | 100R |  | C0402 | 0.00095 | 0.0152 | 0.00521 | 0.08336 | 0.00521 | 0.08336 | Digikey
24 | 32 | R11,R26,R38,R53,R65,R80,R92,R107,R119,R134,R146,R161,R173,R188,R200,R215,R227,R242,R254,R269,R281,R296,R308,R323,R335,R350,R362,R377,R389,R404,R416,R431 | ERJ-2RKF22R0X | P220LCT-ND | 22R |  | C0402 | 0.00095 | 0.0304 | 0.00805 | 0.2576 | 0.00805 | 0.2576 | Digikey
25 | 32 | R12,R13,R39,R40,R66,R67,R93,R94,R120,R121,R147,R148,R174,R175,R201,R202,R228,R229,R255,R256,R282,R283,R309,R310,R336,R337,R363,R364,R390,R391,R417,R418 | ERJ-2RKF2490X | P249LTR-ND | 249R |  | C0402 | 0.00095 | 0.0304 | 0.00634 | 0.20288 | 0.00565 | 0.1808 | Digikey
26 | 16 | R15,R42,R69,R96,R123,R150,R177,R204,R231,R258,R285,R312,R339,R366,R393,R420 | ERJ-2RKF4021X | P4.02KLCT-ND | 4.02K |  | C0402 | 0.00095 | 0.0152 | 0.00521 | 0.08336 | 0.00521 | 0.08336 | Digikey
27 | 16 | R20,R47,R74,R101,R128,R155,R182,R209,R236,R263,R290,R317,R344,R371,R398,R425 | ERJ-2RKF5901X | P5.90KLCT-ND | 5.9K |  | C0402 | 0.00095 | 0.0152 | 0.00521 | 0.08336 | 0.00521 | 0.08336 | Digikey
28 | 32 | R21,R22,R48,R49,R75,R76,R102,R103,R129,R130,R156,R157,R183,R184,R210,R211,R237,R238,R264,R265,R291,R292,R318,R319,R345,R346,R372,R373,R399,R400,R426,R427 | ERJ-2RKF7500X | P750LTR-ND | 750R |  | C0402 | 0.0411 | 1.3152 | 0.00521 | 0.16672 | 0.00465 | 0.1488 | Digikey
29 | 16 | R27,R54,R81,R108,R135,R162,R189,R216,R243,R270,R297,R324,R351,R378,R405,R432 | ERJ-2RKF1400X | P140LCT-ND | 140R |  | C0402 | 0.00095 | 0.0152 | 0.00466 | 0.07456 | 0.00466 | 0.07456 | Digikey
30 | 16 | R28,R55,R82,R109,R136,R163,R190,R217,R244,R271,R298,R325,R352,R379,R406,R433 | ERJ-2RKF20R0X | P20.0LCT-ND | 20R |  | C0402 | 0.0411 | 0.6576 | 0.00521 | 0.08336 | 0.00521 | 0.08336 | Digikey
31 | 16 | R29,R56,R83,R110,R137,R164,R191,R218,R245,R272,R299,R326,R353,R380,R407,R434 | ERJ-2RKF6200X | P620LTR-ND | 620R |  | C0402 | 0.0411 | 0.6576 | 0.00521 | 0.08336 | 0.00521 | 0.08336 | Digikey
32 | 16 | U1,U6,U11,U16,U21,U26,U31,U36,U41,U46,U51,U56,U61,U66,U71,U76 | AD8132ARMZ-REEL7TR-ND | AD8132ARMZ-REEL7 |  |  | MSOP8 | 1.25 | 20 | 2.2743 | 36.3888 | 2.2743 | 36.3888 | Digikey
33 | 32 | U2,U4,U7,U9,U12,U14,U17,U19,U22,U24,U27,U29,U32,U34,U37,U39,U42,U44,U47,U49,U52,U54,U57,U59,U62,U64,U67,U69,U72,U74,U77,U79 | AD8001ARTZ-REEL7 | AD8001ARTZREEL7TR-ND |  |  | SOT23-5 | 2.5 | 80 | 1.7423 | 55.7536 | 1.7423 | 55.7536 | Digikey
34 | 16 | U3,U8,U13,U18,U23,U28,U33,U38,U43,U48,U53,U58,U63,U68,U73,U78 | ADG601BRTZ-REEL7 | ADG601BRTZ-REEL7TR-ND |  |  | SOT23-6 | 1.097 | 17.552 | 1.2555 | 20.088 | 1.2555 | 20.088 | Digikey
35 | 16 | U5,U10,U15,U20,U25,U30,U35,U40,U45,U50,U55,U60,U65,U70,U75,U80 | ADG602BRTZ-REEL7 | ADG602BRTZ-REEL7TR-ND |  |  | SOT23-6 | 1.097 | 17.552 | 1.4364 | 22.9824 | 1.4364 | 22.9824 | Digikey
| 1 | Blank PCB | [5 empty] | 100 | 100 | 200 | 200 | 150 | 150 | EST
| 1 | Setup For Pick&Place | [5 empty] | 200 | 200 |  |  |  |  | EST
| 1 | Assembly | [5 empty] | 115 | 115 | 115 | 115 | 75 | 75 | EST
|  | Unit Total | [6 empty] | 460.7351 |  | 380.5736 |  | 325.2037
|  | Parts Cost | [6 empty] | 260.7351 |  | 380.5736 |  | 325.2037
|  | Assembly Cost | [6 empty] | 315 |  | 115 |  | 75
|  | Total Cost | [6 empty] | 575.7351 |  | 495.5736 |  | 400.2037
|  | NRE | [6 empty] | 450
Turn-Key Fabrication:
| 32 | EMCal Preamp- Sector 0: Vendor Eastend | [5 empty] | 570.3 | 18249.6
| 350 | EMCal Preamp- Sector 1-12: Vendor Eastend | [7 empty] | 451 | 157850
| 1050 | EMCal Preamp- Sector 1-12: Vendor Eastend | [9 empty] | 451 | 473550

## EMCal_Interface_Boards
205-1000-2x10: EMCal Interface
Creation: 28-Dec-2018
Last Revision Date: 21-Mar-2019
Item | Quantity | Reference | MFG Part # | Vendor Part # | Value | Tolerance | PCB Footprint | Sector 0 Unit Cost | Sector 0 Total | Sector 1-12 Unit Cost | Sector 1-12 Total | Sector 13-64 Unit Cost | Sector 13-64 Total | Vendor
1 | 12 | C1,C14,C36,C38,C39,C42,C43,C45,C55,C59,C191,C192 | GRT188R61C106KE13D | 490-12317-1-ND | 10uF |  | C0603 | 0.40986 | 4.9183 | 0.40986 | 4.9183 | 0.35294 | 4.2353 | DigiKey
2 | 93 | C2,C3,C4,C6,C8,C9,C11,C12,C13,C15,C18,C19,C20,C21,C22,C23,C24,C25,C26,C27,C28,C29,C30,C31,C32,C33,C34,C47,C48,C49,C50,C51,C52,C53,C54,C56,C57,C58,C60,C61,C62,C63,C66,C69,C72,C75,C78,C81,C84,C87,C90,C93,C96,C99,C102,C105,C108,C111,C114,C117,C120,C123,C126,C129,C132,C135,C138,C141,C144,C147,C150,C153,C156,C159,C161,C163,C164,C166,C168,C169,C171,C173,C174,C176,C178,C179,C180,C181,C182,C183,C190,C193 | GRM155R61C104KA88D | 490-5415-1-ND | 100nF |  | C0402 | 0.00715 | 0.66495 | 0.00715 | 0.66495 | 0.00715 | 0.66495 | DigiKey
3 | 1 | C5 | CL05C102JA5NNNC | 1276-1634-1-ND | 1nF |  | C0402 | 0.095 | 0.095 | 0.095 | 0.095 | 0.0446 | 0.0446 | DigiKey
4 | 1 | C7 | CL05B272KB5NNNC | 1276-1268-1-ND | 2.7nF |  | C0402 | 0.03 | 0.03 | 0.03 | 0.03 | 0.0135 | 0.0135 | DigiKey
5 | 1 | C10 | GRM155R71E103KA01D | 490-1312-1-ND | 10nF |  | C0402 | 0.03 | 0.03 | 0.03 | 0.03 | 0.0136 | 0.0136 | DigiKey
6 | 10 | C16,C17,C160,C162,C165,C167,C170,C172,C175,C177 | GRM155C81C105KE11D | 490-12700-1-ND | 1uF |  | C0402 | 0.06598 | 0.6598 | 0.06598 | 0.6598 | 0.05498 | 0.5498 | DigiKey
7 | 8 | C35,C41,C44,C46,C186,C187,C188,C189 | C5750X5R0J107M280KA | 445-3501-2-ND | 100uF |  | 2220 | 1.2 | 9.6 | 1.2 | 9.6 | 1.2 | 9.6 | DigiKey
8 | 1 | C37 | 298D226X0010M2T | 718-1718-1-ND | 22uF |  | C0603 | 1.581 | 1.581 | 1.581 | 1.581 | 1.2075 | 1.2075 | DigiKey
9 | 64 | C64,C65,C67,C68,C70,C71,C73,C74,C76,C77,C79,C80,C82,C83,C85,C86,C88,C89,C91,C92,C94,C95,C97,C98,C100,C101,C103,C104,C106,C107,C109,C110,C112,C113,C115,C116,C118,C119,C121,C122,C124,C125,C127,C128,C130,C131,C133,C134,C136,C137,C139,C140,C142,C143,C145,C146,C148,C149,C151,C152,C154,C155,C157,C158 | GRM155C8YA224KE01D | 490-10445-1-ND | 220nF |  | C0402 | 0.1 | 6.4 | 0.1 | 6.4 | 0.1 | 6.4 | DigiKey
10 | 10 | D1,D2,D7,D8,D9,D10,D11,D12,D13,D14 | BAS40-02V-V-G-08 | BAS40-02V-V-G-08GICT-ND | 200mA |  | SOD523_DIODE | 0.11032 | 1.1032 | 0.11032 | 1.1032 | 0.08457 | 0.8457 | DigiKey
11 | 4 | D3,D4,D5,D6 | CDBA240LL | 641-1698-1-ND | 2A |  | DO-214AC | 0.3327 | 1.3308 | 0.3327 | 1.3308 | 0.18851 | 0.75404 | DigiKey
12 | 1 | HDR1 | 877583416 | WM18848-ND |  |  | HDR2X17/2MM | 1.677 | 1.677 | 1.677 | 1.677 | 1.4371 | 1.4371 | DigiKey
13 | 1 | HDR2 | 087831-1420 | WM17469-ND |  |  | HDR2X7/2MM | 1.301 | 1.301 | 1.301 | 1.301 | 1.1151 | 1.1151 | DigiKey
14 | 1 | J1 | 705530002 | WM4901-ND |  |  | WM70553-0002 | 0.982 | 0.982 | 0.982 | 0.982 | 0.8472 | 0.8472 | DigiKey
15 | 1 | J2 | 1-178296-2 | A29452-ND |  |  | DYND-6 | 3.036 | 3.036 | 3.036 | 3.036 | 2.53 | 2.53 | DigiKey
16 | 1 | LED1 | LTST-C191KGKT | 160-1446-1-ND |  |  | LED/0603 | 0.16 | 0.16 | 0.16 | 0.16 | 0.0798 | 0.0798 | DigiKey
17 | 1 | LED2 | LTST-C191KSKT | 160-1448-1-ND |  |  | LED/0603 | 0.17 | 0.17 | 0.17 | 0.17 | 0.08488 | 0.08488 | DigiKey
18 | 1 | L1 | LQM31PN1R0M00L | 490-4039-1-ND | 1uH |  | CC1206 | 0.351 | 0.351 | 0.351 | 0.351 | 0.2416 | 0.2416 | DigiKey
19 | 8 | PRE1,PRE2,PRE3,PRE4,PRE5,PRE6,PRE7,PRE8 | ESW-115-58-G-D | ESW-115-58-G-D-ND |  |  | ESW-115-D | 6.44 | 51.52 | 6.44 | 51.52 | 6.44 | 51.52 | DigiKey
20 | 2 | REG1,REG4 | LT1764AEQ | LT1764AEQ#TRPBFCT-ND |  |  | TO-263-5 | 7.8164 | 15.6328 | 7.8164 | 15.6328 | 7.8164 | 15.6328 | DigiKey
21 | 1 | REG2 | LM1117MPX-3.3 | 296-41282-1-ND |  |  | SOT223 | 1.422 | 1.422 | 1.4222 | 1.4222 | 1.1087 | 1.1087 | DigiKey
22 | 1 | REG3 | NCV8560SN180T1G | NCV8560SN180T1GOSCT-ND |  |  | SOT23-5 | 0.76 | 0.76 | 0.76 | 0.76 | 0.5923 | 0.5923 | DigiKey
23 | 2 | REG5,REG6 | LT3015EQ | LT3015EQ-5#PBF-ND |  | 0.1% | TO-263-5 | 4.376 | 8.752 | 4.376 | 8.752 | 4.376 | 8.752 | DigiKey
24 | 3 | RP1,RP2,RP3 | 742C163470JP | 742C163470JP |  |  | CRN16/CTS742 | 0.196 | 0.588 | 0.196 | 0.588 | 0.14196 | 0.42588 | DigiKey
25 | 1 | RS1 | 705530008 | WM4907-ND |  |  | 705530008 | 2.703 | 2.703 | 2.703 | 2.703 | 2.2526 | 2.2526 | DigiKey
26 | 4 | RT1,RT2,RT3,RT4 | MINISMDC200F-2 | MINISMDC200F-2 |  |  | CC1812 | 0.35816 | 1.4326 | 0.35816 | 1.4326 | 0.27676 | 1.107 | DigiKey
27 | 1 | RT5 | PRG21BC4R7MM1RA | 490-4672-1-ND |  | 0.1% | C0805 | 0.5396 | 0.5396 | 0.5396 | 0.5396 | 0.4597 | 0.4597 | DigiKey
28 | 5 | R1,R39,R56,R73,R90 | ERA-2AED302X | P3.0KDECT-ND | 3K | 0.1% | C0402 | 0.0735 | 0.3675 | 0.0735 | 0.3675 | 0.03077 | 0.15385 | DigiKey
29 | 5 | R2,R7,R9,R12,R167 | RC0402FR-071RL | 311-1.00LRCT-ND | 1 | 0.5% | C0402 | 0.0105 | 0.0525 | 0.0105 | 0.0525 | 0.00495 | 0.02475 | DigiKey
30 | 1 | R3 | ERJ-2RKF33R0X | P33.0LCT-ND | 33 | 0.1% | C0402 | 0.057 | 0.057 | 0.057 | 0.057 | 0.0234 | 0.0234 | DigiKey
31 | 1 | R4 | RG1005P-102-B-T5 | RG1005P-102-B-T5 | 1K |  | C0402 | 0.319 | 0.319 | 0.319 | 0.319 | 0.134 | 0.134 | DigiKey
32 | 1 | R5 | ERJ-PB6B1003V | P20822CT-ND | 100K |  | C0402 | 0.1614 | 0.1614 | 0.1614 | 0.1614 | 0.09184 | 0.09184 | DigiKey
33 | 7 | R6,R11,R157,R160,R163,R166,R169 | RT0402FRE071KL | YAG1234CT-ND | 1K | 0.1% | C0402 | 0.029 | 0.203 | 0.029 | 0.203 | 0.01278 | 0.08946 | DigiKey
34 | 1 | R8 | PNM0402E2502BST1 | 541-1903-1-ND | 25K |  | C0402 | 1.003 | 1.003 | 1.003 | 1.003 | 0.7277 | 0.7277 | DigiKey
35 | 1 | R10 | CRCW080510M0DHEAP | 541-10MAZCT-ND | 10M |  | C1206 | 0.266 | 0.266 | 0.266 | 0.266 | 0.1041 | 0.1041 | DigiKey
36 | 1 | R13 | ERJ-PB6B4993V | P20901CT-ND | 499K | 0.1% | CC0805 | 0.1614 | 0.1614 | 0.1614 | 0.1614 | 0.09184 | 0.09184 | DigiKey
37 | 4 | R14,R15,R18,R22 | ERJ-2RKF1000X | P100LCT-ND | 100 | 0.1% | C0402 | 0.0189 | 0.0756 | 0.0189 | 0.0756 | 0.00884 | 0.03536 | DigiKey
38 | 69 | R16,R17,R91,R92,R93,R94,R95,R96,R97,R98,R99,R100,R101,R102,R103,R104,R105,R106,R107,R108,R109,R110,R111,R112,R113,R114,R115,R116,R117,R118,R119,R120,R121,R122,R123,R124,R125,R126,R127,R128,R129,R130,R131,R132,R133,R134,R135,R136,R137,R138,R139,R140,R141,R142,R143,R144,R145,R146,R147,R148,R149,R150,R151,R152,R153,R154,R174,R175,R176 | ERJ-2RKF1500X | P150LCT-ND | 150 |  | C0402 | 0.0052165 | 0.35994 | 0.0052165 | 0.35994 | 0.0052165 | 0.35994 | DigiKey
39 | 11 | R19,R20,R21,R177,R178,R179,R180,R181,R182,R183,R184 | RMCF0402FT10K0 | RMCF0402FT10K0CT-ND | 10K |  | C0402 | 0.0064 | 0.0704 | 0.0064 | 0.0704 | 0.0025 | 0.0275 | DigiKey
40 | 64 | R23,R24,R25,R26,R27,R28,R29,R30,R31,R32,R33,R34,R35,R36,R37,R38,R40,R41,R42,R43,R44,R45,R46,R47,R48,R49,R50,R51,R52,R53,R54,R55,R57,R58,R59,R60,R61,R62,R63,R64,R65,R66,R67,R68,R69,R70,R71,R72,R74,R75,R76,R77,R78,R79,R80,R81,R82,R83,R84,R85,R86,R87,R88,R89 | RT0402BRE07100RL | YAG4328CT-ND | 100 |  | C0402 | 0.04475 | 2.864 | 0.04475 | 2.864 | 0.04475 | 2.864 | DigiKey
41 | 4 | R155,R158,R161,R164 | ERJ-2RKF6803X | P680KLCT-ND | 680K |  | C0402 | 0.0189 | 0.0756 | 0.00884 | 0.03536 | 0.00884 | 0.03536 | DigiKey
42 | 4 | R156,R159,R162,R165 | RG1005P-2611-B-T5 | RG10P2.61KBCT-ND | 2.61K |  | C0402 | 0.1758 | 0.7032 | 0.1758 | 0.7032 | 0.09702 | 0.38808 | DigiKey
43 | 1 | R168 | RG1005P-103-B-T5 | RG10P10KBCT-ND | 10K |  | C0402 | 0.33 | 0.33 | 0.33 | 0.33 | 0.145 | 0.145 | DigiKey
44 | 4 | R170,R171,R172,R173 | CSR25120R1F | 696-1663-1-ND | 0.1 |  | RES2512 | 0.3188 | 1.2752 | 0.3188 | 1.2752 | 0.20873 | 0.83492 | DigiKey
45 | 2 | R185,R189 | RC0402FR-071K47L | YAG3038CT-ND | 1.47K |  | C0402 | 0.007 | 0.014 | 0.007 | 0.014 | 0.007 | 0.014 | DigiKey
46 | 2 | R187,R191 | ERJ-2RKF1501X | P1.50KLCT-ND | 1.5K |  | C0402 | 0.0232 | 0.0464 | 0.0232 | 0.0464 | 0.0232 | 0.0464 | DigiKey
47 | 4 | R186,R188,R190,R192 | CRGCQ0402F470R | A129623CT-ND | 470 |  | C0402 | 0.0086 | 0.0344 | 0.0086 | 0.0344 | 0.00388 | 0.01552 | DigiKey
48 | 22 | TP1,TP2,TP3,TP4,TP5,TP6,TP7,TP8,TP9,TP10,TP11,TP12,TP13,TP14,TP15,TP16,TP17,TP18,TP19,TP20,TP21,TP22,TP23 | 5015K |  |  |  | TP5015 |  | 0 |  | 0 |  | 0
49 | 1 | U1 | LTC1391IGN | LTC1391IGN#PBF-ND |  |  | SSOP16 | 3.914 | 3.914 | 3.914 | 3.914 | 3.774 | 3.774 | DigiKey
50 | 1 | U2 | LTC1152CS8 | LTC1152CS8#TRPBFCT-ND |  |  | SO8 | 6.7912 | 6.7912 | 6.7912 | 6.7912 | 6.7912 | 6.7912 | DigiKey
51 | 1 | U3 | AD7685ARM | AD7685ARMZRL7CT-ND |  |  | MSOP10 | 13.478 | 13.478 | 13.478 | 13.478 | 11.3829 | 11.3829 | DigiKey
52 | 3 | U4,U6,U42 | LTC2054HV | LTC2054HVCS5#TRMPBFCT-ND |  |  | SOT23-5 | 1.9339 | 5.8017 | 1.9339 | 5.8017 | 1.7728 | 5.3183 | DigiKey
53 | 1 | U5 | ADR4540BRZ | ADR4540BRZ-ND |  |  | SO8 | 8.21 | 8.21 | 8.21 | 8.21 | 6.141 | 6.141 | DigiKey
54 | 3 | U7,U8,U9 | CD74AC541SM96 | 296-31547-1-ND |  |  | SSOP20A | 0.5946 | 1.7838 | 0.5946 | 1.7838 | 0.4912 | 1.4736 | DigiKey
55 | 1 | U10 | ISL32173E | ISL32173EFBZ-ND |  |  | SO16 | 2.125 | 2.125 | 2.125 | 2.125 | 1.8105 | 1.8105 | DigiKey
56 | 1 | U11 | XC2C128-7QG100C | 122-1285-ND |  |  | VQFP-100 | 8.89 | 8.89 | 8.89 | 8.89 | 8.89 | 8.89 | DigiKey
57 | 1 | U12 | ISL3295E | ISL3295EIHZ-TCT-ND |  |  | SOT23-6 | 1.298 | 1.298 | 1.298 | 1.298 | 0.99652 | 0.99652 | DigiKey
58 | 1 | U13 | DS1100LU-50+ | DS1100LU-50+-ND |  |  | MSOP8 | 4.4936 | 4.4936 | 4.4936 | 4.4936 | 4.3605 | 4.3605 | DigiKey
59 | 1 | U14 | SN65LVDS2DBVR | 296-6920-1-ND |  |  | SOT23-5 | 1.416 | 1.416 | 1.416 | 1.416 | 1.104 | 1.104 | DigiKey
60 | 4 | U15,U16,U17,U18 | ADG725B | ADG725BSUZ-ND |  |  | TQFP48 | 9.331 | 37.324 | 9.331 | 37.324 | 8.729 | 34.916 | DigiKey
61 | 2 | U19,U20 | AD5383BSTZ-5 | AD5383BSTZ-5-ND |  |  | TQFP14X14-100 | 64.4176 | 128.8351 | 64.4176 | 128.8351 | 64.4176 | 128.8351 | DigiKey
62 | 16 | U21,U22,U23,U24,U25,U26,U27,U28,U29,U30,U31,U32,U33,U34,U35,U36 | LT1491A | LT1491ACDHC#PBF |  |  | DHC16 | 4.08 | 65.28 | 4.08 | 65.28 | 4.08 | 65.28 | DigiKey
63 | 4 | U37,U38,U39,U40 | AD8221BRZ | AD8221BRZ-ND |  |  | SO8 | 7.6896 | 30.7584 | 7.6896 | 30.7584 | 6.696 | 26.784 | DigiKey
64 | 1 | U41 | ADG731BSU | ADG731BSUZ-ND |  |  | TQFP48 | 9.804 | 9.804 | 9.804 | 9.804 | 7.874 | 7.874 | DigiKey
| 1 | Blank Board | [5 empty] | 100 | 100 | 100 | 100 | 100 | 100 | EST
| 1 | Assembly: R&D Production | [5 empty] | 97.5 | 97.5 | 97.5 | 97.5 | 97.5 | 97.5 | JAGBE
|  | Board Total | [6 empty] | 653.5824 |  | 653.5424 |  | 631.9543
|  | Total Part Cost | [6 empty] | 556.0824 |  | 556.0424 |  | 534.4543
|  | Total Assembly Cos: Production | [6 empty] | 97.5 |  | 97.5 |  | 97.5
|  | Total Cost | [6 empty] | 653.5824 |  | 653.5424 |  | 631.9543
|  | Setup Charge | [5 empty] | 175 |  | 0 |  | 175 |  | JAGBE
|  | Program Charge | [5 empty] | 185 |  | 0 |  | 185 |  | JAGBE
|  | Silk Screen | [5 empty] | 375 |  | 0 |  | 375 |  | JAGBE
|  | NRE | [5 empty] | 500 |  | 0 |  | 500 |  | JAGBE
|  | Total NRE Charges | [6 empty] | 1235 |  | 0 |  | 1235

## HCal_SIPM_DAUGHTERBOARD
205-1000-3x40: sPHENIX HCal SiPM board
Creation 26-Dec-2018
Last Revision Date: 29-Dec-2018
Item | Quantity | Reference | MFG Part # | Vendor Part # | Value | Tolerance | PCB Footprint | Unit Cost | Total
1 | 1 | Bare board | [5 empty] | 0.4 | 0.4
2 | 1 | Pigtail | [5 empty] | 2 | 2
3 | 1 | Assembly | [5 empty] | 10 | 10
[7 empty] | Unit Total |  | 12.4
[7 empty] | Total Parts Cost |  | 2.4
[7 empty] | Total Assembly Costs |  | 10
[7 empty] | Total Board Cost |  | 12.4
[7 empty] | NRE |  | 650

## HCal_PREAMP
205-1000-3x30: sPHENIX Hadronic Preamp
Creation 26-Dec-2018
Last Revision Date: 30-Jan-2019
For Cost estimation only NOT FOR PRODUCTION
Item | Quantity | Reference | MFG Part # | Vendor Part # | Value | Tolerance | PCB Footprint | Modues 1-6 Unit Cost | Modules 1-6 Total | Modues 7-32 Unit Cost | Modules 7-32 Total | Vendor
1 | 1 | C1 | CL21B105KAFNNNE | 1276-1066-1-ND | 1uF |  | C0805 | 0.0366 | 0.0366 | 0.02121 | 0.02121 | Digikey
2 | 2 | C2,C3 | GRT188R61E106ME13D | 490-12323-1-ND | 10uF |  | C0603 | 0.18398 | 0.36796 | 0.15639 | 0.31278 | Digikey
3 | 5 | C4,C7,C25,C28,C34 | CL05B103KB5NNNC | 1276-1028-1-ND | 10nF |  | C0402 | 0.00595 | 0.02975 | 0.00497 | 0.02485 | Digikey
4 | 19 | C5,C6,C8,C11,C14,C18,C19,C20,C21,C23,C26,C27,C29,C33,C35,C37,C38,C40,C41 | CL05A104MP5NNNC | 1276-1443-1-ND | 100nF |  | C0402 | 0.00497 | 0.09443 | 0.00497 | 0.09443 | Digikey
5 | 4 | C9,C13,C24,C30 | CL05A105MQ5NNNC | 1276-1235-1-ND | 1uF |  | C0402 | 0.00638 | 0.02552 | 0.00541 | 0.02164 | Digikey
6 | 4 | C10,C22,C32,C39 | CC0402KRX7R9BB102 | 311-1036-1-ND | 1nF |  | C0402 | 0.00778 | 0.03112 | 0.00661 | 0.02644 | Digikey
7 | 1 | C12 | CL05C100JB5NNNC | 1276-1139-1-ND | 10pF |  | C0402 | 0.0182 | 0.0182 | 0.01051 | 0.01051 | Digikey
8 | 2 | C15,C31 | C0402C473K3RACAUTO | 399-15998-1-ND | 47nF |  | C0402 | 0.0421 | 0.0842 | 0.03243 | 0.06486 | Digikey
9 | 1 | C16 | CL05B181KB5NNNC | 1276-1525-1-ND | 180pF |  | C0402 | 0.0147 | 0.0147 | 0.00849 | 0.00849 | Digikey
10 | 1 | C17 | CC0402JRNPO9BN101 | 311-1024-1-ND | 100pF |  | C0402 | 0.0128 | 0.0128 | 0.00716 | 0.00716 | Digikey
11 | 1 | C36 | GJM1555C1H1R0BB01D | 490-6073-1-ND | 1pF |  | C0402 | 0.0659 | 0.0659 | 0.03987 | 0.03987 | Digikey
12 | 1 | C42 | CL21B104KCFNNNE | 1276-6840-1-ND | 100nF |  | C0805 | 0.0348 | 0.0348 | 0.01953 | 0.01953 | Digikey
13 | 1 | HDR1 | HDR2 |  | CON2 |  |  | 1.5 | 1.5 | 1.5 | 1.5 | EST
14 | 1 | J1 | DF11-10DP-2DS(52) | H2868-ND |  |  |  | 1.0942 | 1.0942 | 0.78161 | 0.78161 | Digikey
15 | 1 | J2 | DF3A-3P-2DS | H3894-ND |  |  |  | 0.1248 | 0.1248 | 0.0864 | 0.0864 | Digikey
16 | 1 | L1 | L-14CR18JV4T | 712-1449-1-ND | 180nH |  | C0603 | 0.0466 | 0.0466 | 0.03261 | 0.03261 | Digikey
17 | 2 | Q1,Q2 | BFR 93AW H6327 | 726-BFR93AWH6327 |  |  | SOT323 | 0.156 | 0.312 | 0.117 | 0.234 | Mouser
18 | 1 | Q3 | NTS4409NT1G | NTS4409NT1GOSCT-ND |  |  | SOT323 | 0.2753 | 0.2753 | 0.12576 | 0.12576 | Mouser
19 | 1 | RT1 | KS103J2 | 615-1075-ND |  |  |  | 3.0525 | 3.0525 | 2.3925 | 2.3925 | Digikey
20 | 1 | R1 | RC0402FR-07100RL | 311-100LRCT-ND | 100R |  | C0402 | 0.007 | 0.007 | 0.00328 | 0.00328 | Digikey
21 | 3 | R2,R12,R22 | RC0402JR-0710RL | 311-10JRCT-ND | 10R |  | C0402 | 0.0082 | 0.0246 | 0.00341 | 0.01023 | Digikey
22 | 3 | R3,R21,R25 | RNCF0402DTE1K02 | RNCF0402DTE1K02CT-ND | 1.02K |  | C0402 | 0.0745 | 0.2235 | 0.02859 | 0.08577 | Digikey
23 | 4 | R4,R11,R13,R16 | RC0402FR-0748R7L | YAG3170CT-ND | 49R9 |  | C0402 | 0.00328 | 0.01312 | 0.00242 | 0.00968 | Digikey
24 | 2 | R5,R19 | RC0402FR-075K9L | YAG3197CT-ND | 5.9K |  | C0402 | 0.007 | 0.014 | 0.00288 | 0.00576 | Digikey
25 | 2 | R6,R26 | ERJ-2RKF27R0X | P27.0LCT-ND | 27R |  | C0402 | 0.0189 | 0.0378 | 0.00775 | 0.0155 | Digikey
26 | 2 | R7,R20 | RC0402FR-07261RL | YAG3078CT-ND | 261R |  | C0402 | 0.007 | 0.014 | 0.00288 | 0.00576 | Digikey
27 | 1 | R8 | CRGCQ0402F220R | A129619CT-ND | 220R |  | C0402 | 0.0086 | 0.0086 | 0.00388 | 0.00388 | Digikey
28 | 4 | R9,R17,R24,R31 | RNCF0402BTE10K0 | RNCF0402BTE10K0CT-ND | 10K |  | C0402 | 0.05891 | 0.23564 | 0.04938 | 0.19752 | Digikey
29 | 2 | R10,R14 | CRCW0402249RFKEDC | 541-4112-1-ND | 249R |  | C0402 | 0.0108 | 0.0216 | 0.00449 | 0.00898 | Digikey
31 | 2 | R18,R27 | ERJ-2RKF7500X | P750LCT-ND | 750R |  | C0402 | 0.0189 | 0.0378 | 0.00775 | 0.0155 | Digikey
32 | 1 | R23 | RMCF0402FT27K0 | RMCF0402FT27K0CT-ND | 27K |  | C0402 | 0.0064 | 0.0064 | 0.00289 | 0.00289 | Digikey
33 | 1 | R28 | ERJ-2RKF1400X | P140LCT-ND | 140R |  | C0402 | 0.0183 | 0.0183 | 0.00823 | 0.00823 | Digikey
34 | 1 | R29 | RC0402FR-07620RL | 311-620LRCT-ND | 620R |  | C0402 | 0.007 | 0.007 | 0.00328 | 0.00328 | Digikey
35 | 1 | R30 | RC0402JR-0720RL | 311-20JRCT-ND | 20R |  | C0402 | 0.0057 | 0.0057 | 0.00267 | 0.00267 | Digikey
36 | 5 | Si1,Si2,Si3,Si4,Si5 | WM73412 |  |  |  |  | 1.5 | 7.5 | 1.5 | 7.5 | EST
37 | 2 | U1,U4 | AD8001ART-REEL7 | AD8001ARTZREEL7CT-ND |  |  | SOT23-5 | 2.2398 | 4.4797 | 1.889 | 3.778 | Digikey
38 | 1 | U2 | ADG601BRTZ-REEL7 | ‎ADG601BRTZ-REEL7 |  |  | SOT23-6 | 2.0403 | 2.1692 | 1.389 | 1.5574 | Digikey
39 | 1 | U3 | AD8132ARM | AD8132ARM-ND |  |  | MSOP8 | 4.35 | 4.35 | 4.35 | 4.35 | Digikey
40 | 1 | U5 | ADG602BRTZ-REEL7 | ADG602BRTZ-REEL7CT-ND |  |  | SOT23-6 | 2.1692 | 2.1692 | 1.5574 | 1.5574 | Digikey
| 1 | PCB-Blank | PCB Board |  |  |  |  | 10 | 10 | 7.5 | 7.5 | EST
| 1 | Assembly | Assembly Charge |  |  |  |  | 7.5 | 7.5 | 7.5 | 7.5 | EST
|  |  | Board Total | [5 empty] | 46.0646 |  | 39.9263
|  | Total Parts Cost | Total Part Cost | [5 empty] | 38.5646 |  | 32.4263
|  | Total Assembly Cost | Total Assembly Cost: Production | [5 empty] | 7.5 |  | 7.5
|  | Total Board Cost | Total Cost | [5 empty] | 46.0646 |  | 39.9263
|  | NRE | NRE Charges | [5 empty] | 500 |  | 500
Turnkey Assembly
| 320 | Module 1-6 Assembly | [5 empty] | 42.76 | 13683.2
| 1 | Tooling Charge |  |  |  |  | NRE | 1019 | 1019
14702.2
| 1375 | Module 17-32 Assembly | [7 empty] | 30.64 | 42130
0
42130

## HCAL_IFCE
205-1000-3x00: HCal Interface
Creation: 28-Dec-2018
Last Revision Date: 01-Jan-2019
Item | Quantity | Reference | MFG # | Vendor Part Number | Value | Tolerance | PCB Footprint | Modules 1-6 Unit Cost | Module 1-6 Total | Modules 7-32 Unit Cost | Module 7-32 Total | Vendor
1 | 5 | C1,C14,C40,C41,C48 | GRT188R61E106ME13D | 490-12323-1-ND | 10uF |  | C0603 | 0.377 | 1.885 | 0.2484 | 1.242 | Digikey
2 | 65 | C2,C3,C4,C6,C9,C10,C12,C13,C15,C16,C18,C19,C20,C21,C22,C23,C25,C26,C27,C28,C29,C30,C31,C32,C33,C34,C35,C36,C44,C45,C46,C47,C49,C50,C51,C52,C53,C56,C59,C62,C65,C68,C71,C74,C77,C80,C83,C86,C89,C92,C95,C98,C101,C103,C105,C106,C108,C110,C111,C112,C113,C114,C115,C116,C117 | CL05B104KO5NNWC | 1276-1509-1-ND | 100nF |  | C0402 | 0.00958 | 0.6227 | 0.00684 | 0.4446 | Digikey
3 | 1 | C5 | CC0402KRX7R9BB102 | 311-1036-1-ND | 1nF |  | C0402 | 0.03 | 0.03 | 0.03 | 0.03 | Digikey
4 | 1 | C7 | CL05A224KO5NNNC | 1276-1456-1-ND | 2.7nF |  | C0402 | 0.095 | 0.095 | 0.095 | 0.095 | Digikey
5 | 6 | C8,C17,C102,C104,C107,C109 | GRM155C81C105KE11D | 490-12700-1-ND | 1uF |  | C0402 | 0.165 | 0.99 | 0.0935 | 0.561 | Digikey
6 | 1 | C11 | CL05B103KB5NNNC | 1276-1028-1-ND | 10nF |  | C0402 | 0.024 | 0.024 | 0.024 | 0.024 | Digikey
7 | 1 | C24 | CL21B104KCFNNNE | 1276-6840-1-ND | 100nF | 100V | C0805 | 0.078 | 0.078 | 0.078 | 0.078 | Digikey
8 | 3 | C37,C39,C42 | 298D226X0010M2T | 718-1718-1-ND | 22uF |  | C0805 | 1.581 | 4.743 | 1.2075 | 3.6225 | Digikey
9 | 2 | C38,C43 | 594D337X0010R2T | 718-1012-1-ND | 594D337X0010R2T |  | 7260A | 6.141 | 12.282 | 4.9128 | 9.8256 | Digikey
10 | 32 | C54,C55,C57,C58,C60,C61,C63,C64,C66,C67,C69,C70,C72,C73,C75,C76,C78,C79,C81,C82,C84,C85,C87,C88,C90,C91,C93,C94,C96,C97,C99,C100 | C0402C224K9PAC7867 | 399-4886-1-ND | 220nF |  | C0402 | 0.0169 | 0.5408 | 0.00949 | 0.30368 | Digikey
11 | 6 | D1,D2,D4,D5,D6,D7 | BAS40-02V-V-G-08 | BAS40-02V-V-G-08GICT-ND | BAS40-02V |  | SOD523_DIODE | 0.294 | 1.764 | 0.1666 | 0.9996 | Digikey
12 | 2 | D8,D9 | CDBA240LL | 641-1698-1-ND | CDBA240LL |  | DO-214AC |  | 0 |  | 0 | Digikey
13 | 2 | HDR1,HDR2 |  |  | HEADER 2 |  | HDR2/2MM |  | 0 |  | 0
14 | 1 | HDR3 | WM0877580816 |  | WM0877580816 |  | HDR2X4/2MM |  | 0 |  | 0 | Digikey
15 | 1 | HDR4 | WM0877583416 |  | WM0877583416 |  | HDR2X17/2MM |  | 0 |  | 0 | Digikey
16 | 1 | HDR5 | 087831-1420 | WM17469-ND | 087831-1420 |  | HDR2X7/2MM | 1.301 | 1.301 | 1.301 | 1.301 | Digikey
17 | 1 | HDR6 | 399-93-104-10-003000 | ED8964-04-ND | 399-93-104-10-003000 |  | SIP4 | 0.763 | 0.763 | 0.6882 | 0.6882 | Digikey
18 | 1 | J1 |  |  | CON3 |  | WM70553-0002 |  | 0 |  | 0 | Digikey
19 | 1 | J2 | 1-178296-2 | A29452-ND | 1-178296-2 |  | DYND-6 | 3.036 | 3.036 | 3.036 | 3.036 | Digikey
20 | 1 | L1 | LQM31PN1R0M00L | 490-4039-1-ND | LQM31PN1R0M00L |  | CC1206 | 0.351 | 0.351 | 0.351 | 0.351 | Digikey
21 | 1 | P1 | VMEP |  |  |  | CNVME96A |  | 0 |  | 0
22 | 1 | REG1 | LT1764AEQ#PBF | LT1764AEQ#PBF-ND | LT1764AEQ |  | TO-263-5 | 7.56 | 7.56 | 5.192 | 5.192 | Digikey
23 | 1 | REG2 | LM1117MPX-3.3/NOPB | LM1117MPX-3.3/NOPBDKR-ND | LM1117MPX-3.3 |  | SOT223 | 1.482 | 1.482 | 1.1317 | 1.1317 | Digikey
24 | 1 | REG3 | TPS79118DBVR | 595-TPS79118DBVR | TPS79118 |  | SOT23-5 | 1.12 | 1.12 | 1.12 | 1.12 | Mouser
25 | 1 | REG4 | LT3015IQ#PBF | LT3015IQ#PBF-ND | LT3015ET |  | TO-263-5 | 7.51 | 7.51 | 5.0288 | 5.0288 | Digikey
26 | 2 | RP1,RP2 | 742C163470JPCT | 742C163470JPCT-ND | 742C163470JPCT |  | CRN16/CTS742 | 0.3548 | 0.7096 | 0.196 | 0.392 | Digikey
27 | 1 | RS1 | 6116075-1 | A130943-ND | 6116075-1 |  | 6116075-1 | 3.676 | 3.676 | 3.2164 | 3.2164 | Digikey
28 | 3 | RT1,RT2,RT3 | MINISMDC200F-2 | MINISMDC200F-2CT-ND | MINISMDC200F-2 |  | CC1812 | 0.546 | 1.638 | 0.3908 | 1.1724 | Digikey
29 | 3 | R1,R39,R48 | ERA-2AED302X | P3.0KDECT-ND | 3K | 0.1% | C0402 | 0.188 | 0.564 | 0.0735 | 0.2205 | Digikey
30 | 5 | R2,R7,R9,R12,R153 | RL0510S-1R0-F | RL05S1.0FCT-ND | 1R |  | C0402 | 0.1844 | 0.922 | 0.11588 | 0.5794 | Digikey
31 | 1 | R3 | RC0402JR-0733RL | 311-33JRCT-ND | 33R |  | C0402 | 0.013 | 0.013 | 0.013 | 0.013 | Digikey
32 | 6 | R4,R6,R11,R149,R152,R155 | RG1005P-102-B-T5 | RG10P1.0KBDKR-ND | 1K |  | C0402 | 0.39678 | 2.3807 | 0.15344 | 0.92064 | Digikey
33 | 1 | R5 | ERA-2AEB104X | P100KDCCT-ND | 100K | 0.1% | C0402 | 0.322 | 0.322 | 0.322 | 0.322 | Digikey
34 | 1 | R8 | PNM0402E2502BST1 | 541-1903-1-ND | 25K | 0.1% | C0402 | 1.003 | 1.003 | 1.003 | 1.003 | Digikey
35 | 1 | R10 | RMCF0402JT10M0 | RMCF0402JT10M0CT-ND | 10M | 0.5% | R1210 | 0.012 | 0.012 | 0.012 | 0.012 | Digikey
36 | 1 | R13 | ERJ-2RKF4993X | P499KLCT-ND | 499K | 0.1% | C0805 | 0.046 | 0.046 | 0.046 | 0.046 | Digikey
37 | 7 | R14,R15,R16,R17,R18,R22,R156 | RC0402FR-07100RL | 311-100LRCT-ND | 100R |  | C0402 | 0.007 | 0.049 | 0.007 | 0.049 | Digikey
38 | 3 | R19,R20,R21 | RNCF0402BTE10K0 | RNCF0402BTE10K0CT-ND | 10K |  | C0402 | 0.299 | 0.897 | 0.1195 | 0.3585 | Digikey
39 | 24 | R23,R24,R25,R26,R27,R28,R29,R30,R31,R32,R33,R34,R35,R36,R37,R38,R40,R41,R42,R43,R44,R45,R46,R47 | RT0402BRD07100RL | YAG2301CT-ND | 100R | 0.1% | C0402 | 0.1214 | 2.9136 | 0.05982 | 1.4357 | Digikey
40 | 1 | R50 | CSR25120R1F | 696-1663-6-ND | 0R |  | C0402 | 0.998 | 0.998 | 0.5265 | 0.5265 | Digikey
41 | 65 | R51,R52,R53,R55,R57,R58,R59,R61,R63,R64,R65,R67,R69,R70,R71,R73,R75,R76,R77,R79,R81,R82,R83,R85,R87,R88,R89,R91,R93,R94,R95,R97,R99,R100,R101,R103,R105,R106,R107,R109,R111,R112,R113,R115,R117,R118,R119,R121,R123,R124,R125,R127,R129,R130,R131,R133,R135,R136,R137,R139,R141,R142,R143,R145,R154 | RNCF0402BTE10K0 | RNCF0402BTE10K0DKR-ND | 10K | 0.1% | C0402 | 0.12668 | 8.2342 | 0.05637 | 3.6641 | Digikey
42 | 32 | R54,R56,R60,R62,R66,R68,R72,R74,R78,R80,R84,R86,R90,R92,R96,R98,R102,R104,R108,R110,R114,R116,R120,R122,R126,R128,R132,R134,R138,R140,R144,R146 | RC0402FR-07150RL | 311-150LRCT-ND | 150R |  | C0402 | 0.007 | 0.224 | 0.00328 | 0.10496 | Digikey
43 | 2 | R147,R150 | RC0402FR-07680KL | YAG3211CT-ND | 680K |  | C0402 | 0.016 | 0.032 | 0.007 | 0.014 | Digikey
44 | 2 | R148,R151 | RMCF0402FT2K61 | RMCF0402FT2K61CT-ND | 2.61K | 0.1% | C0402 | 0.016 | 0.032 | 0.0064 | 0.0128 | Digikey
45 | 2 | R157,R159 | ERJ-2RKF1501X | P1.50KLCT-ND | 1.5K |  | C0402 | 0.056 | 0.112 | 0.0232 | 0.0464 | Digikey
46 | 1 | R158 | ERA-2AEB4750X | P475DCCT-ND | 475R |  | C0402 | 0.321 | 0.321 | 0.321 | 0.321 | Digikey
47 | 1 | R160 | RC0402FR-07470RL | 311-470LRCT-ND | 470R |  | C0402 | 0.016 | 0.016 | 0.016 | 0.016 | Digikey
48 | 3 | TH1,TH2,TH3 | PT103J2 | 615-1010-ND | PT103J2 |  | HDR2/2MM | 1.56 | 4.68 | 1.3 | 3.9 | Digikey
49 | 2 | U1,U6 | LTC1391IGN#PBF | LTC1391IGN#PBF-ND | LTC1391CGN |  | SSOP16 | 3.914 | 7.828 | 3.774 | 7.548 | Digikey
50 | 1 | U2 | LTC1152IS8#PBF | LTC1152IS8#PBF-ND | LTC1152CS8 |  | SO8 | 7.43 | 7.43 | 4.9348 | 4.9348 | Digikey
51 | 1 | U3 | AD7685ARMZRL7 | AD7685ARMZRL7CT-ND | AD7685ARM |  | MSOP10 | 13.478 | 13.478 | 13.478 | 13.478 | Digikey
52 | 3 | U4,U7,U29 | LTC2054HVCS5#TRMPBF | LTC2054HVCS5#TRMPBFDKR-ND | LTC2054HV |  | SOT23-5 | 2.9491 | 8.8473 | 1.9728 | 5.9183 | Digikey
53 | 1 | U5 | ADR4540BRZ | ADR4540BRZ-ND | ADR4540BRZ |  | SO8 | 8.21 | 8.21 | 8.21 | 8.21 | Digikey
54 | 2 | U8,U9 | SN74LVTH541DBR | 296-8727-1-ND | SN74LVTH541DBR |  | SSOP20A | 1.711 | 3.422 | 1.3756 | 2.7512 | Digikey
55 | 1 | U10 | ISL32173EFBZ | ISL32173EFBZ-ND | ISL32173E |  | SO16 | 2.253 | 2.253 | 2.125 | 2.125 | Digikey
56 | 1 | U11 | XC2C128-7VQG100C | 122-1285-ND | XC2C128-7QG100C |  | VQFP-100 | 9.05 | 9.05 | 8.89 | 8.89 | Digikey
57 | 1 | U12 | ISL3295EFHZ-T7A | ISL3295EFHZ-T7ACT-ND | ISL3295E |  | SOT-6 | 1.365 | 1.365 | 1.2876 | 1.2876 | Digikey
58 | 1 | U13 | DS1100LU-50 | DS1100LU-50+-ND | DS1100LU-50+ |  | MSOP8 | 5.738 | 5.738 | 4.4936 | 4.4936 | Mouser
59 | 1 | U14 | SN65LVDS2DBR | 296-11865-1-ND | SN65LVDS2 |  | SOT23-5 | 1.416 | 1.416 | 1.416 | 1.416 | Digikey
60 | 2 | U15,U16 | ADG725BSUZ | AD8221ARZ-R7CT-ND | ADG725B |  | TQFP48 | 5.868 | 11.736 | 4.8585 | 9.717 | Digikey
61 | 1 | U17 | AD5383BSTZ-5 | AD5383BSTZ-5-ND | AD5383-3 |  | TQFP14X14-100 | 69.94 | 69.94 | 69.94 | 69.94 | Digikey
62 | 8 | U18,U19,U20,U21,U22,U23,U24,U25 | LT1491ACDHC#PBF | LT1491ACDHC#PBF-ND | LT1491A |  | DHC16 | 4.08 | 32.64 | 4.08 | 32.64 | Digikey
63 | 2 | U26,U27 | AD8221ARZ-R7 | AD8221ARZ-R7CT-ND | AD8221ARZ |  | SO8 | 5.868 | 11.736 | 4.8585 | 9.717 | Digikey
64 | 1 | U28 | ADG731BSUZ | ADG731BSUZ-ND | ADG731BCP |  | TQFP48 | 9.804 | 9.804 | 9.804 | 9.804 | Digikey
65 | 1 | Bare Board |  |  | Blank PCB |  |  | 100 | 100 | 100 | 100 | Est
66 | 1 | Assembly- 15 Boards |  |  | Assembly |  |  | 97.5 | 97.5 | 97.5 | 97.5 | Jagbe
|  | Total Board Cost | [6 empty] | 478.3659 |  | 443.7914
|  | Total Component Cost | [6 empty] | 380.8659 |  | 346.2914
|  | Total Assembly Cost | [6 empty] | 97.5 |  | 97.5
| 1 | Solder Paste Screen | [5 empty] | 375 | 375 |  | 0 | Jagbe
| 1 | Setup Charge | [5 empty] | 185 | 185 |  | 0 | Jagbe
| 1 | Programming Charge | [5 empty] | 175 | 175 |  | 0 | Jagbe
|  | Total NRE Charges |  | Total NRE |  |  |  |  | 735 |  | 0

## HCAL_INNER_BP-C
205-1000-3x10: HCal Backplane
Creation: 29-Dec-2018
Last Revision Date: 4-Jan-2019
Item | Quantity | Reference | MFG # | Vendor Part Number | Value | Tolerance | PCB Footprint | Modules 1-6 Unit Cost | Module 1-6 Total | Modules 7-32 Unit Cost | Module 7-32 Total | Vendor | Coments
1 | 24 | CH1,CH2,CH3,CH4,CH5,CH6,CH7,CH8,CH9,CH10,CH11,CH12,CH13,CH14,CH15,CH16,CH17,CH18,CH19,CH20,CH21,CH22,CH23,CH24 | 5-103168-4 | A33043-ND |  |  |  | 2.6688 | 64.05 | 1.9348 | 46.4359 | Digikey
2 | 2 | C1,C3 | T520C226M016ATE080 | 399-5119-1-ND | 22uF |  | 6032 | 1.063 | 2.126 | 0.0839 | 0.1678 | Digikey
3 | 2 | C2,C4 | CL10B104KO8NNNC | 1276-1005-1-ND | 100nF |  | CC0603 | 0.036 | 0.072 | 0.0162 | 0.0324 | Digikey
4 | 1 | C5 | 0504B103K101NT | 1763-1204-1-ND | 10nF |  | CC1210 | 0.619 | 0.619 | 0.619 | 0.619 | Digikey
5 | 48 | C6,C7,C8,C9,C10,C11,C12,C13,C14,C15,C16,C17,C18,C19,C20,C21,C22,C23,C24,C25,C26,C27,C28,C29,C30,C31,C32,C33,C34,C35,C36,C37,C38,C39,C40,C41,C42,C43,C44,C45,C46,C47,C48,C49,C50,C51,C52,C53 | GRT188R61E106ME13D | 490-12323-1-ND | 10uF |  | CC0603 | 0.18398 | 8.831 | 0.15639 | 7.5067 | Digikey
6 | 48 | JP1,JP2,JP3,JP4,JP5,JP6,JP7,JP8,JP9,JP10,JP11,JP12,JP13,JP14,JP15,JP16,JP17,JP18,JP19,JP20,JP21,JP22,JP23,JP24,JP25,JP26,JP27,JP28,JP29,JP30,JP31,JP32,JP33,JP34,JP35,JP36,JP37,JP38,JP39,JP40,JP41,JP42,JP43,JP44,JP45,JP46,JP47,JP48 |  |  |  |  | 0402link | 1 | 48 | 1 | 48 | EST
7 | 1 | J1 | CNVME96B |  |  |  |  | 2.5 | 2.5 | 2.5 | 2.5 | EST
8 | 1 | J2 | CN34U |  |  |  |  | 1.4885 | 1.4885 | 1.4885 | 1.4885 | EST
9 | 1 | LED1 | CMD17-21VGD/TR8 | L62505CT-ND |  |  | CC0805 | 0.2972 | 0.2972 | 0.2972 | 0.2972 | Digikey
10 | 48 | RT1,RT2,RT3,RT4,RT5,RT6,RT7,RT8,RT9,RT10,RT11,RT12,RT13,RT14,RT15,RT16,RT17,RT18,RT19,RT20,RT21,RT22,RT23,RT24,RT25,RT26,RT27,RT28,RT29,RT30,RT31,RT32,RT33,RT34,RT35,RT36,RT37,RT38,RT39,RT40,RT41,RT42,RT43,RT44,RT45,RT46,RT47,RT48 | 0603L010YR |  |  |  | CR0603 | 0.6105 | 29.304 | 0.5445 | 26.136 | Digikey
11 | 1 | R1 | RC0603JR-070RL | 311-0.0GRCT-ND | 0R |  | CR0603 | 0.021 | 0.021 | 0.0118 | 0.0118 | Digikey
12 | 1 | R2 | RC0603FR-07330RL | 311-330HRCT-ND | 330R |  | CR0603 | 0.024 | 0.024 | 0.024 | 0.024 | Digikey
13 | 24 | R3,R4,R5,R6,R7,R8,R9,R10,R11,R12,R13,R14,R15,R16,R17,R18,R19,R20,R21,R22,R23,R24,R25,R26 | ESR03EZPJ100 | RHM10DCT-ND | 10R |  | CR0603 | 0.0333 | 0.7992 | 0.01464 | 0.35136 | Digikey
14 | 1 | Bare Board | [5 empty] | 50 | 50 | 50 | 50 | EST
15 | 1 | Assembly | [5 empty] | 0 | 0 | 50 | 50 | EST | Modules 1-6 Done in house
|  | Total Board Cost | [6 empty] | 208.1319 |  | 233.5707
|  | Total Component Cost | [6 empty] | 208.1319 |  | 183.5707
|  | Total Assembly Cost | [6 empty] | 0 |  | 50
| 1 | Solder Paste Screen | [6 empty] | 0 | 375 | 375 | EST
| 1 | Setup Charge | [6 empty] | 0 | 185 | 185 | EST
| 1 | Programming Charge | [6 empty] | 0 | 175 | 175 | EST
|  | Total NRE Charges |  | Total NRE |  |  |  |  | 0 |  | 735

## LED_DRIVER
205-1000-3x20: HCal LED Driver
Creation: 29-Dec-2018
Last Revision Date: 11-Feb-2019
Item | Quantity | Reference | MFG Part # | Vendor Part # | Pvalue | Tolerance | PCB Footprint | Qnty 15 Unit Cost | Quantity 15 Total | Qnty 55 Unit Cost | Quantity 55 Total | Vendor | Comments
1 | 2 | C1,C2 | C5750X5R0J107M280KA | 445-3501-1-ND | 22uF |  | 2220 | 2.372 | 4.744 | 1.8113 | 3.6226 | Digikey
2 | 97 | C3,C4,C8,C9,C10,C11,C13,C15,C16,C17,C18,C20,C22,C23,C24,C25,C27,C29,C30,C31,C32,C34,C36,C37,C38,C39,C41,C43,C45,C46,C47,C48,C49,C50,C51,C52,C53,C55,C57,C58,C59,C61,C63,C64,C65,C66,C67,C68,C69,C70,C71,C73,C75,C76,C77,C79,C81,C82,C83,C84,C85,C86,C87,C88,C89,C91,C93,C94,C95,C97,C99,C100,C101,C102,C103,C104,C105,C106,C107,C109,C111,C112,C113,C115,C117,C118,C119,C120,C121,C122,C123,C124,C125,C127,C129,C130,C131 | CL05A104MP5NNNC | 1276-1443-1-ND | 100nF |  | C0402 | 0.00595 | 0.57715 | 0.00497 | 0.48209 | Digikey
3 | 1 | C5 | CC0402JRNPO9BN470 | 311-1021-1-ND | 47pF |  | C0402 | 0.03 | 0.03 | 0.03 | 0.03 | Digikey
4 | 1 | C6 | 04025A121JAT2A | 478-1083-1-ND | 120pf |  | C0402 | 0.134 | 0.134 | 0.134 | 0.134 | Digikey
5 | 10 | C7,C12,C14,C19,C21,C26,C28,C33,C35,C40 | CL10A106MQ8NNNC | 1276-1119-1-ND | 10uF |  | C0603 | 0.0583 | 0.583 | 0.03842 | 0.3842 | Digikey
6 | 5 | C42,C60,C78,C96,C114 | C0402C151K5RACTU | 399-7771-1-ND | 150pF |  | C0402 | 0.333 | 1.665 | 0.1997 | 0.9985 | Digikey
7 | 5 | C44,C62,C80,C98,C116 | GJM1555C1HR30WB01D | 490-11248-1-ND | 0.3pF |  | C0402 | 0.205 | 1.025 | 0.1161 | 0.5805 | Digikey
8 | 5 | C54,C72,C90,C108,C126 | CL10B102KB8NNNC | 1276-1018-1-ND | 1nF |  | C0603 | 0.04 | 0.2 | 0.0179 | 0.0895 | Digikey
9 | 2 | C132,C133 | CC1210ZKY5V7BB226 | 311-2062-1-ND | 22uF |  | CC1210 | 0.609 | 1.218 | 0.4177 | 0.8354 | Digikey
10 | 5 | D1,D2,D3,D4,D5 | HSMS-2823-TR1G | 630-HSMS-2823-TR1G |  |  | SOT23 | 0.48 | 2.4 | 0.38 | 1.9 | Mouser | End of Life
11 | 2 | FB1,FB2 | BLM18PG121SH1 | 490-7815-1-ND |  |  | C0603 | 0.084 | 0.168 | 0.0533 | 0.1066 | Digikey
12 | 18 | HDR1,HDR2,HDR3,HDR4,HDR5,HDR6,HDR7,HDR8,HDR9,HDR10,HDR11,HDR12,HDR13,HDR14,HDR15,HDR16,HDR17,HDR18 | HEADER 2 |  |  |  | HDR2 | 1.5 | 27 | 1.5 | 27 | EST
13 | 1 | J1 | 5103310-7 | A33186-ND |  |  | CN34U | 3.7 | 3.7 | 3.1524 | 3.1524 | Digikey
14 | 5 | LED1,LED2,LED3,LED4,LED5 | UV3TZ-395-30 | 492-1319-ND |  |  | LXT046 | 1.3352 | 6.676 | 1.0449 | 5.2246 | Digikey
15 | 5 | PD1,PD2,PD3,PD4,PD5 | PS1.0-5B-TO52S1.3 |  | 2K |  | TO-52S1 |  | 0 |  | 0 | est
16 | 2 | RT1,RT2 | 1206L075/16WR | F7138CT-ND | 127R |  | CC1206 | 0.909 | 1.818 | 0.627 | 1.254 | Digikey
17 | 3 | R1,R2,R3 | RT0402BRD072KL | YAG2303CT-ND | 2K |  | C0402 | 0.304 | 0.912 | 0.1214 | 0.3642 | Digikey
18 | 10 | R4,R10,R14,R20,R24,R30,R34,R40,R44,R50 | RP73PF1E127RBTD | A127233CT-ND | 127R |  | C0402 | 0.1953 | 1.953 | 0.1952 | 1.952 | Digikey
19 | 10 | R5,R11,R15,R21,R25,R31,R35,R41,R45,R51 | RC0402FR-07274RL | YAG3084CT-ND | 274R |  | C0402 | 0.007 | 0.07 | 0.007 | 0.07 | Digikey
20 | 10 | R6,R16,R26,R36,R46,R61,R71,R81,R91,R101 | RC0402FR-0748R7L | YAG3170CT-ND | 49R9 |  | C0402 | 0.007 | 0.07 | 0.007 | 0.07 | Digikey
21 | 10 | R7,R12,R17,R22,R27,R32,R37,R42,R47,R52 | ERJ-2RKF68R0X | P68.0LCT-ND | 68R1 |  | C0402 | 0.0189 | 0.189 | 0.0189 | 0.189 | Digikey
22 | 10 | R8,R9,R18,R19,R28,R29,R38,R39,R48,R49 | RC0603FR-0710RL | 311-10.0HRCT-N | 10R |  | CR0603 | 0.0203 | 0.203 | 0.0203 | 0.203 | Digikey
23 | 5 | R13,R23,R33,R43,R53 | RT0402BRD07100RL | YAG2301CT-ND | 100R |  | C0402 | 0.304 | 1.52 | 0.1214 | 0.607 | Digikey
24 | 5 | R54,R64,R74,R84,R94 | RC0402FR-071K1L | 311-1.10KLRCT-ND | 1.1K |  | C0402 | 0.016 | 0.08 | 0.007 | 0.035 | Digikey
25 | 5 | R55,R65,R75,R85,R95 | RT0402BRD0740K2L | YAG1429CT-ND | 40.2K |  | C0402 | 0.304 | 1.52 | 0.1214 | 0.607 | Digikey
26 | 5 | R56,R66,R76,R86,R96 | RC0402FR-07499RL | 311-499LRCT-ND | 499R |  | C0402 | 0.016 | 0.08 | 0.007 | 0.035 | Digikey
27 | 5 | R57,R67,R77,R87,R97 | ERJ-2RKF4993X | P499KLCT-ND | 499K |  | C0402 | 0.046 | 0.23 | 0.0189 | 0.0945 | Digikey
28 | 5 | R58,R68,R78,R88,R98 | ERJ-2RKF2490 | P249LCT-ND | 249R |  | C0402 | 0.056 | 0.28 | 0.023 | 0.115 | Digikey
29 | 5 | R59,R69,R79,R89,R99 | RC0402FR-071ML | 311-1.00MLRCT-ND | 1M |  | C0402 | 0.016 | 0.08 | 0.007 | 0.035 | Digikey
30 | 5 | R60,R70,R80,R90,R100 | ERJ-2RKF7500X | P750LCT-ND | 750R |  | C0402 | 0.046 | 0.23 | 0.0189 | 0.0945 | Digikey
31 | 10 | R62,R63,R72,R73,R82,R83,R92,R93,R102,R103 | ERJ-2RKF1001X | P1.00KLCT-ND | 1K |  | C0402 | 0.056 | 0.56 | 0.0227 | 0.227 | Digikey
32 | 1 | R104 | RC0402FR-0768RL | 311-68.0LRCT-ND | 68R |  | C0402 | 0.016 | 0.016 | 0.016 | 0.016 | Digikey
33 | 1 | U1 | 74HC123D | 74HC123DCT-ND |  |  | SO16 | 0.599 | 0.599 | 0.5244 | 0.5244 | Digikey
34 | 5 | U2,U3,U4,U5,U6 | LMH6553MRE | LMH6553MRE/NOPBCT-ND |  |  | SO8PP | 7.038 | 35.19 | 7.038 | 35.19 | Digikey | Limited Quantity
35 | 5 | U7,U13,U19,U25,U31 | OPA657N | OPA657NB/250CT-ND |  |  | SOT23-5 | 11.748 | 58.74 | 11.748 | 58.74 | Digikey | Limited Quantity
36 | 5 | U8,U14,U20,U26,U32 | ‎AD8001ARTZ-REEL7‎ | 584-AD8001ARTZ-R7 |  |  | SOT23-5 | 1.7 | 8.5 | 1.7 | 8.5 | Mouser
37 | 5 | U9,U15,U21,U27,U33 | THS4271D | 296-13823-5-ND |  |  | SO8 | 5.9943 | 29.9714 | 5.2047 | 26.0236 | Digikey
38 | 5 | U10,U16,U22,U28,U34 | OPA656N | OPA656NB/250CT-ND |  |  | SOT23-5 | 10.601 | 53.005 | 10.601 | 53.005 | Digikey | Limited Quantity
39 | 5 | U11,U17,U23,U29,U35 | LTC6268 | LTC6268IS6#TRMPBFCT-ND |  |  | SOT23-6 | 6.5352 | 32.676 | 3.9046 | 19.5228 | Digikey
40 | 5 | U12,U18,U24,U30,U36 | AD783JRZ | AD783JRZ-ND |  |  | SO8 | 29.37 | 146.85 | 23.1344 | 115.6719 | Digikey
38 | 1 | Bare Board | [5 empty] | 50 | 50 | 50 | 50 | EST
39 | 1 | Assembly | [5 empty] | 250 | 250 | 250 | 250 | EST
|  | Unit Total | [6 empty] | 725.4625 |  | 667.6864
|  | Total Parts Cost | [6 empty] | 475.4625 |  | 417.6864
|  | Total Assembly Cost | [6 empty] | 250 |  | 250
|  | Total Board Cost | [6 empty] | 725.4625 |  | 667.6864
|  | NRE | [5 empty] | 500 |  | 0

## Calorimeter_Controller_Board
205-1000-0x10: Calorimeter Controller
Creation: 29-Dec-2018
Last Revision Date: 31-Dec-2018
Item | Quantity | Reference | MFG Part # | Vendor Part # | Value | Tolorance | PCB Footprint | 15 Module Unit Cost | 15 Module Total Cost | 65 Module Unit Cost | 65 Module Total Cost | Vendor | Comment
1 | 2 | C1,C2 | TCJC226M025R0100 | 478-6632-1-ND | 22uF | 25V | 6032 | 3.30600 | 6.612 | 2.5789 | 5.1578 | DigiKey
2 | 60 | C3,C4,C6,C8,C10,C12,C14,C16,C18,C20,C22,C25,C27,C30,C33,C34,C35,C36,C38,C39,C40,C41,C42,C43,C44,C47,C48,C50,C51,C52,C53,C56,C57,C58,C59,C62,C63,C64,C65,C68,C69,C70,C71,C74,C75,C76,C77,C80,C81,C82,C83,C86,C87,C88,C89,C92,C93,C94,C95,C98 | CL05B104KO5NNWC | 1276-1509-1-ND | 100nF |  | C0402 | 0.00958 | 0.5748 | 0.00684 | 0.4104 | DigiKey
3 | 10 | C5,C7,C9,C11,C13,C15,C17,C19,C21,C23 | CL05B103KB5NNNC | 1276-1028-1-ND | 10nF |  | C0402 | 0.01060 | 0.106 | 0.00756 | 0.0756 | DigiKey
4 | 20 | C24,C26,C29,C31,C54,C55,C60,C61,C66,C67,C72,C73,C78,C79,C84,C85,C90,C91,C96,C97 | CL10A105KQ8NNNC | 1276-1036-1-ND | 1uF |  | C0603 | 0.0146 | 0.292 | 0.00844 | 0.1688 | DigiKey
5 | 1 | C28 | GCM155R71H223KA55D | 490-4763-1-ND | 22nF |  | C0402 | 0.088 | 0.088 | 0.088 | 0.088 | DigiKey
6 | 1 | C32 | CC0402KRX7R9BB471 | 311-1028-1-ND | 470pF |  | C0402 | 0.029 | 0.029 | 0.029 | 0.029 | DigiKey
7 | 1 | C37 | TAJD157K016RNJ | 478-2356-1-ND | 150uF |  | 7343 | 1.023 | 1.023 | 1.023 | 1.023 | DigiKey
8 | 2 | C45,C46 | GRM155C81C105KE11D | 490-12700-1-ND | 1uF |  | C0402 | 0.165 | 0.33 | 0.0935 | 0.187 | DigiKey
9 | 1 | C49 | GRT188R61C106KE13D | 490-12317-1-ND | 10uF |  | CC0603 | 0.74 | 0.74 | 0.74 | 0.74 | DigiKey
10 | 1 | DISP1 | CON20 |  |  |  | SIP20 | 3 | 3 | 3 | 3 | EST
11 | 1 | ENC1 | PES12-42S-N0024 | PES12-42S-N0024-ND |  |  | PES12-4 | 2.781 | 2.781 | 2.3176 | 2.3176 | DigiKey
12 | 1 | F1 | 4527 | 36-4527-ND |  |  | FUSE4527 | 0.55 | 0.55 | 0.44 | 0.44 | DigiKey
13 | 1 | HDR1 | CON10A |  |  |  | HDR2X5 | 3 | 3 | 3 | 3 | EST
14 | 1 | HDR2 | HEADER 3X2 |  |  |  | HDR2X3 | 3 | 3 | 3 | 3 | EST
15 | 1 | HDR3 | HEADER 16X2 |  |  |  | HDR2X16 | 3 | 3 | 3 | 3 | EST
16 | 8 | ISO1,ISO2,ISO3,ISO4,ISO5,ISO6,ISO7,ISO8 | IL261 | 390-1055-5-ND |  |  | SO16W | 8.288 | 66.304 | 8.288 | 66.304 | DigiKey
17 | 1 | J1 | Header6 |  |  |  | HDR6 | 3 | 3 | 3 | 3 | EST
18 | 1 | J2 | AMP5555165-1 | 571-5555165-1 |  |  | MOD6RA | 0.813 | 0.813 | 0.813 | 0.813 | Mouser
19 | 1 | LED1 | SSF-LXH100MHGW | 67-1226-ND |  |  | LEDLUM1 | 0.784 | 0.784 | 0.6544 | 0.6544 | DigiKey
20 | 2 | LED2,LED3 | LTA-1000Y | 160-1068-ND |  |  | DIP20 | 1.1375 | 2.275 | 0.7875 | 1.575 | DigiKey
21 | 1 | L1 | MLZ2012N1R0LT000 | 445-6756-1-ND |  |  | IND-0805 | 0.129 | 0.129 | 0.129 | 0.129 | DigiKey
22 | 1 | OSC1 | ASEMB-50.000MHZ-LC-T | 535-11758-1-ND |  |  | ASEMB | 1.998 | 1.998 | 1.952 | 1.952 | DigiKey
23 | 1 | OSC2 | ASDMB-24.000MHZ-LC-T | 535-11728-1-ND |  |  | ASDMB | 1.353 | 1.353 | 1.3214 | 1.3214 | DigiKey
24 | 6 | PB1,PB2,PB3,PB4,PB5,PB6 | PTS635SK25SM |  |  |  | PTS635SK25SM |  | 0 |  | 0 |  | Obsolete?
25 | 1 | PJ1 | PH1757242 |  |  |  | PH1757242 |  | 0 |  | 0
26 | 1 | P1 | LTL4VMEPADS | LTL4VMEPADS-ND |  |  | CNVME96A | 0.07239 | 0.07239 | 0.07239 | 0.07239
27 | 1 | Q1 | BSS138 | BSS138CT-ND |  |  | SOT23 | 0.279 | 0.279 | 0.279 | 0.279 | DigiKey
28 | 1 | REG1 | MIC29300-3.3T220 | ROE-3.305S-ND |  |  | TO-220 | 2.928 | 2.928 | 2.562 | 2.562 | DigiKey
29 | 8 | REG2,REG3,REG4,REG5,REG6,REG7,REG8,REG9 | ROE-3.305S | 380-1102-ND |  |  | VBSD1 | 4.472 | 35.776 | 3.956 | 31.648 | DigiKey
30 | 1 | RJ1 | SI-50154-F | 742C163332JPCT-ND |  |  | SI-50154 | 0.2636 | 0.2636 | 0.1656 | 0.1656 | DigiKey
31 | 4 | RP1,RP2,RP5,RP6 | 742C163332JP | 767-163-R150P-ND |  |  | CRN16/CTS742 | 2.0402 | 8.1609 | 1.4914 | 5.9654 | DigiKey
32 | 4 | RP3,RP4,RP7,RP8 | 767163151G | A130943-ND | 150R |  | SO16RP | 3.0633 | 12.2532 | 2.6804 | 10.7214 | DigiKey
33 | 8 | RS1,RS2,RS3,RS4,RS5,RS6,RS7,RS8 | 6116075-1 | MICROSMD050F-2CT-ND |  |  | 6116075-1 | 0.534 | 4.272 | 0.4546 | 3.6368 | DigiKey
34 | 1 | RT1 | MICROSMD050F-2 | RNCF0402BTE10K0CT-ND |  |  | CC1210 | 0.1195 | 0.1195 | 0.05891 | 0.05891 | DigiKey
35 | 18 | R1,R6,R20,R32,R35,R36,R37,R41,R42,R43,R44,R45,R56,R57,R58,R59,R60,R61 | RNCF0402BTE10K0 | P1.50KLCT-ND | 10K |  | C0402 | 0.056 | 1.008 | 0.056 | 1.008 | DigiKey
36 | 1 | R2 | ERJ-2RKF1501X | P4.7KDCCT-ND | 1.5K |  | C0402 | 0.321 | 0.321 | 0.1283 | 0.1283 | DigiKey
37 | 6 | R3,R4,R5,R22,R23,R24 | ERA-2AEB472X | YAG3170CT-ND | 4.7K |  | C0402 | 0.016 | 0.096 | 0.007 | 0.042 | DigiKey
38 | 4 | R7,R8,R9,R10 | RC0402FR-0748R7L | 541-4112-1-ND | 49.9R |  | C0402 | 0.026 | 0.104 | 0.0108 | 0.0432 | DigiKey
39 | 2 | R11,R16 | CRCW0402249RFKEDC | 311-33JRCT-ND | 249R |  | C0402 | 0.0057 | 0.0114 | 0.0057 | 0.0114 | DigiKey
40 | 14 | R12,R13,R14,R15,R25,R26,R27,R29,R30,R31,R34,R38,R39,R40 | RC0402JR-0733RL | 696-1663-1-ND | 33R |  | C0402 | 0.4556 | 6.3784 | 0.3567 | 4.9938 | DigiKey
41 | 3 | R17,R18,R21 | CSR25120R1F | P12.1KDCCT-ND | 0R |  | C0402 | 0.321 | 0.963 | 0.321 | 0.963 | DigiKey
42 | 1 | R19 | ERA-2AEB1212X | RG10P1.0KBCT-ND | 12.1K |  | C0402 | 0.319 | 0.319 | 0.319 | 0.319 | DigiKey
43 | 1 | R33 | RG1005P-102-B-T5 | 311-330JRCT-ND | 1K |  | C0402 | 0.013 | 0.013 | 0.0057 | 0.0057 | DigiKey
44 | 6 | R46,R47,R48,R49,R50,R51 | RC0402JR-07330RL | P3.0KDECT-ND | 330R |  | C0402 | 0.188 | 1.128 | 0.0735 | 0.441 | DigiKey
45 | 2 | R52,R53 | ERA-2AED302X | A129619CT-ND | 3K |  | C0402 | 0.021 | 0.042 | 0.0086 | 0.0172 | DigiKey
46 | 2 | R54,R55 | CRGCQ0402F220R | 563-1209-1-ND | 220R |  | C0402 | 2.1992 | 4.3984 | 2.0266 | 4.0532 | DigiKey
47 | 3 | SW1,SW2,SW3 | SH-7010TB | A97799CT-ND |  |  | SH-7000 | 1.829 | 5.487 | 1.656 | 4.968 | DigiKey
48 | 1 | USB1 | 1981584-1 | WM6357CT-ND |  |  | TE1981584-1 | 1.978 | 1.978 | 1.7914 | 1.7914 | DigiKey
49 | 1 | USD1 | 1040310811 | 538-104031-0811 |  |  | SD-104031-001 | 1.67 | 1.67 | 1.67 | 1.67 | Mouser
50 | 1 | U1 | LAN8740AI-EN | LAN8740AI-EN-ND |  |  | SQFN32 | 1.68 | 1.68 | 1.4008 | 1.4008 | DigiKey
51 | 1 | U2 | PIC32MZ2048EFH144-250I/PH | PIC32MZ2048EFH144-250I/PH-ND |  |  | TQFP144 | 13.69 | 13.69 | 12.5456 | 12.5456 | DigiKey
52 | 1 | U3 | SST26VF032-80-5I-S2AE | SST26VF032-80-5I-S2AE-ND |  |  | SOIJ8 | 2.88 | 2.88 | 2.7812 | 2.7812 | DigiKey
53 | 2 | U4,U7 | ADG707BRUZ | ADG707BRUZ-ND |  |  | TSSOP28 | 6.71 | 13.42 | 5.0196 | 10.0392 | DigiKey
54 | 1 | U5 | 74HC138D | 74HC138DCT-ND |  |  | SO16 | 0.352 | 0.352 | 0.2968 | 0.2968 | DigiKey
55 | 1 | U6 | SN74LVTH540DBR | 296-8724-1-ND |  |  | SSO20 | 1.329 | 1.329 | 1.329 | 1.329 | DigiKey
56 | 3 | U8,U10,U11 | SN74LVTH541DBR | 296-8727-1-ND |  |  | SSO20 | 1.711 | 5.133 | 1.3756 | 4.1268 | DigiKey
57 | 2 | U9,U12 | SN74LVC2G17DBVR | 296-13012-1-ND |  |  | SOT-6 | 0.467 | 0.934 | 0.349 | 0.698 | DigiKey
58 | 1 | U13 | SN74LVC1G175DBVR | 296-17617-1-ND |  |  | SOT-6 | 0.3 | 0.3 | 0.3 | 0.3 | DigiKey
59 | 8 | U14,U16,U18,U20,U22,U24,U26,U28 | LTC1688CS | LTC1688CS#PBF-ND |  |  | SO16 | 5.916 | 47.328 | 5.916 | 47.328 | DigiKey
60 | 8 | U15,U17,U19,U21,U23,U25,U27,U29 | LTC1685 | LTC1685IS8#PBF-ND |  |  | SO8 | 3.876 | 31.008 | 3.876 | 31.008 | DigiKey
61 | 8 | U14,U17,U20,U23,U26,U29,U32,U35 | IL261 | 390-1055-5-ND |  |  | SO16W | 8.288 | 66.304 | 8.288 | 66.304 | DigiKey
62 | 8 | U15,U18,U21,U24,U27,U30,U33,U36 | ‎LTC1688CS#PBF‎ | LTC1685IS8#PBF-ND |  |  | SO16 | 3.876 | 31.008 | 3.876 | 31.008 | DigiKey
63 | 8 | U16,U19,U22,U25,U28,U31,U34,U37 | LTC1685IS8#PBF | LTC1688CS#PBF-ND |  |  | SO8 | 5.916 | 47.328 | 5.916 | 47.328 | DigiKey
64 | 1 | Front panel and mounting hardware | [5 empty] | 30 | 30 | 30 | 30 | EST
65 | 1 | Bare Board | [5 empty] | 500 | 500 | 500 | 500 | EST
66 | 1 | Assembly | [5 empty] | 150 | 150 | 150 | 150 | EST
|  | Unit Total | [6 empty] | 1132.5176 |  | 1110.4442
|  | Total Parts Cost | [6 empty] | 982.5176 |  | 960.4442
|  | Total Assembly Cost | [6 empty] | 150 |  | 150
|  | Total Board Cost | [6 empty] | 1132.5176 |  | 1110.4442
|  | NRE-PCB | [5 empty] | 820 |  | 0
|  | NRE-Assembly | [5 empty] | 575 |  | 0
|  | Total NRE | [6 empty] | 1395 |  | 0

## Calorimeter_Controller_Crate
205-1000-2x00: Calorimeter Controller Crate
Creation: 29-Dec-2018
Last Revision Date: 29-Dec-2018
Item | Quantity | Reference | Part |  | Unit Cost | Total
1 | 1 | VME 6U220mm Card Rack | CCA220-6U |  | 219.77 | 219.77
2 | 42 | 220mm Card Guide (pack of 12) | CG1-220/12 |  | 22.62 | 79.17
3 | 1 | 21 slot VME P1 Backplane | VMEBP21J1 |  | 757.47 | 757.47
4 | 1 | 5V @ 20A DIN Rail Power Supply | S8VM-10005CD |  | 155.3 | 155.3
| 1 | Assembly (in house) |  |  | 0 | 0
|  |  |  | Unit Total |  | 1211.71

## Calorimeter_TestPulse_Driver
205-1000-0x20: Calorimeter Test Pulse Driver
Creation: 31-Dec-2018
Last Revision Date: 31-Dec-2018
Item | Quantity | Reference | MFG Part # | Vendor Part # | Value | Tolorance | PCB Footprint | 8 Module Unit Cost | 8 Module Total Cost | 35 Module Unit Cost | 35 Module Total Cost | Vendor | Comment
1 | 64 | C1,C2,C4,C6,C7,C8,C9,C10,C11,C17,C18,C19,C22,C23,C24,C27,C28,C29,C32,C33,C34,C37,C38,C39,C42,C43,C44,C47,C48,C49,C52,C53,C54,C57,C58,C59,C62,C63,C64,C67,C68,C69,C72,C73,C74,C77,C78,C79,C82,C83,C84,C87,C88,C89,C92,C93,C94,C97,C100,C101,C102,C103,C105,C106 | CL05B104KO5NNWC | 1276-1509-1-ND | 100NF |  |  | 0.0134 | 0.8576 | 0.00753 | 0.48192 | DigiKey
2 | 1 | C3 | CL05C100JB5NNNC | 1276-1139-1-ND | 10PF |  |  | 0.1 | 0.1 | 0.04 | 0.04 | DigiKey
3 | 1 | C5 | CL05B103KB5NNNC | 1276-1028-1-ND | 10NF |  |  | 0.1 | 0.1 | 0.024 | 0.024 | DigiKey
4 | 4 | C12,C13,C15,C16 | TAJD157K016RNJ | 478-2356-1-ND | 150UF |  |  | 1.023 | 4.092 | 1.023 | 4.092 | DigiKey
5 | 1 | C14 | CL10A105KQ8NNNC | 1276-1036-1-ND | 10UF |  |  | 0.1 | 0.1 | 0.032 | 0.032 | DigiKey
6 | 32 | C20,C21,C25,C26,C30,C31,C35,C36,C40,C41,C45,C46,C50,C51,C55,C56,C60,C61,C65,C66,C70,C71,C75,C76,C80,C81,C85,C86,C90,C91,C95,C96 | CL10A106MQ8NNNC | 1276-1119-1-ND | 1UF |  |  | 0.0538 | 1.7216 | 0.03842 | 1.2294 | DigiKey
7 | 2 | C98,C99 | CC0402JRNPO9BN470 | 311-1021-1-ND | 47PF |  |  | 0.03 | 0.06 | 0.03 | 0.06 | DigiKey
8 | 1 | C104 | CC0402KRX7R8BB472 | 311-1039-1-ND | 4.7NF |  |  | 0.1 | 0.1 | 0.029 | 0.029 | DigiKey
9 | 1 | DLY1 | DS1023-25+ | [5 empty] | 0 |  | 0 | DigiKey
10 | 1 | DLY2 | DS1023-100+ | [5 empty] | 0 |  | 0 | DigiKey
11 | 1 | D1 | BAS40-04-TP‎ | BAS40-04TPMSCT-ND |  |  |  | 0.27 | 0.27 | 0.243 | 0.243 | DigiKey
12 | 1 | D2 | CDBA240LL-G‎ | 641-1532-1-ND |  |  |  | 0.54 | 0.54 | 0.454 | 0.454 | DigiKey
13 | 1 | F1 | 4527 | 36-4527-ND |  |  |  | 0.73 | 0.73 | 0.55 | 0.55 | DigiKey
14 | 2 | HDR1,HDR2 | HEADER 2 |  |  |  |  | 1.5 | 3 | 1.5 | 3 | EST
15 | 1 | HDR3 | HEADER 10 |  |  |  |  | 1.5 | 1.5 | 1.5 | 1.5 | EST
16 | 16 | ISO1,ISO2,ISO3,ISO4,ISO5,ISO6,ISO7,ISO8,ISO9,ISO10,ISO11,ISO12,ISO13,ISO14,ISO15,ISO16 | ISO721MDR | 296-41275-1-ND |  |  |  | 3.226 | 51.616 | 2.6432 | 42.2912 | DigiKey
17 | 3 | J1,J2,J3 | LEMO-DUAL-EPY |  |  |  |  | 5 | 15 | 5 | 15 | EST
18 | 1 | J4 | ‎PJ-002AH-SMT-TR‎ | CP-002AHPJCT-ND |  |  |  | 1.44 | 1.44 | 1.268 | 1.268 | DigiKey
19 | 1 | J5 | AMP520425-3 | [5 empty] | 0 |  | 0
20 | 1 | LED1 | SSF-LXH100MGD | 67-1228-ND |  |  |  | 0.53 | 0.53 | 0.42 | 0.42 | DigiKey
21 | 1 | LED2 | SSF-LXH100MYD | 67-1229-ND |  |  |  | 0.76 | 0.76 | 0.592 | 0.592 | DigiKey
22 | 1 | LED3 | SSF-LXH100USBD-01 | SSF-LXH100USBD-01-ND |  |  |  | 1.8131 | 1.8131 | 1.8131 | 1.8131 | DigiKey
23 | 1 | LED4 | SSF-LXH100GD | 67-1228-ND |  |  |  | 0.53 | 0.53 | 0.42 | 0.42 | DigiKey
24 | 1 | LED5 | SSF-LXH100MYD | 67-1229-ND |  |  |  | 0.76 | 0.76 | 0.592 | 0.592 | DigiKey
25 | 16 | LVD1,LVD2,LVD3,LVD4,LVD5,LVD6,LVD7,LVD8,LVD9,LVD10,LVD11,LVD12,LVD13,LVD14,LVD15,LVD16 | SN65LVDS391PW | 296-6930-5-ND |  |  |  | 3.142 | 50.272 | 2.574 | 41.184 | DigiKey
26 | 16 | PDS1,PDS2,PDS3,PDS4,PDS5,PDS6,PDS7,PDS8,PDS9,PDS10,PDS11,PDS12,PDS13,PDS14,PDS15,PDS16 | PDS1-S5-S3-M | PDS1-S5-S3-M-ND |  |  |  | 4.2406 | 67.849 | 4.2406 | 67.849 | DigiKey
27 | 1 | REG1 | MIC29150-5.0WT | 576-1106-ND |  |  |  | 3.96 | 3.96 | 3.96 | 3.96 | DigiKey
28 | 16 | RJ1,RJ2,RJ3,RJ4,RJ5,RJ6,RJ7,RJ8,RJ9,RJ10,RJ11,RJ12,RJ13,RJ14,RJ15,RJ16 | 1-406541-5 | A102038-ND |  |  |  | 2.3668 | 37.8688 | 2.2541 | 36.0656 | DigiKey
29 | 4 | R1,R4,R7,R8 | RC0402JR-0733RL | 311-33JRCT-ND |  |  |  | 0.013 | 0.052 | 0.013 | 0.052 | DigiKey
30 | 3 | R2,R44,R46 | RG1005P-102-B-T5 | RG10P1.0KBCT-ND |  |  |  | 0.319 | 0.957 | 0.319 | 0.957 | DigiKey
31 | 6 | R3,R10,R12,R13,R15,R17 | ESR03EZPJ510 | RHM51DCT-ND |  |  |  | 0.087 | 0.522 | 0.0333 | 0.1998 | DigiKey
32 | 2 | R5,R6 | ERJ-2RKF1001X | P1.00KLCT-ND |  |  |  | 0.054 | 0.108 | 0.054 | 0.108 | DigiKey
33 | 1 | R9 | RC0402JR-074K7L | 311-4.7KJRCT-ND |  |  |  | 0.1 | 0.1 | 0.013 | 0.013 | DigiKey
34 | 1 | R11 | RR0816P-103-D | RR08P10.0KDCT-ND |  |  |  | 0.11 | 0.11 | 0.1 | 0.1 | DigiKey
35 | 3 | R14,R42,R45 | RNCF0402BTE10K0 | RNCF0402BTE10K0CT-ND |  |  |  | 0.299 | 0.897 | 0.299 | 0.897 | DigiKey
36 | 3 | R16,R18,R19 | RC0402JR-07330RL | 311-330JRCT-ND |  |  |  | 0.013 | 0.039 | 0.013 | 0.039 | DigiKey
37 | 16 | R20,R21,R22,R23,R24,R25,R26,R27,R28,R29,R30,R31,R32,R33,R34,R35 | RR0816P-101-D | RR08P100DCT-ND |  |  |  | 0.1 | 1.6 | 0.0394 | 0.6304 | DigiKey
38 | 2 | R36,R37 | RC0402FR-07470RL | 311-470LRCT-ND |  |  |  | 0.016 | 0.032 | 0.016 | 0.032 | DigiKey
39 | 2 | R38,R39 | ERJ-2RKF27R0X | P27.0LCT-ND |  |  |  | 0.046 | 0.092 | 0.046 | 0.092 | DigiKey
40 | 1 | R40 | ERJ-2RKF4021X | P4.02KLCT-ND |  |  |  | 0.1 | 0.1 | 0.046 | 0.046 | DigiKey
41 | 1 | R41 | RC0402FR-071ML | 311-1.00MLRCT-ND |  |  |  | 0.1 | 0.1 | 0.016 | 0.016 | DigiKey
42 | 1 | R43 | RT0402BRD07100RL | YAG2301CT-ND |  |  |  | 0.42 | 0.42 | 0.304 | 0.304 | DigiKey
43 | 1 | R47 | RC0402FR-07499RL | 311-499LRCT-ND |  |  |  | 0.1 | 0.1 | 0.016 | 0.016 | DigiKey
44 | 1 | R48 | RC0402FR-07392RL | YAG3145CT-ND |  |  |  | 0.1 | 0.1 | 0.016 | 0.016 | DigiKey
45 | 1 | S1 | PTS365SL43S |  |  |  |  | 2.5 | 2.5 | 2.5 | 2.5 | Est
46 | 1 | USB1 | 61729-0010BLF | 609-1039-ND |  |  |  | 1.04 | 1.04 | 0.916 | 0.916 | DigiKey
47 | 2 | U1,U6 | 74LVC125AS14-13‎ | 74LVC125AS14-13DICT-ND |  |  |  | 0.29 | 0.58 | 0.29 | 0.58 | DigiKey
48 | 1 | U2 | ‎SN74LVC1G123DCTR‎ | 296-18758-1-ND |  |  |  | 0.7 | 0.7 | 0.619 | 0.619 | DigiKey
49 | 1 | U3 | 296-24202-1-ND‎ | 296-24202-1-ND |  |  |  | 0.42 | 0.42 | 0.339 | 0.339 | DigiKey
50 | 1 | U4 | MC100ELT25DR2G‎ | MC100ELT25DR2G-ND |  |  |  | 1.33 | 1.33 | 1.33 | 1.33 | DigiKey
51 | 1 | U5 | SN74LVC1G3157DCKR | 595-SN74LVC1G3157DCK |  |  |  | 0.276 | 0.276 | 0.276 | 0.276 | Mouser
52 | 1 | U7 | LTC660CS8#TRPBF‎ |  |  |  |  | 6.46 | 6.46 | 6.46 | 6.46 | DigiKey
53 | 1 | U8 | FT230XS-R | 768-1135-1-ND |  |  |  | 2.04 | 2.04 | 2.04 | 2.04 | DigiKey
54 | 1 | U9 | PIC18F46K80-I/PT | PIC18F46K80-I/PT-ND |  |  |  | 3.47 | 3.47 | 3.47 | 3.47 | DigiKey
55 | 1 | U10 | LTC6993CS6-1#TRMPBF‎ | LTC6993CS6-1#TRMPBFCT-ND |  |  |  | 3.42 | 3.42 | 3.42 | 3.42 | DigiKey
56 | 1 | Enclosure | RM1U1908SBK | HM995-ND |  |  |  | 113.498 | 113.498 | 109.4444 | 109.4444 | DigiKey
57 | 1 | Bare Board | [5 empty] | 75 | 75 | 75 | 75 | EST
58 | 1 | Assembly | [5 empty] | 150 | 150 | 150 | 150 | EST
|  | Unit Total | [6 empty] | 610.7754 |  | 582.6209
|  | Total Parts Cost | [6 empty] | 460.7754 |  | 432.6209
|  | Total Assembly Cost | [6 empty] | 150 |  | 150
|  | Total Board Cost | [6 empty] | 610.7754 |  | 582.6209
|  | NRE-PCB | [5 empty] | 820
|  | NRE-Assembly | [5 empty] | 575
|  | Total NRE | [6 empty] | 1395 |  | 0
64

## Cables
Calorimeter Cables
Creation: 31-Dec-2018
Last Revision Date: 21-Mar-2019
| Description | Part Number | Sector Quantity | Sector 0 Quanatity | Sector 0 Unit Cost | Sector 0 Cost | Sector 1-12 Quanatity | Sector 1-12 Unit Cost | Sector 1-12 Cost | Sector 13-64 Quanatity | Sector 13-64 Unit Cost | Sector 13-64 Cost | Sector 13-64 High Eta | Sector 13-64 Unit Cost | Total Cost- High Eta
External EMCal Cables
| EMCal Power Umbilical Assy | P/N 205-1000-6200 | 1 | 1 | 66.4031 | 66.4031 | 12 | 66.4031 | 796.8374 | 52 | 66.4031 | 3452.9622 | 0 | 66.4031 | 0
| EMCal Comm Trunk Cable Assy | P/N 205-1000-6230 | 6 | 6 | 19.28 | 115.68 | 72 | 19.28 | 1388.16 | 312 | 19.28 | 6015.36 | 0 | 19.28 | 0
| EMCal Test Pulse Trunk Cable Assy | P/N 205-1000-6240 | 2 | 2 | 19.28 | 38.56 | 24 | 19.28 | 462.72 | 104 | 19.28 | 2005.12 | 0 | 19.28 | 0
| Signal Trunk | P/N 205-1000-6220 | 24 | 24 | 160 | 3840 | 288 | 160 | 46080 | 936 | 160 | 149760 | 312 | 160 | 49920
| Total External |  |  |  |  | 4060.6431 |  |  | 48727.7174 |  |  | 161233.4422 |  |  | 49920
Internal EMCal Cables
| Endcap Power Harness Assy | P/N 205-1000-2205 | 6 | 6 | 14.2852 | 85.7112 | 72 | 14.053 | 1011.816 | 260 | 14.053 | 3653.78 | 52 | 14.053 | 730.756
| FlatFlex SiPM Cable 150mm | P/N 205-1000-2135A-150 | 48 | 48 | 21.32 | 1023.36 | 576 | 7.21 | 4152.96 | 1872 | 5.48 | 10258.56 | 624 | 5.48 | 3419.52
| FlatFlex SiPM Cable 200mm | P/N 205-1000-2135A-200 | 48 | 48 | 21.32 | 1023.36 | 576 | 7.21 | 4152.96 | 1872 | 5.48 | 10258.56 | 624 | 5.48 | 3419.52
| Signal Cable A Assy | P/N 205-1000-2240A | 48 | 48 | 63.85 | 3064.8 | 576 | 49.7 | 28627.2 | 1872 | 44.4 | 83116.8 | 624 | 44.4 | 27705.6
| Signal Cable B Assy | P/N 205-1000-2241A | 48 | 48 | 63.85 | 3064.8 | 576 | 49.7 | 28627.2 | 1872 | 44.4 | 83116.8 | 624 | 44.4 | 27705.6
| Endcap Signal Transition | P/N 205-1000-2160B | 6 | 6 | 102.4639 | 614.7835 | 72 | 92.4639 | 6657.4022 | 312 | 75.6363 | 23598.5194 | 0 | 75.6363 | 0
| Endcap Comm Transition | P/N 205-1000-2170B | 2 | 2 | 97.9839 | 195.9678 | 24 | 87.9839 | 2111.6141 | 104 | 78.1963 | 8132.4131 | 0 | 78.1963 | 0
| Comm Cable Assy | P/N 205-1000-2270A | 6 | 6 | 7.2882 | 43.7292 | 72 | 6.2881 | 452.7418 | 260 | 6.1267 | 1592.9524 | 52 | 6.1267 | 318.5905
| Test Pulse Cable Assy | P/N 205-1000-2271A | 6 | 6 | 10.096 | 60.576 | 72 | 9.7468 | 701.7696 | 260 | 7.6752 | 1995.552 | 52 | 7.6752 | 399.1104
| Total Internal |  |  |  |  | 9177.0878 |  |  | 76495.6637 |  |  | 225723.9369 |  |  | 63698.6969
| Total EMCal |  |  |  |  | 13237.7309 |  |  | 125223.3811 |  |  | 386957.3791 |  |  | 113618.6969
| Description | Part Number | Module Quantity | Module 1-6 Quanatity | Module 1-6 Unit Cost | Module 1-6 Cost | Module 7-32 Quanatity | Module 7-32 Unit Cost | Module 7-32 Cost
External HCal Cables
| HCal Power Umbilical Assembly | P/N 205-1000-6210 | 2 | 12 | 20 | 240 | 52 | 20 | 1040
| HCal Comm Trunk Cable Assy | P/N 205-1000-6230 | 2 | 12 | 19.28 | 231.36 | 52 | 19.28 | 1002.56
| HCal Test Pulse Trunk Cable Assy | P/N 205-1000-6240 | 1 | 6 | 19.28 | 115.68 | 26 | 19.28 | 501.28
| Signal Trunk | P/N 205-1000-6220 | 3 | 18 | 160 | 2880 | 78 | 160 | 12480
| Total External |  |  |  |  | 3467.04 |  |  | 15023.84
Internal HCal Cables
| HCal Signal Cable | P/N 73116-0016 | 24 | 144 | 90.596 | 13045.824 | 624 | 77.5394 | 48384.5856
| HCal Preamp Cable Assembly | P/N 205-1000-3250 | 48 | 288 | 20.9057 | 6020.8358 | 1248 | 20.472 | 25549.0061
| LED Driver Cable Assembly | P/N 205-1000-3060 | 2 | 12 | 5.671 | 68.052 | 52 | 4.962 | 258.024
| Total Internal |  |  |  |  | 19066.6598 |  |  | 73933.5917
| Total Hcal |  |  |  |  | 22533.6998 |  |  | 88957.4317

## Cable_Details
Calorimeter Cables |  |  | Calorimeter Cables
Creation: 31-Dec-2018 |  |  | Creation: 1-Mar-2019
Last Revision Date: 18-Mar-2019 |  |  | Last Revision Date: 18-Mar-2019
|  | Part Number | Description | Componets | Part Number | Quantity/Assem | Cost-Sector 0 | Cable Cost | Cost Sector 1-12 | Cable Cost | Cost Sector 13-64 | Cable Cost | Vendor
|  | P/N 205-1000-6200 | EMCal Power Umbilical Assy
|  |  | P/N 205-1000-6200 | Pins | A1342-ND | 37 | 0.39576 | 14.6431 | 0.39576 | 14.6431 | 0.39576 | 14.6431 | Digikey
|  |  |  | Connector | A1359-D | 1 | 6.76 | 6.76 | 6.76 | 6.76 | 6.76 | 6.76 | Digikey
|  |  |  | Cable |  | 1 | 45 | 45 | 45 | 45 | 45 | 45 | EST
|  |  |  | Total |  |  |  | 66.4031 |  | 66.4031 |  | 66.4031
|  | P/N 205-1000-6230 | EMCal Comm Trunk Cable Assy
|  |  | P/N 205-1000-6230 | RJ45 Cable, 10m | AE10210-ND | 1 | 19.28 | 19.28 | 19.28 | 19.28 | 19.28 | 19.28 | Digikey
|  | P/N 205-1000-6240 | EMCal Test Pulse Trunk Cable Assy
|  |  | P/N 205-1000-6240 | RJ45 Cable, 10m | AE10210-ND | 1 | 19.28 | 19.28 | 19.28 | 19.28 | 19.28 | 19.28 | Digikey
|  | P/N 205-1000-6220 | Signal Trunk
|  |  | P/N 205-1000-6220 | 10 M Meritec cable |  | 1 | 160 | 160 | 160 | 160 | 160 | 160 | Est
EMCal- Internal
|  | P/N 205-1000-2205 | Endcap Power Harness Assy
|  |  | P/N 205-1000-2205 | Pins | Amp: 175196-2 | 12 | 0.1746 | 2.0952 | 0.1746 | 2.0952 | 0.1746 | 2.0952 | Digikey
|  |  |  | Connector | Amp: 1-178288-6 | 2 | 0.845 | 1.69 | 0.7289 | 1.4578 | 0.7289 | 1.4578 | Digikey
|  |  |  | Cable | 5366C SL001 | 1 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | Digikey
|  |  |  | Total |  |  |  | 14.2852 |  | 14.053 |  | 14.053
|  | P/N 205-1000-2135A-150 | FlatFlex SiPM Cable 150mm
|  |  | P/N 205-1000-2135A-150 | Cable | 205-1000-2280 | 1 | 21.32 | 21.32 | 7.21 | 7.21 | 5.48 | 5.48 | PalPilot
|  | P/N 205-1000-2135A-200 | FlatFlex SiPM Cable 200mm
|  |  | P/N 205-1000-2135A-200 | Cable | 205-1000-2280 | 1 | 21.32 | 21.32 | 7.21 | 7.21 | 5.48 | 5.48 | PalPilot
|  | P/N 205-1000-2240A | Signal Cable A Assy
|  |  | P/N 205-1000-2240A | Paddle Board A | 205-1000-2140A | 1 | 3.08 | 3.08 | 3.08 | 3.08 | 0.63 | 0.63
|  |  |  | EndCap Paddle Board | 205-1000-2142A | 1 | 3 | 3 | 3 | 3 | 0.63 | 0.63
|  |  |  | Connector | M22-6540542R | 1 | 0.82 | 0.82 | 0.82 | 0.82 | 0.58 | 0.58 | DigiKey
|  |  |  | Connector | DF9-19P-1V(32) | 1 | 1.09 | 1.09 | 1.09 | 1.09 | 0.85 | 0.85 | DigiKey
|  |  |  | Cable |  | 1 | 17.28 | 17.28 | 13.04 | 13.04 | 13.04 | 13.04 | DigiKey
|  |  |  | Assembly |  | 1 | 38.58 | 38.58 | 28.67 | 28.67 | 28.67 | 28.67 | EastEnd
|  |  |  | Total |  |  |  | 63.85 |  | 49.7 |  | 44.4
|  | P/N 205-1000-2241A | Signal Cable B Assy
|  |  | P/N 205-1000-2241A | Paddle Board B | 205-1000-2140B | 1 | 3.08 | 3.08 | 3.08 | 3.08 | 0.63 | 0.63
|  |  |  | EndCap Paddle Board | 205-1000-2142B | 1 | 3 | 3 | 3 | 3 | 0.63 | 0.63
|  |  |  | Connector | M22-6540542R | 1 | 0.82 | 0.82 | 0.82 | 0.82 | 0.58 | 0.58
|  |  |  | Connector | DF9-19P-1V(32) | 1 | 1.09 | 1.09 | 1.09 | 1.09 | 0.85 | 0.85
|  |  |  | Cable |  | 1 | 17.28 | 17.28 | 13.04 | 13.04 | 13.04 | 13.04 | DigiKey
|  |  |  | Assembly |  | 1 | 38.58 | 38.58 | 28.67 | 28.67 | 28.67 | 28.67 | EastEnd
|  |  |  | Total |  |  |  | 63.85 |  | 49.7 |  | 44.4
|  | P/N 205-1000-2160B | Endcap Signal Transition
|  |  | P/N 205-1000-2160B | Connector | 5106012-1 | 4 | 12.636 | 50.5439 | 12.636 | 50.5439 | 12.3991 | 49.5963 | DigiKey
|  |  |  | Connector | DF9-19S-1V(32) | 16 | 1.37 | 21.92 | 1.37 | 21.92 | 0.69 | 11.04 | DigiKey
|  |  |  | PC Board |  | 1 | 10 | 10 | 5 | 5 | 5 | 5
|  |  |  | Assembly |  | 1 | 20 | 20 | 15 | 15 | 10 | 10
|  |  |  | Total |  |  |  | 102.4639 |  | 92.4639 |  | 75.6363
|  | P/N 205-1000-2170B | Endcap Comm Transition
|  |  | P/N 205-1000-2170B | Connector | 5106012-1 | 4 | 12.636 | 50.5439 | 12.636 | 50.5439 | 12.3991 | 49.5963 | DigiKey
|  |  |  | Connector |  | 16 | 1.09 | 17.44 | 1.09 | 17.44 | 0.85 | 13.6 | DigiKey
|  |  |  | PC Board |  | 1 | 10 | 10 | 5 | 5 | 5 | 5
|  |  |  | Assembly |  | 1 | 20 | 20 | 15 | 15 | 10 | 10
|  |  |  | Total |  |  |  | 97.9839 |  | 87.9839 |  | 78.1963
|  | P/N 205-1000-2270A | Comm Cable Assy
|  |  | P/N 205-1000-2270A | Pins | Molex: 16020103 | 18 | 0.1149 | 2.0682 | 0.07956 | 1.4321 | 0.07293 | 1.3127 | DigiKey
|  |  |  | Connector | Molex: 50579409 | 2 | 0.61 | 1.22 | 0.428 | 0.856 | 0.407 | 0.814 | DigiKey
|  |  |  | Cable | 6204C SL001 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | DigiKey
|  |  |  | Total |  |  |  | 7.2882 |  | 6.2881 |  | 6.1267
|  | P/N 205-1000-2271A | Test Pulse Cable Assy
|  |  | P/N 205-1000-2271A | Pins | Molex: 16020103 | 6 | 0.11 | 0.66 | 0.08 | 0.48 | 0.07 | 0.42 | DigiKey
|  |  |  | Connector | Molex 50-57-9403 | 2 | 0.218 | 0.436 | 0.1334 | 0.2668 | 0.1276 | 0.2552 | DigiKey
|  |  |  | Cable | Alpha: 3231 SL005 | 1 | 9 | 9 | 9 | 9 | 7 | 7 | DigiKey
|  |  |  | Total |  |  |  | 10.096 |  | 9.7468 |  | 7.6752
HCal
[7 empty] | Modules 1-6 |  | Modules7-32
HCal Power Umbilical Assembly
|  | P/N 205-1000-6210 | P/N 205-1000-6210
HCal Comm Trunk Cable Assy
|  | P/N 205-1000-6230 | P/N 205-1000-6230 | RJ45 Cable, 10m | AE10210-ND | 1 | 19.28 | 19.28 | 19.28 | 19.28 |  |  | Digikey
HCal Test Pulse Trunk Cable Assy
|  | P/N 205-1000-6240 | P/N 205-1000-6240 | RJ45 Cable, 10m | AE10210-ND | 1 | 19.28 | 19.28 | 19.28 | 19.28 |  |  | Digikey
Signal Trunk
|  | P/N 205-1000-6220 | P/N 205-1000-6220 | Cable | 2mm HM 10 M | 3 | 180 | 540 | 160 | 480 |  |  | KC Electronics
HCal Signal Cable
|  |  | P/N 73116-0016 | Cable | 2 mm HM, 16ft | 1 | 90 | 90 | 77 | 77 |  |  | KC Electronics
|  |  |  | Connector | DF3-3S-2C | 2 | 0.055 | 0.11 | 0.0462 | 0.0924 |  |  | Digikey
|  | P/N 73116-0016 |  | Pins | DF3-2428SCC | 6 | 0.081 | 0.486 | 0.0745 | 0.447 |  |  | Digikey
|  |  |  | Total |  |  |  | 90.596 |  | 77.5394
HCal Preamp Cable Assembly
|  | P/N 205-1000-3250 | P/N 205-1000-3250 | Connector | AMP 87977-4 | 2 | 1.0301 | 2.0602 | 0.81326 | 1.6265 |  |  | Digikey
|  |  |  | Pins | AMP 87756-4 | 24 | 0.11856 | 2.8454 | 0.11856 | 2.8454 |  |  | Digikey
|  |  |  | Cable | Alpha M13176 SL005 | 1 | 16 | 16 | 16 | 16 |  |  | Digikey
|  |  |  | Total |  |  |  | 20.9057 |  | 20.472
LED Driver Cable Assembly
|  | P/N 205-1000-3060 | P/N 205-1000-3060 | Assembled Cable, 6" | A3DDH-3406G | 1 | 5.671 | 5.671 | 4.962 | 4.962 |  |  | Digikey

## PowerSystems
Power Systems EMCal & Hcal
Creation Date: 04-Jan-2019
Last Revision Date: 11-Feb-2019
Item | Quantity | MFG Part # | Vendor Part # | Value | Tol | PCB Footprint | Unit Cost | Total | Vendor
EMCal PreProduction
| 1 | VICOR Chasis |  |  |  |  | 4500 | 4500 | Vicor
| 6 | VICOR Q-Pacs |  |  |  |  | 750 | 4500 | Vicor
| 1 | Misc Parts |  |  |  |  | 5000 | 5000
|  | LV Total | [5 empty] | 14000
| 9 | Bias Supplies | MPV8120I_HR |  |  |  | 3297 | 29673 | Weiner/Iseg
| 1 | Bias Crate | MPOD EC LV |  |  |  | 4933 | 4933 | Weiner/Iseg
|  | Bias Total | [5 empty] | 34606
EMCal Production
| 3 | VICOR Chasis |  |  |  |  | 4500 | 13500 | Vicor
| 18 | VICOR Q-Pacs |  |  |  |  | 750 | 13500 | Vicor
| 1 | Misc Parts |  |  |  |  | 5000 | 5000
|  | LV Total | [5 empty] | 32000
| 33 | Bias Supplies | MPV8120I_HR |  |  |  | 3115 | 102795 | Weiner/Iseg
| 4 | Bias Crate | MPOD EC LV |  |  |  | 4785 | 19140 | Weiner/Iseg
|  | Bias Total | [5 empty] | 121935
Hcal Production
| 1 | VICOR Chassis |  |  |  |  | 4500 | 4500 | Vicor
| 6 | VICOR Q-Pacs |  |  |  |  | 500 | 3000 | Vicor
| 1 | Misc Parts |  |  |  |  | 5000 | 5000
|  | LV Total | [5 empty] | 12500
| 10 | LV Supplies | MPV8008I |  |  |  | 3297 | 32970 | Weiner/Iseg
| 8 | Bias Supplies | MPV8120I_HR |  |  |  | 2445 | 19560 | Weiner/Iseg
| 2 | Bias Crates | MPOD EC LV |  |  |  | 4933 | 9866 | Weiner/Iseg
|  | Bias Total | [5 empty] | 62396

## ModuleCounts
Towers |  |  | Totals | Notes:
| V2.1 Prototype EMCal Eta | 8
| V2.1 Prototype EMCal Phi | 8
| V2.1Prototype Total EMCal Towers |  | 64
| Preproduction Prototype EMCal Eta | 48
| Preprodcution Prototype EMCal Phi | 8
| Preproduction EMCal 1/2-Sectors | 1
| V2.1Prototype Total EMCal Towers |  | 384
| R&D EMCal 1/2-Sector Eta | 48
| R&D EMCal 1/2-Sector Phi | 8
| R&D EMCal 1/2-Sectors | 12
| R&D Total EMCal Towers |  | 4608
| Descoped EMCal 1/2-Sector Eta | 36
| Descoped EMCal 1/2-Sector Phi | 8
| Descoped EMCal 1/2-Sectors | 52
| Descoped Total EMCal Towers |  | 14976
| HCal Eta: V2.1 Prototype | 4
| HCal Phi: V2.1 Prototype | 4
| Total Hcal Towers: V2.1 Prototype |  | 16
| HCal Eta: R&D Production | 24
| HCal Phi: R&D Production | 12
| Total Hcal Towers: R&D Production |  | 288
| HCal Eta: Production | 24
| HCal Phi: Production | 52
| Total Hcal Towers: Production |  | 1248
EMCal Electronics
| EMCal SiPM Daughter Boards: V2.1 Protoype | 16 |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: V2.1 Prototyp | 4 |  | 16 towers/Preamp Board
| EMCal Interface Boards | 4 |  | 1 interface/4 Preamp Boards- Min Lot Size of 4
| Calorimeter Controller Boards- EMCal | 4 |  | 1 Controller/ 1/2-Sector- Min Lot Size of 4
| EMCal SiPM Daughter Boards: Sector 0 | 96 |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sector 0 | 24 |  | 16 towers/Preamp Board
| EMCal Interface Board: Sector 0 | 6 |  | 1 interface/4 Preamp Boards
| Calorimeter Controller Boards: Sector 0 | 1 |  | 1 Controller/ 1/2-Sector- Expect to use V2.1 Prototyp
| EMCal SiPM Daughter Boards: Production Sectors 1-12 | 1152 |  | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Production Sectors 1-12 | 288 |  | 16 towers/Preamp Board
| EMCal Interface Board: Production Sectors 1-12 | 72 |  | 1 interface/4 Preamp Boards
| Calorimeter Controller Boards: Production Sectors 1-12 | 12 |  | 1 Controller/ 1/2-Sector
| Calorimeter Test Pulse Driver Modules | 2
| EMCal Bias Power Systems: Sectors 1-12 | 1
| EMCal Low Voltage System: Sectors 1-12 | 1
| EMCal SiPM Daughter Boards: Sectors 13-64 | 3744 | 4992 | 4 Towers/SiPM Daughter Board
| EMCal Preamp Boards: Sectors 13-64 | 936 | 1248 | 16 towers/Preamp Board
| EMCal Interface Board: Sectors 13-64 | 260 | 338 | 1 interface/4 Preamp Boards
| Calorimeter Controller Boards- Sectors 13-64/Modules 7-32 | 52 | 65 | 1 Controller/ 1/2-Sector
| Calorimeter Test Pulse Driver Modules | 6
| EMCal Bias Power Systems: Sectors 13-64 | 3 | 4
| EMCal Low Voltage System: Sectors 13-64 | 3 | 1156
| HCal SiPM Boards: V2.1 Prototype | 64 |  | Inner HCal only, reuse outer HCal prototype
| HCal Preamps: V2.1 Prototype | 32 |  | 1 per tower, Inner and Outer HCal
| HCal Interface: V2.1 Prototype | 2 |  | One inner, one outer HCal
| HCal LED Driver: V2.1 Prototype | 2 |  | One inner, one outer HCal
| HCal Backplane: V2.1 Prototype | 1 |  | Inner HCal only
| HCal Contoller: V2.1 Prototype | 0 |  | Use EMCal controller
| HCal Crates: V2.1 Prototype | 0 |  | Reuse from prevous prototypes
| HCal SiPM Boards: Production Modules 1-6 | 1440
| HCal Preamps: Production Modules 1-6 | 288
| HCal Interface: Production Modules 1-6 | 12
| HCal LED Driver: Production Modules 1-6 | 12
| HCal Backplane: Production Modules 1-6 | 12
| HCal Contoller: Production Modules 1-6 | 2
| HCal Crates: Production Modules 1-6 | 1
| Calorimeter Test Pulse Driver Modules: Production Modules 1-6 | 1
| Hcal Power Systems | 1
| HCal SiPM Boards: Production Module 7-32 | 6240
| HCal Preamps: Production Module 7-32 | 1248
| HCal Interface: Production Module 7-32 | 52
| HCal LED Driver: Production Module 7-32 | 52
| HCal Backplane: Production Module 7-32 | 52
| HCal Contoller: Production Module 7-32 | 6
| HCal Crates: Production Module 7-32 | 1
| Calorimeter Test Pulse Driver Modules: Production Modules 1-6 | 1
Hcal Power Systems
Descoped Detectors Counts:
| EMCal SiPMs | 19968
| EMCal SiPM Daughter Boards | 1248
| EMCal Interface Boards | 64
| HCal SiPM Boards: Production Inner HCal | 6144
| HCal Preamps: Production Inner HCal | 1536
| HCal Interface: Production Inner HCal | 52
| HCal LED Driver: Production Inner HCal | 52
| HCal Backplane: Production Inner HCal | 52
| HCal Contoller: Production Inner HCal | 8
| HCal Crates: Production Inner HCal | 8
| Calorimeter Test Pulse Driver Modules: Production Modules 1-6 | 4
| Hcal Power Systems | 1