## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number
Minimum Bias Trigger Detector |  | 1.07
| Work Package Name |  | WBS Number | Basis of Estimate Link
| Testing of BBC PMTs |  | 1.07 | MBD Details

## MBD Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2019-03-31
[7 empty] | Prepared By: | Mickey Chiu
[7 empty] | DocNo. (refer Rev. Log) | 151 v1
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
Testing of BBC PMTs |  |  |  | 1.07
WBS Dictionary Definition:
1) Do testing of PHENIX BBC PMTs with laser and in magnetic field to understand their parameters for operation in sPHENIX. 2) A disc/shaper prototype board will be developed to stretch the PMT pulses to be optimized for the sampling frequency of the sPHENIX 60 MHz ADC digitizers. The board will create a fast discriminator circuit capable of satisfying the sPHENIX Min Bias trigger timing requirements, which is 50 ps in offline and 120 ps at the L1 trigger level. 3) Purchase the Front-End Electronics, and test them with full MB detector in the lab. 4) Covers installation and commissioning of the MB trigger detector after installation into PHENIX, using the calibraton system (LED or laser).
Estimate Type (check all that apply):
| x | Work Complete
| x | Existing Purchase Order
| x | Catalog Listing or Industrial Construction Database
| x | Documented Vendor Quotation based on Drawings/Sketches/Specifications
| x | Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| x | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| x | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Standard rates for travel were assumed ($1500/person). The cost for the laser accessories were based on previous purchases of similar items. Estimates were based on experience at Nevis Laboratories developing similar boards. Nevis has made a great many boards of similar complexity over the past few decades. For the digitizers, which are just the same as the ones used for the calorimeters in sPHENIX, all costs are assumed to be the same as WBS 1.05.03. For the Disc/Shaper Board, the cost basis is based on experience from the physicists/engineers at Nevis Labs, who have built many similar boards. Standard labor rates are applied.
Details of the Base Estimate (explanation of the Work)
A laser attenuator to get down to single photon levels will be bought, to check the PMT single photoelectron time response. Travel costs to an off-site magnetic field facility are required in order to test the PMT in fields up to 1.5 T, which is the maximum expected in sPHENIX. | [8 empty] | THIS WORK IS COMPLETE
A contract will be offered to develop a discriminator/shaper board to interface the BBC PMTs with the sPHENIX digitizers. The board should provide shaping that measures the integrated charge produced by the PMT pulse, plus some mechanism to determine the time of the pulse from the PMT with a resolution of 50 ps using the offline data, and 120 ps at the Level-1 trigger level.
These are the front end electronics and digitizers for the MBD readout. The readout will use the same digitizers as those for the sPHENIX calorimeters. The disc/shaper board is split and shape the PMT signal into timing (discrimator) and charge (shaper) shaped signals to the digitizer. The trigger boards are covered under DAQ-Trigger, WBS 1.6, and will send the trigger primitives up to the LL1 board.
No fixed costs are expected. Estimate is that testing can make use of experience gained on the similar electronics from WBS 1.05.03 for testing the digitizers and related boards in this WBS. Testing for the Discriminator/Shaper boards will be established during prototyping phase. Total testing is for 30 boards, at 2.5 hours each of Student and Scientist labor. Round up to 80 hours total each, or 160 total hours
Cost Summary
(follow link for detailed summary)
`
[5 empty] | Grand Total | Labor Hours
[5 empty] | 111957.42 | 616
Contingency
M&S Estimate Uncertainty Rules Applied:
Parts procurement (based on others' experiences): 40%
Labor Estimate Uncertainty Rules Applied:
L4 Analogous design 40%

## MBD Details
sPHENIX WBS 1.07: Minimum Bias Detector
2019-03-31
MATERIALS
Activity ID | DESCRIPTION | MANUFACTURER | PART NO. | QUANT. | VENDOR | UNIT COST | COST | Basis | STATUS
| Laser Accessories | PiLas |  | 1 | PiLas | 2000 | 2000 |  | Complete
| Travel to Magnet Facility |  |  | 2 |  | 1500 | 3000 |  | Complete
S272000 - S272600 | Procure Prototype Shaper/Disc Electronics - Delivery Acceptance | Nevis Labs, Columbia U |  | 1 | Nevis Labs, Columbia U | 70000 | 70000 | Quote from W. Sippach, Nevis, based on original MBD Electronics boards
S273500 | Procure sPHENIX Production Digitizers - Delivery Acceptance (S247450)
| Digitizer Boards | Nevis Labs, Columbia U |  | 4 | Nevis Labs, Columbia U | 1920.07 | 7680.28 | WBS 1.05.03 - more of same board estimated there
| XMIT Boards | Nevis Labs, Columbia U |  | 2 | Nevis Labs, Columbia U | 414.36 | 828.72 | WBS 1.05.03 - more of same board estimated there
| Controller | Nevis Labs, Columbia U |  | 2 | Nevis Labs, Columbia U | 436.7 | 873.4 | WBS 1.05.03 - more of same board estimated there
| Clockmaster Board | Nevis Labs, Columbia U |  | 2 | Nevis Labs, Columbia U | 1500 | 3000 | WBS 1.05.03 - more of same board estimated there
| Trigger Iface Board | Nevis Labs, Columbia U |  | 4 | Nevis Labs, Columbia U | 50 | 200 | WBS 1.05.03 - more of same board estimated there
| Crate Backplane | Nevis Labs, Columbia U |  | 1 | Nevis Labs, Columbia U | 987.51 | 987.51 | WBS 1.05.03 - more of same board estimated there
| Crate + Misc | Nevis Labs, Columbia U |  | 1 | Nevis Labs, Columbia U | 1200 | 1200 | WBS 1.05.03 - more of same board estimated there
[6 empty] | Digitizer Subtotal (S273500) | 14769.91
S273600 | Procure Shaper/Disc Board 128 Channels - Delivery Acceptance (S247460)
| Disc/Shaper Board | Nevis Labs, Columbia U |  | 10 | Nevis Labs, Columbia U | 2000 | 20000 | Nevis Lab similar prior boards
| D/S Controller Board | Nevis Labs, Columbia U |  | 2 | Nevis Labs, Columbia U | 2500 | 5000 | Nevis Lab similar prior boards
| Crate Backplane | Nevis Labs, Columbia U |  | 1 | Nevis Labs, Columbia U | 987.51 | 987.51 | Nevis Lab similar prior boards
| Crate + Misc | Nevis Labs, Columbia U |  | 1 | Nevis Labs, Columbia U | 1200 | 1200 | Nevis Lab similar prior boards
[6 empty] | Shaper/Discriminator Subtotal (S273600) | 27187.51
[6 empty] | TOTAL Materials | 111957.42
LABOR
Activity ID | Description | Labor Type | Hours | Total Hours for Activity | Basis | STATUS
S272000 | Procure Prototype Shaper/Disc Electronics - Provide Requirements to Procurement | Scientist | 24 | 72 | BNL Physics Dept. experience with past PRs to Nevis Labs | Complete
|  | Engineer | 24
|  | Student | 24
S272700 | Prototype Shaper/Disc Board Testing; make any revisions to design and layout | Scientist | 72 | 216 | BNL Physics and Instrumentation experience with prior layout changes and requirements updates communicated to Nevis
|  | Engineer | 72
|  | Student | 72
S272800 | Procure Min/Bias Electronics - Provide Requirements to Procurement | Scientist | 112 | 112 | BNL Physics Dept. experience with past PRs to Nevis Labs
|  | Engineer | 0
|  | Student | 0
S273700 | Oversight of sPHENIX Digitizers Procurement | Scientist | 16 | 16 | BNL Physics and Instrumentation experience with prior contracts executed at Nevis
Engineer
Student
S2173800 | Test Full Min/Bias Electronics | Scientist | 48 | 112 | BNL Physics and Instrumentation experience with testing of similar boards and earlier MBD electronics
|  | Engineer | 16
|  | Student | 48
S274000 | Bench Test MinBias Detector | Scientist | 80 | 160 | BNL Physics and Instrumentation experience with testing of similar boards and earlier MBD electronics
Engineer
|  | Student | 80
|  |  | TOTAL Hours | 616