## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
DAQ/Trigger |  | 1.06 |  | Timing System |  | 1.06.04
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| DAQ/Trigger: Timing System Design |  | 1.06.04.1 |  | Timing System Design Summary
| DAQ/Trigger: Timing System Prototype |  | 1.06.04.2 |  | Timing System Prototype Summary
| DAQ/Trigger: Timing System Production |  | 1.06.04.3 |  | Timing System Production Summary

## Timing System Design Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-08
[6 empty] | Prepared By: | M.L. Purschke
[6 empty] | DocNo. (refer Rev. Log) | 77 v7
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: Timing System Design |  |  |  | 1.06.04.01
WBS Dictionary Definition:
This work package covers the design of the DAQ system, components, and their interconnects.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The following assumptions were used in the estimate: We have virtually all requireed hardware in hand from the PHENIX experiment. This will allow us to perform test of all design features where decisions based on test have to be made.
Details of the Base Estimate (explanation of the Work)
This work package covers the design of the timing system. As needed, tests with actual hardware will be performed to validate the design. No procurement or fabrication costs are foreseen.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
|  | Parts Procurement | Catalogue/Quote/Eng Estimate |  | 0
Contingency
M&S Contigency Rules Applied
Labor Contingency Rules Applied:

## Timing System Prototype Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  | Date of Est: | 2019-02-08
[6 empty] | Prepared By: | M.L. Purschke
[6 empty] | DocNo. (refer Rev. Log) | 77 v7
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: Timing System Protoype |  |  |  | 1.06.04.02
WBS Dictionary Definition:
This work package covers the prototype of the DAQ system, components, and most interconnects.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the timing system prototype, which will be used to validate the design with actual front-end hardware, and will be used by the detector groups to test their detectors.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
|  | Procurement | Catalogue/Quote/Eng Estimate |  | 0
Contingency
M&S Contigency Rules Applied
The Procurement estimate is based on quotes and is assigned the standard 10%
Labor Contingency Rules Applied:

## Timing Syst. Production Summary
|  |  | sPHENIX Detector |  |  | Date of Est: | 2019-02-08
Relativistic Heavy Ion Collider
|  |  | BASIS of ESTIMATE (BoE) |  |  | Prepared By: | M.L. Purschke
[6 empty] | DocNo. | 77 v7
(refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  | Control Account Number
DAQ/Trigger: Timing System Production |  |  |  | 1.06.04.03
WBS Dictionary Definition:
This work package covers the production of the DAQ system
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
The following assumptions were used in the estimate: 1) The full complement of hardware need to be procured
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the data acquisition production system and its deployment.
Cost Summary
Follow links for detailed summary
|  | Task | Cost Basis |  | Cost
|  | Procurement | Catalogue/Quote/Eng Estimate |  | 41600
Contingency
M&S Contigency Rules Applied
Standard items have been assigned 10%
The DCM-2 carry 40% because of an issue with the availability of the main chip, which might trigger a re-layout of the board
The computers procured in the late stage carry 25% because of the uncertainty of the price development.
Labor Contingency Rules Applied:

## 1.6.4.1 Timing System Design
1.06.04.01 |  | Timing system design |  |  |  | 0
WBS | Activity | Description | Item | Unit Price $ | Quantity | Sum | Unit Price $ | Quantity | Sum | Part nr / What | Quote / Info
[5 empty] | Primary |  |  | Alternate
[5 empty] | TOTAL Materials | 0
Labor |  | 1.6.4.1
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.04.01 | 268300 | Timing Design: Evaluate Performance Requirements | previous PHENIX timing system | PROF | 0 | 240 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 240
1.06.04.01 | 268400 | Timing: Write design specifications | previous PHENIX timing system | PROF | 80 | 240 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 160
|  | TOTAL Hours |  |  | 0 | 0

## 1.6.4.2 Timing System Prototype
1.06.04.02 |  | Timing System Prototype
WBS | Activity | Description | Items | Unit Price $ | Quantity | Sum | Unit Price $ | Quantity | Sum | Part nr / What | Quote / Info
[5 empty] | Primary |  |  | Alternate
1.06.04.02 | 268700 | Procure Hardware | [9 empty] | Complete
|  |  | FPGA Board | 2953 | 3 | 8859 |  |  |  |  | Already bought, BNL internal req.
|  |  | Optical transmitter breakout board | 2000 | 10 | 20000
|  |  | Fibers | 200 | 10 | 2000 |  |  |  |  | catalog price
[5 empty] | TOTAL Materials | 0
Labor |  | 1.6.4.2
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.04.02 | 268500 | Timing Proto: Select FPGA Board | previous PHENIX timing system | PROF | 24 | 72 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 48
1.06.04.02 | 268600 | Timing Proto: Procure Hardware Labor | previous PHENIX timing system | PROF | 24 | 48 | Complete
|  |  |  | TECH | 0
|  |  |  | SCI | 24
1.06.04.02 | 268900 / 268910 | Timing Proto: Develop firmware | previous PHENIX timing system | PROF | 636 | 698
|  |  |  | TECH | 0
|  |  |  | STUD | 0
|  |  |  | SCI | 62
1.06.04.02 | 269100 | Timing Proto: Design I/O Transition Module | previous PHENIX timing system | PROF | 0 | 76
|  |  |  | TECH | 76
|  |  |  | SCI | 0
1.06.04.02 | 269300 / 269310 | Timing Proto: Set up hardware | previous PHENIX timing system | PROF | 67 | 67
|  |  |  | TECH | 0
|  |  |  | SCI | 0
1.06.04.02 | 269400 | Timing Proto: test prototype | previous PHENIX timing system | PROF | 0 | 180
|  |  |  | TECH | 0
|  |  |  | STUD | 120
|  |  |  | SCI | 60
1.06.04.02 | 269500 | Timing Proto: Evaluate performance | previous PHENIX timing system | PROF | 0 | 136
|  |  |  | TECH | 0
|  |  |  | STUD | 80
|  |  |  | SCI | 56
1.06.04.02 | 269600 | Timing Proto: Update Design Specifications | previous PHENIX timing system | PROF | 0 | 42
|  |  |  | TECH | 0
|  |  |  | SCI | 42
|  | TOTAL Labor |  |  | 1199 | 1199

## 1.6.4.3 Timing Syst. Production
1.06.04.03 |  | Timing System production
WBS | Activity | Description | Item | Unit Price $ | Quantity | Sum | Unit Price $ | Quantity | Sum | Part nr / What | Q / Info
Primary
1.06.04.3 | 270300 | Procure FPGA boards | FPGA Board | 6000 | 3 | 18000 | [5 empty] | Only if we have to make a new version of the board.
|  |  | Optical transmitter breakout board | 2000 | 10 | 20000
|  |  | Trunk fiber | 5600 | 4 |  | 5600 | 4
|  |  | MTP <-> MPT fiber couplers | 225 | 4 | 900 | 225 | 4 | 900 | 48 -> 4x12 | Catalog item
|  |  | Fiber patch panel | 450 | 6 | 2700 | 450 | 6 | 2700 | 48 ports | catalog item
[5 empty] | TOTAL Materials | 41600
Labor |  | 1.6.4.3
WBS |  | Description | Justification | Category | Hours | TOTAL
1.06.04.03 | 269700 | Timing Production: Provide Requirements | previous PHENIX timing system | PROF | 40 | 160
|  |  |  | TECH | 0
|  |  |  | SCI | 120
1.06.04.03 | 270500 / 270510 | Timing Production: final firmware updates | previous PHENIX timing system | PROF | 882 | 1010
|  |  |  | TECH | 0
|  |  |  | SCI | 128
1.06.04.03 | 270600 / 270610 | Timing Production: install timing system | previous PHENIX timing system | PROF | 240 | 600
|  |  |  | TECH | 320
|  |  |  | STUD | 0
|  |  |  | SCI | 40
1.06.04.03 | 270700 / 270710 | Timing Production: commission timing system | previous PHENIX timing system | PROF | 512 | 832
|  |  |  | TECH | 0
|  |  |  | STUD | 0
|  |  |  | SCI | 320
1.06.04.03 | 270800 | Timing Production: additional firmware updates | previous PHENIX timing system | PROF | 0 | 144
|  |  |  | TECH | 144
|  |  |  | STUD | 0
|  |  |  | SCI | 0
|  | TOTAL Hours |  |  | 2746 | 2746