## Nav
sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE)
L2 Project Name |  | L2 WBS Number |  | L3 Project Name (Control Account) |  | L3 WBS Number
DAQ/Trigger |  | 1.06 |  | Trigger |  | 1.06.02
| Work Package Name |  | WBS Number |  | Basis of Estimate Link
| LL1 Trigger: Design |  | 1.06.02.01 |  | LL1 Trigger Design Summary
| LL1 Trigger: Prototype v1 |  | 1.06.02.02 |  | LL1 Trigger Prototype v1 Summary
| LL1 Trigger: Preproduction Prototype |  | 1.06.02.03 |  | LL1 Trigger Preproduction Summary
| LL1 Trigger: Production |  | 1.06.02.04 |  | LL1 Trigger Production

## LL1 Trigger Design Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2018-02-04
[7 empty] | Prepared By: | J.L. Nagle
[7 empty] | DocNo. (refer Rev. Log) | DocDB-75-v4
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
DAQ/Trigger: Trigger Design |  |  |  | 1.06.02.01
WBS Dictionary Definition:
This work package covers the design of the Local Level-1 Trigger system, the components, and their interconnects. The system includes the fiber inputs from the Electromagnetic Calorimeter, Hadronic Calorimeter, and Minimum Bias Detector Front End Electronics, and the output from the Local Level-1 system to the Global Level-1 Trigger Master and data logging via the DCM 2 system. This does not include the Front End Electronics, the Global Level-1 Trigger Master, not the DCM2 for readout. No other subsystem Front End Electronics input is included in this scope.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
There are two design options being considered: (1) a custom set of digital electronics with the form factor, slow controls, and mechanics modeled from the sPHENIX Calorimeter Digitizer Electronics and (2) a re-implementation of the ATLAS gFEX board. The estimate is based on option (1) utilizing specific price quotes for the specific likely components (FPGA, fiber inputs, etc) and the cost from the prototype experience with the sPHENIX Calorimeter Digitizer Electronics. Initial estimates for option (2) are similar in scale with detailed costs for the gFEX board itself known and a somewhat larger uncertainty on the engineering required (for example for new FPGA programming, new clock management).
Details of the Base Estimate (explanation of the Work)
This work package covers the design of the sPHENIX Local Level-1 Trigger System as defined above. No procurement or fabrication costs are foreseen in this initial design phase. The estimate for engineering and labor is based on previous experience with the Calorimeter Digitizer Electronics design by the same groups.
Cost Summary
Follow links for detailed summary
[5 empty] | Grand Total | Labor Hours
[5 empty] | 90000 | 80
Estimate Uncertainty
For the design phase, the estimated uncertainty is 50% due to the early phase of schematic board design, and since the downselect of technology make require additional engineering resources depending on the choice.

## LL1Trigger Prototype v1 Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2018-02-04
[7 empty] | Prepared By: | J.L. Nagle
[7 empty] | DocNo. (refer Rev. Log) | DocDB-75-v4
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
DAQ/Trigger: Trigger Protoype V1 |  |  |  | 1.06.02.02
WBS Dictionary Definition:
This work package covers the prototype of the Local Level-1 Trigger system, the components, and their interconnects. The system includes the fiber inputs from the Electromagnetic Calorimeter, Hadronic Calorimeter, and Minimum Bias Detector Front End Electronics, and the output from the Local Level-1 system to the Global Level-1 Trigger Master and data logging via the DCM 2 system. This does not include the Front End Electronics, the Global Level-1 Trigger Master, nor the DCM2 for readout. No other subsystem Front End Electronics input is included in this scope. This phase includes layout, fabrication, and testing of the prototype V1 system.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
There are two design options being considered: (1) a custom set of digital electronics with the form factor, slow controls, and mechanics modeled from the sPHENIX Calorimeter Digitizer Electronics and (2) a re-implementation of the ATLAS gFEX board. The estimate is based on option (1) utilizing specific price quotes for the specific likely components (FPGA, fiber inputs, etc) and the cost from the prototype experience with the sPHENIX Calorimeter Digitizer Electronics. Initial estimates for option (2) are similar in scale with detailed costs for the gFEX board itself known and a somewhat larger uncertainty on the engineering required (for example for new FPGA programming, new clock management). At the prototype V1 phase, there will already be a downselect.
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the first round sPHENIX Local Level-1 Trigger prototype. The basis of estimate is made in terms of detailed vendor quotes and experience from the sPHENIX Calorimeter Digitizer Electronics project.
Cost Summary
Follow links for detailed summary
[5 empty] | Grand Total | Labor Hours
[5 empty] | 83000 | 352
Estimate Uncertainty
For this phase, the estimated uncertainty is 50% due to the early phase of schematic board design, and since the downselect of technology make require additional engineering resources depending on the choice. Although specific quotes exist for components, etc. it is prudent to remain conservative until the full design is complete.

## LL1 Trigger Preprod Summary
|  |  | sPHENIX Detector Relativistic Heavy Ion Collider BASIS of ESTIMATE (BoE) |  |  |  | Date of Est: | 2018-02-04
[7 empty] | Prepared By: | J.L. Nagle
[7 empty] | DocNo. (refer Rev. Log) | DocDB-75-v4
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
DAQ/Trigger: Trigger LL1 Preproduction Prototype |  |  |  | 1.06.02.03
WBS Dictionary Definition:
This work package covers the preproduction of the Local Level-1 Trigger system, the components, and their interconnects. The system includes the fiber inputs from the Electromagnetic Calorimeter, Hadronic Calorimeter, and Minimum Bias Detector Front End Electronics, and the output from the Local Level-1 system to the Global Level-1 Trigger Master and data logging via the DCM 2 system. This does not include the Front End Electronics, the Global Level-1 Trigger Master, nor the DCM2 for readout. No other subsystem Front End Electronics input is included in this scope.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
There are two design options being considered: (1) a custom set of digital electronics with the form factor, slow controls, and mechanics modeled from the sPHENIX Calorimeter Digitizer Electronics and (2) a re-implementation of the ATLAS gFEX board. The estimate is based on option (1) utilizing specific price quotes for the specific likely components (FPGA, fiber inputs, etc) and the cost from the prototype experience with the sPHENIX Calorimeter Digitizer Electronics. Initial estimates for option (2) are similar in scale with detailed costs for the gFEX board itself known and a somewhat larger uncertainty on the engineering required (for example for new FPGA programming, new clock management).
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the Trigger preproduction prototype. We established the need for two rounds of prototyping.
Cost Summary
Follow links for detailed summary
[5 empty] | Grand Total | Labor Hours
[5 empty] | 60000 | 402
Estimate Uncertainty
For this phase, the estimated uncertainty is 50% due to the early phase of schematic board design, and since the downselect of technology make require additional engineering resources depending on the choice. Although specific quotes exist for components, etc. it is prudent to remain conservative until the full design is complete.

## LL1 Trigger Production Summary
|  |  | sPHENIX Detector |  |  |  | Date of Est: | 2018-02-04
Relativistic Heavy Ion Collider
|  |  | BASIS of ESTIMATE (BoE) |  |  |  | Prepared By: | J.L. Nagle
[7 empty] | DocNo. | DocDB-75-v4
(refer Rev. Log)
Work Package Name: |  |  |  | WBS Number: |  |  |  | Control Account Number
DAQ/Trigger: Trigger Production |  |  |  | 1.06.02.04
WBS Dictionary Definition:
This work package covers the production of the Local Level-1 Trigger system, the components, and their interconnects. The system includes the fiber inputs from the Electromagnetic Calorimeter, Hadronic Calorimeter, and Minimum Bias Detector Front End Electronics, and the output from the Local Level-1 system to the Global Level-1 Trigger Master and data logging via the DCM 2 system. This does not include the Front End Electronics, the Global Level-1 Trigger Master, nor the DCM2 for readout. No other subsystem Front End Electronics input is included in this scope.
Estimate Type (check all that apply):
Work Complete
| X | Existing Purchase Order
| X | Catalog Listing or Industrial Construction Database
| X | Documented Vendor Quotation based on Drawings/Sketches/Specifications
Budgetary Estimate by Vendor/Fabricator based on Sketches, Drawings, or other Written Correspondence
| X | Engineering Estimate based on Similar Items or Procedures
Engineering Estimate based on Analysis
| X | Expert Opinion
Supporting Documents (including but not limited to):
Assumptions Used in Developing Estimate
There are two design options being considered: (1) a custom set of digital electronics with the form factor, slow controls, and mechanics modeled from the sPHENIX Calorimeter Digitizer Electronics and (2) a re-implementation of the ATLAS gFEX board. The estimate is based on option (1) utilizing specific price quotes for the specific likely components (FPGA, fiber inputs, etc) and the cost from the prototype experience with the sPHENIX Calorimeter Digitizer Electronics. Initial estimates for option (2) are similar in scale with detailed costs for the gFEX board itself known and a somewhat larger uncertainty on the engineering required (for example for new FPGA programming, new clock management).
Details of the Base Estimate (explanation of the Work)
This work package covers the implementation of the production sPHENIX Local Level-1 Trigger system and its deployment/ commissioning.
Cost Summary
Follow links for detailed summary
[5 empty] | Grand Total | Labor Hours
[5 empty] | 117000 | 560
Estimate Uncertainty
For this phase, the estimated uncertainty is 50% due to the early phase of schematic board design, and since the downselect of technology make require additional engineering resources depending on the choice. Although specific quotes exist for components, etc. it is prudent to remain conservative until the full design is complete.

## 1.06.02.01 Trigger Design
Material
WBS | Activity | Description | Item | Vendor | Total | Status | Basis of Estimate | Grand Total
1.06.02.01 |  | Trigger Design | [5 empty] | 90000
1.06.02.01 | 261600 | Trigger Design, Layout Custom LL1 - Delivery Acceptance |  |  | 90000 |  | Experience, possible use of existing board |  | Quote is from Nevis Labs in February 2018. Conversations with Nevis personnel during January - March 2019 indicate that the esimate quoted remains valid. The work is for the design and layout of the Local Level-1 trigger board. The remaining M&S estimates in WBS 1.06.02 LL1 Trigger are for M&S costs to fabricated prototype and later production LL1 trigger baords
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.02.01 | 260900 | Trigger Design: Write design specifications | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 240 | Complete
|  |  |  | SCI | 240
|  |  |  | STUD | 0
1.06.02.01 | 261000 | Trigger Design, Layout Custom LL1 - Provide Requirements to Procurement | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 40 | Complete
|  |  |  | SCI | 40
|  |  |  | STUD | 0
1.06.02.1 | 261700 | Trigger Design, per Downselect of gFEX mod versus Layout Custom LL1 | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 80
|  |  |  | TECH | 80
|  |  |  | SCI | 0
|  | Grand Total |  |  | 80 | 80

## 1.06.02.02 Trigger Prototype v1
Material
WBS |  | Description | Item | Vendor | Unit Cost | Number Units | Total | Status | Basis of Estimate | Grand Total
1.06.02.02 | Activity | Trigger Prototype V1 | [7 empty] | 83000
1.06.02.02 | 262500 | Procure Prototype V1 Trigger Board - Delivery Acceptance |  |  |  |  | 83000
|  |  | FPGA | ALTERA Arria 10 FPGA, 10AX115N4F40E3SG | 2203 | 4 | 8812 |  | Quote
|  |  | Fiber Tranceivers | Finisar CXP module, FTLD10CE1C, can handle 12 fibers each ($490 each) | 1960 | 4 | 7840 |  | Quote
|  |  | Board Comp. |  | 250 | 4 | 1000 |  | Experience with Calorimeter digitizer prototype cost
|  |  | PCB Production |  | 350 | 4 | 1400 |  | Quote from Calorimeter digitizer prototype case
|  |  | Board Assembly |  | 400 | 4 | 1600 |  | Quote from Calorimeter digitizer prototype case
|  |  | MTP Fiber | Fibertronics MTP | 550 | 4 | 2200 |  | Quote
|  |  | PCB Setup Charge |  | 950 | 1 | 950 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Board Assembly Setup |  | 1600 | 1 | 1600 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Crate and Backplane |  | 2754 | 2 | 5508 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Crate Controller |  | 2013 | 2 | 4026 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Contracted Labor at Nevis Laboratories |  | 48064 | 1 | 48064 |  | Experience with Calorimeter digitizer prototype cost
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.02.02 | 261900 | Procure Prototype V1 Trigger Board - Provide Requirements to Procurement | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 48
|  |  |  | SCI | 48
|  |  |  | STUD | 0
1.06.02.02 | 262600 | Trigger Prototpe v1: Test trigger systems | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 240
|  |  |  | TECH | 0
|  |  |  | SCI | 240
1.06.02.02 | 262700 | Trigger Prototpe v1: R&D complete | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 0 | Milestone
|  |  |  | TECH | 0
|  |  |  | SCI | 0
1.06.02.02 | 262800 | Trigger Prototpe v1: Preproduction Readiness Review design specifications update | Previous experience with Calorimeter Digitizer Electronics | PROF | 32 | 64
|  |  |  | TECH | 0
|  |  |  | SCI | 32
|  | Grand Total |  |  | 352 | 352

## 1.06.02.03 Trigger Preprod
Material
WBS | Activity | Description | Item | Vendor | Unit Cost | Number Units | Total | Status | Basis of Estimate | Grand Total
1.06.02.03 |  | Trigger Prototype V1 | [7 empty] | 60000
1.06.02.03 | 263600 | Procure Trigger Preproduction Prototype LL1 - Delivery Acceptance |  |  |  |  | 60000
|  |  | FPGA | ALTERA Arria 10 FPGA, 10AX115N4F40E3SG | 2203 | 4 | 8812 |  | Quote
|  |  | Fiber Tranceivers | Finisar CXP module, FTLD10CE1C, can handle 12 fibers each ($490 each) | 1960 | 4 | 7840 |  | Quote
|  |  | Board Comp. |  | 250 | 4 | 1000 |  | Experience with Calorimeter digitizer prototype cost
|  |  | PCB Production |  | 350 | 4 | 1400 |  | Quote from Calorimeter digitizer prototype case
|  |  | Board Assembly |  | 400 | 4 | 1600 |  | Quote from Calorimeter digitizer prototype case
|  |  | MTP Fiber | Fibertronics MTP | 550 | 4 | 2200 |  | Quote
|  |  | PCB Setup Charge |  | 950 | 1 | 950 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Board Assembly Setup |  | 1600 | 1 | 1600 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Crate and Backplane |  | 2754 | 2 | 5508 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Crate Controller |  | 2013 | 2 | 4026 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Contracted Labor at Nevis Laboratories |  | 25064 | 1 | 25064 |  | Experience with Calorimeter digitizer prototype cost
Labor
WBS | Activity | Description | Justification | Category | Hours | TOTAL
1.06.02.03 | 262900 | Trigger LL1 Preproduction Prototype: Electrical Safety Review | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 10
|  |  |  | SCI | 10
|  |  |  | STUD | 0
1.06.02.03 | 263000 | Procure Trigger Preproduction Prototype LL1 - Provide Requirements to Procurement | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 48
|  |  |  | SCI | 48
|  |  |  | STUD | 0
1.06.02.03 | 263700 | Trigger LL1 Preproduction Prototype: Test trigger systems | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 280
|  |  |  | TECH | 0
|  |  |  | SCI | 280
1.06.02.03 | 263900 | Trigger LL1 Preproduction R&D complete | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 0
|  |  |  | TECH | 0
|  |  |  | SCI | 0
1.06.02.03 | 263800 | Review LL1 Preproduction Prototype board | Previous experience with Calorimeter Digitizer Electronics | PROF | 32 | 64
|  |  |  | TECH | 0
|  |  |  | SCI | 32
|  | Grand Total |  |  | 402 | 402

## 1.06.02.04 Trigger Production
Material
WBS | Activity | Description | Item | Vendor | Unit Cost | Number Units | Total | Status | Basis of Estimate | Grand Total
1.06.02.04 |  | Trigger LL1 Production | [7 empty] | 117000
1.06.02.04 | 264900 | Procure Production LL1 System - Delivery Acceptance |  |  |  |  | 117000
|  |  | FPGA | ALTERA Arria 10 FPGA, 10AX115N4F40E3SG | 2203 | 14 | 30842 |  | Quote
|  |  | Fiber Tranceivers | Finisar CXP module, FTLD10CE1C, can handle 12 fibers each ($490 each) | 1960 | 14 | 27440 |  | Quote
|  |  | Board Comp. |  | 250 | 14 | 3500 |  | Experience with Calorimeter digitizer prototype cost
|  |  | PCB Production |  | 350 | 14 | 4900 |  | Quote from Calorimeter digitizer prototype case
|  |  | Board Assembly |  | 400 | 14 | 5600 |  | Quote from Calorimeter digitizer prototype case
|  |  | MTP Fiber | Fibertronics MTP | 550 | 14 | 7700 |  | Quote
|  |  | PCB Setup Charge |  | 950 | 1 | 950 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Board Assembly Setup |  | 1600 | 1 | 1600 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Crate and Backplane |  | 2754 | 2 | 5508 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Crate Controller |  | 2013 | 2 | 4026 |  | Experience with Calorimeter digitizer prototype cost
|  |  | Contracted Labor at Nevis Laboratories |  | 24934 | 1 | 24934 |  | Experience with Calorimeter digitizer prototype cost
Labor
WBS |  | Description | Justification | Category | Hours | TOTAL
1.06.02.04 | 264000 | Trigger LL1 Production: Updates to trigger board: Production | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 136
|  |  |  | SCI | 136
|  |  |  | STUD | 0
1.06.02.04 | 264100 | Trigger LL1 Production: final updates to trigger crate requirements | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 20
|  |  |  | SCI | 20
|  |  |  | STUD | 0
1.06.02.04 | 264200 | Trigger LL1 Production: Readiness Review | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 64
|  |  |  | SCI | 64
|  |  |  | STUD | 0
1.06.02.04 | 264300 | Procure Production LL1 System - Provide Requirements to Procurement | Previous experience with Calorimeter Digitizer Electronics | TECH | 0 | 40
|  |  |  | SCI | 40
|  |  |  | STUD | 0
1.06.02.04 | 265000 | Trigger LL1 Production: Program and commission trigger boards | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 60
|  |  |  | TECH | 0
|  |  |  | SCI | 60
1.06.02.04 | 265100 | Trigger LL1 Production: Assemble trigger system | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 120
|  |  |  | TECH | 0
|  |  |  | SCI | 120
1.06.02.04 | 265200 | Trigger LL1 Production: Commission trigger systems | Previous experience with Calorimeter Digitizer Electronics | PROF | 0 | 120
|  |  |  | TECH | 0
|  |  |  | SCI | 120
|  | Grand Total |  |  | 560 | 560