## Slide 1: sPHENIX Director’s Review Technical Status
John Haggerty
April 9-11, 2019
BNL

## Slide 2: sPHENIX projects
1.x sPHENIX MIE
  TPC
  TPC electronics
  EMCAL
  Outer HCAL
  Calorimeter electronics
  DAQ and Trigger
2.x Infrastructure, Installation, and Integration
  Cryo
  Magnet power supply and quench protection
  Magnetic field measurement
  Carriage/cradle, barrel steel, end doors, bridge
  Electrical power, gas, safety system
  Installation
3.x Silicon tracking detectors (covered in later talk)
  MVTX
  INTT

## Slide 3: PHENIX Remove and Repurpose

## Slide 4: Solenoid
Solenoid leaving
SLAC 1/2015
Full current test February 2018
Full 3-D OPERA field calculation
with measured steel magnetization

## Slide 5: Cryogenics
RHIC Cryo group is supporting the solenoid
Recent Design Review and Procurement Readiness Review of cryo components showed that the design is very far advanced

## Slide 6: Barrel steel sectors

## Slide 7: Barrel steel
Test assembly of sectors
Cable routing on sector
Survey and checking the gap

## Slide 8: HCAL tile production
Delivery of about 1500 R&D tiles close to half complete
Exercise of option to purchase remaining 6000 tiles
Anthony Hodges at GSU has been overseeing the tile testing
Begin instrumenting HCAL sectors over the summer

## Slide 9: EMCAL
Block manufacture for Sector 0 ongoing at UIUC
Most components for sector assembly at BNL
Mechanical tolerances and dark fiber are being pursued and improved

## Slide 10: Calorimeter Electronics
Prototype electronics for the R&D sectors (EMCAL 1-12 and HCAL 1-6) are in progress
EMCAL Sector 0 (not intended for installation) is under construction
SiPM order (LLP) placed with Hamamatsu
  8500/month until 2020
  Michigan group is working with Debrecen on testing
Last year’s beam test prototype (V2.1) has been retrofitted with new electronics (V2.2) for mechanical, electronic, and radiation damage testing
Single pixel peaks from Debrecen tester

## Slide 11: Calorimeter beam tests
February 2014
Proof of principle
February 2016
η~0
sPHENIX geometry
February 2017
η~0.9
https://arxiv.org/abs/1704.01461
(published IEEE TNS)
February 2018

## Slide 12: TPC key features
Compact—outer radius 80 cm Field cage and ”wagon wheels” at SBU
3 (radial) x 12 (azimuthal) GEM chambers per end Prototypes being constructed
FEE board being developed around SAMPA ASIC to be used by ALICE and STAR iTPC SAMPA V5 component test (multi-project wafer) complete, under test; design of V5 under way
Fast gas low diffusion to achieve position resolution < 200 μ
Field distortions minimized by
  Minimize Ion Back Flow by judicious choice of electric field between GEM foils, pioneered by ALICE
  Gas choice (low mass, fast drift)
  High electric field
  Inner field cage fiducial volume begins at 30 cm (10 cm from inner radius)
  Looking for further optimizations
Continuous streaming readout Ongoing development with prototype FEE cards and FELIX by John Kuczewski

## Slide 13: TPC v1
TPC field cage constructed at SBU
“Wagon wheels” complete
Design of cooling/cabling in progress
Prototype GEM modules

## Slide 14: TPC electronics
SAMPA v5 mods under test in MPW at USP
Lund will test production chips
FEE and FELIX development at BNL

## Slide 15: DAQ/Trigger
Commodity servers with custom PCIe cards (FELIX, JSEB II)
Ethernet switch
Local data logging in 1008 before transmission to RACF
Timing system to be implemented in firmware on Zynq boards developed for NSLS II
Columbia/Colorado developing calorimeter trigger

## Slide 16: Cradle/Carriage
Engineering group led by Jim Mills and Jon Hock
Preliminary Design Review 2/11/2019
Rack and cabling layouts coordinated with Office of System Integration and Cryo group

## Slide 17: Silicon detectors

## Slide 18: Simulation
A lot of activity in simulation in the collaboration
Pythia 8 jets embedded in HIJING, FastJet anti-kT jets in R=0.2, 0.4 cones, underlying event subtracted
Many other physics simulations driving the detector design

## Slide 19: Engineering Reviews
Cradle/Carriage Conceptual Design Review
DAQ/Trigger Pre-CD-1 Conceptual Design Review
TPC Pre-CD-1 Conceptual Design Review
Calorimeter Electronics Pre-CD-1 Conceptual Design Review
EMCAL Pre-CD-1 Conceptual Design Review
Nov HCAL Pre-CD-1 Conceptual Design Review
sPHENIX Calorimeter Prototype v2.1 IDR closeout & PRR
EMCAL Light Guide Preliminary Design Review
Time Projection Chamber mini-review
MAPs Vertex Detector mini-Review
sPHENIX Full Field Flux Return - Mechanical Design Review
sPHENIX Calorimeter Prototype Support Structure Mechanical design Review
Cost and Schedule Review Magnet/Decom/Install/Integn/Infra Practice
sPHENIX EMCal Review
sPHENIX EMCal Practice
sPHENIX Calorimeter Electronics Review
sPHENIX HCal Review
sPHENIX Decommissioning and Installation Review
sPHENIX Magnet Review
MAGNET Preliminary Design Review and Pressure Safety Review
sPHENIX CRYOGENIC SYSTEM Procurement Readiness Review
sPHENIX Cradle/Carriage Preliminary Engineering Review
Calorimeter Trigger Preliminary Design Review
Calorimeter Electronics Digitizer System Design Review
LESHC 18-10 Review of the Cryogenic Systems for sPHENIX SC Solenoid IP8
MVTX Interim Design Review
Interim Design Review of Preproduction On-Detector HCAL Electronics
EMCAL Sector 1-12 Powder Review
sPHENIX HCAL Assembly Area Safety Review
EMCal Sector 0 Mechanics Preproduction Design Review
EMCal Sector 0 Electronics Preproduction Design Review
TPC Wagon Wheel Production Readiness Review
sPHENIX software and computing review
Outer HCal Scintillator Interim Design Review
EMCal Sector 0 Electronics Preproduction Design Review
EMCAL Block Design Review
sPHENIX Outer HCal Sector Steel Review Follow Up Review
INTT Pre-CD-1 Conceptual Design Review
sPHENIX Outer HCal Steel Sector Procurement Readiness/Design Review
sPHENIX Risk Registry and Mitigation Plan Review
EMCAL Fiber Procurement Readiness Review
Infrastructure, Installation and Integration Pre-CD-1 Conceptual Design Review
Convened by Project Manager, chaired by Project Scientist/Project Engineer
Over 40 Reviews Performed Over the Last 3 Years
Frequent detector engineering meetings
Many more to come in P6 schedule

## Slide 20: Summary
Since CD-1/3a in May 2018, prototyping has completed or advanced substantially in all systems
Engineering design and detailed design is now in full swing
Technical progress is monitored in frequent dedicated meetings and reviews