## Slide 1: sPHENIX Director’s Review TPC Factory Production
Vicki Greene, Vanderbilt University
April 9-11, 2019
BNL

## Slide 2: The L3 Component
1.02.03: TPC R2 Modules Factory
(also on behalf of R1/R3 Module Fact. - 1.02.02/1.02.04)
  Central Membrane CM
  Endplates EP, 2 in z
  Modules, 12 in f, 3 in r

## Slide 3: L3 Technical Overview
Emphasize any technical issues that still need to be resolved. If all has been decided put it on the slide.
Production of final modules framed & tested GEMs:
  Framed & Tested GEMs -- Factory
  Strong backs & Readout boards  SBU
  Module Testing & Characterization  SBU
ALICE model.
ALICE-based QA
No duplication:
  Gas Systems,
  Radiation sources,
  Translation Stages
NOTE: We have adopted the ALICE factory model at all relevant stages.

## Slide 4: L3 Scope
Factories are responsible for:
  Preparation of factories for production
  Testing quality of components: frames & GEMs
  Assembly of components: Framing of GEMs
  Testing quality of assembly: 1GEM arrival, 2After gluing, 3After trimming
  Shipping to final destination (SBU/BNL)
Conservative yield assumptions:
  Fragile items (GEMs) and irrecoverable (after gluing) items are assumed to have a 24/30 yield (24 modules required…materials for 30 modules).

## Slide 5: L3 Scope – Basic Workflow
PCB Workshop @ CERN
  Produces GEMs, attaches resistors, cleans, tests, and only ships working GEMs
Test Regimen before Framing
  Visual inspection
  Resistors value measurements (4.65 MΩ – 5.35 MΩ)
  Leakage current measurements before framing (nitrogen, -500 V, < 10% RH): 15 min
  Long term leakage current after framing (nitrogen, -500 V, < 10% RH): at least 5 h
Test Regimen after Framing
  Leakage current measurements before trimming (nitrogen, -500 V, < 10% RH): 15 min
  Leakage current measurements after trimming (nitrogen, -500 V, < 10% RH): 15 min
Shipping “booklet”
Time
ALICE, typical

## Slide 6: L3 Collaborators
Wayne State University: Bill Llope* (L3 manager) Oleg Grachov*
Vanderbilt University: Vicki Greene (L3manager) Julia Velkovska
Temple University: Bernd Surrow (L3 manager) Matt Posik
Weizmann Institute: Sasha Milov (L3 manager) Evgeny Shulga
(Yale University: Dick Majka**, Nikolai Smirnov**)
*Llope/Grachov ran ALICE IROC GEM Factory; wrote sPHENIX TPC GEM Factory QA Documents/Procedures
**Majka/Smirnov ran ALICE IROC Module Testing; wrote sPHENIX TPC Module Testing QA Documents/Procedures

## Slide 7: Schedule Drivers
Module production begins based upon first ability to make initial procurements.
Module production rate entirely limited by CERN GEM delivery schedule.
driver

## Slide 8: Cost Drivers
Module Cost Drivers: GEMs (1.02.01…centralizes purchase for all factories)
“L3-visible” Cost Driver: Pad Planes (2.7mil gap between pads…sole source--TTM)

## Slide 9: Status and Highlights
GEM Foil Design (R3)
Framed GEM (R2)
Stack (R1)
Pre-Production Frames. (R2)
J-contact limits solder migration
Pocketed frame allows R-potting
Pogo-pin protection
Prototype Framed GEM
Prototype Module
Prototype Padplane
R2 Glue-plate Design
Gravity-tensioned
Prototyping
PreProd
Prototype Module

## Slide 10: Issues and Concerns
Mostly the TPC factory production is contributed labor (good).
One scientist from WSU is paid, thereby creating a limited “standing army” issue.
  Performed all ALICE IROC factory work.
  Wrote sPHENIX QA procedures.
  Designs gluing fixtures for all sites.
  Provides training to all factory sites.
  Well-justified exceptional expense.
Student labor must be realized at production time.
These labor risks are captured in the Risk Registry.

## Slide 11: Summary
sPHENIX has maximally adapted our plans to the ALICE model, successfully leveraging the experience of Wayne State University (sPHENIX collaborators…ALICE GEM framing factory) and Yale (fully engaged in all R&D leading up to start of production).
Preproduction designs benefit both from the successful test beam run (June 2018) and all known concerns discovered and mitigated during the ALICE production.
Factories shall produce framed GEMs that are extensively tested and characterized.
sPHENIX 1.2.2-4 are ready for PD2/3 approval.

## Slide 12: Back Up