## Slide 1: sPHENIX Director’s Review WBS 1.05: Calorimeter Electronics
Eric J. Mannel
April 9-11, 2019
BNL

## Slide 2: WBS 1.05: Calorimeter Electronics
“Common” design for both EMCal and HCal
  Optical Sensor: Silicon Photomultiplier (SiPM)
  Front End Analog Section:
    Amplification/Shaping
    Gain adjustment
    Different packaging for EMCal and HCal
  Digital Backend Section:
    Continuous waveform digitization
    Trigger primitives
  Common Low Voltage and Bias Voltage Systems
Advance Design:
  4 Stages of prototypes and beam testing.
  Use commercial “Off the Shelf” components- No custom ASICS
EMCal V2.2 Prototype instrumented with preproduction electronics

## Slide 3: Calorimeter Electronics Block Diagram
WBS 1.05
WBS 1.06
WBS 2.09

## Slide 4: Calorimeter Electronics Technical Overview
Silicon Photomultipliers:
  Selected Device: Hamamatsu 12572-015P
  Immune to magnetic fields
  Pixels: 15 x 15 mm2
  Dynamic range: 104
  Gain: 2x105
  Device: 3 x 3 mm2
  Susceptible to neutron damage: increased leakage current
Analog Front End
  Shaping time of 30 nSec
  Switchable gain
    normal gain
    x 16 for calibration
  Differential analog drivers
  LED calibration/test system
  Monitoring of voltages, current and temperature
  Gain adjustment via bias voltage

## Slide 5: Calorimeter Electronics Technical Overview
Digitizer Back End
  Identical for EMCal/HCal
  Located “near” detector
  14 Bit ADC (12 bit effective)
  65 MHz maximum sampling frequency, operates at 6 x BCO
  40 BCO latency for triggering
  Maximum of 32 samples/channel/event
  5 Event buffering
  Generate trigger primitives based on 2x2 towers
Advance stage of design and Prototyping
Digitizer Board
2x8 EMCal Preamp
Noise Measurement

## Slide 6: WBS 1.05: Scope
MIE Request excluding yields
Optical Sensors
  CD-3A Request: 77K devices ordered
    EMCal: 70000
    HCal: 7000
EMCal Front End Electronics
  2x2 EMCal SiPM Daughter board: 3744
  2x8 EMCal Preamp Boards: 936
  64 Channel EMCal Interface Modules: 234
  EMCal Controllers: 52
  Crates, Power Systems and Cables
HCal Front End Electronics
  HCal SiPM Daughter board:6240
  HCal Preamp Boards: 1248
  52 Channel HCal Interface, Backplane & LED Driver Modules: 64
  HCal Controllers: 8
  Crates, Power Systems and Cables
Digitizer System
  Digitizers Modules: 367
  XMIT Modules: 92
  Controllers/Crates: 23
  Clock Master: 6
  Power systems & Patch Fibers

## Slide 7: Radiation Damage Studies
SiPMs subject to neutron damage- Increased leakage current
Front end electronics subject to potential damage from ionizing radiation and neutrons
  Component failure
  Single event upsets
Digitizers are sufficiently shielded.
Details in breakout sessions
  Silicon Photomultipliers: C. Aidala
  Calorimeter Front End Electronics: S. Boose
Extensive studies of neutron damage on Hamamatsu 12572-015P
  Expect 5x1010 -1011 n/cm2/run
  Increased leakage current, ~400 mA/device after 5 years with moderate cooling
  Front end electronics designed to handle increased current after 5 years running:
    Power capacity
    Cooling
  Paper submitted to IEEE TNS: arXiv:1809.04594

## Slide 8: Radiation Damage Studies
Ionizing radiation studies done at the Solid State Gamma Ray Irradiation Facility at BNL.
Expect ~1-2k Rad/run at EMCal
  Based on simulations
  PHENIX IR measurements
Irradiate front end electronics up to 240 kRad.
Device selection based on studies.
Radiation dose (rad)
45 krad
Performance of selected regulators for EMCal and HCal front end electornics
50 krad

## Slide 9: WBS 1.05: Subsystem Collaborators
Brookhaven National Lab:
  Eric Mannel, L2 for WBS 1.5
  Steve Boose, L3 for analog front end electronics
  Front end electronics design, production & testing
Columbia Univ./Nevis Labs:
  Cheng-Yi Chi, L3 for digital back end system
  Back end electronics design, production & testing
University of Michigan
  Christine Aidala, L3 for optical sensor testing
  Optical sensor testing
University of Debrecen
  Testing Equipment design and production
  Optical sensor testing
Augustana University
  Database management
  Electronics testing

## Slide 10: WBS 1.05: Schedule Drivers
SiPMs:
  CD-3A request for 77K Devices, $669K budgeted cost, order placed
  First 17K delivered March 4 & April 1, 2019, 10 month delivery schedule
  Extensive testing prior to assembly
  Required for EMCal module assembly
  31 Days of float
EMCal SiPM Daughter Boards/Preamps/Interface Boards and Interior Cables
  PD-3 Request
  Required for EMCal sector assembly.
  On or near critical path

## Slide 11: WBS 1.05: Cost Drivers
Cost Drivers:
  SiPMS: $669K, CD-3A item, order placed.
  EMCal Preamps: $474K
  EMCal Cables/Power Systems: $600K
  HCal Preamps: $41K
  HCal Cables/Power Systems: $169K
  Digitizer System: $860K
    Parts: $516K
    Board Fabrication: $145K
    Assembly: $124K
    Other Costs: $75K
EMCal Preamps
Digitizer Crate
EMCal SiPM Daughter Board

## Slide 12: WBS 1.05: Basis of Estimate & Resource-Loaded Schedule
Cost and Labor estimates are based on:
  Recent Prototype designs
  Budgetary quotes for designs that are well developed
  Engineering estimates and past experience for designs still in preliminary stages.
Schedule based on:
  Budgetary quoted delivery schedule when available
  Engineering experience
BOEs were used to develop the RLS.

## Slide 13: WBS 1.05 MIE Labor + M&S Profile
Electronics fabrication is done by commercial vendors
Detailed parts quotes/catalog pricings
Vendor assembly quotes
Labor is for Q/A testing

## Slide 14: WBS 1.05 MIE FTE Labor Profile
Electronics fabrication is done by commercial vendors.
Labor is for order placement, and Q/A testing and inspection.
Installation labor is part of detectors and/or installation WBS’s.

## Slide 15: WBS 1.05 Estimate of Uncertainty
BoEs are based on recent board design
Preproduction orders
Detailed parts quotes/catalog pricings
Vendor assembly quotes

## Slide 16: WBS 1.05 Risk Registery

## Slide 17: WBS 1.05 Status and Highlights
First 2 deliveries of SiPMs received: Mar 4 & April 2, 2019.
Test stands for Q/A testing setup and ready.
EMCal prototype updated with Sector 0 (preproduction) electronics.
EMCal Sector 0 electronics ready for installation.
HCal modules 1-6 electronics ready for installation
2 trays of SiPMs from the first delivery. Devices are sorted according to Vop
EMCal Interface and Preamp Q/A test stand in Hcal lab
Test fit of HCal electronics on Module 0 in bldg. 912

## Slide 18: Issues and Concerns
SiPMs
  Testing/Assembly
    Critical for EMCal/Hcal performance
    Tied to SiPM delivery schedule
    Monitor schedule closely, multiple test facilities/sites
    Value Engineer assembly process with potential assembly house(s)
Front End Electronics Assembly & Testing
  Needed for EMCal Sector/HCal assembly
  Closely monitor schedule
  Early design of test procedures, value engineering
Advance Stage of design, 4 prototype stages complete and tested under “beam” conditions

## Slide 19: Summary
CD-3A request for 77K SiPMs has been placed, first delivery March 4, 2019
The Calorimeter Electronics design is in an advance stage with 4 prototype rounds and testing at the Fermilab Beam Test Facility, arXiv:1704.01461
Additional radiation damage studies are being planned.
Design of cooling system is preliminary (WBS 1.03).
A resource loaded schedule has been developed based on knowledge gained from the prototype rounds.
Support documentation (e.g. BoEs, Testing Plans) have been developed.
Based on the advanced prototyping, there are no technical issues to be resolved.
Calorimeter Electronics is ready for PD-2/3!

## Slide 20: Back Up