## Slide 1: sPHENIX Director’s Review DAQ/Trigger
Ed Desmond
(standing in for Martin Purschke)
April 9-11, 2019
BNL

## Slide 2: The DAQ/Trigger Subsystem
L2 Manager: Martin L Purschke, BNL
DAQ System Requirements
Configure detectors for operation
Control / Monitor detector systems
Readout detectors @ 15 kHz event rate @ 90% livetime
Stored data @ ~ 135 Gbit/sec to HPSS
Timing/Trigger

## Slide 3: DAQ Technical Overview
RHIC Clock
DCM
DCM
DCM
DCM2
SEB
SEB
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
SEB
EBDC
DAM
EBDC
DAM
EBDC
DAM
40+ Gigabit
Crossbar
Switch
Buffer Box
Buffer Box
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
  DAQ interfaces to all detector systems built and working
  Calorimeter, TPC, MVTX detectors successfully read out
  Integration of separate DAQ components into an overall DAQ architecture now in development
Interaction Region
Rack Room
To
HPSS
Slow Controls
vGTM
GL1
MTM
LL1 Trigger
sPHENIX Trigger System

## Slide 4: Scope
Deliverables:
Take 15 kHz event rate with 90% live time
store and transfer ~135 Gbit/s data
Provide sufficient rejection with Local Level 1 to get to 15 kHz
Configuration, Control and Monitoring system software

## Slide 5: Hardware and procurements
Data Collection Modules ( DCM-II) 25 needed
SubEvent Buffers (SEB) (18) : commodity PC
Buffer Boxes (6) : commodity PC/File server
  40 Gbit/sec per BufferBox
JSEB2 input cards (33) ( 40% in hand) custom board
Control Machines - control, monitoring (4) : commodity PC
Global level 1 system Xilinx FPGA based board in hand
Timing system Xilinx FPGA based board in hand
Network switches (one or two) : commodity switch

## Slide 6: DAQ Technical Status
Data Collection Modules (DCM-II) reused from PHENIX with well known functional characteristics
sPHENIX Digitizer electronics already integrated into DAQ readout system
  Tested extensively and used at the FermiLab beam test Feb – May 2018
Significant progress made with TPC readout with ATLAS Felix card
  8 Sampa chip front-end card read out into FELIX cards
  FELIX card integrated into our standard RCDAQ software and successfully read out
Global Level 1
  New Xilinx FPGA based boards in hand
  Basic operational functions now in place and used to trigger TPC readout
SubEvent Buffers (SEB ) , BufferBox components are commercial PCs
Reuse of PHENIX control software where appropriate
Readout of detector monitor data ( temp, DAC gain, status) available and in routine use ( extensively used at the Fermilab test beam with the Calorimeter Control Board)

## Slide 7: GL1 / Timing system
FPGA board selected (same for both GL1 and Timing system, different firmware)
Based on in-house development for the NSLS-2, design under our control, IP under our control, boards readily available
Zynq FPGA at its core, provides additional CPUs running Linux for all slow controls/configuration needs
Plenty of I/O blocks to cater to early R&D-themed needs
“Granule Timing Module” (GTM) firmware in use with TPC front end

## Slide 8: Slow Controls
Configuration and control of Emcal, Hcal, and MBD digitizer and DCM-II components implemented through standard JSEB-II components
  Used extensively in the PHENIX project
  Well understood and established communication protocol
Detector Component Monitoring
  Readout of Calorimeter temperature, DAC gains, and access to status parameters is implemented through in house developed Calorimeter Control Module
  HV control via Weiner-ISEG and LeCroy HV (MBD)
  ADAM/MODBUS Low Voltage control, reuse from PHENIX
  Development of a standard API for these devices is in development

## Slide 9: Subsystem Collaborators
1.6 Data Acquisition and Trigger (M. Purschke, BNL)
  1.6.1 The core DAQ system (Ed Desmond, BNL)
  1.6.2 Local-Level 1 Triggers (Jamie Nagle, U Colorado)
  1.6.3 Global Level 1 Trigger (Ed Desmond, BNL)
  1.6.4 Timing system (M. Purschke )
Joe Mead, BNL/instrumentation (Timing)
John Kuczewski, BNL/instrumentation (Timing,GL1, Time Projection Chamber interfaces)
Cheng-Yi Chi, Columbia/Nevis (Local Level-1) Dennis Perepelitsa, U Colorado (Local Level-1)

## Slide 10: Schedule Drivers
Task | Finish date
GL1 Prototype Ready | Dec 2018
DAQ prototype ready for production | Aug 2019
Timing system prototype | Sep 2019
Local Level-1 prototype v1 ready | April 2020
Local Level-1 preproduction prototype | Oct 2020
DAQ components ready for operation | Dec 2020
Timing system ready | Dec 2020
GL1 ready | Mar 2021
Local Level-1 ready | Jul 2021

## Slide 11: Cost Drivers
DCM2 Components $120.6k
  8 DCM2 cards @ $12000/ea + 6 JSEB2 cards @ $4100
Commodity PCs $48.26k
  18 SEBs @ $2280
  4 JSEB2 hosts @ $2107
Buffer Boxes $268k
  6 RAID boxes @ 44708
Network switch $79.8k
  2 10Gb switches

## Slide 12: Cost Distribution WBS 1.6 DAQ/Trigger

## Slide 13: WBS 1.06 Estimate of Uncertainty

## Slide 14: Status and highlights
We can already read the main components (calorimeters, Time Projection Chamber, …) with actual sPHENIX hardware (DCM2s, TPC front-end boards, etc)
We have a “legacy” high-end 10Gbit/s network switch available for development
We have enough PCs in hand for all development and similar tasks
Local-level-1 technology selected
The Global Level-1 and Timing technology is selected, procured and development underway and partially implemented
Final data format defined and software already implemented

## Slide 15: GL1 and Timing system (GTM) Status
We have demonstrated the readout of the TPC front-end card under the control of the timing system (GTM, Granule Timing Module)
GTM distributes a trigger and started the readout
Can in turn be controlled by a GL1 unit
EBDC
Timing System
Felix Card
Timing fiber Trigger Signal

## Slide 16: GL1 and Timing system TPC triggering
Test stand readout of the TPC front-end card with scope trace of GTM to FEE trigger signal
GTM/FEE trigger trace
Test stand for FEE/GTM

## Slide 17: 1.6 DAQ/Trigger Risks

## Slide 18: Issues and Concerns
The TPC data rate could be higher than currently estimated from simulations
This may lead to more expensive network switches and more file servers, or reduced buffering depth

## Slide 19: Summary
DAQ interface to all sPHENIX detector sub-systems in place and functional
The control and readout of the TPC, MVTX and Calorimeter detectors has been successfully implemented using the standard DAQ software
Calorimeter detectors successfully read out at Feb 2018 Fermilab test beam
A baseline Global level 1 has been implemented, including readout of trigger parameters
TPC and MVTX front-ends have used the GL1 information transmitted through the GTM timing system
DAQ system used for all tests implements standard sPHENIX data formats, allowing re-use of monitoring and analysis software.
The sPHENIX DAQ system is ready for PD-2/3

## Slide 20: Back Up

## Slide 21: Buffering and average data rates
We have ”built in” a factor of 0.6 for the combined sPHENIX x RHIC uptime (optimistic)
With buffering, we can take ~1.5 times the HPSS logging rate
The longer you can buffer, the higher the local rate can get
2016 PHENIX numbers: 12 Gbit/s local max from the DAQ
uptime: ~ 50%
12 hour average 6 Gbit/s
2-day average 4 Gbit/s
week < 3 Gbit/s
entire Run ~2Gbit/s
You average over machine-development days, short accesses, APEX days, and other small no-beam periods